## Sheet1
NPT_ID | Date | Well_ID | Rig_ID | Rig_Age | Rig_Name | Rig_Type | Contractor | Rig_Status | Rig_Day_Rate | Operator | Block | Well_Type | Country | Water_Depth_ft | Target_Depth_ft | Mechanical_Flag | Weather_Flag | Drilling_Flag | Logistics_Flag | Personnel_Flag | NPT_Flag | Lost_Drilling_Days | Productivity_Loss_pct | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Duration_hr | Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Duration_Bucket | Cost_Bucket | Severity | Downtime_Type | Shift | Corrective_Action | Action_Status | Month | Quarter | Season
NPT00001 | 19-04-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | 2 | 40833 | 101446 | 142279 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | Open | April | Q2 | Dry Season
NPT00002 | 22-04-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 2 | 40833 | 70917 | 111750 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Open | April | Q2 | Dry Season
NPT00003 | 29-04-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | 2 | 40833 | 60855 | 101688 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | In Progress | April | Q2 | Dry Season
NPT00004 | 30-04-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 6 | 122500 | 251157 | 373657 | Moderate | $250K - $500K | Medium | Unplanned | Day | Expedite Shipment | Closed | April | Q2 | Dry Season
NPT00005 | 05-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 6 | 122500 | 128869 | 251369 | Moderate | $250K - $500K | Medium | Unplanned | Night | Repair Component | Closed | May | Q2 | Long Rainy Season
NPT00006 | 08-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | High Waves | Strong Wind | Weather | 8 | 163333 | 105854 | 269187 | Moderate | $250K - $500K | Medium | Unplanned | Night | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00007 | 10-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Differential Sticking | Operator | 4 | 81666 | 85703 | 167369 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00008 | 18-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Differential Sticking | Operator | 2 | 40833 | 94533 | 135366 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Closed | May | Q2 | Long Rainy Season
NPT00009 | 23-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Storm | Weather | 4 | 81666 | 108862 | 190528 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | In Progress | May | Q2 | Long Rainy Season
NPT00010 | 26-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | High Waves | Marine Operations | 4 | 81666 | 124254 | 205920 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Open | May | Q2 | Long Rainy Season
NPT00011 | 29-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | High Waves | Weather | 2 | 40833 | 78584 | 119417 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | May | Q2 | Long Rainy Season
NPT00012 | 30-05-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | 4 | 81666 | 152013 | 233679 | Minor | $100K - $250K | Low | Planned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00013 | 04-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Lightning | Weather | 6 | 122500 | 139841 | 262341 | Moderate | $250K - $500K | Medium | Unplanned | Day | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00014 | 06-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | 6 | 122500 | 230529 | 353029 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | In Progress | June | Q2 | Long Rainy Season
NPT00015 | 09-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | High Waves | Storm | Marine Operations | 12 | 245000 | 394548 | 639548 | Major | $500K - $1M | Medium | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00016 | 12-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 4 | 81666 | 185722 | 267388 | Minor | $250K - $500K | Low | Unplanned | Night | Increase Mud Weight | Closed | June | Q2 | Long Rainy Season
NPT00017 | 15-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 81666 | 90708 | 172374 | Minor | $100K - $250K | Low | Unplanned | Night | Preventive Maintenance | In Progress | June | Q2 | Long Rainy Season
NPT00018 | 20-06-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Heavy Rain | Marine Operations | 6 | 122500 | 205768 | 328268 | Moderate | $250K - $500K | Medium | Unplanned | Night | Suspend Operations | In Progress | June | Q2 | Long Rainy Season
NPT00019 | 03-07-2023 | W001 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5528 | 16495 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | 4 | 81666 | 198718 | 280384 | Minor | $250K - $500K | Low | Planned | Night | Expedite Shipment | Closed | July | Q3 | Long Rainy Season
NPT00020 | 14-03-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Bit Wear | Directional Drilling | 6 | 118750 | 226214 | 344964 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | March | Q1 | Dry Season
NPT00021 | 30-03-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Bit Wear | Operator | 6 | 118750 | 68245 | 186995 | Moderate | $100K - $250K | Medium | Unplanned | Night | Run Fishing Tools | Open | March | Q1 | Dry Season
NPT00022 | 02-04-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | 2 | 39583 | 70254 | 109837 | Minor | $100K - $250K | Low | Planned | Day | Increase Mud Weight | Closed | April | Q2 | Dry Season
NPT00023 | 10-04-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 2 | 39583 | 76363 | 115946 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Closed | April | Q2 | Dry Season
NPT00024 | 21-04-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | 18 | 356250 | 753050 | 1109300 | Major | > $1M | High | Unplanned | Day | Repair Component | Closed | April | Q2 | Dry Season
NPT00025 | 25-04-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | 6 | 118750 | 98071 | 216821 | Moderate | $100K - $250K | Medium | Unplanned | Night | Expedite Shipment | Closed | April | Q2 | Dry Season
NPT00026 | 26-04-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 6 | 118750 | 188958 | 307708 | Moderate | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | April | Q2 | Dry Season
NPT00027 | 02-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | 6 | 118750 | 64902 | 183652 | Moderate | $100K - $250K | Medium | Planned | Day | Repair Component | Closed | May | Q2 | Long Rainy Season
NPT00028 | 05-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Bit Wear | Operator | 8 | 158333 | 316860 | 475193 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | In Progress | May | Q2 | Long Rainy Season
NPT00029 | 17-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 4 | 79166 | 173712 | 252878 | Minor | $250K - $500K | Low | Unplanned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00030 | 23-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | 8 | 158333 | 235732 | 394065 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Open | May | Q2 | Long Rainy Season
NPT00031 | 24-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Heavy Rain | Marine Operations | 4 | 79166 | 137466 | 216632 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | May | Q2 | Long Rainy Season
NPT00032 | 25-05-2024 | W002 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5002 | 18304 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | 12 | 237500 | 394870 | 632370 | Major | $500K - $1M | Medium | Unplanned | Day | Repair Component | In Progress | May | Q2 | Long Rainy Season
NPT00033 | 08-10-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | 18 | 367500 | 863362 | 1230862 | Major | > $1M | High | Unplanned | Day | Adjust Drilling Parameters | Open | October | Q4 | Dry Season
NPT00034 | 12-10-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 6 | 122500 | 294100 | 416600 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | In Progress | October | Q4 | Dry Season
NPT00035 | 21-10-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Safety Stand Down | Training Requirement | Rig Management | 6 | 122500 | 101091 | 223591 | Moderate | $100K - $250K | Medium | Unplanned | Night | Safety Briefing | Closed | October | Q4 | Dry Season
NPT00036 | 30-10-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | 24 | 490000 | 1057580 | 1547580 | Critical | > $1M | High | Unplanned | Night | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00037 | 01-11-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | 2 | 40833 | 94991 | 135824 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | November | Q4 | Short Rainy Season
NPT00038 | 13-11-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | 4 | 81666 | 198934 | 280600 | Minor | $250K - $500K | Low | Unplanned | Day | Repair Component | Closed | November | Q4 | Short Rainy Season
NPT00039 | 14-11-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Boat | Customs Clearance | Procurement | 4 | 81666 | 188346 | 270012 | Minor | $250K - $500K | Low | Unplanned | Night | Air Freight Materials | Closed | November | Q4 | Short Rainy Season
NPT00040 | 20-11-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | 4 | 81666 | 64854 | 146520 | Minor | $100K - $250K | Low | Unplanned | Night | Air Freight Materials | Closed | November | Q4 | Short Rainy Season
NPT00041 | 30-11-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | 6 | 122500 | 177370 | 299870 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | November | Q4 | Short Rainy Season
NPT00042 | 04-12-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 2 | 40833 | 50164 | 90997 | Minor | < $100K | Low | Unplanned | Day | Repair Component | In Progress | December | Q4 | Short Rainy Season
NPT00043 | 07-12-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Boat | Material Shortage | Procurement | 2 | 40833 | 27318 | 68151 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Closed | December | Q4 | Short Rainy Season
NPT00044 | 16-12-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 6 | 122500 | 191741 | 314241 | Moderate | $250K - $500K | Medium | Unplanned | Day | Preventive Maintenance | Closed | December | Q4 | Short Rainy Season
NPT00045 | 20-12-2023 | W003 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4897 | 18763 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | Strong Wind | Marine Operations | 4 | 81666 | 119164 | 200830 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | December | Q4 | Short Rainy Season
NPT00046 | 24-04-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 38333 | 23125 | 61458 | Minor | < $100K | Low | Unplanned | Day | Preventive Maintenance | Closed | April | Q2 | Dry Season
NPT00047 | 25-04-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 2 | 38333 | 82098 | 120431 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | April | Q2 | Dry Season
NPT00048 | 08-05-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Marine Operations | 2 | 38333 | 95062 | 133395 | Minor | $100K - $250K | Low | Unplanned | Day | Wait on Weather | Open | May | Q2 | Long Rainy Season
NPT00049 | 21-05-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 12 | 230000 | 495852 | 725852 | Major | $500K - $1M | Medium | Unplanned | Day | Increase Mud Weight | Closed | May | Q2 | Long Rainy Season
NPT00050 | 11-06-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Heavy Rain | Marine Operations | 4 | 76666 | 120129 | 196795 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00051 | 18-06-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 4 | 76666 | 57881 | 134547 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | June | Q2 | Long Rainy Season
NPT00052 | 21-06-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Weather | 6 | 115000 | 137010 | 252010 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | June | Q2 | Long Rainy Season
NPT00053 | 02-07-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 2 | 38333 | 24450 | 62783 | Minor | < $100K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | July | Q3 | Long Rainy Season
NPT00054 | 03-07-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | 2 | 38333 | 89763 | 128096 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | In Progress | July | Q3 | Long Rainy Season
NPT00055 | 08-07-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | High Waves | Marine Operations | 4 | 76666 | 91438 | 168104 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00056 | 14-07-2023 | W004 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5370 | 20232 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 12 | 230000 | 121023 | 351023 | Major | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Closed | July | Q3 | Long Rainy Season
NPT00057 | 15-03-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Lightning | Weather | 4 | 76666 | 160965 | 237631 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | March | Q1 | Dry Season
NPT00058 | 29-03-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | Storm | Weather | 6 | 115000 | 222173 | 337173 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | March | Q1 | Dry Season
NPT00059 | 31-03-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | 6 | 115000 | 185545 | 300545 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Closed | March | Q1 | Dry Season
NPT00060 | 08-04-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Storm | Marine Operations | 2 | 38333 | 51475 | 89808 | Minor | < $100K | Low | Planned | Day | Suspend Operations | Closed | April | Q2 | Dry Season
NPT00061 | 23-04-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Material Shortage | Procurement | 4 | 76666 | 100056 | 176722 | Minor | $100K - $250K | Low | Unplanned | Night | Mobilize Supply Vessel | Closed | April | Q2 | Dry Season
NPT00062 | 27-04-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 0 | 0 | 0 | 1 | 1 | 0.33 | 33.3 | Personnel | Medical Evacuation | Training Requirement | HR | 8 | 153333 | 97266 | 250599 | Moderate | $250K - $500K | Medium | Unplanned | Night | Safety Briefing | Closed | April | Q2 | Dry Season
NPT00063 | 01-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | 8 | 153333 | 252476 | 405809 | Moderate | $250K - $500K | Medium | Unplanned | Night | Repair Component | Closed | May | Q2 | Long Rainy Season
NPT00064 | 09-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | 4 | 76666 | 183892 | 260558 | Minor | $250K - $500K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00065 | 12-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Strong Wind | Marine Operations | 6 | 115000 | 134376 | 249376 | Moderate | $100K - $250K | Medium | Planned | Day | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00066 | 14-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 6 | 115000 | 241365 | 356365 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Closed | May | Q2 | Long Rainy Season
NPT00067 | 19-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | 4 | 76666 | 150606 | 227272 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | Closed | May | Q2 | Long Rainy Season
NPT00068 | 29-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 4 | 76666 | 67864 | 144530 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | May | Q2 | Long Rainy Season
NPT00069 | 30-05-2023 | W005 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 4892 | 16853 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Storm | Marine Operations | 2 | 38333 | 69012 | 107345 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | May | Q2 | Long Rainy Season
NPT00070 | 08-12-2024 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | 2 | 38333 | 55949 | 94282 | Minor | < $100K | Low | Planned | Day | Preventive Maintenance | Open | December | Q4 | Short Rainy Season
NPT00071 | 12-12-2024 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Marine Operations | 2 | 38333 | 74025 | 112358 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | December | Q4 | Short Rainy Season
NPT00072 | 16-12-2024 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 153333 | 347820 | 501153 | Moderate | $500K - $1M | Medium | Unplanned | Night | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00073 | 21-12-2024 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Lightning | Marine Operations | 2 | 38333 | 92556 | 130889 | Minor | $100K - $250K | Low | Planned | Day | Suspend Operations | Open | December | Q4 | Short Rainy Season
NPT00074 | 06-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Material Shortage | Procurement | 4 | 76666 | 169001 | 245667 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | Open | January | Q1 | Short Rainy Season
NPT00075 | 07-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Lightning | Marine Operations | 4 | 76666 | 45813 | 122479 | Minor | $100K - $250K | Low | Unplanned | Day | Wait on Weather | Closed | January | Q1 | Short Rainy Season
NPT00076 | 10-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | 4 | 76666 | 142294 | 218960 | Minor | $100K - $250K | Low | Unplanned | Night | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00077 | 27-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Waiting on Cement | Customs Clearance | Procurement | 8 | 153333 | 232289 | 385622 | Moderate | $250K - $500K | Medium | Unplanned | Night | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00078 | 28-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | 6 | 115000 | 236864 | 351864 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Closed | January | Q1 | Short Rainy Season
NPT00079 | 29-01-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 4 | 76666 | 64974 | 141640 | Minor | $100K - $250K | Low | Unplanned | Night | Air Freight Materials | Closed | January | Q1 | Short Rainy Season
NPT00080 | 05-02-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | 6 | 115000 | 145730 | 260730 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | Closed | February | Q1 | Dry Season
NPT00081 | 06-02-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | 4 | 76666 | 107545 | 184211 | Minor | $100K - $250K | Low | Unplanned | Night | Air Freight Materials | Closed | February | Q1 | Dry Season
NPT00082 | 11-02-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Bit Failure | Bit Wear | Mud Engineering | 18 | 345000 | 462111 | 807111 | Major | $500K - $1M | High | Unplanned | Day | Increase Mud Weight | Closed | February | Q1 | Dry Season
NPT00083 | 20-02-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | 4 | 76666 | 157410 | 234076 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | February | Q1 | Dry Season
NPT00084 | 25-02-2025 | W006 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4706 | 20616 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | 8 | 153333 | 286906 | 440239 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | In Progress | February | Q1 | Dry Season
NPT00085 | 21-01-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 4 | 79166 | 115572 | 194738 | Minor | $100K - $250K | Low | Planned | Day | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00086 | 27-01-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Formation Instability | Operator | 2 | 39583 | 64096 | 103679 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | Closed | January | Q1 | Short Rainy Season
NPT00087 | 28-01-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | High Waves | Marine Operations | 4 | 79166 | 60596 | 139762 | Minor | $100K - $250K | Low | Planned | Day | Suspend Operations | Closed | January | Q1 | Short Rainy Season
NPT00088 | 03-02-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Well Control | Bit Wear | Directional Drilling | 18 | 356250 | 798690 | 1154940 | Major | > $1M | High | Planned | Day | Condition Hole | Closed | February | Q1 | Dry Season
NPT00089 | 08-02-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 4 | 79166 | 52507 | 131673 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00090 | 09-02-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 2 | 39583 | 82308 | 121891 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | In Progress | February | Q1 | Dry Season
NPT00091 | 20-02-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | 18 | 356250 | 702062 | 1058312 | Major | > $1M | High | Unplanned | Night | Repair Component | Closed | February | Q1 | Dry Season
NPT00092 | 26-02-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Lightning | Storm | Marine Operations | 8 | 158333 | 192897 | 351230 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | In Progress | February | Q1 | Dry Season
NPT00093 | 10-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Marine Operations | 6 | 118750 | 152256 | 271006 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | In Progress | March | Q1 | Dry Season
NPT00094 | 16-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Training | Training Requirement | Medical Team | 2 | 39583 | 85410 | 124993 | Minor | $100K - $250K | Low | Unplanned | Day | Medical Clearance | Closed | March | Q1 | Dry Season
NPT00095 | 23-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | 8 | 158333 | 144349 | 302682 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | Closed | March | Q1 | Dry Season
NPT00096 | 24-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | 18 | 356250 | 843510 | 1199760 | Major | > $1M | High | Planned | Day | Replace Equipment | Closed | March | Q1 | Dry Season
NPT00097 | 27-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | 2 | 39583 | 39917 | 79500 | Minor | < $100K | Low | Unplanned | Night | Preventive Maintenance | Closed | March | Q1 | Dry Season
NPT00098 | 31-03-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | 6 | 118750 | 164765 | 283515 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | March | Q1 | Dry Season
NPT00099 | 11-04-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 0 | 0 | 0 | 1 | 0 | 1 | 0.75 | 75 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | 18 | 356250 | 426483 | 782733 | Major | $500K - $1M | High | Unplanned | Night | Air Freight Materials | Closed | April | Q2 | Dry Season
NPT00100 | 18-04-2023 | W007 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5538 | 21585 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | 8 | 158333 | 357164 | 515497 | Moderate | $500K - $1M | Medium | Unplanned | Day | Replace Equipment | Closed | April | Q2 | Dry Season
NPT00101 | 18-09-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 4 | 76666 | 111806 | 188472 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | Closed | September | Q3 | Dry Season
NPT00102 | 19-09-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Weather | 2 | 38333 | 76426 | 114759 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | September | Q3 | Dry Season
NPT00103 | 25-09-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Safety Stand Down | Training Requirement | Medical Team | 2 | 38333 | 66496 | 104829 | Minor | $100K - $250K | Low | Unplanned | Day | Safety Briefing | In Progress | September | Q3 | Dry Season
NPT00104 | 01-10-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | 2 | 38333 | 59428 | 97761 | Minor | < $100K | Low | Unplanned | Night | Expedite Shipment | In Progress | October | Q4 | Dry Season
NPT00105 | 03-10-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 8 | 153333 | 77458 | 230791 | Moderate | $100K - $250K | Medium | Unplanned | Day | Increase Mud Weight | In Progress | October | Q4 | Dry Season
NPT00106 | 21-10-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | High Waves | Marine Operations | 4 | 76666 | 73637 | 150303 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | October | Q4 | Dry Season
NPT00107 | 26-10-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | 4 | 76666 | 90633 | 167299 | Minor | $100K - $250K | Low | Unplanned | Night | Preventive Maintenance | Open | October | Q4 | Dry Season
NPT00108 | 11-11-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | 6 | 115000 | 286152 | 401152 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | November | Q4 | Short Rainy Season
NPT00109 | 16-11-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Fishing Operation | Formation Instability | Operator | 6 | 115000 | 161085 | 276085 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Open | November | Q4 | Short Rainy Season
NPT00110 | 01-12-2024 | W008 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6381 | 19659 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | 2 | 38333 | 48369 | 86702 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Closed | December | Q4 | Short Rainy Season
NPT00111 | 18-05-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Lightning | Marine Operations | 2 | 39583 | 93632 | 133215 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | Closed | May | Q2 | Long Rainy Season
NPT00112 | 23-05-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Formation Instability | Mud Engineering | 4 | 79166 | 43669 | 122835 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Open | May | Q2 | Long Rainy Season
NPT00113 | 24-05-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 6 | 118750 | 110684 | 229434 | Moderate | $100K - $250K | Medium | Unplanned | Day | Air Freight Materials | Closed | May | Q2 | Long Rainy Season
NPT00114 | 28-05-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | 100 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 24 | 475000 | 464721 | 939721 | Critical | $500K - $1M | High | Planned | Night | Run Fishing Tools | Closed | May | Q2 | Long Rainy Season
NPT00115 | 29-05-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | 6 | 118750 | 114628 | 233378 | Moderate | $100K - $250K | Medium | Unplanned | Night | OEM Inspection | In Progress | May | Q2 | Long Rainy Season
NPT00116 | 14-06-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Storm | Marine Operations | 2 | 39583 | 69610 | 109193 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00117 | 16-06-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | 6 | 118750 | 89584 | 208334 | Moderate | $100K - $250K | Medium | Unplanned | Day | OEM Inspection | In Progress | June | Q2 | Long Rainy Season
NPT00118 | 25-06-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 4 | 79166 | 182360 | 261526 | Minor | $250K - $500K | Low | Unplanned | Night | Repair Component | Open | June | Q2 | Long Rainy Season
NPT00119 | 02-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Lightning | Weather | 4 | 79166 | 143929 | 223095 | Minor | $100K - $250K | Low | Planned | Day | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00120 | 04-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | 4 | 79166 | 68905 | 148071 | Minor | $100K - $250K | Low | Unplanned | Night | Preventive Maintenance | Closed | July | Q3 | Long Rainy Season
NPT00121 | 06-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | 6 | 118750 | 291172 | 409922 | Moderate | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | In Progress | July | Q3 | Long Rainy Season
NPT00122 | 08-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | High Waves | Marine Operations | 6 | 118750 | 128920 | 247670 | Moderate | $100K - $250K | Medium | Planned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00123 | 15-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | High Waves | Marine Operations | 6 | 118750 | 279850 | 398600 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | July | Q3 | Long Rainy Season
NPT00124 | 18-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | 12 | 237500 | 223755 | 461255 | Major | $250K - $500K | Medium | Unplanned | Day | Air Freight Materials | Closed | July | Q3 | Long Rainy Season
NPT00125 | 23-07-2023 | W009 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5984 | 16291 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Heavy Rain | High Waves | Weather | 8 | 158333 | 384790 | 543123 | Moderate | $500K - $1M | Medium | Unplanned | Night | Suspend Operations | Open | July | Q3 | Long Rainy Season
NPT00126 | 11-04-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 153333 | 152314 | 305647 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Open | April | Q2 | Dry Season
NPT00127 | 14-04-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Storm | Marine Operations | 6 | 115000 | 139238 | 254238 | Moderate | $250K - $500K | Medium | Unplanned | Night | Suspend Operations | In Progress | April | Q2 | Dry Season
NPT00128 | 17-04-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Unexpected Pressure | Operator | 2 | 38333 | 30581 | 68914 | Minor | < $100K | Low | Unplanned | Day | Run Fishing Tools | Closed | April | Q2 | Dry Season
NPT00129 | 29-04-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 2 | 38333 | 24138 | 62471 | Minor | < $100K | Low | Unplanned | Day | Condition Hole | Closed | April | Q2 | Dry Season
NPT00130 | 09-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | 8 | 153333 | 121885 | 275218 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | May | Q2 | Long Rainy Season
NPT00131 | 12-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 100 | Weather | Heavy Rain | Strong Wind | Marine Operations | 24 | 460000 | 815283 | 1275283 | Critical | > $1M | High | Unplanned | Night | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00132 | 14-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | Lightning | Heavy Rain | Marine Operations | 18 | 345000 | 286552 | 631552 | Major | $500K - $1M | High | Unplanned | Night | Suspend Operations | Closed | May | Q2 | Long Rainy Season
NPT00133 | 21-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Bit Wear | Operator | 4 | 76666 | 146588 | 223254 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | May | Q2 | Long Rainy Season
NPT00134 | 23-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | 2 | 38333 | 89900 | 128233 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00135 | 25-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | Strong Wind | Marine Operations | 4 | 76666 | 104095 | 180761 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00136 | 30-05-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Formation Instability | Operator | 4 | 76666 | 150640 | 227306 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | In Progress | May | Q2 | Long Rainy Season
NPT00137 | 01-06-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | 8 | 153333 | 121122 | 274455 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | June | Q2 | Long Rainy Season
NPT00138 | 09-06-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 6 | 115000 | 223747 | 338747 | Moderate | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | June | Q2 | Long Rainy Season
NPT00139 | 10-06-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | 4 | 76666 | 168661 | 245327 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | June | Q2 | Long Rainy Season
NPT00140 | 16-06-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Heavy Rain | Weather | 2 | 38333 | 31793 | 70126 | Minor | < $100K | Low | Unplanned | Day | Wait on Weather | In Progress | June | Q2 | Long Rainy Season
NPT00141 | 28-06-2024 | W010 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5363 | 18581 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | 4 | 76666 | 96663 | 173329 | Minor | $100K - $250K | Low | Unplanned | Night | Repair Component | Closed | June | Q2 | Long Rainy Season
NPT00142 | 12-08-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Strong Wind | Weather | 4 | 81666 | 60048 | 141714 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | August | Q3 | Long Rainy Season
NPT00143 | 17-08-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 4 | 81666 | 126974 | 208640 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | August | Q3 | Long Rainy Season
NPT00144 | 20-08-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | 8 | 163333 | 235581 | 398914 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | Closed | August | Q3 | Long Rainy Season
NPT00145 | 30-08-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Storm | Marine Operations | 4 | 81666 | 98387 | 180053 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | August | Q3 | Long Rainy Season
NPT00146 | 04-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | 2 | 40833 | 26711 | 67544 | Minor | < $100K | Low | Unplanned | Night | Increase Mud Weight | Open | September | Q3 | Dry Season
NPT00147 | 09-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | 12 | 245000 | 250040 | 495040 | Major | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | September | Q3 | Dry Season
NPT00148 | 13-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Lightning | Weather | 4 | 81666 | 47696 | 129362 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | September | Q3 | Dry Season
NPT00149 | 22-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Training | Crew Rotation | Medical Team | 6 | 122500 | 90710 | 213210 | Moderate | $100K - $250K | Medium | Unplanned | Day | Safety Briefing | In Progress | September | Q3 | Dry Season
NPT00150 | 23-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 6 | 122500 | 73044 | 195544 | Moderate | $100K - $250K | Medium | Unplanned | Day | Repair Component | Closed | September | Q3 | Dry Season
NPT00151 | 30-09-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 24 | 490000 | 1059746 | 1549746 | Critical | > $1M | High | Unplanned | Day | Preventive Maintenance | Open | September | Q3 | Dry Season
NPT00152 | 02-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | 2 | 40833 | 27130 | 67963 | Minor | < $100K | Low | Unplanned | Day | Replace Equipment | Closed | October | Q4 | Dry Season
NPT00153 | 05-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Weather | 6 | 122500 | 186779 | 309279 | Moderate | $250K - $500K | Medium | Unplanned | Night | Suspend Operations | In Progress | October | Q4 | Dry Season
NPT00154 | 06-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Heavy Rain | Weather | 4 | 81666 | 107304 | 188970 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | In Progress | October | Q4 | Dry Season
NPT00155 | 08-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | 2 | 40833 | 71255 | 112088 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00156 | 15-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 4 | 81666 | 48082 | 129748 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Closed | October | Q4 | Dry Season
NPT00157 | 23-10-2023 | W011 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5063 | 22974 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Bit Failure | Bit Wear | Mud Engineering | 12 | 245000 | 554806 | 799806 | Major | $500K - $1M | Medium | Unplanned | Day | Condition Hole | Closed | October | Q4 | Dry Season
NPT00158 | 27-11-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 2 | 40833 | 30300 | 71133 | Minor | < $100K | Low | Unplanned | Day | Run Fishing Tools | Closed | November | Q4 | Short Rainy Season
NPT00159 | 30-11-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | 6 | 122500 | 63732 | 186232 | Moderate | $100K - $250K | Medium | Unplanned | Day | Repair Component | Closed | November | Q4 | Short Rainy Season
NPT00160 | 06-12-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | 2 | 40833 | 67554 | 108387 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Closed | December | Q4 | Short Rainy Season
NPT00161 | 07-12-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | 6 | 122500 | 226126 | 348626 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | Closed | December | Q4 | Short Rainy Season
NPT00162 | 26-12-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Boat | Port Congestion | Procurement | 6 | 122500 | 255221 | 377721 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | December | Q4 | Short Rainy Season
NPT00163 | 28-12-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | 2 | 40833 | 100241 | 141074 | Minor | $100K - $250K | Low | Unplanned | Night | Mobilize Supply Vessel | In Progress | December | Q4 | Short Rainy Season
NPT00164 | 30-12-2023 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | 4 | 81666 | 62073 | 143739 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00165 | 07-01-2024 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Bit Failure | Unexpected Pressure | Operator | 18 | 367500 | 574959 | 942459 | Major | $500K - $1M | High | Unplanned | Night | Condition Hole | Closed | January | Q1 | Short Rainy Season
NPT00166 | 02-02-2024 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | 2 | 40833 | 57857 | 98690 | Minor | < $100K | Low | Unplanned | Night | Air Freight Materials | Closed | February | Q1 | Dry Season
NPT00167 | 03-02-2024 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Formation Instability | Operator | 4 | 81666 | 116402 | 198068 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | In Progress | February | Q1 | Dry Season
NPT00168 | 24-02-2024 | W012 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5520 | 18457 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | 12 | 245000 | 372611 | 617611 | Major | $500K - $1M | Medium | Planned | Night | Mobilize Supply Vessel | Closed | February | Q1 | Dry Season
NPT00169 | 05-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 6 | 120000 | 253064 | 373064 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | April | Q2 | Dry Season
NPT00170 | 09-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Safety Stand Down | Medical Emergency | HR | 2 | 40000 | 25522 | 65522 | Minor | < $100K | Low | Planned | Day | Safety Briefing | Closed | April | Q2 | Dry Season
NPT00171 | 10-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 0 | 0 | 1 | 1 | 0.33 | 33.3 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | 8 | 160000 | 104847 | 264847 | Moderate | $250K - $500K | Medium | Unplanned | Day | Crew Replacement | Closed | April | Q2 | Dry Season
NPT00172 | 13-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | Strong Wind | Marine Operations | 6 | 120000 | 223619 | 343619 | Moderate | $250K - $500K | Medium | Planned | Day | Suspend Operations | Closed | April | Q2 | Dry Season
NPT00173 | 14-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | 2 | 40000 | 42480 | 82480 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | In Progress | April | Q2 | Dry Season
NPT00174 | 27-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | 2 | 40000 | 64200 | 104200 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | Closed | April | Q2 | Dry Season
NPT00175 | 29-04-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Cement | Customs Clearance | Procurement | 4 | 80000 | 159783 | 239783 | Minor | $100K - $250K | Low | Unplanned | Night | Air Freight Materials | Open | April | Q2 | Dry Season
NPT00176 | 01-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Strong Wind | Storm | Weather | 8 | 160000 | 158983 | 318983 | Moderate | $250K - $500K | Medium | Planned | Night | Resume Operations | Open | May | Q2 | Long Rainy Season
NPT00177 | 04-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | High Waves | Marine Operations | 4 | 80000 | 185590 | 265590 | Minor | $250K - $500K | Low | Unplanned | Night | Resume Operations | Closed | May | Q2 | Long Rainy Season
NPT00178 | 07-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Formation Instability | Operator | 6 | 120000 | 231131 | 351131 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | In Progress | May | Q2 | Long Rainy Season
NPT00179 | 14-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | 4 | 80000 | 113231 | 193231 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | May | Q2 | Long Rainy Season
NPT00180 | 18-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Lost Circulation | Formation Instability | Operator | 12 | 240000 | 542475 | 782475 | Major | $500K - $1M | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00181 | 23-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | 2 | 40000 | 26827 | 66827 | Minor | < $100K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00182 | 24-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | 6 | 120000 | 278656 | 398656 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | In Progress | May | Q2 | Long Rainy Season
NPT00183 | 28-05-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Formation Instability | Directional Drilling | 2 | 40000 | 74203 | 114203 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00184 | 03-06-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 4 | 80000 | 122873 | 202873 | Minor | $100K - $250K | Low | Planned | Day | Replace Equipment | Closed | June | Q2 | Long Rainy Season
NPT00185 | 06-06-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Marine Operations | 6 | 120000 | 129874 | 249874 | Moderate | $100K - $250K | Medium | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00186 | 14-06-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Differential Sticking | Operator | 8 | 160000 | 104193 | 264193 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | June | Q2 | Long Rainy Season
NPT00187 | 18-06-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Bit Wear | Operator | 2 | 40000 | 73930 | 113930 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | Closed | June | Q2 | Long Rainy Season
NPT00188 | 26-06-2024 | W013 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 4595 | 22554 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | 2 | 40000 | 48341 | 88341 | Minor | < $100K | Low | Unplanned | Day | Preventive Maintenance | Closed | June | Q2 | Long Rainy Season
NPT00189 | 06-04-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Medical Evacuation | Training Requirement | Medical Team | 2 | 40833 | 98245 | 139078 | Minor | $100K - $250K | Low | Unplanned | Day | Medical Clearance | Closed | April | Q2 | Dry Season
NPT00190 | 13-04-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 4 | 81666 | 198783 | 280449 | Minor | $250K - $500K | Low | Unplanned | Day | Preventive Maintenance | Closed | April | Q2 | Dry Season
NPT00191 | 30-04-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Cement | Port Congestion | Procurement | 4 | 81666 | 60188 | 141854 | Minor | $100K - $250K | Low | Planned | Day | Expedite Shipment | Closed | April | Q2 | Dry Season
NPT00192 | 05-05-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Bit Wear | Operator | 12 | 245000 | 508399 | 753399 | Major | $500K - $1M | Medium | Unplanned | Night | Run Fishing Tools | Closed | May | Q2 | Long Rainy Season
NPT00193 | 13-05-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | High Waves | Marine Operations | 2 | 40833 | 98036 | 138869 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | In Progress | May | Q2 | Long Rainy Season
NPT00194 | 03-06-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | 4 | 81666 | 154123 | 235789 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | Closed | June | Q2 | Long Rainy Season
NPT00195 | 11-06-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | 4 | 81666 | 77766 | 159432 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Closed | June | Q2 | Long Rainy Season
NPT00196 | 15-06-2023 | W014 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6423 | 22280 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | 6 | 122500 | 135468 | 257968 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | June | Q2 | Long Rainy Season
NPT00197 | 09-01-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | 8 | 160000 | 164904 | 324904 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | Open | January | Q1 | Short Rainy Season
NPT00198 | 14-01-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Bit Wear | Operator | 4 | 80000 | 168562 | 248562 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Open | January | Q1 | Short Rainy Season
NPT00199 | 15-01-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 8 | 160000 | 393128 | 553128 | Moderate | $500K - $1M | Medium | Unplanned | Day | Repair Component | Closed | January | Q1 | Short Rainy Season
NPT00200 | 27-01-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 4 | 80000 | 127428 | 207428 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | Closed | January | Q1 | Short Rainy Season
NPT00201 | 29-01-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 2 | 40000 | 30537 | 70537 | Minor | < $100K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00202 | 11-02-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Formation Instability | Operator | 4 | 80000 | 93447 | 173447 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | February | Q1 | Dry Season
NPT00203 | 14-02-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | 6 | 120000 | 295691 | 415691 | Moderate | $250K - $500K | Medium | Planned | Day | Air Freight Materials | Closed | February | Q1 | Dry Season
NPT00204 | 17-02-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 0 | 1 | 0 | 1 | 0.75 | 75 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | 18 | 360000 | 883515 | 1243515 | Major | > $1M | High | Unplanned | Day | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00205 | 18-02-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Differential Sticking | Operator | 2 | 40000 | 25923 | 65923 | Minor | < $100K | Low | Unplanned | Day | Condition Hole | Closed | February | Q1 | Dry Season
NPT00206 | 25-02-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Formation Instability | Mud Engineering | 2 | 40000 | 27367 | 67367 | Minor | < $100K | Low | Unplanned | Night | Run Fishing Tools | Closed | February | Q1 | Dry Season
NPT00207 | 07-03-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | 6 | 120000 | 245352 | 365352 | Moderate | $250K - $500K | Medium | Unplanned | Night | Repair Component | Open | March | Q1 | Dry Season
NPT00208 | 10-03-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 6 | 120000 | 208139 | 328139 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Closed | March | Q1 | Dry Season
NPT00209 | 18-03-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 4 | 80000 | 147308 | 227308 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | Closed | March | Q1 | Dry Season
NPT00210 | 23-03-2024 | W015 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6257 | 16636 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Safety Stand Down | Training Requirement | HR | 2 | 40000 | 53981 | 93981 | Minor | < $100K | Low | Planned | Night | Crew Replacement | Closed | March | Q1 | Dry Season
NPT00211 | 19-04-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 6 | 122500 | 96624 | 219124 | Moderate | $100K - $250K | Medium | Unplanned | Day | Air Freight Materials | Closed | April | Q2 | Dry Season
NPT00212 | 29-04-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | 6 | 122500 | 78520 | 201020 | Moderate | $100K - $250K | Medium | Unplanned | Day | Repair Component | In Progress | April | Q2 | Dry Season
NPT00213 | 05-05-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Strong Wind | Weather | 6 | 122500 | 264246 | 386746 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00214 | 15-05-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Lightning | Marine Operations | 2 | 40833 | 90548 | 131381 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00215 | 24-05-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | 8 | 163333 | 216971 | 380304 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | May | Q2 | Long Rainy Season
NPT00216 | 27-05-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 2 | 40833 | 42270 | 83103 | Minor | < $100K | Low | Unplanned | Day | Condition Hole | In Progress | May | Q2 | Long Rainy Season
NPT00217 | 11-06-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | 4 | 81666 | 165749 | 247415 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | In Progress | June | Q2 | Long Rainy Season
NPT00218 | 30-06-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Heavy Rain | Marine Operations | 4 | 81666 | 146635 | 228301 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00219 | 01-07-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Strong Wind | Strong Wind | Marine Operations | 8 | 163333 | 228822 | 392155 | Moderate | $250K - $500K | Medium | Unplanned | Day | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00220 | 06-07-2023 | W016 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6778 | 18696 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Heavy Rain | Marine Operations | 4 | 81666 | 192615 | 274281 | Minor | $250K - $500K | Low | Unplanned | Day | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00221 | 28-10-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | 6 | 118750 | 239519 | 358269 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | October | Q4 | Dry Season
NPT00222 | 29-10-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | 6 | 118750 | 120704 | 239454 | Moderate | $100K - $250K | Medium | Unplanned | Day | Preventive Maintenance | In Progress | October | Q4 | Dry Season
NPT00223 | 18-11-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | High Waves | Weather | 6 | 118750 | 136446 | 255196 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | Closed | November | Q4 | Short Rainy Season
NPT00224 | 30-11-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Formation Instability | Operator | 4 | 79166 | 127827 | 206993 | Minor | $100K - $250K | Low | Planned | Night | Condition Hole | In Progress | November | Q4 | Short Rainy Season
NPT00225 | 01-12-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Formation Instability | Directional Drilling | 6 | 118750 | 81777 | 200527 | Moderate | $100K - $250K | Medium | Unplanned | Day | Increase Mud Weight | Closed | December | Q4 | Short Rainy Season
NPT00226 | 11-12-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Formation Instability | Operator | 2 | 39583 | 44552 | 84135 | Minor | < $100K | Low | Unplanned | Night | Increase Mud Weight | Closed | December | Q4 | Short Rainy Season
NPT00227 | 14-12-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | 6 | 118750 | 154929 | 273679 | Moderate | $250K - $500K | Medium | Planned | Night | Air Freight Materials | Closed | December | Q4 | Short Rainy Season
NPT00228 | 16-12-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Bit Wear | Directional Drilling | 2 | 39583 | 49805 | 89388 | Minor | < $100K | Low | Unplanned | Night | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00229 | 31-12-2024 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | 6 | 118750 | 236976 | 355726 | Moderate | $250K - $500K | Medium | Unplanned | Day | Crew Replacement | Closed | December | Q4 | Short Rainy Season
NPT00230 | 04-01-2025 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | 2 | 39583 | 55699 | 95282 | Minor | < $100K | Low | Unplanned | Day | Run Fishing Tools | In Progress | January | Q1 | Short Rainy Season
NPT00231 | 14-01-2025 | W017 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6178 | 17999 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | 8 | 158333 | 274332 | 432665 | Moderate | $250K - $500K | Medium | Planned | Day | Expedite Shipment | Closed | January | Q1 | Short Rainy Season
NPT00232 | 12-05-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Storm | Marine Operations | 6 | 122500 | 92594 | 215094 | Moderate | $100K - $250K | Medium | Unplanned | Night | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00233 | 24-05-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 100 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | 24 | 490000 | 397460 | 887460 | Critical | $500K - $1M | High | Unplanned | Day | Air Freight Materials | Open | May | Q2 | Long Rainy Season
NPT00234 | 28-05-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Formation Instability | Operator | 2 | 40833 | 48398 | 89231 | Minor | < $100K | Low | Unplanned | Night | Condition Hole | In Progress | May | Q2 | Long Rainy Season
NPT00235 | 31-05-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Strong Wind | Weather | 2 | 40833 | 71375 | 112208 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | In Progress | May | Q2 | Long Rainy Season
NPT00236 | 03-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | High Waves | Marine Operations | 4 | 81666 | 130214 | 211880 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00237 | 07-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 4 | 81666 | 121285 | 202951 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | June | Q2 | Long Rainy Season
NPT00238 | 16-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 6 | 122500 | 117557 | 240057 | Moderate | $100K - $250K | Medium | Unplanned | Day | Repair Component | Closed | June | Q2 | Long Rainy Season
NPT00239 | 20-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | 2 | 40833 | 96130 | 136963 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | In Progress | June | Q2 | Long Rainy Season
NPT00240 | 23-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Storm | Marine Operations | 4 | 81666 | 202290 | 283956 | Minor | $250K - $500K | Low | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00241 | 24-06-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Storm | Weather | 6 | 122500 | 74361 | 196861 | Moderate | $100K - $250K | Medium | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00242 | 08-07-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 8 | 163333 | 204429 | 367762 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | Closed | July | Q3 | Long Rainy Season
NPT00243 | 13-07-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | 4 | 81666 | 86316 | 167982 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | July | Q3 | Long Rainy Season
NPT00244 | 29-07-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | 12 | 245000 | 278344 | 523344 | Major | $500K - $1M | Medium | Unplanned | Night | Condition Hole | Closed | July | Q3 | Long Rainy Season
NPT00245 | 01-08-2023 | W018 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5040 | 18152 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Heavy Rain | Weather | 4 | 81666 | 138389 | 220055 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | August | Q3 | Long Rainy Season
NPT00246 | 01-11-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 100 | Weather | Lightning | High Waves | Weather | 24 | 480000 | 674701 | 1154701 | Critical | > $1M | High | Unplanned | Night | Resume Operations | Closed | November | Q4 | Short Rainy Season
NPT00247 | 11-11-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | 12 | 240000 | 123301 | 363301 | Major | $250K - $500K | Medium | Unplanned | Night | Preventive Maintenance | Open | November | Q4 | Short Rainy Season
NPT00248 | 27-11-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 4 | 80000 | 66304 | 146304 | Minor | $100K - $250K | Low | Unplanned | Night | Condition Hole | Closed | November | Q4 | Short Rainy Season
NPT00249 | 28-11-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | 6 | 120000 | 217687 | 337687 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | November | Q4 | Short Rainy Season
NPT00250 | 02-12-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | 6 | 120000 | 111527 | 231527 | Moderate | $100K - $250K | Medium | Unplanned | Day | Expedite Shipment | Closed | December | Q4 | Short Rainy Season
NPT00251 | 03-12-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 12 | 240000 | 479117 | 719117 | Major | $500K - $1M | Medium | Unplanned | Night | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00252 | 08-12-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | 2 | 40000 | 65954 | 105954 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | December | Q4 | Short Rainy Season
NPT00253 | 09-12-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 2 | 40000 | 24142 | 64142 | Minor | < $100K | Low | Unplanned | Night | Condition Hole | In Progress | December | Q4 | Short Rainy Season
NPT00254 | 17-12-2024 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Bit Wear | Operator | 4 | 80000 | 52250 | 132250 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | December | Q4 | Short Rainy Season
NPT00255 | 01-01-2025 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Well Control | Bit Wear | Mud Engineering | 18 | 360000 | 827467 | 1187467 | Major | > $1M | High | Planned | Day | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00256 | 11-01-2025 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | 8 | 160000 | 163949 | 323949 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00257 | 14-01-2025 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Formation Instability | Operator | 4 | 80000 | 108553 | 188553 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00258 | 17-01-2025 | W019 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5559 | 15698 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 12 | 240000 | 366765 | 606765 | Major | $500K - $1M | Medium | Unplanned | Night | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00259 | 05-11-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | 18 | 360000 | 663187 | 1023187 | Major | > $1M | High | Unplanned | Night | OEM Inspection | Closed | November | Q4 | Short Rainy Season
NPT00260 | 12-11-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Formation Instability | Directional Drilling | 4 | 80000 | 107175 | 187175 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | November | Q4 | Short Rainy Season
NPT00261 | 16-11-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | 2 | 40000 | 72937 | 112937 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Open | November | Q4 | Short Rainy Season
NPT00262 | 20-11-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Port Congestion | Procurement | 2 | 40000 | 24049 | 64049 | Minor | < $100K | Low | Unplanned | Night | Mobilize Supply Vessel | Closed | November | Q4 | Short Rainy Season
NPT00263 | 21-11-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Bit Wear | Operator | 6 | 120000 | 69661 | 189661 | Moderate | $100K - $250K | Medium | Planned | Night | Increase Mud Weight | Closed | November | Q4 | Short Rainy Season
NPT00264 | 02-12-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | High Waves | Marine Operations | 4 | 80000 | 70919 | 150919 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Open | December | Q4 | Short Rainy Season
NPT00265 | 03-12-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 4 | 80000 | 156404 | 236404 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | December | Q4 | Short Rainy Season
NPT00266 | 15-12-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 80000 | 95170 | 175170 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Closed | December | Q4 | Short Rainy Season
NPT00267 | 18-12-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 160000 | 130021 | 290021 | Moderate | $250K - $500K | Medium | Unplanned | Night | Preventive Maintenance | Closed | December | Q4 | Short Rainy Season
NPT00268 | 23-12-2023 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Medical Evacuation | Training Requirement | Medical Team | 2 | 40000 | 71032 | 111032 | Minor | $100K - $250K | Low | Unplanned | Night | Safety Briefing | Closed | December | Q4 | Short Rainy Season
NPT00269 | 01-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | High Waves | Heavy Rain | Marine Operations | 8 | 160000 | 364772 | 524772 | Moderate | $500K - $1M | Medium | Planned | Night | Suspend Operations | Open | January | Q1 | Short Rainy Season
NPT00270 | 08-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | 2 | 40000 | 81266 | 121266 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | Closed | January | Q1 | Short Rainy Season
NPT00271 | 09-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | 2 | 40000 | 79766 | 119766 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | January | Q1 | Short Rainy Season
NPT00272 | 11-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | 2 | 40000 | 52909 | 92909 | Minor | < $100K | Low | Unplanned | Day | Preventive Maintenance | Closed | January | Q1 | Short Rainy Season
NPT00273 | 12-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | 2 | 40000 | 33971 | 73971 | Minor | < $100K | Low | Unplanned | Day | OEM Inspection | Closed | January | Q1 | Short Rainy Season
NPT00274 | 16-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 6 | 120000 | 141830 | 261830 | Moderate | $250K - $500K | Medium | Planned | Day | Air Freight Materials | Closed | January | Q1 | Short Rainy Season
NPT00275 | 19-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | 6 | 120000 | 223111 | 343111 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | January | Q1 | Short Rainy Season
NPT00276 | 22-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | 2 | 40000 | 92216 | 132216 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | January | Q1 | Short Rainy Season
NPT00277 | 24-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | 4 | 80000 | 143184 | 223184 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Closed | January | Q1 | Short Rainy Season
NPT00278 | 28-01-2024 | W020 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5683 | 17160 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Heavy Rain | Weather | 2 | 40000 | 91903 | 131903 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | Closed | January | Q1 | Short Rainy Season
NPT00279 | 13-12-2023 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | 12 | 230000 | 265392 | 495392 | Major | $250K - $500K | Medium | Unplanned | Night | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00280 | 19-12-2023 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Formation Instability | Mud Engineering | 6 | 115000 | 172490 | 287490 | Moderate | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | December | Q4 | Short Rainy Season
NPT00281 | 23-12-2023 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | 2 | 38333 | 40806 | 79139 | Minor | < $100K | Low | Unplanned | Night | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00282 | 31-12-2023 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | 6 | 115000 | 207678 | 322678 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00283 | 04-01-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | 8 | 153333 | 239111 | 392444 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00284 | 23-01-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | 4 | 76666 | 173767 | 250433 | Minor | $250K - $500K | Low | Unplanned | Day | Preventive Maintenance | In Progress | January | Q1 | Short Rainy Season
NPT00285 | 29-01-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 0 | 1 | 0 | 1 | 0.75 | 75 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | 18 | 345000 | 573898 | 918898 | Major | $500K - $1M | High | Unplanned | Day | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00286 | 01-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Strong Wind | Marine Operations | 6 | 115000 | 80176 | 195176 | Moderate | $100K - $250K | Medium | Unplanned | Day | Wait on Weather | Closed | February | Q1 | Dry Season
NPT00287 | 02-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | 6 | 115000 | 90497 | 205497 | Moderate | $100K - $250K | Medium | Unplanned | Day | Preventive Maintenance | In Progress | February | Q1 | Dry Season
NPT00288 | 06-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Medical Evacuation | Training Requirement | HR | 2 | 38333 | 79231 | 117564 | Minor | $100K - $250K | Low | Unplanned | Night | Medical Clearance | Closed | February | Q1 | Dry Season
NPT00289 | 09-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 6 | 115000 | 286496 | 401496 | Moderate | $250K - $500K | Medium | Unplanned | Day | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00290 | 10-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 2 | 38333 | 40658 | 78991 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00291 | 11-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Weather | 2 | 38333 | 88590 | 126923 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | February | Q1 | Dry Season
NPT00292 | 18-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | 6 | 115000 | 196670 | 311670 | Moderate | $250K - $500K | Medium | Unplanned | Night | Preventive Maintenance | Closed | February | Q1 | Dry Season
NPT00293 | 23-02-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 6 | 115000 | 90381 | 205381 | Moderate | $100K - $250K | Medium | Unplanned | Night | Run Fishing Tools | Open | February | Q1 | Dry Season
NPT00294 | 05-03-2024 | W021 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6222 | 19097 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | 2 | 38333 | 78798 | 117131 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | March | Q1 | Dry Season
NPT00295 | 17-05-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Hole Cleaning | Bit Wear | Operator | 12 | 237500 | 199439 | 436939 | Major | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | May | Q2 | Long Rainy Season
NPT00296 | 18-05-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Strong Wind | Weather | 2 | 39583 | 63322 | 102905 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | May | Q2 | Long Rainy Season
NPT00297 | 20-05-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | High Waves | Weather | 6 | 118750 | 138221 | 256971 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | In Progress | May | Q2 | Long Rainy Season
NPT00298 | 03-06-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 158333 | 298315 | 456648 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Open | June | Q2 | Long Rainy Season
NPT00299 | 04-06-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Strong Wind | Weather | 2 | 39583 | 32358 | 71941 | Minor | < $100K | Low | Unplanned | Day | Resume Operations | In Progress | June | Q2 | Long Rainy Season
NPT00300 | 23-06-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | Strong Wind | Marine Operations | 4 | 79166 | 120835 | 200001 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | In Progress | June | Q2 | Long Rainy Season
NPT00301 | 24-06-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Weather | 2 | 39583 | 52686 | 92269 | Minor | < $100K | Low | Unplanned | Day | Suspend Operations | Closed | June | Q2 | Long Rainy Season
NPT00302 | 27-06-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | Heavy Rain | Marine Operations | 4 | 79166 | 104081 | 183247 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | Closed | June | Q2 | Long Rainy Season
NPT00303 | 01-07-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | 6 | 118750 | 120114 | 238864 | Moderate | $100K - $250K | Medium | Unplanned | Night | Expedite Shipment | In Progress | July | Q3 | Long Rainy Season
NPT00304 | 10-07-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Waiting on Materials | Port Congestion | Procurement | 8 | 158333 | 193285 | 351618 | Moderate | $250K - $500K | Medium | Unplanned | Night | Expedite Shipment | Open | July | Q3 | Long Rainy Season
NPT00305 | 24-07-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Bit Wear | Operator | 6 | 118750 | 59595 | 178345 | Moderate | $100K - $250K | Medium | Unplanned | Day | Adjust Drilling Parameters | In Progress | July | Q3 | Long Rainy Season
NPT00306 | 26-07-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Poor Visibility | Strong Wind | Marine Operations | 12 | 237500 | 561306 | 798806 | Major | $500K - $1M | Medium | Planned | Day | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00307 | 29-07-2024 | W022 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6319 | 19737 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Heavy Rain | Marine Operations | 2 | 39583 | 34235 | 73818 | Minor | < $100K | Low | Unplanned | Day | Wait on Weather | Open | July | Q3 | Long Rainy Season
NPT00308 | 18-02-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | 4 | 81666 | 189343 | 271009 | Minor | $250K - $500K | Low | Unplanned | Day | Repair Component | Closed | February | Q1 | Dry Season
NPT00309 | 27-02-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 6 | 122500 | 274722 | 397222 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | February | Q1 | Dry Season
NPT00310 | 02-03-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | 6 | 122500 | 257837 | 380337 | Moderate | $250K - $500K | Medium | Unplanned | Day | Expedite Shipment | Closed | March | Q1 | Dry Season
NPT00311 | 04-03-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 0 | 0 | 1 | 1 | 0.75 | 75 | Personnel | Crew Change | Medical Emergency | Medical Team | 18 | 367500 | 774135 | 1141635 | Major | > $1M | High | Unplanned | Day | Medical Clearance | Closed | March | Q1 | Dry Season
NPT00312 | 07-03-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Bit Wear | Mud Engineering | 4 | 81666 | 55231 | 136897 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | In Progress | March | Q1 | Dry Season
NPT00313 | 24-03-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Lightning | Storm | Weather | 12 | 245000 | 431874 | 676874 | Major | $500K - $1M | Medium | Planned | Night | Resume Operations | Closed | March | Q1 | Dry Season
NPT00314 | 31-03-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 4 | 81666 | 112807 | 194473 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Closed | March | Q1 | Dry Season
NPT00315 | 04-04-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Medical Evacuation | Medical Emergency | HR | 6 | 122500 | 253590 | 376090 | Moderate | $250K - $500K | Medium | Unplanned | Day | Crew Replacement | Closed | April | Q2 | Dry Season
NPT00316 | 19-04-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | 2 | 40833 | 34121 | 74954 | Minor | < $100K | Low | Unplanned | Night | Repair Component | Closed | April | Q2 | Dry Season
NPT00317 | 20-04-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | 8 | 163333 | 324715 | 488048 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Open | April | Q2 | Dry Season
NPT00318 | 25-04-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | 2 | 40833 | 86980 | 127813 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | Closed | April | Q2 | Dry Season
NPT00319 | 29-04-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | 4 | 81666 | 185627 | 267293 | Minor | $250K - $500K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | April | Q2 | Dry Season
NPT00320 | 07-05-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | 4 | 81666 | 71396 | 153062 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Open | May | Q2 | Long Rainy Season
NPT00321 | 16-05-2024 | W023 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6097 | 21363 | 0 | 0 | 0 | 0 | 1 | 1 | 0.17 | 16.7 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | 4 | 81666 | 60840 | 142506 | Minor | $100K - $250K | Low | Unplanned | Day | Medical Clearance | Closed | May | Q2 | Long Rainy Season
NPT00322 | 21-01-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | 8 | 153333 | 152401 | 305734 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Closed | January | Q1 | Short Rainy Season
NPT00323 | 25-01-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 12 | 230000 | 245724 | 475724 | Major | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | In Progress | January | Q1 | Short Rainy Season
NPT00324 | 09-02-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | High Waves | Marine Operations | 4 | 76666 | 44941 | 121607 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | February | Q1 | Dry Season
NPT00325 | 13-02-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 4 | 76666 | 67775 | 144441 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | February | Q1 | Dry Season
NPT00326 | 14-02-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Materials | Material Shortage | Procurement | 12 | 230000 | 541101 | 771101 | Major | $500K - $1M | Medium | Unplanned | Night | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00327 | 08-03-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Differential Sticking | Operator | 4 | 76666 | 70081 | 146747 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | March | Q1 | Dry Season
NPT00328 | 16-03-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | 2 | 38333 | 86372 | 124705 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Open | March | Q1 | Dry Season
NPT00329 | 22-03-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | 2 | 38333 | 86067 | 124400 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | In Progress | March | Q1 | Dry Season
NPT00330 | 23-03-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | 6 | 115000 | 184818 | 299818 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | March | Q1 | Dry Season
NPT00331 | 04-04-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Formation Instability | Operator | 2 | 38333 | 66638 | 104971 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | Closed | April | Q2 | Dry Season
NPT00332 | 08-04-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Differential Sticking | Operator | 4 | 76666 | 132348 | 209014 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | April | Q2 | Dry Season
NPT00333 | 18-04-2024 | W024 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5295 | 20685 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | 8 | 153333 | 260743 | 414076 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Closed | April | Q2 | Dry Season
NPT00334 | 16-07-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 6 | 122500 | 144551 | 267051 | Moderate | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | July | Q3 | Long Rainy Season
NPT00335 | 18-07-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Formation Instability | Mud Engineering | 4 | 81666 | 144601 | 226267 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | Closed | July | Q3 | Long Rainy Season
NPT00336 | 21-07-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Storm | Weather | 4 | 81666 | 127004 | 208670 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00337 | 23-07-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 6 | 122500 | 154285 | 276785 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | In Progress | July | Q3 | Long Rainy Season
NPT00338 | 10-08-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Lightning | Weather | 2 | 40833 | 43926 | 84759 | Minor | < $100K | Low | Planned | Night | Suspend Operations | Closed | August | Q3 | Long Rainy Season
NPT00339 | 16-08-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | 4 | 81666 | 86786 | 168452 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | In Progress | August | Q3 | Long Rainy Season
NPT00340 | 23-08-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Strong Wind | Weather | 6 | 122500 | 265620 | 388120 | Moderate | $250K - $500K | Medium | Unplanned | Day | Resume Operations | Open | August | Q3 | Long Rainy Season
NPT00341 | 24-08-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | 2 | 40833 | 48689 | 89522 | Minor | < $100K | Low | Unplanned | Night | Repair Component | Closed | August | Q3 | Long Rainy Season
NPT00342 | 12-09-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Storm | Marine Operations | 2 | 40833 | 62499 | 103332 | Minor | $100K - $250K | Low | Planned | Day | Suspend Operations | In Progress | September | Q3 | Dry Season
NPT00343 | 13-09-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | 12 | 245000 | 539466 | 784466 | Major | $500K - $1M | Medium | Unplanned | Day | Condition Hole | Closed | September | Q3 | Dry Season
NPT00344 | 15-09-2023 | W025 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5551 | 15854 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 6 | 122500 | 138722 | 261222 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | In Progress | September | Q3 | Dry Season
NPT00345 | 04-10-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | High Waves | Strong Wind | Marine Operations | 12 | 245000 | 580843 | 825843 | Major | $500K - $1M | Medium | Unplanned | Night | Suspend Operations | In Progress | October | Q4 | Dry Season
NPT00346 | 18-10-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 1 | 0 | 0 | 0 | 1 | 1 | 100 | Weather | Heavy Rain | Storm | Weather | 24 | 490000 | 614657 | 1104657 | Critical | > $1M | High | Unplanned | Night | Resume Operations | Closed | October | Q4 | Dry Season
NPT00347 | 01-11-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | 4 | 81666 | 185274 | 266940 | Minor | $250K - $500K | Low | Unplanned | Day | OEM Inspection | Closed | November | Q4 | Short Rainy Season
NPT00348 | 09-11-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Bit Failure | Bit Wear | Mud Engineering | 8 | 163333 | 234179 | 397512 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | November | Q4 | Short Rainy Season
NPT00349 | 22-11-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 163333 | 249120 | 412453 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | November | Q4 | Short Rainy Season
NPT00350 | 28-11-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 2 | 40833 | 48430 | 89263 | Minor | < $100K | Low | Unplanned | Day | OEM Inspection | Closed | November | Q4 | Short Rainy Season
NPT00351 | 06-12-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | 2 | 40833 | 31395 | 72228 | Minor | < $100K | Low | Planned | Day | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00352 | 10-12-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | 6 | 122500 | 186115 | 308615 | Moderate | $250K - $500K | Medium | Unplanned | Night | Mobilize Supply Vessel | In Progress | December | Q4 | Short Rainy Season
NPT00353 | 15-12-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 0 | 0 | 0 | 1 | 1 | 0.75 | 75 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | 18 | 367500 | 388821 | 756321 | Major | $500K - $1M | High | Unplanned | Night | Crew Replacement | In Progress | December | Q4 | Short Rainy Season
NPT00354 | 18-12-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 4 | 81666 | 55037 | 136703 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | December | Q4 | Short Rainy Season
NPT00355 | 25-12-2023 | W026 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6143 | 20855 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Materials | Customs Clearance | Procurement | 2 | 40833 | 41456 | 82289 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Open | December | Q4 | Short Rainy Season
NPT00356 | 08-07-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | 18 | 345000 | 565252 | 910252 | Major | $500K - $1M | High | Unplanned | Night | Adjust Drilling Parameters | In Progress | July | Q3 | Long Rainy Season
NPT00357 | 13-07-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Heavy Rain | Marine Operations | 2 | 38333 | 72075 | 110408 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00358 | 20-07-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | High Waves | Marine Operations | 4 | 76666 | 85784 | 162450 | Minor | $100K - $250K | Low | Unplanned | Day | Wait on Weather | In Progress | July | Q3 | Long Rainy Season
NPT00359 | 30-07-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 8 | 153333 | 335435 | 488768 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | Open | July | Q3 | Long Rainy Season
NPT00360 | 02-08-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | 6 | 115000 | 112412 | 227412 | Moderate | $100K - $250K | Medium | Unplanned | Day | Mobilize Supply Vessel | In Progress | August | Q3 | Long Rainy Season
NPT00361 | 13-08-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Lightning | High Waves | Weather | 12 | 230000 | 258903 | 488903 | Major | $250K - $500K | Medium | Unplanned | Day | Suspend Operations | Closed | August | Q3 | Long Rainy Season
NPT00362 | 14-08-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | 2 | 38333 | 85268 | 123601 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | In Progress | August | Q3 | Long Rainy Season
NPT00363 | 19-08-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | 4 | 76666 | 38651 | 115317 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | August | Q3 | Long Rainy Season
NPT00364 | 27-08-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Storm | Weather | 2 | 38333 | 61637 | 99970 | Minor | < $100K | Low | Unplanned | Day | Suspend Operations | Closed | August | Q3 | Long Rainy Season
NPT00365 | 06-09-2023 | W027 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5863 | 22392 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | 8 | 153333 | 342295 | 495628 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | Open | September | Q3 | Dry Season
NPT00366 | 09-04-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 6 | 115000 | 87189 | 202189 | Moderate | $100K - $250K | Medium | Unplanned | Night | Run Fishing Tools | Closed | April | Q2 | Dry Season
NPT00367 | 17-04-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Storm | Marine Operations | 4 | 76666 | 169923 | 246589 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | April | Q2 | Dry Season
NPT00368 | 25-04-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | 8 | 153333 | 276056 | 429389 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | In Progress | April | Q2 | Dry Season
NPT00369 | 29-04-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Strong Wind | Marine Operations | 2 | 38333 | 68316 | 106649 | Minor | $100K - $250K | Low | Unplanned | Day | Resume Operations | Closed | April | Q2 | Dry Season
NPT00370 | 02-05-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 0 | 0 | 1 | 1 | 0.17 | 16.7 | Personnel | Crew Change | Training Requirement | Rig Management | 4 | 76666 | 79447 | 156113 | Minor | $100K - $250K | Low | Unplanned | Night | Crew Replacement | Closed | May | Q2 | Long Rainy Season
NPT00371 | 04-05-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | 12 | 230000 | 150405 | 380405 | Major | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | May | Q2 | Long Rainy Season
NPT00372 | 14-05-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | 4 | 76666 | 154351 | 231017 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Open | May | Q2 | Long Rainy Season
NPT00373 | 19-05-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | 2 | 38333 | 40944 | 79277 | Minor | < $100K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00374 | 03-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Lightning | Marine Operations | 6 | 115000 | 249425 | 364425 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00375 | 04-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Formation Instability | Operator | 4 | 76666 | 159300 | 235966 | Minor | $100K - $250K | Low | Planned | Night | Condition Hole | In Progress | June | Q2 | Long Rainy Season
NPT00376 | 08-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Heavy Rain | Weather | 6 | 115000 | 194047 | 309047 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00377 | 22-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | 18 | 345000 | 380594 | 725594 | Major | $500K - $1M | High | Unplanned | Night | Adjust Drilling Parameters | Closed | June | Q2 | Long Rainy Season
NPT00378 | 25-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | 2 | 38333 | 83567 | 121900 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Closed | June | Q2 | Long Rainy Season
NPT00379 | 27-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | Storm | Weather | 4 | 76666 | 41042 | 117708 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Open | June | Q2 | Long Rainy Season
NPT00380 | 28-06-2024 | W028 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6481 | 21528 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 8 | 153333 | 283449 | 436782 | Moderate | $250K - $500K | Medium | Unplanned | Day | Preventive Maintenance | Closed | June | Q2 | Long Rainy Season
NPT00381 | 11-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Differential Sticking | Operator | 2 | 38333 | 53610 | 91943 | Minor | < $100K | Low | Planned | Night | Increase Mud Weight | Open | November | Q4 | Short Rainy Season
NPT00382 | 19-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | 4 | 76666 | 74370 | 151036 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Closed | November | Q4 | Short Rainy Season
NPT00383 | 23-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | 8 | 153333 | 279943 | 433276 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | In Progress | November | Q4 | Short Rainy Season
NPT00384 | 28-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Crew Change | Medical Emergency | HR | 6 | 115000 | 117452 | 232452 | Moderate | $100K - $250K | Medium | Unplanned | Night | Medical Clearance | In Progress | November | Q4 | Short Rainy Season
NPT00385 | 29-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Strong Wind | Marine Operations | 2 | 38333 | 24538 | 62871 | Minor | < $100K | Low | Unplanned | Night | Wait on Weather | In Progress | November | Q4 | Short Rainy Season
NPT00386 | 30-11-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | 8 | 153333 | 130015 | 283348 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Closed | November | Q4 | Short Rainy Season
NPT00387 | 03-12-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | Lightning | Marine Operations | 6 | 115000 | 262434 | 377434 | Moderate | $250K - $500K | Medium | Unplanned | Day | Resume Operations | Closed | December | Q4 | Short Rainy Season
NPT00388 | 10-12-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | 4 | 76666 | 185391 | 262057 | Minor | $250K - $500K | Low | Unplanned | Night | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00389 | 15-12-2023 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 4 | 76666 | 148435 | 225101 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Closed | December | Q4 | Short Rainy Season
NPT00390 | 22-01-2024 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Strong Wind | High Waves | Marine Operations | 4 | 76666 | 100636 | 177302 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | In Progress | January | Q1 | Short Rainy Season
NPT00391 | 27-01-2024 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Medical Evacuation | Training Requirement | HR | 2 | 38333 | 37984 | 76317 | Minor | < $100K | Low | Unplanned | Day | Safety Briefing | Closed | January | Q1 | Short Rainy Season
NPT00392 | 02-02-2024 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Heavy Rain | Weather | 6 | 115000 | 152059 | 267059 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | February | Q1 | Dry Season
NPT00393 | 04-02-2024 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Materials | Material Shortage | Procurement | 6 | 115000 | 239219 | 354219 | Moderate | $250K - $500K | Medium | Unplanned | Day | Expedite Shipment | In Progress | February | Q1 | Dry Season
NPT00394 | 06-02-2024 | W029 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5854 | 18474 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Differential Sticking | Operator | 8 | 153333 | 201314 | 354647 | Moderate | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | February | Q1 | Dry Season
NPT00395 | 25-01-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 0 | 0 | 1 | 1 | 0.33 | 33.3 | Personnel | Safety Stand Down | Training Requirement | Rig Management | 8 | 153333 | 91956 | 245289 | Moderate | $100K - $250K | Medium | Unplanned | Day | Medical Clearance | Closed | January | Q1 | Short Rainy Season
NPT00396 | 26-01-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 2 | 38333 | 20240 | 58573 | Minor | < $100K | Low | Unplanned | Day | Run Fishing Tools | In Progress | January | Q1 | Short Rainy Season
NPT00397 | 31-01-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 2 | 38333 | 56371 | 94704 | Minor | < $100K | Low | Unplanned | Day | Condition Hole | Closed | January | Q1 | Short Rainy Season
NPT00398 | 01-02-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Formation Instability | Operator | 6 | 115000 | 74266 | 189266 | Moderate | $100K - $250K | Medium | Unplanned | Night | Increase Mud Weight | Closed | February | Q1 | Dry Season
NPT00399 | 10-02-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | 4 | 76666 | 52243 | 128909 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Open | February | Q1 | Dry Season
NPT00400 | 13-02-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | 6 | 115000 | 233024 | 348024 | Moderate | $250K - $500K | Medium | Unplanned | Day | Expedite Shipment | Closed | February | Q1 | Dry Season
NPT00401 | 17-02-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | 8 | 153333 | 363755 | 517088 | Moderate | $500K - $1M | Medium | Unplanned | Day | Replace Equipment | Closed | February | Q1 | Dry Season
NPT00402 | 08-03-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | 2 | 38333 | 43940 | 82273 | Minor | < $100K | Low | Unplanned | Day | OEM Inspection | Open | March | Q1 | Dry Season
NPT00403 | 21-03-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | High Waves | High Waves | Marine Operations | 12 | 230000 | 429330 | 659330 | Major | $500K - $1M | Medium | Unplanned | Day | Resume Operations | Closed | March | Q1 | Dry Season
NPT00404 | 30-03-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | 12 | 230000 | 418094 | 648094 | Major | $500K - $1M | Medium | Unplanned | Day | Preventive Maintenance | Closed | March | Q1 | Dry Season
NPT00405 | 03-04-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 8 | 153333 | 123054 | 276387 | Moderate | $250K - $500K | Medium | Unplanned | Day | Preventive Maintenance | Closed | April | Q2 | Dry Season
NPT00406 | 08-04-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 38333 | 94383 | 132716 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Closed | April | Q2 | Dry Season
NPT00407 | 10-04-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | 6 | 115000 | 69074 | 184074 | Moderate | $100K - $250K | Medium | Unplanned | Night | Expedite Shipment | Closed | April | Q2 | Dry Season
NPT00408 | 11-04-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | 8 | 153333 | 169026 | 322359 | Moderate | $250K - $500K | Medium | Unplanned | Night | Repair Component | In Progress | April | Q2 | Dry Season
NPT00409 | 18-04-2023 | W030 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6163 | 20757 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | 4 | 76666 | 173634 | 250300 | Minor | $250K - $500K | Low | Unplanned | Night | OEM Inspection | Open | April | Q2 | Dry Season
NPT00410 | 12-09-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Heavy Rain | Weather | 4 | 76666 | 191641 | 268307 | Minor | $250K - $500K | Low | Unplanned | Day | Resume Operations | In Progress | September | Q3 | Dry Season
NPT00411 | 13-09-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Differential Sticking | Operator | 2 | 38333 | 69018 | 107351 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Closed | September | Q3 | Dry Season
NPT00412 | 14-09-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 0 | 0 | 1 | 1 | 0.17 | 16.7 | Personnel | Safety Stand Down | Training Requirement | Rig Management | 4 | 76666 | 99814 | 176480 | Minor | $100K - $250K | Low | Planned | Day | Medical Clearance | In Progress | September | Q3 | Dry Season
NPT00413 | 26-09-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | 4 | 76666 | 115177 | 191843 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Open | September | Q3 | Dry Season
NPT00414 | 11-10-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | 4 | 76666 | 44040 | 120706 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Closed | October | Q4 | Dry Season
NPT00415 | 21-10-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | 4 | 76666 | 128931 | 205597 | Minor | $100K - $250K | Low | Unplanned | Day | Air Freight Materials | Closed | October | Q4 | Dry Season
NPT00416 | 06-11-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Strong Wind | Weather | 4 | 76666 | 41049 | 117715 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | Closed | November | Q4 | Short Rainy Season
NPT00417 | 08-11-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 4 | 76666 | 93803 | 170469 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | November | Q4 | Short Rainy Season
NPT00418 | 17-11-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Formation Instability | Operator | 4 | 76666 | 100999 | 177665 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | November | Q4 | Short Rainy Season
NPT00419 | 19-11-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | 2 | 38333 | 54487 | 92820 | Minor | < $100K | Low | Unplanned | Day | Replace Equipment | In Progress | November | Q4 | Short Rainy Season
NPT00420 | 26-11-2023 | W031 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6029 | 20249 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 100 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 24 | 460000 | 943802 | 1403802 | Critical | > $1M | High | Unplanned | Day | Replace Equipment | In Progress | November | Q4 | Short Rainy Season
NPT00421 | 16-07-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | 2 | 40833 | 99458 | 140291 | Minor | $100K - $250K | Low | Planned | Night | Expedite Shipment | Closed | July | Q3 | Long Rainy Season
NPT00422 | 20-07-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Heavy Rain | Lightning | Marine Operations | 8 | 163333 | 288692 | 452025 | Moderate | $250K - $500K | Medium | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00423 | 21-07-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | Strong Wind | Weather | 6 | 122500 | 75891 | 198391 | Moderate | $100K - $250K | Medium | Unplanned | Day | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00424 | 27-07-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | High Waves | Marine Operations | 4 | 81666 | 171063 | 252729 | Minor | $250K - $500K | Low | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00425 | 30-07-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Lightning | Weather | 4 | 81666 | 184832 | 266498 | Minor | $250K - $500K | Low | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00426 | 04-08-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | 6 | 122500 | 76832 | 199332 | Moderate | $100K - $250K | Medium | Unplanned | Night | Repair Component | Closed | August | Q3 | Long Rainy Season
NPT00427 | 14-08-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | Lightning | Strong Wind | Weather | 18 | 367500 | 445857 | 813357 | Major | $500K - $1M | High | Unplanned | Night | Suspend Operations | Closed | August | Q3 | Long Rainy Season
NPT00428 | 01-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | 8 | 163333 | 152781 | 316114 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | September | Q3 | Dry Season
NPT00429 | 03-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Storm | Marine Operations | 2 | 40833 | 27339 | 68172 | Minor | < $100K | Low | Unplanned | Day | Suspend Operations | Open | September | Q3 | Dry Season
NPT00430 | 09-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | 6 | 122500 | 301536 | 424036 | Moderate | $250K - $500K | Medium | Unplanned | Night | Air Freight Materials | Closed | September | Q3 | Dry Season
NPT00431 | 15-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 0 | 0 | 0 | 1 | 1 | 0.17 | 16.7 | Personnel | Safety Stand Down | Training Requirement | Medical Team | 4 | 81666 | 94096 | 175762 | Minor | $100K - $250K | Low | Unplanned | Day | Medical Clearance | In Progress | September | Q3 | Dry Season
NPT00432 | 20-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 6 | 122500 | 231858 | 354358 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | September | Q3 | Dry Season
NPT00433 | 29-09-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 2 | 40833 | 33061 | 73894 | Minor | < $100K | Low | Unplanned | Day | Repair Component | Closed | September | Q3 | Dry Season
NPT00434 | 06-10-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | 8 | 163333 | 267513 | 430846 | Moderate | $250K - $500K | Medium | Unplanned | Day | Repair Component | Closed | October | Q4 | Dry Season
NPT00435 | 10-10-2024 | W032 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6538 | 20172 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Formation Instability | Mud Engineering | 2 | 40833 | 45052 | 85885 | Minor | < $100K | Low | Unplanned | Night | Condition Hole | Closed | October | Q4 | Dry Season
NPT00436 | 22-04-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | 6 | 115000 | 177855 | 292855 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | April | Q2 | Dry Season
NPT00437 | 23-04-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | 12 | 230000 | 161849 | 391849 | Major | $250K - $500K | Medium | Unplanned | Day | Preventive Maintenance | Open | April | Q2 | Dry Season
NPT00438 | 29-04-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Storm | Marine Operations | 2 | 38333 | 72796 | 111129 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | Closed | April | Q2 | Dry Season
NPT00439 | 01-05-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 4 | 76666 | 107302 | 183968 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Open | May | Q2 | Long Rainy Season
NPT00440 | 12-05-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | 6 | 115000 | 225265 | 340265 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Open | May | Q2 | Long Rainy Season
NPT00441 | 19-05-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | 4 | 76666 | 165696 | 242362 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | Open | May | Q2 | Long Rainy Season
NPT00442 | 24-05-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | High Waves | Marine Operations | 2 | 38333 | 41966 | 80299 | Minor | < $100K | Low | Unplanned | Day | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00443 | 07-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.5 | 50 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 12 | 230000 | 219568 | 449568 | Major | $250K - $500K | Medium | Unplanned | Day | Repair Component | In Progress | June | Q2 | Long Rainy Season
NPT00444 | 12-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | 2 | 38333 | 82613 | 120946 | Minor | $100K - $250K | Low | Unplanned | Night | Preventive Maintenance | Open | June | Q2 | Long Rainy Season
NPT00445 | 15-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Poor Visibility | Lightning | Marine Operations | 8 | 153333 | 182342 | 335675 | Moderate | $250K - $500K | Medium | Unplanned | Day | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00446 | 19-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Strong Wind | High Waves | Weather | 8 | 153333 | 347209 | 500542 | Moderate | $500K - $1M | Medium | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00447 | 24-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | High Waves | Marine Operations | 2 | 38333 | 65027 | 103360 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Open | June | Q2 | Long Rainy Season
NPT00448 | 26-06-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | 12 | 230000 | 407608 | 637608 | Major | $500K - $1M | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | June | Q2 | Long Rainy Season
NPT00449 | 03-07-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | High Waves | Marine Operations | 4 | 76666 | 124855 | 201521 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00450 | 06-07-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | 4 | 76666 | 55282 | 131948 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Open | July | Q3 | Long Rainy Season
NPT00451 | 16-07-2024 | W033 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5996 | 16707 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | 2 | 38333 | 81222 | 119555 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | Closed | July | Q3 | Long Rainy Season
NPT00452 | 04-03-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Fishing Operation | Formation Instability | Operator | 18 | 356250 | 822305 | 1178555 | Major | > $1M | High | Unplanned | Day | Adjust Drilling Parameters | Closed | March | Q1 | Dry Season
NPT00453 | 12-03-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | 4 | 79166 | 107969 | 187135 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Closed | March | Q1 | Dry Season
NPT00454 | 16-03-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Formation Instability | Mud Engineering | 4 | 79166 | 76620 | 155786 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | March | Q1 | Dry Season
NPT00455 | 01-04-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | 18 | 356250 | 284572 | 640822 | Major | $500K - $1M | High | Unplanned | Day | Repair Component | Closed | April | Q2 | Dry Season
NPT00456 | 10-04-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | High Waves | Lightning | Marine Operations | 8 | 158333 | 332867 | 491200 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | April | Q2 | Dry Season
NPT00457 | 13-04-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 4 | 79166 | 55237 | 134403 | Minor | $100K - $250K | Low | Unplanned | Night | Preventive Maintenance | Closed | April | Q2 | Dry Season
NPT00458 | 28-04-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Storm | Weather | 4 | 79166 | 124715 | 203881 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | Closed | April | Q2 | Dry Season
NPT00459 | 29-04-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | 2 | 39583 | 57298 | 96881 | Minor | < $100K | Low | Unplanned | Day | Repair Component | Closed | April | Q2 | Dry Season
NPT00460 | 01-05-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | 4 | 79166 | 187319 | 266485 | Minor | $250K - $500K | Low | Unplanned | Day | Air Freight Materials | Closed | May | Q2 | Long Rainy Season
NPT00461 | 08-05-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | 4 | 79166 | 45728 | 124894 | Minor | $100K - $250K | Low | Unplanned | Night | OEM Inspection | Closed | May | Q2 | Long Rainy Season
NPT00462 | 18-05-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Boat | Material Shortage | Procurement | 2 | 39583 | 75663 | 115246 | Minor | $100K - $250K | Low | Unplanned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00463 | 28-05-2023 | W034 | R001 | 13 | Noble Bob Douglas | Drillship | Noble | Active | 475000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 6737 | 17777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Bit Wear | Operator | 2 | 39583 | 22675 | 62258 | Minor | < $100K | Low | Unplanned | Night | Run Fishing Tools | Open | May | Q2 | Long Rainy Season
NPT00464 | 26-05-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Stuck Pipe | Differential Sticking | Operator | 18 | 360000 | 208849 | 568849 | Major | $500K - $1M | High | Unplanned | Night | Run Fishing Tools | Closed | May | Q2 | Long Rainy Season
NPT00465 | 16-06-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Heavy Rain | Weather | 6 | 120000 | 88739 | 208739 | Moderate | $100K - $250K | Medium | Unplanned | Day | Suspend Operations | Closed | June | Q2 | Long Rainy Season
NPT00466 | 25-06-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 2 | 40000 | 69853 | 109853 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | June | Q2 | Long Rainy Season
NPT00467 | 26-06-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Strong Wind | Weather | 6 | 120000 | 243625 | 363625 | Moderate | $250K - $500K | Medium | Unplanned | Night | Wait on Weather | Closed | June | Q2 | Long Rainy Season
NPT00468 | 30-06-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Differential Sticking | Mud Engineering | 2 | 40000 | 30168 | 70168 | Minor | < $100K | Low | Unplanned | Night | Run Fishing Tools | Closed | June | Q2 | Long Rainy Season
NPT00469 | 04-07-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | High Waves | Strong Wind | Marine Operations | 18 | 360000 | 200297 | 560297 | Major | $500K - $1M | High | Unplanned | Day | Resume Operations | Open | July | Q3 | Long Rainy Season
NPT00470 | 15-07-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | 2 | 40000 | 58559 | 98559 | Minor | < $100K | Low | Unplanned | Night | Condition Hole | Closed | July | Q3 | Long Rainy Season
NPT00471 | 16-07-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Strong Wind | Heavy Rain | Weather | 12 | 240000 | 122437 | 362437 | Major | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | Closed | July | Q3 | Long Rainy Season
NPT00472 | 25-07-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Differential Sticking | Operator | 6 | 120000 | 273652 | 393652 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Closed | July | Q3 | Long Rainy Season
NPT00473 | 06-08-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 12 | 240000 | 291067 | 531067 | Major | $500K - $1M | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | August | Q3 | Long Rainy Season
NPT00474 | 07-08-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | 2 | 40000 | 38248 | 78248 | Minor | < $100K | Low | Unplanned | Night | Mobilize Supply Vessel | Closed | August | Q3 | Long Rainy Season
NPT00475 | 19-08-2024 | W035 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5908 | 20791 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 6 | 120000 | 130403 | 250403 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | August | Q3 | Long Rainy Season
NPT00476 | 16-11-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Boat | Customs Clearance | Procurement | 2 | 38333 | 93792 | 132125 | Minor | $100K - $250K | Low | Unplanned | Day | Air Freight Materials | Closed | November | Q4 | Short Rainy Season
NPT00477 | 26-11-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 4 | 76666 | 153896 | 230562 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | In Progress | November | Q4 | Short Rainy Season
NPT00478 | 29-11-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Formation Instability | Directional Drilling | 6 | 115000 | 253781 | 368781 | Moderate | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | November | Q4 | Short Rainy Season
NPT00479 | 05-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | 4 | 76666 | 152544 | 229210 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Closed | December | Q4 | Short Rainy Season
NPT00480 | 06-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 18 | 345000 | 776256 | 1121256 | Major | > $1M | High | Unplanned | Day | Repair Component | Closed | December | Q4 | Short Rainy Season
NPT00481 | 08-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Stuck Pipe | Differential Sticking | Operator | 2 | 38333 | 84839 | 123172 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00482 | 15-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | 6 | 115000 | 202496 | 317496 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | Closed | December | Q4 | Short Rainy Season
NPT00483 | 19-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 4 | 76666 | 78814 | 155480 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | December | Q4 | Short Rainy Season
NPT00484 | 20-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | 4 | 76666 | 112293 | 188959 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00485 | 22-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | 2 | 38333 | 91400 | 129733 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Closed | December | Q4 | Short Rainy Season
NPT00486 | 26-12-2024 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | 18 | 345000 | 526177 | 871177 | Major | $500K - $1M | High | Unplanned | Night | Preventive Maintenance | Closed | December | Q4 | Short Rainy Season
NPT00487 | 02-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Differential Sticking | Operator | 6 | 115000 | 111365 | 226365 | Moderate | $100K - $250K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00488 | 11-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | 6 | 115000 | 150140 | 265140 | Moderate | $250K - $500K | Medium | Unplanned | Day | Run Fishing Tools | Closed | January | Q1 | Short Rainy Season
NPT00489 | 13-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Lightning | Marine Operations | 6 | 115000 | 123339 | 238339 | Moderate | $100K - $250K | Medium | Unplanned | Day | Resume Operations | Closed | January | Q1 | Short Rainy Season
NPT00490 | 16-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 2 | 38333 | 67158 | 105491 | Minor | $100K - $250K | Low | Planned | Night | Air Freight Materials | Closed | January | Q1 | Short Rainy Season
NPT00491 | 24-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | 4 | 76666 | 67923 | 144589 | Minor | $100K - $250K | Low | Unplanned | Night | Replace Equipment | In Progress | January | Q1 | Short Rainy Season
NPT00492 | 25-01-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | 4 | 76666 | 85809 | 162475 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | In Progress | January | Q1 | Short Rainy Season
NPT00493 | 01-02-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | 4 | 76666 | 58910 | 135576 | Minor | $100K - $250K | Low | Unplanned | Night | Mobilize Supply Vessel | Open | February | Q1 | Dry Season
NPT00494 | 08-02-2025 | W036 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5900 | 16733 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 6 | 115000 | 150582 | 265582 | Moderate | $250K - $500K | Medium | Unplanned | Night | Run Fishing Tools | Closed | February | Q1 | Dry Season
NPT00495 | 02-05-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 4 | 76666 | 106832 | 183498 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | May | Q2 | Long Rainy Season
NPT00496 | 04-05-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Lightning | Marine Operations | 4 | 76666 | 55100 | 131766 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | Closed | May | Q2 | Long Rainy Season
NPT00497 | 09-05-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 4 | 76666 | 159831 | 236497 | Minor | $100K - $250K | Low | Unplanned | Night | OEM Inspection | In Progress | May | Q2 | Long Rainy Season
NPT00498 | 07-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Poor Visibility | Strong Wind | Weather | 8 | 153333 | 204824 | 358157 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | Closed | June | Q2 | Long Rainy Season
NPT00499 | 14-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 4 | 76666 | 126288 | 202954 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | In Progress | June | Q2 | Long Rainy Season
NPT00500 | 16-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | 12 | 230000 | 132340 | 362340 | Major | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Closed | June | Q2 | Long Rainy Season
NPT00501 | 19-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | 8 | 153333 | 197597 | 350930 | Moderate | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | June | Q2 | Long Rainy Season
NPT00502 | 20-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | 4 | 76666 | 67775 | 144441 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | Open | June | Q2 | Long Rainy Season
NPT00503 | 24-06-2024 | W037 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5806 | 20535 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 100 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | 24 | 460000 | 763810 | 1223810 | Critical | > $1M | High | Unplanned | Night | Expedite Shipment | In Progress | June | Q2 | Long Rainy Season
NPT00504 | 08-12-2024 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Poor Visibility | Lightning | Marine Operations | 2 | 40833 | 41869 | 82702 | Minor | < $100K | Low | Unplanned | Day | Wait on Weather | Closed | December | Q4 | Short Rainy Season
NPT00505 | 15-12-2024 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | 8 | 163333 | 237483 | 400816 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | Closed | December | Q4 | Short Rainy Season
NPT00506 | 17-12-2024 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Formation Instability | Operator | 4 | 81666 | 183089 | 264755 | Minor | $250K - $500K | Low | Unplanned | Night | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00507 | 27-12-2024 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 6 | 122500 | 244320 | 366820 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | December | Q4 | Short Rainy Season
NPT00508 | 31-12-2024 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Waiting on Materials | Port Congestion | Procurement | 2 | 40833 | 42029 | 82862 | Minor | < $100K | Low | Unplanned | Night | Air Freight Materials | Closed | December | Q4 | Short Rainy Season
NPT00509 | 02-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | 4 | 81666 | 55857 | 137523 | Minor | $100K - $250K | Low | Planned | Day | OEM Inspection | Open | January | Q1 | Short Rainy Season
NPT00510 | 07-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | 6 | 122500 | 88110 | 210610 | Moderate | $100K - $250K | Medium | Planned | Day | Replace Equipment | In Progress | January | Q1 | Short Rainy Season
NPT00511 | 10-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | High Waves | Heavy Rain | Marine Operations | 2 | 40833 | 72180 | 113013 | Minor | $100K - $250K | Low | Planned | Night | Resume Operations | Open | January | Q1 | Short Rainy Season
NPT00512 | 14-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | 4 | 81666 | 161966 | 243632 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | In Progress | January | Q1 | Short Rainy Season
NPT00513 | 19-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Storm | Marine Operations | 4 | 81666 | 141093 | 222759 | Minor | $100K - $250K | Low | Unplanned | Night | Resume Operations | In Progress | January | Q1 | Short Rainy Season
NPT00514 | 20-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Marine Operations | 6 | 122500 | 237410 | 359910 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | January | Q1 | Short Rainy Season
NPT00515 | 26-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Lightning | Marine Operations | 4 | 81666 | 195140 | 276806 | Minor | $250K - $500K | Low | Planned | Night | Resume Operations | Open | January | Q1 | Short Rainy Season
NPT00516 | 30-01-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Formation Instability | Operator | 6 | 122500 | 270926 | 393426 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | In Progress | January | Q1 | Short Rainy Season
NPT00517 | 21-02-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 8 | 163333 | 141844 | 305177 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | February | Q1 | Dry Season
NPT00518 | 25-02-2025 | W038 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5472 | 21390 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Port Congestion | Procurement | 2 | 40833 | 53993 | 94826 | Minor | < $100K | Low | Unplanned | Night | Mobilize Supply Vessel | Closed | February | Q1 | Dry Season
NPT00519 | 09-07-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 4 | 76666 | 145357 | 222023 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | July | Q3 | Long Rainy Season
NPT00520 | 16-07-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | 6 | 115000 | 137040 | 252040 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | In Progress | July | Q3 | Long Rainy Season
NPT00521 | 18-07-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | 6 | 115000 | 109082 | 224082 | Moderate | $100K - $250K | Medium | Unplanned | Day | Air Freight Materials | Closed | July | Q3 | Long Rainy Season
NPT00522 | 22-07-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Lightning | Weather | 2 | 38333 | 30704 | 69037 | Minor | < $100K | Low | Unplanned | Day | Wait on Weather | Closed | July | Q3 | Long Rainy Season
NPT00523 | 05-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | 2 | 38333 | 52302 | 90635 | Minor | < $100K | Low | Unplanned | Night | Safety Briefing | Closed | August | Q3 | Long Rainy Season
NPT00524 | 12-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Lightning | Heavy Rain | Marine Operations | 12 | 230000 | 493028 | 723028 | Major | $500K - $1M | Medium | Unplanned | Night | Wait on Weather | In Progress | August | Q3 | Long Rainy Season
NPT00525 | 17-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Lightning | Weather | 4 | 76666 | 63467 | 140133 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | August | Q3 | Long Rainy Season
NPT00526 | 19-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 4 | 76666 | 47093 | 123759 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | Closed | August | Q3 | Long Rainy Season
NPT00527 | 25-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | 2 | 38333 | 90911 | 129244 | Minor | $100K - $250K | Low | Planned | Night | Mobilize Supply Vessel | Closed | August | Q3 | Long Rainy Season
NPT00528 | 27-08-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Heavy Rain | Heavy Rain | Weather | 12 | 230000 | 239440 | 469440 | Major | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | Open | August | Q3 | Long Rainy Season
NPT00529 | 07-09-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 6 | 115000 | 124749 | 239749 | Moderate | $100K - $250K | Medium | Unplanned | Night | Run Fishing Tools | In Progress | September | Q3 | Dry Season
NPT00530 | 13-09-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Strong Wind | Marine Operations | 6 | 115000 | 203939 | 318939 | Moderate | $250K - $500K | Medium | Planned | Night | Resume Operations | Closed | September | Q3 | Dry Season
NPT00531 | 04-10-2023 | W039 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6268 | 19931 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Material Shortage | Procurement | 4 | 76666 | 44616 | 121282 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | In Progress | October | Q4 | Dry Season
NPT00532 | 17-11-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Formation Instability | Mud Engineering | 2 | 38333 | 80604 | 118937 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | Closed | November | Q4 | Short Rainy Season
NPT00533 | 28-11-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | 6 | 115000 | 215251 | 330251 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | November | Q4 | Short Rainy Season
NPT00534 | 06-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | 4 | 76666 | 95465 | 172131 | Minor | $100K - $250K | Low | Unplanned | Day | Replace Equipment | In Progress | December | Q4 | Short Rainy Season
NPT00535 | 09-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Heavy Rain | Strong Wind | Weather | 8 | 153333 | 310650 | 463983 | Moderate | $250K - $500K | Medium | Unplanned | Day | Suspend Operations | Closed | December | Q4 | Short Rainy Season
NPT00536 | 18-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 4 | 76666 | 129558 | 206224 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | Closed | December | Q4 | Short Rainy Season
NPT00537 | 23-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Poor Visibility | Heavy Rain | Weather | 12 | 230000 | 561616 | 791616 | Major | $500K - $1M | Medium | Unplanned | Night | Suspend Operations | Closed | December | Q4 | Short Rainy Season
NPT00538 | 26-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Lightning | Weather | 4 | 76666 | 95669 | 172335 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | December | Q4 | Short Rainy Season
NPT00539 | 28-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | High Waves | Marine Operations | 6 | 115000 | 220006 | 335006 | Moderate | $250K - $500K | Medium | Unplanned | Night | Wait on Weather | In Progress | December | Q4 | Short Rainy Season
NPT00540 | 31-12-2024 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Formation Instability | Mud Engineering | 4 | 76666 | 41323 | 117989 | Minor | $100K - $250K | Low | Unplanned | Night | Run Fishing Tools | Open | December | Q4 | Short Rainy Season
NPT00541 | 02-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 0 | 0 | 1 | 1 | 0.17 | 16.7 | Personnel | Crew Change | Medical Emergency | Rig Management | 4 | 76666 | 150344 | 227010 | Minor | $100K - $250K | Low | Unplanned | Day | Safety Briefing | In Progress | January | Q1 | Short Rainy Season
NPT00542 | 03-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | 2 | 38333 | 34861 | 73194 | Minor | < $100K | Low | Unplanned | Night | Preventive Maintenance | Closed | January | Q1 | Short Rainy Season
NPT00543 | 06-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | 2 | 38333 | 71989 | 110322 | Minor | $100K - $250K | Low | Unplanned | Night | Repair Component | Closed | January | Q1 | Short Rainy Season
NPT00544 | 09-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | 8 | 153333 | 344980 | 498313 | Moderate | $250K - $500K | Medium | Unplanned | Night | Mobilize Supply Vessel | Closed | January | Q1 | Short Rainy Season
NPT00545 | 16-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | 12 | 230000 | 275951 | 505951 | Major | $500K - $1M | Medium | Unplanned | Day | Condition Hole | Closed | January | Q1 | Short Rainy Season
NPT00546 | 19-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | 4 | 76666 | 122362 | 199028 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Open | January | Q1 | Short Rainy Season
NPT00547 | 26-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Heavy Rain | Marine Operations | 6 | 115000 | 282556 | 397556 | Moderate | $250K - $500K | Medium | Unplanned | Night | Suspend Operations | Closed | January | Q1 | Short Rainy Season
NPT00548 | 27-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 4 | 76666 | 51458 | 128124 | Minor | $100K - $250K | Low | Unplanned | Night | Adjust Drilling Parameters | Closed | January | Q1 | Short Rainy Season
NPT00549 | 30-01-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | 6 | 115000 | 192955 | 307955 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Open | January | Q1 | Short Rainy Season
NPT00550 | 05-02-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | Heavy Rain | Marine Operations | 6 | 115000 | 74637 | 189637 | Moderate | $100K - $250K | Medium | Unplanned | Day | Resume Operations | Open | February | Q1 | Dry Season
NPT00551 | 09-02-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | 18 | 345000 | 503296 | 848296 | Major | $500K - $1M | High | Unplanned | Day | Preventive Maintenance | Open | February | Q1 | Dry Season
NPT00552 | 12-02-2025 | W040 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5782 | 18510 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 8 | 153333 | 272919 | 426252 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | February | Q1 | Dry Season
NPT00553 | 18-07-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | 6 | 115000 | 247320 | 362320 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Open | July | Q3 | Long Rainy Season
NPT00554 | 19-07-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 0 | 1 | 0 | 1 | 0.33 | 33.3 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | 8 | 153333 | 317647 | 470980 | Moderate | $250K - $500K | Medium | Unplanned | Night | Air Freight Materials | Closed | July | Q3 | Long Rainy Season
NPT00555 | 01-08-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | Lightning | Lightning | Weather | 8 | 153333 | 183394 | 336727 | Moderate | $250K - $500K | Medium | Unplanned | Night | Wait on Weather | Closed | August | Q3 | Long Rainy Season
NPT00556 | 08-08-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | 8 | 153333 | 210689 | 364022 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | In Progress | August | Q3 | Long Rainy Season
NPT00557 | 26-08-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | 8 | 153333 | 214639 | 367972 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | August | Q3 | Long Rainy Season
NPT00558 | 04-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 76666 | 58805 | 135471 | Minor | $100K - $250K | Low | Unplanned | Day | Preventive Maintenance | Closed | September | Q3 | Dry Season
NPT00559 | 05-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Unexpected Pressure | Operator | 4 | 76666 | 102592 | 179258 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | Closed | September | Q3 | Dry Season
NPT00560 | 09-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | 2 | 38333 | 33873 | 72206 | Minor | < $100K | Low | Unplanned | Day | Air Freight Materials | Closed | September | Q3 | Dry Season
NPT00561 | 13-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Formation Instability | Operator | 2 | 38333 | 28172 | 66505 | Minor | < $100K | Low | Unplanned | Night | Run Fishing Tools | Closed | September | Q3 | Dry Season
NPT00562 | 16-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | 2 | 38333 | 71728 | 110061 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | September | Q3 | Dry Season
NPT00563 | 21-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | High Waves | Weather | 2 | 38333 | 71077 | 109410 | Minor | $100K - $250K | Low | Planned | Night | Resume Operations | Closed | September | Q3 | Dry Season
NPT00564 | 27-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Marine Operations | 2 | 38333 | 81289 | 119622 | Minor | $100K - $250K | Low | Unplanned | Day | Suspend Operations | In Progress | September | Q3 | Dry Season
NPT00565 | 28-09-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 18 | 345000 | 390612 | 735612 | Major | $500K - $1M | High | Unplanned | Night | Condition Hole | In Progress | September | Q3 | Dry Season
NPT00566 | 05-10-2024 | W041 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5209 | 15202 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Unexpected Pressure | Operator | 2 | 38333 | 43647 | 81980 | Minor | < $100K | Low | Unplanned | Night | Condition Hole | Closed | October | Q4 | Dry Season
NPT00567 | 22-07-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Lightning | Lightning | Marine Operations | 6 | 122500 | 254150 | 376650 | Moderate | $250K - $500K | Medium | Unplanned | Day | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00568 | 25-07-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Differential Sticking | Operator | 8 | 163333 | 191207 | 354540 | Moderate | $250K - $500K | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | July | Q3 | Long Rainy Season
NPT00569 | 29-07-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | 2 | 40833 | 49540 | 90373 | Minor | < $100K | Low | Unplanned | Night | Expedite Shipment | Closed | July | Q3 | Long Rainy Season
NPT00570 | 07-08-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | Poor Visibility | Heavy Rain | Marine Operations | 18 | 367500 | 390071 | 757571 | Major | $500K - $1M | High | Unplanned | Day | Suspend Operations | In Progress | August | Q3 | Long Rainy Season
NPT00571 | 16-08-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | 6 | 122500 | 159958 | 282458 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | Open | August | Q3 | Long Rainy Season
NPT00572 | 06-09-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 6 | 122500 | 203927 | 326427 | Moderate | $250K - $500K | Medium | Unplanned | Day | Preventive Maintenance | Closed | September | Q3 | Dry Season
NPT00573 | 08-10-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Strong Wind | Marine Operations | 2 | 40833 | 23324 | 64157 | Minor | < $100K | Low | Unplanned | Day | Resume Operations | Closed | October | Q4 | Dry Season
NPT00574 | 17-10-2024 | W042 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 5979 | 18255 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | 4 | 81666 | 64325 | 145991 | Minor | $100K - $250K | Low | Unplanned | Night | Increase Mud Weight | Closed | October | Q4 | Dry Season
NPT00575 | 01-09-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Materials | Customs Clearance | Procurement | 4 | 76666 | 72518 | 149184 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | Open | September | Q3 | Dry Season
NPT00576 | 06-09-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 6 | 115000 | 248026 | 363026 | Moderate | $250K - $500K | Medium | Unplanned | Night | Increase Mud Weight | Closed | September | Q3 | Dry Season
NPT00577 | 13-09-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 8 | 153333 | 86363 | 239696 | Moderate | $100K - $250K | Medium | Unplanned | Night | Run Fishing Tools | Open | September | Q3 | Dry Season
NPT00578 | 04-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Lightning | Heavy Rain | Marine Operations | 4 | 76666 | 61263 | 137929 | Minor | $100K - $250K | Low | Planned | Day | Resume Operations | Closed | October | Q4 | Dry Season
NPT00579 | 05-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | 2 | 38333 | 84686 | 123019 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00580 | 10-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Fishing Operation | Bit Wear | Operator | 2 | 38333 | 49722 | 88055 | Minor | < $100K | Low | Unplanned | Night | Adjust Drilling Parameters | In Progress | October | Q4 | Dry Season
NPT00581 | 17-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Crew Change | Medical Emergency | Rig Management | 2 | 38333 | 62593 | 100926 | Minor | $100K - $250K | Low | Unplanned | Day | Safety Briefing | Closed | October | Q4 | Dry Season
NPT00582 | 21-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | 2 | 38333 | 29667 | 68000 | Minor | < $100K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | October | Q4 | Dry Season
NPT00583 | 23-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 2 | 38333 | 35940 | 74273 | Minor | < $100K | Low | Unplanned | Night | Adjust Drilling Parameters | In Progress | October | Q4 | Dry Season
NPT00584 | 28-10-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | 2 | 38333 | 37321 | 75654 | Minor | < $100K | Low | Unplanned | Day | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00585 | 02-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Lightning | Weather | 6 | 115000 | 236890 | 351890 | Moderate | $250K - $500K | Medium | Planned | Night | Suspend Operations | Open | November | Q4 | Short Rainy Season
NPT00586 | 11-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 6 | 115000 | 178383 | 293383 | Moderate | $250K - $500K | Medium | Unplanned | Night | Preventive Maintenance | Open | November | Q4 | Short Rainy Season
NPT00587 | 13-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Delayed Helicopter | Port Congestion | Procurement | 6 | 115000 | 199093 | 314093 | Moderate | $250K - $500K | Medium | Unplanned | Night | Expedite Shipment | Closed | November | Q4 | Short Rainy Season
NPT00588 | 14-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Unexpected Pressure | Operator | 4 | 76666 | 39001 | 115667 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | November | Q4 | Short Rainy Season
NPT00589 | 16-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | 18 | 345000 | 418285 | 763285 | Major | $500K - $1M | High | Unplanned | Night | Replace Equipment | Closed | November | Q4 | Short Rainy Season
NPT00590 | 17-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 38333 | 57717 | 96050 | Minor | < $100K | Low | Unplanned | Day | Repair Component | Closed | November | Q4 | Short Rainy Season
NPT00591 | 18-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | 12 | 230000 | 403320 | 633320 | Major | $500K - $1M | Medium | Unplanned | Night | Expedite Shipment | Closed | November | Q4 | Short Rainy Season
NPT00592 | 27-11-2023 | W043 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5934 | 19218 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Formation Instability | Operator | 6 | 115000 | 247949 | 362949 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Closed | November | Q4 | Short Rainy Season
NPT00593 | 21-05-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 2 | 40000 | 25031 | 65031 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00594 | 26-05-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | Poor Visibility | Heavy Rain | Weather | 18 | 360000 | 773348 | 1133348 | Major | > $1M | High | Unplanned | Night | Suspend Operations | In Progress | May | Q2 | Long Rainy Season
NPT00595 | 27-05-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | 6 | 120000 | 106088 | 226088 | Moderate | $100K - $250K | Medium | Unplanned | Day | Run Fishing Tools | Closed | May | Q2 | Long Rainy Season
NPT00596 | 30-06-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | 2 | 40000 | 88171 | 128171 | Minor | $100K - $250K | Low | Planned | Day | Expedite Shipment | Closed | June | Q2 | Long Rainy Season
NPT00597 | 05-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Formation Instability | Operator | 2 | 40000 | 85034 | 125034 | Minor | $100K - $250K | Low | Unplanned | Day | Increase Mud Weight | In Progress | July | Q3 | Long Rainy Season
NPT00598 | 06-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Bit Wear | Mud Engineering | 4 | 80000 | 130288 | 210288 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | July | Q3 | Long Rainy Season
NPT00599 | 07-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | 2 | 40000 | 51341 | 91341 | Minor | < $100K | Low | Unplanned | Day | Expedite Shipment | Closed | July | Q3 | Long Rainy Season
NPT00600 | 12-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Storm | Weather | 2 | 40000 | 61338 | 101338 | Minor | $100K - $250K | Low | Unplanned | Night | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00601 | 15-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 1 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Weather | High Waves | Lightning | Weather | 8 | 160000 | 339780 | 499780 | Moderate | $250K - $500K | Medium | Unplanned | Night | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00602 | 26-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | 8 | 160000 | 185853 | 345853 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | July | Q3 | Long Rainy Season
NPT00603 | 29-07-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Strong Wind | Weather | 6 | 120000 | 228519 | 348519 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | Closed | July | Q3 | Long Rainy Season
NPT00604 | 02-08-2024 | W044 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5148 | 19496 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 4 | 80000 | 63153 | 143153 | Minor | $100K - $250K | Low | Unplanned | Day | Air Freight Materials | In Progress | August | Q3 | Long Rainy Season
NPT00605 | 11-06-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 1 | 0 | 0 | 0 | 1 | 0.75 | 75 | Weather | Poor Visibility | Strong Wind | Marine Operations | 18 | 367500 | 851850 | 1219350 | Major | > $1M | High | Unplanned | Night | Suspend Operations | Closed | June | Q2 | Long Rainy Season
NPT00606 | 23-06-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | 2 | 40833 | 55477 | 96310 | Minor | < $100K | Low | Unplanned | Night | Replace Equipment | Open | June | Q2 | Long Rainy Season
NPT00607 | 25-06-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 8 | 163333 | 376966 | 540299 | Moderate | $500K - $1M | Medium | Planned | Night | Adjust Drilling Parameters | Closed | June | Q2 | Long Rainy Season
NPT00608 | 26-06-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 0 | 0 | 1 | 0 | 1 | 0.08 | 8.3 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | 2 | 40833 | 67011 | 107844 | Minor | $100K - $250K | Low | Unplanned | Night | Expedite Shipment | Closed | June | Q2 | Long Rainy Season
NPT00609 | 02-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Heavy Rain | Heavy Rain | Weather | 12 | 245000 | 133994 | 378994 | Major | $250K - $500K | Medium | Unplanned | Day | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00610 | 07-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | 4 | 81666 | 186247 | 267913 | Minor | $250K - $500K | Low | Unplanned | Night | Replace Equipment | Closed | July | Q3 | Long Rainy Season
NPT00611 | 11-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Materials | Material Shortage | Procurement | 6 | 122500 | 64878 | 187378 | Moderate | $100K - $250K | Medium | Unplanned | Day | Expedite Shipment | Closed | July | Q3 | Long Rainy Season
NPT00612 | 14-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Lightning | Lightning | Weather | 2 | 40833 | 40713 | 81546 | Minor | < $100K | Low | Unplanned | Day | Suspend Operations | Closed | July | Q3 | Long Rainy Season
NPT00613 | 21-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Heavy Rain | Heavy Rain | Weather | 2 | 40833 | 98596 | 139429 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | July | Q3 | Long Rainy Season
NPT00614 | 27-07-2023 | W045 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 4817 | 15766 | 0 | 0 | 0 | 1 | 0 | 1 | 1 | 100 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 24 | 490000 | 1044504 | 1534504 | Critical | > $1M | High | Unplanned | Day | Air Freight Materials | Closed | July | Q3 | Long Rainy Season
NPT00615 | 30-04-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 8 | 160000 | 137440 | 297440 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Open | April | Q2 | Dry Season
NPT00616 | 20-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | 12 | 240000 | 374455 | 614455 | Major | $500K - $1M | Medium | Unplanned | Day | Expedite Shipment | Closed | May | Q2 | Long Rainy Season
NPT00617 | 21-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Strong Wind | Marine Operations | 4 | 80000 | 174948 | 254948 | Minor | $250K - $500K | Low | Unplanned | Night | Resume Operations | Closed | May | Q2 | Long Rainy Season
NPT00618 | 23-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 6 | 120000 | 270341 | 390341 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | May | Q2 | Long Rainy Season
NPT00619 | 25-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | 8 | 160000 | 306975 | 466975 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | May | Q2 | Long Rainy Season
NPT00620 | 26-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | 8 | 160000 | 96020 | 256020 | Moderate | $250K - $500K | Medium | Unplanned | Night | Replace Equipment | In Progress | May | Q2 | Long Rainy Season
NPT00621 | 28-05-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 1 | 0 | 0 | 0 | 1 | 0.5 | 50 | Weather | Heavy Rain | Heavy Rain | Weather | 12 | 240000 | 397476 | 637476 | Major | $500K - $1M | Medium | Unplanned | Day | Wait on Weather | Closed | May | Q2 | Long Rainy Season
NPT00622 | 10-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 4 | 80000 | 89940 | 169940 | Minor | $100K - $250K | Low | Unplanned | Night | OEM Inspection | Open | June | Q2 | Long Rainy Season
NPT00623 | 11-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 6 | 120000 | 86494 | 206494 | Moderate | $100K - $250K | Medium | Unplanned | Night | Preventive Maintenance | Closed | June | Q2 | Long Rainy Season
NPT00624 | 13-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 2 | 40000 | 98735 | 138735 | Minor | $100K - $250K | Low | Unplanned | Night | Condition Hole | Closed | June | Q2 | Long Rainy Season
NPT00625 | 14-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | 4 | 80000 | 199919 | 279919 | Minor | $250K - $500K | Low | Unplanned | Day | Expedite Shipment | Closed | June | Q2 | Long Rainy Season
NPT00626 | 19-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Strong Wind | Strong Wind | Marine Operations | 6 | 120000 | 250242 | 370242 | Moderate | $250K - $500K | Medium | Unplanned | Day | Wait on Weather | In Progress | June | Q2 | Long Rainy Season
NPT00627 | 24-06-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Hole Cleaning | Bit Wear | Operator | 4 | 80000 | 117922 | 197922 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | June | Q2 | Long Rainy Season
NPT00628 | 10-07-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 8 | 160000 | 218432 | 378432 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Open | July | Q3 | Long Rainy Season
NPT00629 | 20-07-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Poor Visibility | Heavy Rain | Weather | 6 | 120000 | 81245 | 201245 | Moderate | $100K - $250K | Medium | Unplanned | Day | Resume Operations | Closed | July | Q3 | Long Rainy Season
NPT00630 | 26-07-2024 | W046 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5757 | 19389 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | 4 | 80000 | 91574 | 171574 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | July | Q3 | Long Rainy Season
NPT00631 | 10-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | 4 | 81666 | 77971 | 159637 | Minor | $100K - $250K | Low | Unplanned | Night | Condition Hole | In Progress | October | Q4 | Dry Season
NPT00632 | 12-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Bit Failure | Bit Wear | Operator | 2 | 40833 | 84650 | 125483 | Minor | $100K - $250K | Low | Planned | Day | Increase Mud Weight | In Progress | October | Q4 | Dry Season
NPT00633 | 14-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 1 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Weather | Strong Wind | Storm | Weather | 2 | 40833 | 73113 | 113946 | Minor | $100K - $250K | Low | Unplanned | Night | Wait on Weather | Closed | October | Q4 | Dry Season
NPT00634 | 16-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Differential Sticking | Operator | 8 | 163333 | 205525 | 368858 | Moderate | $250K - $500K | Medium | Planned | Night | Run Fishing Tools | Closed | October | Q4 | Dry Season
NPT00635 | 23-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 8 | 163333 | 392949 | 556282 | Moderate | $500K - $1M | Medium | Unplanned | Day | Repair Component | In Progress | October | Q4 | Dry Season
NPT00636 | 26-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | 4 | 81666 | 77527 | 159193 | Minor | $100K - $250K | Low | Unplanned | Night | Repair Component | Closed | October | Q4 | Dry Season
NPT00637 | 31-10-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | 8 | 163333 | 334485 | 497818 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00638 | 08-11-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 0 | 0 | 1 | 1 | 0.75 | 75 | Personnel | Crew Change | Crew Rotation | Rig Management | 18 | 367500 | 236304 | 603804 | Major | $500K - $1M | High | Unplanned | Day | Medical Clearance | Closed | November | Q4 | Short Rainy Season
NPT00639 | 15-11-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Heavy Rain | Lightning | Weather | 4 | 81666 | 190813 | 272479 | Minor | $250K - $500K | Low | Unplanned | Day | Wait on Weather | Closed | November | Q4 | Short Rainy Season
NPT00640 | 21-11-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 8 | 163333 | 248690 | 412023 | Moderate | $250K - $500K | Medium | Unplanned | Day | Adjust Drilling Parameters | Closed | November | Q4 | Short Rainy Season
NPT00641 | 05-12-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 4 | 81666 | 146922 | 228588 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | December | Q4 | Short Rainy Season
NPT00642 | 08-12-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Well Control | Bit Wear | Directional Drilling | 6 | 122500 | 196965 | 319465 | Moderate | $250K - $500K | Medium | Planned | Day | Increase Mud Weight | Closed | December | Q4 | Short Rainy Season
NPT00643 | 30-12-2024 | W047 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Exploration | Guyana | 5183 | 17327 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Lost Circulation | Unexpected Pressure | Operator | 2 | 40833 | 59674 | 100507 | Minor | $100K - $250K | Low | Unplanned | Day | Run Fishing Tools | In Progress | December | Q4 | Short Rainy Season
NPT00644 | 24-01-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 0 | 0 | 0 | 1 | 1 | 0.08 | 8.3 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | 2 | 38333 | 43207 | 81540 | Minor | < $100K | Low | Unplanned | Day | Medical Clearance | Closed | January | Q1 | Short Rainy Season
NPT00645 | 17-02-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 2 | 38333 | 46414 | 84747 | Minor | < $100K | Low | Unplanned | Night | Replace Equipment | Closed | February | Q1 | Dry Season
NPT00646 | 19-02-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 4 | 76666 | 109609 | 186275 | Minor | $100K - $250K | Low | Unplanned | Day | Condition Hole | Closed | February | Q1 | Dry Season
NPT00647 | 02-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 8 | 153333 | 295021 | 448354 | Moderate | $250K - $500K | Medium | Unplanned | Day | Replace Equipment | Closed | March | Q1 | Dry Season
NPT00648 | 06-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 76666 | 129373 | 206039 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | In Progress | March | Q1 | Dry Season
NPT00649 | 07-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.75 | 75 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | 18 | 345000 | 423942 | 768942 | Major | $500K - $1M | High | Unplanned | Night | OEM Inspection | Closed | March | Q1 | Dry Season
NPT00650 | 23-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.33 | 33.3 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | 8 | 153333 | 294473 | 447806 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | In Progress | March | Q1 | Dry Season
NPT00651 | 24-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | High Waves | Weather | 6 | 115000 | 70319 | 185319 | Moderate | $100K - $250K | Medium | Unplanned | Night | Wait on Weather | Closed | March | Q1 | Dry Season
NPT00652 | 28-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | 8 | 153333 | 289177 | 442510 | Moderate | $250K - $500K | Medium | Unplanned | Night | Condition Hole | Closed | March | Q1 | Dry Season
NPT00653 | 29-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | Poor Visibility | Lightning | Weather | 4 | 76666 | 130194 | 206860 | Minor | $100K - $250K | Low | Unplanned | Day | Wait on Weather | In Progress | March | Q1 | Dry Season
NPT00654 | 30-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | 6 | 115000 | 272813 | 387813 | Moderate | $250K - $500K | Medium | Unplanned | Night | OEM Inspection | Closed | March | Q1 | Dry Season
NPT00655 | 31-03-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | 6 | 115000 | 241901 | 356901 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Closed | March | Q1 | Dry Season
NPT00656 | 18-04-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 1 | 0 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 4 | 76666 | 85043 | 161709 | Minor | $100K - $250K | Low | Unplanned | Day | Repair Component | Closed | April | Q2 | Dry Season
NPT00657 | 20-04-2023 | W048 | R002 | 11 | Stena Carron | Drillship | Stena Drilling | Active | 460000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 5163 | 17931 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 6 | 115000 | 129108 | 244108 | Moderate | $100K - $250K | Medium | Unplanned | Night | Increase Mud Weight | Closed | April | Q2 | Dry Season
NPT00658 | 23-06-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | 4 | 80000 | 121829 | 201829 | Minor | $100K - $250K | Low | Unplanned | Day | Mobilize Supply Vessel | In Progress | June | Q2 | Long Rainy Season
NPT00659 | 12-07-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.75 | 75 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 18 | 360000 | 314096 | 674096 | Major | $500K - $1M | High | Unplanned | Day | Run Fishing Tools | Closed | July | Q3 | Long Rainy Season
NPT00660 | 25-07-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 0 | 1 | 0 | 1 | 0.17 | 16.7 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | 4 | 80000 | 183601 | 263601 | Minor | $250K - $500K | Low | Unplanned | Day | Mobilize Supply Vessel | Closed | July | Q3 | Long Rainy Season
NPT00661 | 04-08-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 8 | 160000 | 279871 | 439871 | Moderate | $250K - $500K | Medium | Unplanned | Day | Increase Mud Weight | Open | August | Q3 | Long Rainy Season
NPT00662 | 13-08-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | 6 | 120000 | 270679 | 390679 | Moderate | $250K - $500K | Medium | Unplanned | Day | OEM Inspection | Closed | August | Q3 | Long Rainy Season
NPT00663 | 20-08-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 6 | 120000 | 60226 | 180226 | Moderate | $100K - $250K | Medium | Unplanned | Night | Expedite Shipment | In Progress | August | Q3 | Long Rainy Season
NPT00664 | 03-09-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.08 | 8.3 | Drilling | Well Control | Bit Wear | Operator | 2 | 40000 | 85472 | 125472 | Minor | $100K - $250K | Low | Unplanned | Night | Condition Hole | Closed | September | Q3 | Dry Season
NPT00665 | 06-09-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | Heavy Rain | Strong Wind | Weather | 6 | 120000 | 143523 | 263523 | Moderate | $250K - $500K | Medium | Unplanned | Night | Wait on Weather | Open | September | Q3 | Dry Season
NPT00666 | 10-09-2023 | W049 | R003 | 8 | Stena DrillMAX | Drillship | Stena Drilling | Maintenance | 480000 | Atlantic Energy Guyana | Stabroek | Development | Guyana | 6498 | 22777 | 0 | 0 | 1 | 0 | 0 | 1 | 0.25 | 25 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | 6 | 120000 | 294858 | 414858 | Moderate | $250K - $500K | Medium | Unplanned | Day | Condition Hole | Closed | September | Q3 | Dry Season
NPT00667 | 16-10-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Lost Circulation | Bit Wear | Operator | 8 | 163333 | 405188 | 568521 | Moderate | $500K - $1M | Medium | Unplanned | Night | Run Fishing Tools | Open | October | Q4 | Dry Season
NPT00668 | 19-10-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 0 | 1 | 0 | 1 | 0.25 | 25 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | 6 | 122500 | 174028 | 296528 | Moderate | $250K - $500K | Medium | Unplanned | Day | Mobilize Supply Vessel | Closed | October | Q4 | Dry Season
NPT00669 | 20-10-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 1 | 0 | 0 | 0 | 0 | 1 | 0.08 | 8.3 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 40833 | 91284 | 132117 | Minor | $100K - $250K | Low | Unplanned | Day | OEM Inspection | Closed | October | Q4 | Dry Season
NPT00670 | 22-10-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 0 | 1 | 0 | 1 | 0.5 | 50 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | 12 | 245000 | 512335 | 757335 | Major | $500K - $1M | Medium | Unplanned | Day | Mobilize Supply Vessel | Open | October | Q4 | Dry Season
NPT00671 | 02-11-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 1 | 0 | 0 | 0 | 1 | 0.17 | 16.7 | Weather | High Waves | Storm | Weather | 4 | 81666 | 110150 | 191816 | Minor | $100K - $250K | Low | Planned | Day | Resume Operations | Closed | November | Q4 | Short Rainy Season
NPT00672 | 14-11-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 1 | 0 | 0 | 0 | 0 | 1 | 0.25 | 25 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | 6 | 122500 | 116840 | 239340 | Moderate | $100K - $250K | Medium | Unplanned | Day | Replace Equipment | Closed | November | Q4 | Short Rainy Season
NPT00673 | 28-11-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 1 | 0 | 0 | 1 | 0.5 | 50 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 12 | 245000 | 368627 | 613627 | Major | $500K - $1M | Medium | Unplanned | Night | Adjust Drilling Parameters | Closed | November | Q4 | Short Rainy Season
NPT00674 | 17-12-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 1 | 0 | 0 | 0 | 1 | 0.25 | 25 | Weather | High Waves | High Waves | Marine Operations | 6 | 122500 | 126592 | 249092 | Moderate | $100K - $250K | Medium | Unplanned | Day | Wait on Weather | Closed | December | Q4 | Short Rainy Season
NPT00675 | 22-12-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 1 | 0 | 0 | 1 | 0.17 | 16.7 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | 4 | 81666 | 122727 | 204393 | Minor | $100K - $250K | Low | Unplanned | Day | Adjust Drilling Parameters | Closed | December | Q4 | Short Rainy Season
NPT00676 | 24-12-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 1 | 0 | 0 | 1 | 0.33 | 33.3 | Drilling | Stuck Pipe | Formation Instability | Operator | 8 | 163333 | 182981 | 346314 | Moderate | $250K - $500K | Medium | Planned | Day | Increase Mud Weight | Closed | December | Q4 | Short Rainy Season
NPT00677 | 29-12-2023 | W050 | R004 | 6 | Noble Don Taylor | Drillship | Noble | StandBy | 490000 | Atlantic Energy Guyana | Stabroek | Appraisal | Guyana | 6131 | 15197 | 0 | 0 | 0 | 0 | 1 | 1 | 0.25 | 25 | Personnel | Medical Evacuation | Training Requirement | HR | 6 | 122500 | 172937 | 295437 | Moderate | $250K - $500K | Medium | Unplanned | Night | Medical Clearance | Closed | December | Q4 | Short Rainy Season