## FACT NPT
NPT_ID | Date | Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Duration_hr | Severity | NPT_Rig_Cost_USD | Deferred_Production_Impact_USD | Total_Impact_USD
NPT00001 | 2023-04-17 | W001 | R004 | Personnel | Personnel Availability | Training requirement | 2 | Low | 40833.33 | 86030.88 | 126864.21
NPT00002 | 2023-04-25 | W001 | R004 | Logistics | Mud / Chemical Supply | Late delivery | 2 | Low | 40833.33 | 78362.08 | 119195.41
NPT00003 | 2023-05-01 | W001 | R004 | Drilling | Lost Time While Drilling | Drilling parameter issue | 4 | Low | 81666.67 | 159273.55 | 240940.22
NPT00004 | 2023-05-04 | W001 | R004 | Mechanical | Mud Pump | Preventive maintenance issue | 4 | Low | 81666.67 | 233228.51 | 314895.18
NPT00005 | 2024-03-15 | W002 | R001 | Mechanical | Power Generation | Hydraulic issue | 2 | Low | 39583.33 | 106413.23 | 145996.56
NPT00006 | 2024-03-22 | W002 | R001 | Mechanical | Mud Pump | Electrical fault | 4 | Low | 79166.67 | 190437.78 | 269604.44
NPT00007 | 2024-04-02 | W002 | R001 | Weather | Rough Seas | Marine conditions | 4 | Low | 79166.67 | 206290.17 | 285456.83
NPT00008 | 2024-04-05 | W002 | R001 | Mechanical | Power Generation | Hydraulic issue | 2 | Low | 39583.33 | 86950.18 | 126533.51
NPT00009 | 2024-04-06 | W002 | R001 | Drilling | Hole Cleaning | Drilling parameter issue | 2 | Low | 39583.33 | 80481.7 | 120065.03
NPT00010 | 2023-09-30 | W003 | R004 | Personnel | Personnel Availability | Training requirement | 6 | Medium | 122500 | 213808.79 | 336308.79
NPT00011 | 2023-10-06 | W003 | R004 | Logistics | Supply Boat Delay | Supplier delay | 2 | Low | 40833.33 | 96337.57 | 137170.9
NPT00012 | 2023-10-07 | W003 | R004 | Logistics | Mud / Chemical Supply | Marine logistics | 2 | Low | 40833.33 | 84567.44 | 125400.78
NPT00013 | 2023-10-12 | W003 | R004 | Weather | High Wind | Weather suspension | 2 | Low | 40833.33 | 61561.94 | 102395.27
NPT00014 | 2023-10-13 | W003 | R004 | Drilling | Lost Time While Drilling | Drilling parameter issue | 2 | Low | 40833.33 | 96484.89 | 137318.22
NPT00015 | 2023-10-16 | W003 | R004 | Personnel | Personnel Availability | Crew availability | 2 | Low | 40833.33 | 88932.67 | 129766
NPT00016 | 2023-04-17 | W004 | R002 | Logistics | Supply Boat Delay | Late delivery | 4 | Low | 76666.67 | 188645.78 | 265312.45
NPT00017 | 2023-04-18 | W004 | R002 | Drilling | Hole Cleaning | Hole cleaning | 2 | Low | 38333.33 | 111491.8 | 149825.13
NPT00018 | 2023-04-19 | W004 | R002 | Mechanical | Mud Pump | Electrical fault | 2 | Low | 38333.33 | 79673.78 | 118007.12
NPT00019 | 2023-04-29 | W004 | R002 | Mechanical | Hydraulic System | Component failure | 2 | Low | 38333.33 | 109888.64 | 148221.97
NPT00020 | 2023-05-08 | W004 | R002 | Mechanical | Drawworks | Hydraulic issue | 6 | Medium | 115000 | 179461.9 | 294461.9
NPT00021 | 2023-05-10 | W004 | R002 | Mechanical | Hydraulic System | Component failure | 4 | Low | 76666.67 | 149651.79 | 226318.45
NPT00022 | 2023-05-14 | W004 | R002 | Mechanical | Top Drive | Component failure | 2 | Low | 38333.33 | 104212.69 | 142546.03
NPT00023 | 2023-03-16 | W005 | R002 | Logistics | Port Delay | Late delivery | 2 | Low | 38333.33 | 103029.14 | 141362.47
NPT00024 | 2023-03-21 | W005 | R002 | Drilling | Stuck Pipe | Drilling parameter issue | 2 | Low | 38333.33 | 61227.17 | 99560.5
NPT00025 | 2023-03-30 | W005 | R002 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 38333.33 | 92461.57 | 130794.9
NPT00026 | 2024-12-05 | W006 | R002 | Mechanical | Top Drive | Component failure | 2 | Low | 38333.33 | 115973.14 | 154306.47
NPT00027 | 2024-12-07 | W006 | R002 | Logistics | Port Delay | Supplier delay | 2 | Low | 38333.33 | 59239.21 | 97572.54
NPT00028 | 2024-12-08 | W006 | R002 | Mechanical | Top Drive | Component failure | 2 | Low | 38333.33 | 97291.51 | 135624.84
NPT00029 | 2024-12-17 | W006 | R002 | Mechanical | Drawworks | Electrical fault | 2 | Low | 38333.33 | 83300.99 | 121634.33
NPT00030 | 2024-12-18 | W006 | R002 | Drilling | Lost Time While Drilling | Hole cleaning | 2 | Low | 38333.33 | 54156.95 | 92490.28
NPT00031 | 2024-12-20 | W006 | R002 | Logistics | Equipment Delivery | Marine logistics | 2 | Low | 38333.33 | 112358.2 | 150691.54
NPT00032 | 2024-12-31 | W006 | R002 | Drilling | Lost Circulation | Wellbore condition | 2 | Low | 38333.33 | 79400.94 | 117734.28
NPT00033 | 2023-02-10 | W007 | R001 | Drilling | Lost Time While Drilling | Hole cleaning | 2 | Low | 39583.33 | 126710.42 | 166293.75
NPT00034 | 2023-02-18 | W007 | R001 | Drilling | Hole Cleaning | Formation response | 2 | Low | 39583.33 | 95794.44 | 135377.77
NPT00035 | 2024-09-11 | W008 | R002 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 76666.67 | 207397.03 | 284063.69
NPT00036 | 2024-09-18 | W008 | R002 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 76666.67 | 161331.17 | 237997.84
NPT00037 | 2024-09-30 | W008 | R002 | Logistics | Supply Boat Delay | Marine logistics | 2 | Low | 38333.33 | 104887.71 | 143221.04
NPT00038 | 2024-10-01 | W008 | R002 | Drilling | Lost Circulation | Hole cleaning | 4 | Low | 76666.67 | 173367.69 | 250034.36
NPT00039 | 2023-05-02 | W009 | R001 | Personnel | Crew Change | Operational meeting | 2 | Low | 39583.33 | 58513.56 | 98096.9
NPT00040 | 2023-05-07 | W009 | R001 | Logistics | Supply Boat Delay | Inventory constraint | 2 | Low | 39583.33 | 61441.75 | 101025.08
NPT00041 | 2023-05-12 | W009 | R001 | Mechanical | BOP / Well Control | Hydraulic issue | 2 | Low | 39583.33 | 69084.23 | 108667.56
NPT00042 | 2023-05-14 | W009 | R001 | Logistics | Mud / Chemical Supply | Inventory constraint | 2 | Low | 39583.33 | 105849.66 | 145433
NPT00043 | 2023-05-17 | W009 | R001 | Drilling | Lost Time While Drilling | Drilling parameter issue | 4 | Low | 79166.67 | 217539.37 | 296706.04
NPT00044 | 2023-05-18 | W009 | R001 | Weather | Lightning | Weather suspension | 4 | Low | 79166.67 | 197846.98 | 277013.64
NPT00045 | 2023-05-19 | W009 | R001 | Drilling | Lost Time While Drilling | Drilling parameter issue | 2 | Low | 39583.33 | 63850.23 | 103433.56
NPT00046 | 2023-05-21 | W009 | R001 | Mechanical | Mud Pump | Electrical fault | 4 | Low | 79166.67 | 225452.95 | 304619.62
NPT00047 | 2023-05-26 | W009 | R001 | Personnel | Personnel Availability | Training requirement | 2 | Low | 39583.33 | 101938.65 | 141521.99
NPT00048 | 2023-05-29 | W009 | R001 | Weather | Heavy Rain | Reduced operating window | 4 | Low | 79166.67 | 121455.14 | 200621.8
NPT00049 | 2024-04-23 | W010 | R002 | Weather | Heavy Rain | Weather suspension | 2 | Low | 38333.33 | 95261.75 | 133595.09
NPT00050 | 2023-08-09 | W011 | R004 | Mechanical | Top Drive | Electrical fault | 4 | Low | 81666.67 | 144897.83 | 226564.5
NPT00051 | 2023-08-11 | W011 | R004 | Weather | Heavy Rain | Marine conditions | 4 | Low | 81666.67 | 237047.68 | 318714.35
NPT00052 | 2023-08-13 | W011 | R004 | Drilling | Wellbore Instability | Wellbore condition | 2 | Low | 40833.33 | 126674.33 | 167507.67
NPT00053 | 2023-08-22 | W011 | R004 | Drilling | Stuck Pipe | Drilling parameter issue | 2 | Low | 40833.33 | 129130.64 | 169963.97
NPT00054 | 2023-08-26 | W011 | R004 | Drilling | Stuck Pipe | Wellbore condition | 2 | Low | 40833.33 | 110426.41 | 151259.75
NPT00055 | 2023-08-29 | W011 | R004 | Logistics | Supply Boat Delay | Late delivery | 2 | Low | 40833.33 | 89215.8 | 130049.14
NPT00056 | 2023-09-01 | W011 | R004 | Logistics | Mud / Chemical Supply | Marine logistics | 4 | Low | 81666.67 | 207232.52 | 288899.19
NPT00057 | 2023-09-03 | W011 | R004 | Weather | High Wind | Reduced operating window | 4 | Low | 81666.67 | 177211.6 | 258878.27
NPT00058 | 2023-12-03 | W012 | R004 | Weather | Rough Seas | Reduced operating window | 2 | Low | 40833.33 | 64200.53 | 105033.86
NPT00059 | 2023-12-07 | W012 | R004 | Logistics | Port Delay | Late delivery | 2 | Low | 40833.33 | 50585.16 | 91418.49
NPT00060 | 2023-12-21 | W012 | R004 | Drilling | Hole Cleaning | Hole cleaning | 2 | Low | 40833.33 | 102328.19 | 143161.53
NPT00061 | 2024-04-06 | W013 | R003 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 80000 | 174395.75 | 254395.75
NPT00062 | 2024-04-10 | W013 | R003 | Drilling | Lost Time While Drilling | Wellbore condition | 2 | Low | 40000 | 115806.65 | 155806.65
NPT00063 | 2024-04-11 | W013 | R003 | Weather | Heavy Rain | Reduced operating window | 2 | Low | 40000 | 107060.66 | 147060.66
NPT00064 | 2024-04-17 | W013 | R003 | Drilling | Stuck Pipe | Hole cleaning | 6 | Medium | 120000 | 273511.04 | 393511.04
NPT00065 | 2024-04-19 | W013 | R003 | Weather | Rough Seas | Weather suspension | 4 | Low | 80000 | 236444.98 | 316444.98
NPT00066 | 2024-04-28 | W013 | R003 | Mechanical | Power Generation | Component failure | 2 | Low | 40000 | 114594.53 | 154594.53
NPT00067 | 2024-05-03 | W013 | R003 | Drilling | Fishing | Hole cleaning | 4 | Low | 80000 | 162779.05 | 242779.05
NPT00068 | 2024-05-06 | W013 | R003 | Weather | Heavy Rain | Marine conditions | 2 | Low | 40000 | 51413.5 | 91413.5
NPT00069 | 2023-04-15 | W014 | R004 | Weather | Rough Seas | Marine conditions | 4 | Low | 81666.67 | 170141.8 | 251808.47
NPT00070 | 2023-04-24 | W014 | R004 | Drilling | Wellbore Instability | Wellbore condition | 2 | Low | 40833.33 | 84637.8 | 125471.13
NPT00071 | 2023-04-25 | W014 | R004 | Personnel | Crew Change | Crew availability | 2 | Low | 40833.33 | 55242.43 | 96075.77
NPT00072 | 2023-04-29 | W014 | R004 | Mechanical | Top Drive | Component failure | 2 | Low | 40833.33 | 105855.18 | 146688.51
NPT00073 | 2024-01-08 | W015 | R003 | Mechanical | Top Drive | Component failure | 2 | Low | 40000 | 89160.16 | 129160.16
NPT00074 | 2024-01-22 | W015 | R003 | Drilling | Stuck Pipe | Hole cleaning | 2 | Low | 40000 | 53789.92 | 93789.92
NPT00075 | 2024-01-23 | W015 | R003 | Logistics | Supply Boat Delay | Inventory constraint | 2 | Low | 40000 | 58850.36 | 98850.36
NPT00076 | 2024-01-29 | W015 | R003 | Logistics | Supply Boat Delay | Late delivery | 4 | Low | 80000 | 223669.98 | 303669.98
NPT00077 | 2023-04-23 | W016 | R004 | Mechanical | Top Drive | Electrical fault | 2 | Low | 40833.33 | 108014.67 | 148848
NPT00078 | 2023-04-30 | W016 | R004 | Mechanical | Top Drive | Component failure | 4 | Low | 81666.67 | 181166.83 | 262833.5
NPT00079 | 2023-05-03 | W016 | R004 | Mechanical | BOP / Well Control | Preventive maintenance issue | 4 | Low | 81666.67 | 243568.35 | 325235.02
NPT00080 | 2023-05-09 | W016 | R004 | Drilling | Hole Cleaning | Formation response | 2 | Low | 40833.33 | 116899.61 | 157732.95
NPT00081 | 2024-10-26 | W017 | R001 | Drilling | Lost Time While Drilling | Wellbore condition | 2 | Low | 39583.33 | 98861.61 | 138444.94
NPT00082 | 2024-11-06 | W017 | R001 | Drilling | Stuck Pipe | Drilling parameter issue | 2 | Low | 39583.33 | 121172.51 | 160755.85
NPT00083 | 2024-11-10 | W017 | R001 | Personnel | Crew Change | Operational meeting | 2 | Low | 39583.33 | 123006.62 | 162589.95
NPT00084 | 2024-11-21 | W017 | R001 | Logistics | Mud / Chemical Supply | Inventory constraint | 2 | Low | 39583.33 | 57989 | 97572.33
NPT00085 | 2023-05-12 | W018 | R004 | Personnel | Personnel Availability | Operational meeting | 2 | Low | 40833.33 | 81570.39 | 122403.72
NPT00086 | 2023-05-24 | W018 | R004 | Mechanical | Drawworks | Hydraulic issue | 4 | Low | 81666.67 | 252783.74 | 334450.41
NPT00087 | 2023-05-26 | W018 | R004 | Drilling | Lost Circulation | Drilling parameter issue | 4 | Low | 81666.67 | 129722.58 | 211389.25
NPT00088 | 2023-05-30 | W018 | R004 | Drilling | Hole Cleaning | Formation response | 2 | Low | 40833.33 | 89640.52 | 130473.86
NPT00089 | 2023-05-31 | W018 | R004 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 40833.33 | 122131.35 | 162964.68
NPT00090 | 2023-06-05 | W018 | R004 | Mechanical | Mud Pump | Hydraulic issue | 2 | Low | 40833.33 | 57758.23 | 98591.56
NPT00091 | 2024-10-26 | W019 | R003 | Mechanical | BOP / Well Control | Electrical fault | 6 | Medium | 120000 | 221047.89 | 341047.89
NPT00092 | 2024-11-04 | W019 | R003 | Logistics | Port Delay | Supplier delay | 2 | Low | 40000 | 117718.28 | 157718.28
NPT00093 | 2024-11-17 | W019 | R003 | Logistics | Cement Delay | Marine logistics | 4 | Low | 80000 | 184759.31 | 264759.31
NPT00094 | 2023-11-08 | W020 | R003 | Mechanical | Mud Pump | Preventive maintenance issue | 2 | Low | 40000 | 126256.44 | 166256.44
NPT00095 | 2023-11-09 | W020 | R003 | Drilling | Lost Circulation | Wellbore condition | 2 | Low | 40000 | 59516.26 | 99516.26
NPT00096 | 2023-11-22 | W020 | R003 | Logistics | Supply Boat Delay | Late delivery | 2 | Low | 40000 | 77392.29 | 117392.29
NPT00097 | 2023-12-10 | W021 | R002 | Personnel | Crew Change | Training requirement | 2 | Low | 38333.33 | 60322.4 | 98655.74
NPT00098 | 2023-12-11 | W021 | R002 | Drilling | Lost Time While Drilling | Drilling parameter issue | 2 | Low | 38333.33 | 75532.52 | 113865.85
NPT00099 | 2023-12-26 | W021 | R002 | Weather | Rough Seas | Weather suspension | 4 | Low | 76666.67 | 185026.21 | 261692.88
NPT00100 | 2024-05-11 | W022 | R001 | Mechanical | BOP / Well Control | Hydraulic issue | 4 | Low | 79166.67 | 206065.55 | 285232.22
NPT00101 | 2024-05-12 | W022 | R001 | Weather | Rough Seas | Reduced operating window | 2 | Low | 39583.33 | 69734.43 | 109317.76
NPT00102 | 2024-05-15 | W022 | R001 | Mechanical | Drawworks | Hydraulic issue | 2 | Low | 39583.33 | 103978.92 | 143562.26
NPT00103 | 2024-06-02 | W022 | R001 | Weather | Rough Seas | Marine conditions | 2 | Low | 39583.33 | 124875 | 164458.33
NPT00104 | 2024-03-12 | W023 | R004 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 40833.33 | 117133.91 | 157967.24
NPT00105 | 2024-03-13 | W023 | R004 | Logistics | Port Delay | Marine logistics | 2 | Low | 40833.33 | 65407.27 | 106240.6
NPT00106 | 2024-03-14 | W023 | R004 | Weather | Lightning | Reduced operating window | 2 | Low | 40833.33 | 128465.69 | 169299.02
NPT00107 | 2024-03-15 | W023 | R004 | Mechanical | Drawworks | Preventive maintenance issue | 4 | Low | 81666.67 | 206152.52 | 287819.19
NPT00108 | 2024-03-16 | W023 | R004 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 81666.67 | 180122.58 | 261789.25
NPT00109 | 2024-01-21 | W024 | R002 | Drilling | Lost Circulation | Drilling parameter issue | 4 | Low | 76666.67 | 167964.31 | 244630.97
NPT00110 | 2024-01-22 | W024 | R002 | Drilling | Lost Time While Drilling | Drilling parameter issue | 2 | Low | 38333.33 | 116569.61 | 154902.94
NPT00111 | 2024-01-31 | W024 | R002 | Drilling | Stuck Pipe | Formation response | 2 | Low | 38333.33 | 84905.33 | 123238.67
NPT00112 | 2024-02-02 | W024 | R002 | Drilling | Stuck Pipe | Formation response | 4 | Low | 76666.67 | 123498.2 | 200164.86
NPT00113 | 2024-02-09 | W024 | R002 | Weather | Heavy Rain | Weather suspension | 4 | Low | 76666.67 | 180668.58 | 257335.24
NPT00114 | 2024-02-16 | W024 | R002 | Mechanical | Hydraulic System | Hydraulic issue | 2 | Low | 38333.33 | 60976.9 | 99310.23
NPT00115 | 2024-02-16 | W024 | R002 | Logistics | Cement Delay | Inventory constraint | 4 | Low | 76666.67 | 240013.47 | 316680.14
NPT00116 | 2023-07-17 | W025 | R004 | Mechanical | Mud Pump | Preventive maintenance issue | 2 | Low | 40833.33 | 70814.77 | 111648.11
NPT00117 | 2023-07-31 | W025 | R004 | Mechanical | Hydraulic System | Hydraulic issue | 2 | Low | 40833.33 | 63756.83 | 104590.16
NPT00118 | 2023-08-05 | W025 | R004 | Mechanical | Top Drive | Electrical fault | 4 | Low | 81666.67 | 208724.32 | 290390.99
NPT00119 | 2023-10-04 | W026 | R004 | Mechanical | Top Drive | Component failure | 2 | Low | 40833.33 | 118822.55 | 159655.88
NPT00120 | 2023-10-08 | W026 | R004 | Weather | Rough Seas | Weather suspension | 2 | Low | 40833.33 | 66431.22 | 107264.56
NPT00121 | 2023-10-11 | W026 | R004 | Mechanical | Top Drive | Component failure | 4 | Low | 81666.67 | 220683.44 | 302350.11
NPT00122 | 2023-10-15 | W026 | R004 | Weather | Lightning | Reduced operating window | 2 | Low | 40833.33 | 96148.88 | 136982.21
NPT00123 | 2023-10-17 | W026 | R004 | Personnel | Training | Crew availability | 2 | Low | 40833.33 | 80458.59 | 121291.92
NPT00124 | 2023-10-20 | W026 | R004 | Weather | Heavy Rain | Reduced operating window | 2 | Low | 40833.33 | 119291.57 | 160124.9
NPT00125 | 2023-06-14 | W027 | R002 | Mechanical | Mud Pump | Hydraulic issue | 2 | Low | 38333.33 | 95013.79 | 133347.13
NPT00126 | 2023-06-21 | W027 | R002 | Personnel | HSE Meeting | Crew availability | 2 | Low | 38333.33 | 96318.2 | 134651.54
NPT00127 | 2023-06-22 | W027 | R002 | Mechanical | BOP / Well Control | Component failure | 4 | Low | 76666.67 | 218953.59 | 295620.26
NPT00128 | 2023-06-26 | W027 | R002 | Weather | High Wind | Weather suspension | 6 | Medium | 115000 | 285618.7 | 400618.7
NPT00129 | 2023-06-28 | W027 | R002 | Logistics | Cement Delay | Late delivery | 2 | Low | 38333.33 | 127086.39 | 165419.73
NPT00130 | 2023-07-06 | W027 | R002 | Logistics | Cement Delay | Inventory constraint | 2 | Low | 38333.33 | 128571.54 | 166904.88
NPT00131 | 2023-07-13 | W027 | R002 | Logistics | Port Delay | Supplier delay | 4 | Low | 76666.67 | 239893.48 | 316560.15
NPT00132 | 2024-04-04 | W028 | R002 | Drilling | Hole Cleaning | Drilling parameter issue | 2 | Low | 38333.33 | 63071.34 | 101404.67
NPT00133 | 2024-04-08 | W028 | R002 | Drilling | Lost Circulation | Drilling parameter issue | 2 | Low | 38333.33 | 65077.94 | 103411.28
NPT00134 | 2024-04-11 | W028 | R002 | Personnel | HSE Meeting | Crew availability | 2 | Low | 38333.33 | 127953.37 | 166286.7
NPT00135 | 2024-04-12 | W028 | R002 | Drilling | Hole Cleaning | Drilling parameter issue | 4 | Low | 76666.67 | 168972.22 | 245638.88
NPT00136 | 2024-04-13 | W028 | R002 | Drilling | Lost Time While Drilling | Drilling parameter issue | 4 | Low | 76666.67 | 106463.88 | 183130.54
NPT00137 | 2024-04-17 | W028 | R002 | Personnel | Crew Change | Crew availability | 2 | Low | 38333.33 | 116776.61 | 155109.95
NPT00138 | 2024-04-18 | W028 | R002 | Drilling | Hole Cleaning | Formation response | 4 | Low | 76666.67 | 163557.33 | 240223.99
NPT00139 | 2024-04-20 | W028 | R002 | Personnel | Crew Change | Training requirement | 2 | Low | 38333.33 | 127149.86 | 165483.19
NPT00140 | 2024-04-21 | W028 | R002 | Drilling | Lost Time While Drilling | Drilling parameter issue | 6 | Medium | 115000 | 352117.12 | 467117.12
NPT00141 | 2024-04-24 | W028 | R002 | Logistics | Cement Delay | Inventory constraint | 2 | Low | 38333.33 | 127744.31 | 166077.64
NPT00142 | 2024-05-05 | W028 | R002 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 76666.67 | 248909.52 | 325576.18
NPT00143 | 2024-05-07 | W028 | R002 | Mechanical | Hydraulic System | Hydraulic issue | 2 | Low | 38333.33 | 91260.45 | 129593.79
NPT00144 | 2023-11-12 | W029 | R002 | Mechanical | Top Drive | Component failure | 2 | Low | 38333.33 | 95485.58 | 133818.91
NPT00145 | 2023-11-22 | W029 | R002 | Mechanical | Hydraulic System | Hydraulic issue | 2 | Low | 38333.33 | 111661.86 | 149995.19
NPT00146 | 2023-12-02 | W029 | R002 | Personnel | Crew Change | Training requirement | 2 | Low | 38333.33 | 89811.82 | 128145.15
NPT00147 | 2023-01-25 | W030 | R002 | Drilling | Hole Cleaning | Hole cleaning | 2 | Low | 38333.33 | 128510.97 | 166844.3
NPT00148 | 2023-01-29 | W030 | R002 | Logistics | Mud / Chemical Supply | Late delivery | 4 | Low | 76666.67 | 168507.18 | 245173.84
NPT00149 | 2023-02-17 | W030 | R002 | Mechanical | Power Generation | Component failure | 4 | Low | 76666.67 | 143613.84 | 220280.51
NPT00150 | 2023-02-18 | W030 | R002 | Personnel | Crew Change | Operational meeting | 2 | Low | 38333.33 | 73306.36 | 111639.69
NPT00151 | 2023-02-23 | W030 | R002 | Drilling | Lost Circulation | Formation response | 2 | Low | 38333.33 | 60182.1 | 98515.43
NPT00152 | 2023-09-10 | W031 | R002 | Logistics | Equipment Delivery | Marine logistics | 4 | Low | 76666.67 | 171718.5 | 248385.17
NPT00153 | 2023-09-14 | W031 | R002 | Drilling | Lost Circulation | Wellbore condition | 2 | Low | 38333.33 | 75107.74 | 113441.08
NPT00154 | 2023-09-17 | W031 | R002 | Weather | High Wind | Reduced operating window | 2 | Low | 38333.33 | 68879.78 | 107213.11
NPT00155 | 2023-10-03 | W031 | R002 | Mechanical | Mud Pump | Preventive maintenance issue | 2 | Low | 38333.33 | 95453.39 | 133786.72
NPT00156 | 2023-10-06 | W031 | R002 | Mechanical | Hydraulic System | Preventive maintenance issue | 4 | Low | 76666.67 | 259171.87 | 335838.54
NPT00157 | 2024-07-21 | W032 | R004 | Mechanical | Mud Pump | Component failure | 8 | Medium | 163333.33 | 418025.43 | 581358.76
NPT00158 | 2024-07-24 | W032 | R004 | Logistics | Equipment Delivery | Inventory constraint | 2 | Low | 40833.33 | 61204.43 | 102037.77
NPT00159 | 2024-08-11 | W032 | R004 | Drilling | Stuck Pipe | Formation response | 4 | Low | 81666.67 | 183026.34 | 264693.01
NPT00160 | 2024-08-13 | W032 | R004 | Weather | High Wind | Weather suspension | 4 | Low | 81666.67 | 130213.83 | 211880.49
NPT00161 | 2024-08-14 | W032 | R004 | Drilling | Hole Cleaning | Hole cleaning | 6 | Medium | 122500 | 385916.92 | 508416.92
NPT00162 | 2024-04-24 | W033 | R002 | Drilling | Stuck Pipe | Hole cleaning | 2 | Low | 38333.33 | 87106.25 | 125439.58
NPT00163 | 2024-05-02 | W033 | R002 | Personnel | Crew Change | Training requirement | 2 | Low | 38333.33 | 81935.62 | 120268.96
NPT00164 | 2024-05-03 | W033 | R002 | Mechanical | Power Generation | Hydraulic issue | 4 | Low | 76666.67 | 133749.5 | 210416.17
NPT00165 | 2024-05-08 | W033 | R002 | Logistics | Mud / Chemical Supply | Supplier delay | 2 | Low | 38333.33 | 60263.46 | 98596.79
NPT00166 | 2024-05-29 | W035 | R003 | Weather | Heavy Rain | Reduced operating window | 2 | Low | 40000 | 113023.43 | 153023.43
NPT00167 | 2024-06-09 | W035 | R003 | Mechanical | BOP / Well Control | Electrical fault | 2 | Low | 40000 | 54416.8 | 94416.8
NPT00168 | 2024-06-13 | W035 | R003 | Weather | Heavy Rain | Marine conditions | 2 | Low | 40000 | 109976.46 | 149976.46
NPT00169 | 2024-06-24 | W035 | R003 | Personnel | Personnel Availability | Training requirement | 2 | Low | 40000 | 92529.03 | 132529.03
NPT00170 | 2024-11-19 | W036 | R002 | Personnel | HSE Meeting | Operational meeting | 2 | Low | 38333.33 | 76573.04 | 114906.38
NPT00171 | 2024-11-20 | W036 | R002 | Mechanical | Top Drive | Preventive maintenance issue | 2 | Low | 38333.33 | 129185.85 | 167519.18
NPT00172 | 2024-11-21 | W036 | R002 | Mechanical | BOP / Well Control | Component failure | 4 | Low | 76666.67 | 223906.75 | 300573.42
NPT00173 | 2024-12-03 | W036 | R002 | Logistics | Supply Boat Delay | Inventory constraint | 2 | Low | 38333.33 | 117365.61 | 155698.95
NPT00174 | 2024-12-07 | W036 | R002 | Drilling | Lost Circulation | Formation response | 2 | Low | 38333.33 | 105112.12 | 143445.45
NPT00175 | 2024-04-26 | W037 | R002 | Drilling | Stuck Pipe | Wellbore condition | 4 | Low | 76666.67 | 165445.62 | 242112.29
NPT00176 | 2024-04-27 | W037 | R002 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 38333.33 | 68964.97 | 107298.3
NPT00177 | 2024-05-12 | W037 | R002 | Drilling | Wellbore Instability | Hole cleaning | 6 | Medium | 115000 | 380928 | 495928
NPT00178 | 2024-05-14 | W037 | R002 | Mechanical | Top Drive | Preventive maintenance issue | 2 | Low | 38333.33 | 84555.65 | 122888.99
NPT00179 | 2024-05-17 | W037 | R002 | Drilling | Lost Time While Drilling | Wellbore condition | 2 | Low | 38333.33 | 100131.14 | 138464.47
NPT00180 | 2023-07-13 | W039 | R002 | Mechanical | Mud Pump | Component failure | 4 | Low | 76666.67 | 136458.85 | 213125.51
NPT00181 | 2023-07-18 | W039 | R002 | Weather | Rough Seas | Reduced operating window | 2 | Low | 38333.33 | 55195.74 | 93529.08
NPT00182 | 2023-07-19 | W039 | R002 | Drilling | Lost Time While Drilling | Drilling parameter issue | 2 | Low | 38333.33 | 62431.77 | 100765.1
NPT00183 | 2023-07-24 | W039 | R002 | Logistics | Supply Boat Delay | Supplier delay | 4 | Low | 76666.67 | 244624.67 | 321291.34
NPT00184 | 2023-07-26 | W039 | R002 | Mechanical | Power Generation | Component failure | 2 | Low | 38333.33 | 97954.14 | 136287.48
NPT00185 | 2023-08-03 | W039 | R002 | Weather | Heavy Rain | Weather suspension | 2 | Low | 38333.33 | 101520.75 | 139854.09
NPT00186 | 2023-08-08 | W039 | R002 | Drilling | Lost Circulation | Drilling parameter issue | 4 | Low | 76666.67 | 106808.29 | 183474.96
NPT00187 | 2024-11-19 | W040 | R002 | Logistics | Supply Boat Delay | Supplier delay | 2 | Low | 38333.33 | 51428.88 | 89762.21
NPT00188 | 2024-11-22 | W040 | R002 | Logistics | Equipment Delivery | Inventory constraint | 2 | Low | 38333.33 | 127656.81 | 165990.15
NPT00189 | 2024-11-25 | W040 | R002 | Logistics | Mud / Chemical Supply | Marine logistics | 4 | Low | 76666.67 | 191494.72 | 268161.38
NPT00190 | 2024-11-27 | W040 | R002 | Drilling | Fishing | Drilling parameter issue | 2 | Low | 38333.33 | 117918.27 | 156251.61
NPT00191 | 2024-12-04 | W040 | R002 | Mechanical | Hydraulic System | Electrical fault | 2 | Low | 38333.33 | 67219.5 | 105552.83
NPT00192 | 2024-07-18 | W041 | R002 | Mechanical | Drawworks | Electrical fault | 4 | Low | 76666.67 | 111399.12 | 188065.78
NPT00193 | 2024-07-30 | W041 | R002 | Logistics | Supply Boat Delay | Marine logistics | 2 | Low | 38333.33 | 105002.71 | 143336.05
NPT00194 | 2024-07-31 | W041 | R002 | Mechanical | Mud Pump | Component failure | 4 | Low | 76666.67 | 183500.23 | 260166.9
NPT00195 | 2024-08-02 | W041 | R002 | Weather | Heavy Rain | Marine conditions | 4 | Low | 76666.67 | 139727.08 | 216393.75
NPT00196 | 2024-08-10 | W041 | R002 | Drilling | Wellbore Instability | Formation response | 2 | Low | 38333.33 | 58022.99 | 96356.33
NPT00197 | 2024-07-22 | W042 | R004 | Drilling | Lost Circulation | Wellbore condition | 2 | Low | 40833.33 | 100588.4 | 141421.74
NPT00198 | 2024-07-25 | W042 | R004 | Weather | Heavy Rain | Reduced operating window | 4 | Low | 81666.67 | 153805.73 | 235472.4
NPT00199 | 2024-07-27 | W042 | R004 | Drilling | Lost Circulation | Formation response | 4 | Low | 81666.67 | 256487.32 | 338153.99
NPT00200 | 2024-07-29 | W042 | R004 | Mechanical | Drawworks | Preventive maintenance issue | 2 | Low | 40833.33 | 90325.11 | 131158.45
NPT00201 | 2024-07-30 | W042 | R004 | Weather | High Wind | Reduced operating window | 4 | Low | 81666.67 | 141413.7 | 223080.37
NPT00202 | 2024-08-11 | W042 | R004 | Mechanical | Top Drive | Hydraulic issue | 4 | Low | 81666.67 | 207970.04 | 289636.71
NPT00203 | 2023-09-08 | W043 | R002 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 38333.33 | 114555.54 | 152888.87
NPT00204 | 2023-09-18 | W043 | R002 | Drilling | Stuck Pipe | Formation response | 2 | Low | 38333.33 | 99048.75 | 137382.09
NPT00205 | 2023-09-19 | W043 | R002 | Mechanical | Top Drive | Hydraulic issue | 2 | Low | 38333.33 | 71912.49 | 110245.83
NPT00206 | 2023-09-20 | W043 | R002 | Mechanical | Mud Pump | Component failure | 2 | Low | 38333.33 | 77120.62 | 115453.95
NPT00207 | 2023-09-22 | W043 | R002 | Mechanical | Hydraulic System | Component failure | 6 | Medium | 115000 | 277637.73 | 392637.73
NPT00208 | 2024-05-19 | W044 | R003 | Personnel | Crew Change | Training requirement | 2 | Low | 40000 | 102498.37 | 142498.37
NPT00209 | 2024-05-20 | W044 | R003 | Logistics | Equipment Delivery | Marine logistics | 4 | Low | 80000 | 144147.81 | 224147.81
NPT00210 | 2024-05-22 | W044 | R003 | Mechanical | Mud Pump | Component failure | 2 | Low | 40000 | 120352.94 | 160352.94
NPT00211 | 2024-05-31 | W044 | R003 | Weather | High Wind | Marine conditions | 2 | Low | 40000 | 70537.74 | 110537.74
NPT00212 | 2024-06-05 | W044 | R003 | Drilling | Lost Time While Drilling | Wellbore condition | 2 | Low | 40000 | 96732.97 | 136732.97
NPT00213 | 2024-06-08 | W044 | R003 | Drilling | Hole Cleaning | Formation response | 2 | Low | 40000 | 55402.19 | 95402.19
NPT00214 | 2024-06-12 | W044 | R003 | Logistics | Supply Boat Delay | Inventory constraint | 2 | Low | 40000 | 75861.27 | 115861.27
NPT00215 | 2024-06-16 | W044 | R003 | Mechanical | Mud Pump | Preventive maintenance issue | 4 | Low | 80000 | 177180.16 | 257180.16
NPT00216 | 2024-06-18 | W044 | R003 | Mechanical | Hydraulic System | Hydraulic issue | 2 | Low | 40000 | 75177.4 | 115177.4
NPT00217 | 2023-05-19 | W045 | R004 | Mechanical | Drawworks | Electrical fault | 2 | Low | 40833.33 | 57521.7 | 98355.03
NPT00218 | 2023-05-23 | W045 | R004 | Weather | High Wind | Marine conditions | 2 | Low | 40833.33 | 73749.48 | 114582.81
NPT00219 | 2023-05-24 | W045 | R004 | Weather | High Wind | Weather suspension | 2 | Low | 40833.33 | 70951.71 | 111785.04
NPT00220 | 2024-04-30 | W046 | R003 | Weather | Lightning | Weather suspension | 2 | Low | 40000 | 86670.1 | 126670.1
NPT00221 | 2024-05-01 | W046 | R003 | Drilling | Fishing | Formation response | 2 | Low | 40000 | 107874.51 | 147874.51
NPT00222 | 2024-05-08 | W046 | R003 | Drilling | Lost Time While Drilling | Hole cleaning | 2 | Low | 40000 | 101871.81 | 141871.81
NPT00223 | 2024-05-16 | W046 | R003 | Logistics | Supply Boat Delay | Marine logistics | 2 | Low | 40000 | 127765.61 | 167765.61
NPT00224 | 2024-05-23 | W046 | R003 | Drilling | Stuck Pipe | Drilling parameter issue | 2 | Low | 40000 | 108359.61 | 148359.61
NPT00225 | 2024-10-14 | W047 | R004 | Weather | High Wind | Weather suspension | 2 | Low | 40833.33 | 63962.97 | 104796.3
NPT00226 | 2024-10-18 | W047 | R004 | Mechanical | Top Drive | Preventive maintenance issue | 2 | Low | 40833.33 | 71018.37 | 111851.7
NPT00227 | 2024-10-30 | W047 | R004 | Weather | Lightning | Reduced operating window | 4 | Low | 81666.67 | 190839.3 | 272505.96
NPT00228 | 2024-10-31 | W047 | R004 | Mechanical | Power Generation | Preventive maintenance issue | 2 | Low | 40833.33 | 73044.8 | 113878.13
NPT00229 | 2024-11-02 | W047 | R004 | Logistics | Supply Boat Delay | Marine logistics | 4 | Low | 81666.67 | 109006.21 | 190672.88
NPT00230 | 2023-02-01 | W048 | R002 | Mechanical | Hydraulic System | Component failure | 4 | Low | 76666.67 | 206434.23 | 283100.9
NPT00231 | 2023-02-13 | W048 | R002 | Drilling | Hole Cleaning | Wellbore condition | 2 | Low | 38333.33 | 69002.85 | 107336.19
NPT00232 | 2023-02-14 | W048 | R002 | Mechanical | Top Drive | Hydraulic issue | 6 | Medium | 115000 | 329537.03 | 444537.03
NPT00233 | 2023-02-15 | W048 | R002 | Drilling | Wellbore Instability | Hole cleaning | 4 | Low | 76666.67 | 195230.3 | 271896.96
NPT00234 | 2023-02-20 | W048 | R002 | Mechanical | BOP / Well Control | Component failure | 4 | Low | 76666.67 | 226763.33 | 303430
NPT00235 | 2023-07-03 | W049 | R003 | Logistics | Supply Boat Delay | Inventory constraint | 2 | Low | 40000 | 57754.76 | 97754.76
NPT00236 | 2023-07-06 | W049 | R003 | Drilling | Fishing | Wellbore condition | 2 | Low | 40000 | 116255.83 | 156255.83
NPT00237 | 2023-07-19 | W049 | R003 | Mechanical | Mud Pump | Hydraulic issue | 4 | Low | 80000 | 107851.85 | 187851.85
NPT00238 | 2023-10-07 | W050 | R004 | Mechanical | Hydraulic System | Electrical fault | 2 | Low | 40833.33 | 104324.12 | 145157.46
NPT00239 | 2023-10-08 | W050 | R004 | Drilling | Fishing | Wellbore condition | 2 | Low | 40833.33 | 97476.5 | 138309.84
NPT00240 | 2023-10-17 | W050 | R004 | Mechanical | Mud Pump | Hydraulic issue | 2 | Low | 40833.33 | 125531.49 | 166364.83
NPT00241 | 2023-10-21 | W050 | R004 | Weather | High Wind | Reduced operating window | 4 | Low | 81666.67 | 228432.8 | 310099.46
NPT00242 | 2023-10-22 | W050 | R004 | Drilling | Wellbore Instability | Wellbore condition | 4 | Low | 81666.67 | 108151.05 | 189817.72