## Validation_Dashboard
Validation | Result
Duplicate NPT_ID | PASS
Null NPT_ID | PASS
Negative Duration | PASS
Negative Direct Cost | PASS
Negative Deferred Cost | PASS
Negative Total Impact | PASS
Economic Reconciliation | PASS
Addressable Impact Non-Negative | PASS
Conservative Savings Non-Negative | PASS
Target Savings Non-Negative | PASS
Stretch Savings Non-Negative | PASS
Double Counting Reconciliation | PASS
OVERALL STATUS | PASS

## Economic_Reconciliation
Metric | Value
Total NPT Events | 677
Total NPT Hours | 4008
Direct NPT Cost USD | 79204408
Deferred Cost USD | 118945770
Calculated Total Impact USD | 198150178
Recorded Total Impact USD | 198150178
Economic Difference USD | 0
Addressable Impact USD | 77064618.5875
Conservative Savings USD | 15412923.7175
Target Savings USD | 30825847.435
Stretch Savings USD | 46238771.1525
Addressable Impact % of Total | 38.892
Conservative Savings % of Total Impact | 7.7784
Target Savings % of Total Impact | 15.5568
Stretch Savings % of Total Impact | 23.3352
Unique NPT IDs | 677
Duplicate NPT IDs | 0
Null NPT IDs | 0
Negative Duration Rows | 0
Negative Direct Cost Rows | 0
Negative Deferred Cost Rows | 0
Negative Total Impact Rows | 0
Economic Mismatch Rows | 0

## Rig_Validation
Rig_ID | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | Target_Savings_%_of_Impact
R002 | 282 | 1610 | 76560445 | 30956296.0125 | 6191259.2025 | 12382518.405 | 18573777.6075 | 16.1735
R004 | 199 | 1186 | 61470399 | 23318438.95 | 4663687.79 | 9327375.58 | 13991063.37 | 15.1738
R003 | 116 | 694 | 34396458 | 12568730.0125 | 2513746.0025 | 5027492.005 | 7541238.0075 | 14.6163
R001 | 80 | 518 | 25722876 | 10221153.6125 | 2044230.7225 | 4088461.445 | 6132692.1675 | 15.8943

## Well_Validation
Priority_Rank | Well_ID | Rig_ID | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | Target_Savings_%_of_Impact
1 | W003 | R004 | 13 | 88 | 5225678 | 2730076.025 | 546015.205 | 1092030.41 | 1638045.615 | 20.8974
2 | W011 | R004 | 16 | 104 | 5187621 | 2647862.075 | 529572.415 | 1059144.83 | 1588717.245 | 20.4168
3 | W007 | R001 | 16 | 128 | 6815911 | 2638464.85 | 527692.97 | 1055385.94 | 1583078.91 | 15.4842
4 | W040 | R002 | 21 | 130 | 6620110 | 2589362.3 | 517872.46 | 1035744.92 | 1553617.38 | 15.6454
5 | W002 | R001 | 13 | 88 | 4546361 | 2278951.175 | 455790.235 | 911580.47 | 1367370.705 | 20.0508
6 | W036 | R002 | 19 | 108 | 5411508 | 2188568.9125 | 437713.7825 | 875427.565 | 1313141.3475 | 16.1771
7 | W033 | R002 | 16 | 90 | 4243450 | 1962145.55 | 392429.11 | 784858.22 | 1177287.33 | 18.4958
8 | W046 | R003 | 16 | 102 | 5032158 | 1941940.85 | 388388.17 | 776776.34 | 1165164.51 | 15.4362
9 | W019 | R003 | 13 | 114 | 5561717 | 1928002.325 | 385600.465 | 771200.93 | 1156801.395 | 13.8662
10 | W015 | R003 | 14 | 76 | 4385282 | 1878341.95 | 375668.39 | 751336.78 | 1127005.17 | 17.1331
11 | W023 | R004 | 14 | 84 | 4828213 | 1863016.9 | 372603.38 | 745206.76 | 1117810.14 | 15.4344
12 | W048 | R002 | 14 | 86 | 4208923 | 1851299.95 | 370259.99 | 740519.98 | 1110779.97 | 17.594
13 | W020 | R003 | 20 | 90 | 4565483 | 1812456.825 | 362491.365 | 724982.73 | 1087474.095 | 15.8797
14 | W006 | R002 | 15 | 84 | 4231281 | 1800698.425 | 360139.685 | 720279.37 | 1080419.055 | 17.0227
15 | W009 | R001 | 15 | 100 | 4669372 | 1783363.675 | 356672.735 | 713345.47 | 1070018.205 | 15.2771
16 | W030 | R002 | 15 | 90 | 4137386 | 1768676.775 | 353735.355 | 707470.71 | 1061206.065 | 17.0995
17 | W043 | R002 | 18 | 94 | 4350399 | 1761792.3375 | 352358.4675 | 704716.935 | 1057075.4025 | 16.1989
18 | W013 | R003 | 20 | 96 | 4883822 | 1758756.1375 | 351751.2275 | 703502.455 | 1055253.6825 | 14.4048
19 | W050 | R004 | 11 | 74 | 3894520 | 1744529.725 | 348905.945 | 697811.89 | 1046717.835 | 17.9178
20 | W021 | R002 | 16 | 94 | 4506303 | 1732894.9 | 346578.98 | 693157.96 | 1039736.94 | 15.382
21 | W027 | R002 | 10 | 66 | 3222709 | 1615250.7375 | 323050.1475 | 646100.295 | 969150.4425 | 20.0484
22 | W031 | R002 | 11 | 60 | 3032755 | 1606002.5 | 321200.5 | 642401 | 963601.5 | 21.1821
23 | W047 | R004 | 13 | 78 | 3918083 | 1574679.725 | 314935.945 | 629871.89 | 944807.835 | 16.076
24 | W041 | R002 | 14 | 76 | 3512146 | 1565498.85 | 313099.77 | 626199.54 | 939299.31 | 17.8295
25 | W028 | R002 | 15 | 90 | 4143050 | 1536386.575 | 307277.315 | 614554.63 | 921831.945 | 14.8334
26 | W010 | R002 | 16 | 106 | 4734861 | 1462338.625 | 292467.725 | 584935.45 | 877403.175 | 12.3538
27 | W026 | R004 | 11 | 90 | 4452824 | 1461938.9 | 292387.78 | 584775.56 | 877163.34 | 13.1327
28 | W001 | R004 | 19 | 88 | 4605541 | 1454525.3875 | 290905.0775 | 581810.155 | 872715.2325 | 12.6328
29 | W038 | R004 | 15 | 68 | 3555637 | 1420920.25 | 284184.05 | 568368.1 | 852552.15 | 15.985
30 | W018 | R004 | 14 | 88 | 3855804 | 1380726.475 | 276145.295 | 552290.59 | 828435.885 | 14.3236
31 | W029 | R002 | 14 | 70 | 3349062 | 1338967.275 | 267793.455 | 535586.91 | 803380.365 | 15.9921
32 | W037 | R002 | 9 | 72 | 3194393 | 1331400.5 | 266280.1 | 532560.2 | 798840.3 | 16.6717
33 | W022 | R001 | 13 | 74 | 3442372 | 1328960.275 | 265792.055 | 531584.11 | 797376.165 | 15.4424
34 | W024 | R002 | 12 | 68 | 3242338 | 1272312.45 | 254462.49 | 508924.98 | 763387.47 | 15.6962
35 | W034 | R001 | 12 | 74 | 3657546 | 1271949.425 | 254389.885 | 508779.77 | 763169.655 | 13.9104
36 | W049 | R003 | 9 | 60 | 2954155 | 1238486.15 | 247697.23 | 495394.46 | 743091.69 | 16.7694
37 | W045 | R004 | 10 | 80 | 4553567 | 1204652.675 | 240930.535 | 481861.07 | 722791.605 | 10.5821
38 | W012 | R004 | 11 | 64 | 3233740 | 1160885.175 | 232177.035 | 464354.07 | 696531.105 | 14.3597
39 | W032 | R004 | 15 | 86 | 4251690 | 1152206.925 | 230441.385 | 460882.77 | 691324.155 | 10.84
40 | W035 | R003 | 12 | 92 | 3595897 | 1132565.075 | 226513.015 | 453026.03 | 679539.045 | 12.5984
41 | W025 | R004 | 11 | 54 | 2858646 | 1116298.15 | 223259.63 | 446519.26 | 669778.89 | 15.62
42 | W005 | R002 | 13 | 64 | 3143733 | 995582.725 | 199116.545 | 398233.09 | 597349.635 | 12.6675
43 | W039 | R002 | 13 | 70 | 3123391 | 979160.5625 | 195832.1125 | 391664.225 | 587496.3375 | 12.5397
44 | W017 | R001 | 11 | 54 | 2591314 | 919464.2125 | 183892.8425 | 367785.685 | 551678.5275 | 14.193
45 | W044 | R003 | 12 | 64 | 3417944 | 878180.7 | 175636.14 | 351272.28 | 526908.42 | 10.2773
46 | W042 | R004 | 8 | 52 | 2398167 | 865003.175 | 173000.635 | 346001.27 | 519001.905 | 14.4277
47 | W004 | R002 | 11 | 52 | 2334494 | 826182.3 | 165236.46 | 330472.92 | 495709.38 | 14.1561
48 | W014 | R004 | 8 | 38 | 2106838 | 804775.825 | 160955.165 | 321910.33 | 482865.495 | 15.2793
49 | W008 | R002 | 10 | 40 | 1818153 | 771773.7625 | 154354.7525 | 308709.505 | 463064.2575 | 16.9793
50 | W016 | R004 | 10 | 50 | 2543830 | 736341.5625 | 147268.3125 | 294536.625 | 441804.9375 | 11.5785

## Root_Cause_Validation
Priority_Rank | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | Target_Savings_%_of_Impact
1 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 4 | 44 | 2657621 | 1969788.15 | 393957.63 | 787915.26 | 1181872.89 | 29.6474
2 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 5 | 48 | 2373432 | 1485052.65 | 297010.53 | 594021.06 | 891031.59 | 25.0279
3 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | 3 | 38 | 2000357 | 1292487.6 | 258497.52 | 516995.04 | 775492.56 | 25.8451
4 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 4 | 34 | 1884068 | 1170621.675 | 234124.335 | 468248.67 | 702373.005 | 24.8531
5 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 7 | 38 | 2003193 | 1112858.55 | 222571.71 | 445143.42 | 667715.13 | 22.2217
6 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | 3 | 30 | 1954748 | 1099258.2 | 219851.64 | 439703.28 | 659554.92 | 22.4941
7 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | 3 | 34 | 2092267 | 1042276.5 | 208455.3 | 416910.6 | 625365.9 | 19.9263
8 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 5 | 50 | 2213914 | 1032688 | 206537.6 | 413075.2 | 619612.8 | 18.6581
9 | Drilling | Fishing Operation | Formation Instability | Operator | 7 | 42 | 2358345 | 974856.675 | 194971.335 | 389942.67 | 584914.005 | 16.5346
10 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | 3 | 32 | 1617385 | 901808.8 | 180361.76 | 360723.52 | 541085.28 | 22.3029
11 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 26 | 1123514 | 887314.5 | 177462.9 | 354925.8 | 532388.7 | 31.5907
12 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 5 | 42 | 2212195 | 884878 | 176975.6 | 353951.2 | 530926.8 | 16
13 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 6 | 50 | 2798735 | 839620.5 | 167924.1 | 335848.2 | 503772.3 | 12
14 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | 5 | 30 | 1517511 | 802511.6 | 160502.32 | 321004.64 | 481506.96 | 21.1534
15 | Drilling | Bit Failure | Bit Wear | Mud Engineering | 3 | 38 | 2004429 | 801771.6 | 160354.32 | 320708.64 | 481062.96 | 16
16 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | 3 | 28 | 1561022 | 767458.35 | 153491.67 | 306983.34 | 460475.01 | 19.6655
17 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | 5 | 48 | 2175389 | 766791.025 | 153358.205 | 306716.41 | 460074.615 | 14.0994
18 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | 3 | 28 | 987517 | 758255.85 | 151651.17 | 303302.34 | 454953.51 | 30.7136
19 | Drilling | Hole Cleaning | Bit Wear | Operator | 6 | 36 | 1482907 | 748773.6 | 149754.72 | 299509.44 | 449264.16 | 20.1975
20 | Drilling | Lost Circulation | Bit Wear | Operator | 4 | 20 | 1095366 | 665554.8 | 133110.96 | 266221.92 | 399332.88 | 24.3044
21 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 26 | 1175492 | 654134.85 | 130826.97 | 261653.94 | 392480.91 | 22.2591
22 | Drilling | Well Control | Bit Wear | Mud Engineering | 3 | 26 | 1534652 | 641240.2 | 128248.04 | 256496.08 | 384744.12 | 16.7136
23 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | 2 | 18 | 1065290 | 639174 | 127834.8 | 255669.6 | 383504.4 | 24
24 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 5 | 20 | 1230413 | 634323.15 | 126864.63 | 253729.26 | 380593.89 | 20.6215
25 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | 3 | 22 | 1087628 | 631715.85 | 126343.17 | 252686.34 | 379029.51 | 23.2328
26 | Drilling | Well Control | Bit Wear | Directional Drilling | 3 | 26 | 1563793 | 625517.2 | 125103.44 | 250206.88 | 375310.32 | 16
27 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | 3 | 28 | 1379275 | 620673.75 | 124134.75 | 248269.5 | 372404.25 | 18
28 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | 4 | 30 | 1410677 | 619549.125 | 123909.825 | 247819.65 | 371729.475 | 17.5674
29 | Drilling | Fishing Operation | Unexpected Pressure | Operator | 5 | 24 | 1065519 | 618899.775 | 123779.955 | 247559.91 | 371339.865 | 23.2337
30 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | 2 | 16 | 869101 | 596587.05 | 119317.41 | 238634.82 | 357952.23 | 27.4577
31 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | 2 | 26 | 1353054 | 589487.7 | 117897.54 | 235795.08 | 353692.62 | 17.4269
32 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | 3 | 36 | 1425621 | 570248.4 | 114049.68 | 228099.36 | 342149.04 | 16
33 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | 6 | 30 | 1385402 | 564893.875 | 112978.775 | 225957.55 | 338936.325 | 16.3099
34 | Logistics | Waiting on Materials | Material Shortage | Procurement | 5 | 32 | 1610702 | 554535.75 | 110907.15 | 221814.3 | 332721.45 | 13.7713
35 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 5 | 32 | 1569191 | 552435.65 | 110487.13 | 220974.26 | 331461.39 | 14.082
36 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 6 | 30 | 1519765 | 532882.8375 | 106576.5675 | 213153.135 | 319729.7025 | 14.0254
37 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | 1 | 24 | 887460 | 532476 | 106495.2 | 212990.4 | 319485.6 | 24
38 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 4 | 22 | 1069198 | 531426.6 | 106285.32 | 212570.64 | 318855.96 | 19.8813
39 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | 4 | 24 | 1176410 | 515175.8625 | 103035.1725 | 206070.345 | 309105.5175 | 17.5169
40 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | 3 | 26 | 1130603 | 508771.35 | 101754.27 | 203508.54 | 305262.81 | 18
41 | Weather | Poor Visibility | Heavy Rain | Weather | 5 | 46 | 2582238 | 506538.975 | 101307.795 | 202615.59 | 303923.385 | 7.8465
42 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | 3 | 14 | 638424 | 503349.525 | 100669.905 | 201339.81 | 302009.715 | 31.537
43 | Drilling | Stuck Pipe | Bit Wear | Operator | 2 | 16 | 1001961 | 500209.2 | 100041.84 | 200083.68 | 300125.52 | 19.9692
44 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | 1 | 18 | 1109300 | 499185 | 99837 | 199674 | 299511 | 18
45 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 6 | 34 | 1655444 | 496633.2 | 99326.64 | 198653.28 | 297979.92 | 12
46 | Drilling | Lost Circulation | Formation Instability | Operator | 3 | 22 | 1322159 | 486760.4625 | 97352.0925 | 194704.185 | 292056.2775 | 14.7262
47 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | 5 | 26 | 1187896 | 475158.4 | 95031.68 | 190063.36 | 285095.04 | 16
48 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | 2 | 14 | 671086 | 466397.1 | 93279.42 | 186558.84 | 279838.26 | 27.7995
49 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | 2 | 12 | 662865 | 461333.25 | 92266.65 | 184533.3 | 276799.95 | 27.8387
50 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | 1 | 18 | 1023187 | 460434.15 | 92086.83 | 184173.66 | 276260.49 | 18
51 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | 2 | 24 | 1475042 | 442512.6 | 88502.52 | 177005.04 | 265507.56 | 12
52 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | 2 | 14 | 645736 | 435871.8 | 87174.36 | 174348.72 | 261523.08 | 27
53 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 5 | 18 | 867546 | 429179.85 | 85835.97 | 171671.94 | 257507.91 | 19.7882
54 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | 3 | 12 | 756920 | 427674 | 85534.8 | 171069.6 | 256604.4 | 22.6008
55 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | 3 | 18 | 926009 | 416704.05 | 83340.81 | 166681.62 | 250022.43 | 18
56 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | 3 | 22 | 935897 | 409760.325 | 81952.065 | 163904.13 | 245856.195 | 17.5131
57 | Drilling | Stuck Pipe | Differential Sticking | Operator | 4 | 26 | 1008386 | 403354.4 | 80670.88 | 161341.76 | 242012.64 | 16
58 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 4 | 26 | 881316 | 401832.4375 | 80366.4875 | 160732.975 | 241099.4625 | 18.2378
59 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | 7 | 22 | 1146364 | 398141.9 | 79628.38 | 159256.76 | 238885.14 | 13.8923
60 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | 2 | 20 | 881030 | 396463.5 | 79292.7 | 158585.4 | 237878.1 | 18
61 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | 3 | 16 | 697523 | 386416.125 | 77283.225 | 154566.45 | 231849.675 | 22.1593
62 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 4 | 24 | 933650 | 380741.4 | 76148.28 | 152296.56 | 228444.84 | 16.312
63 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | 2 | 12 | 727418 | 372951.6 | 74590.32 | 149180.64 | 223770.96 | 20.5082
64 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | 2 | 10 | 458634 | 365895.45 | 73179.09 | 146358.18 | 219537.27 | 31.9118
65 | Drilling | Well Control | Formation Instability | Operator | 3 | 16 | 809998 | 364118.3 | 72823.66 | 145647.32 | 218470.98 | 17.9812
66 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | 3 | 20 | 917930 | 363011.35 | 72602.27 | 145204.54 | 217806.81 | 15.8187
67 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | 2 | 22 | 800015 | 360006.75 | 72001.35 | 144002.7 | 216004.05 | 18
68 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | 3 | 18 | 1045924 | 356460.9 | 71292.18 | 142584.36 | 213876.54 | 13.6324
69 | Drilling | Stuck Pipe | Formation Instability | Operator | 5 | 22 | 1095578 | 356062.85 | 71212.57 | 142425.14 | 213637.71 | 13
70 | Drilling | Bit Failure | Unexpected Pressure | Operator | 3 | 22 | 1093353 | 355339.725 | 71067.945 | 142135.89 | 213203.835 | 13
71 | Weather | High Waves | Strong Wind | Marine Operations | 2 | 30 | 1386140 | 353903.775 | 70780.755 | 141561.51 | 212342.265 | 10.2126
72 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | 2 | 14 | 881833 | 352733.2 | 70546.64 | 141093.28 | 211639.92 | 16
73 | Weather | Lightning | Heavy Rain | Marine Operations | 4 | 40 | 1820777 | 351963.75 | 70392.75 | 140785.5 | 211178.25 | 7.7322
74 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | 3 | 22 | 1003340 | 351169 | 70233.8 | 140467.6 | 210701.4 | 14
75 | Weather | Heavy Rain | Heavy Rain | Weather | 5 | 42 | 1845394 | 347225.1 | 69445.02 | 138890.04 | 208335.06 | 7.5263
76 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | 2 | 12 | 685540 | 346394.7 | 69278.94 | 138557.88 | 207836.82 | 20.2115
77 | Personnel | Crew Change | Medical Emergency | Medical Team | 1 | 18 | 1141635 | 342490.5 | 68498.1 | 136996.2 | 205494.3 | 12
78 | Weather | Poor Visibility | Strong Wind | Marine Operations | 3 | 34 | 2273104 | 340965.6 | 68193.12 | 136386.24 | 204579.36 | 6
79 | Drilling | Fishing Operation | Differential Sticking | Operator | 4 | 22 | 852025 | 340810 | 68162 | 136324 | 204486 | 16
80 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | 2 | 14 | 851293 | 340517.2 | 68103.44 | 136206.88 | 204310.32 | 16
81 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | 1 | 18 | 756321 | 340344.45 | 68068.89 | 136137.78 | 204206.67 | 18
82 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 4 | 14 | 732703 | 329716.35 | 65943.27 | 131886.54 | 197829.81 | 18
83 | Weather | Strong Wind | Strong Wind | Marine Operations | 8 | 40 | 1895190 | 327046.725 | 65409.345 | 130818.69 | 196228.035 | 6.9027
84 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | 1 | 12 | 363301 | 326970.9 | 65394.18 | 130788.36 | 196182.54 | 36
85 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 4 | 20 | 1002841 | 322325.25 | 64465.05 | 128930.1 | 193395.15 | 12.8565
86 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | 2 | 10 | 433494 | 322178.4 | 64435.68 | 128871.36 | 193307.04 | 29.7285
87 | Weather | Lightning | Lightning | Marine Operations | 7 | 30 | 1622815 | 319721.85 | 63944.37 | 127888.74 | 191833.11 | 7.8807
88 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | 3 | 16 | 576449 | 311912.1 | 62382.42 | 124764.84 | 187147.26 | 21.6437
89 | Drilling | Hole Cleaning | Differential Sticking | Operator | 3 | 16 | 687166 | 311643.6 | 62328.72 | 124657.44 | 186986.16 | 18.1408
90 | Drilling | Well Control | Formation Instability | Mud Engineering | 5 | 18 | 818050 | 304212.675 | 60842.535 | 121685.07 | 182527.605 | 14.875
91 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | 4 | 14 | 676390 | 297573.6 | 59514.72 | 119029.44 | 178544.16 | 17.5978
92 | Weather | Poor Visibility | Heavy Rain | Marine Operations | 4 | 32 | 1600060 | 296826.825 | 59365.365 | 118730.73 | 178096.095 | 7.4204
93 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | 2 | 16 | 865026 | 296620.05 | 59324.01 | 118648.02 | 177972.03 | 13.7161
94 | Weather | Lightning | Lightning | Weather | 9 | 36 | 1680506 | 294172.575 | 58834.515 | 117669.03 | 176503.545 | 7.002
95 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | 1 | 8 | 433276 | 292461.3 | 58492.26 | 116984.52 | 175476.78 | 27
96 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | 2 | 14 | 516750 | 290142 | 58028.4 | 116056.8 | 174085.2 | 22.459
97 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | 1 | 8 | 429389 | 289837.575 | 57967.515 | 115935.03 | 173902.545 | 27
98 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | 2 | 8 | 518346 | 289603.125 | 57920.625 | 115841.25 | 173761.875 | 22.3482
99 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 4 | 14 | 551021 | 287480 | 57496 | 114992 | 172488 | 20.8689
100 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | 4 | 20 | 879433 | 285815.725 | 57163.145 | 114326.29 | 171489.435 | 13
101 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | 3 | 10 | 538226 | 284628.6 | 56925.72 | 113851.44 | 170777.16 | 21.1531
102 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | 3 | 16 | 944545 | 283363.5 | 56672.7 | 113345.4 | 170018.1 | 12
103 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | 2 | 12 | 704567 | 281826.8 | 56365.36 | 112730.72 | 169096.08 | 16
104 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | 3 | 16 | 742227 | 276792.2625 | 55358.4525 | 110716.905 | 166075.3575 | 14.9169
105 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | 1 | 18 | 918898 | 275669.4 | 55133.88 | 110267.76 | 165401.64 | 12
106 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | 2 | 10 | 491661 | 273401.6 | 54680.32 | 109360.64 | 164040.96 | 22.2431
107 | Weather | Heavy Rain | Storm | Weather | 3 | 34 | 1650500 | 272862.975 | 54572.595 | 109145.19 | 163717.785 | 6.6129
108 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | 3 | 12 | 714816 | 272844.325 | 54568.865 | 109137.73 | 163706.595 | 15.2679
109 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | 2 | 16 | 768896 | 271341.6 | 54268.32 | 108536.64 | 162804.96 | 14.1159
110 | Weather | High Waves | Heavy Rain | Marine Operations | 4 | 18 | 937830 | 264787.8 | 52957.56 | 105915.12 | 158872.68 | 11.2936
111 | Logistics | Waiting on Cement | Customs Clearance | Procurement | 2 | 12 | 625405 | 259556.4 | 51911.28 | 103822.56 | 155733.84 | 16.6009
112 | Weather | Heavy Rain | Strong Wind | Marine Operations | 3 | 32 | 1681773 | 256981.275 | 51396.255 | 102792.51 | 154188.765 | 6.1122
113 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | 2 | 14 | 566863 | 255088.35 | 51017.67 | 102035.34 | 153053.01 | 18
114 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 4 | 18 | 726230 | 254180.5 | 50836.1 | 101672.2 | 152508.3 | 14
115 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | 3 | 10 | 609626 | 252192.9 | 50438.58 | 100877.16 | 151315.74 | 16.5474
116 | Weather | Lightning | High Waves | Weather | 2 | 36 | 1643604 | 246540.6 | 49308.12 | 98616.24 | 147924.36 | 6
117 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | 3 | 14 | 546514 | 245453.4875 | 49090.6975 | 98181.395 | 147272.0925 | 17.965
118 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | 2 | 16 | 798666 | 239599.8 | 47919.96 | 95839.92 | 143759.88 | 12
119 | Logistics | Waiting on Materials | Port Congestion | Procurement | 2 | 10 | 434480 | 235829.4 | 47165.88 | 94331.76 | 141497.64 | 21.7114
120 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | 1 | 18 | 782733 | 234819.9 | 46963.98 | 93927.96 | 140891.94 | 12
121 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | 1 | 8 | 515497 | 231973.65 | 46394.73 | 92789.46 | 139184.19 | 18
122 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | 2 | 10 | 506500 | 227925 | 45585 | 91170 | 136755 | 18
123 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | 2 | 8 | 379853 | 227642.85 | 45528.57 | 91057.14 | 136585.71 | 23.9717
124 | Weather | Heavy Rain | Lightning | Marine Operations | 4 | 20 | 1237646 | 227167.8 | 45433.56 | 90867.12 | 136300.68 | 7.3419
125 | Weather | High Waves | Strong Wind | Weather | 4 | 22 | 1123837 | 226793.55 | 45358.71 | 90717.42 | 136076.13 | 8.0721
126 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | 2 | 10 | 521011 | 226695.7875 | 45339.1575 | 90678.315 | 136017.4725 | 17.4043
127 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | 3 | 16 | 680577 | 225334.2 | 45066.84 | 90133.68 | 135200.52 | 13.2437
128 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | 3 | 10 | 435937 | 224993.25 | 44998.65 | 89997.3 | 134995.95 | 20.6446
129 | Drilling | Bit Failure | Bit Wear | Operator | 2 | 8 | 312478 | 224885.8 | 44977.16 | 89954.32 | 134931.48 | 28.7874
130 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | 3 | 10 | 485384 | 223742.1875 | 44748.4375 | 89496.875 | 134245.3125 | 18.4384
131 | Personnel | Medical Evacuation | Training Requirement | HR | 4 | 18 | 739917 | 221975.1 | 44395.02 | 88790.04 | 133185.06 | 12
132 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | 3 | 12 | 622130 | 220750.8 | 44150.16 | 88300.32 | 132450.48 | 14.1932
133 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | 2 | 10 | 510463 | 220566.5 | 44113.3 | 88226.6 | 132339.9 | 17.2836
134 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | 2 | 10 | 630034 | 220511.9 | 44102.38 | 88204.76 | 132307.14 | 14
135 | Personnel | Safety Stand Down | Training Requirement | Rig Management | 3 | 18 | 645360 | 220080 | 44016 | 88032 | 132048 | 13.6408
136 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | 3 | 16 | 711208 | 213362.4 | 42672.48 | 85344.96 | 128017.44 | 12
137 | Weather | High Waves | High Waves | Marine Operations | 4 | 24 | 1194641 | 210084.15 | 42016.83 | 84033.66 | 126050.49 | 7.0342
138 | Weather | Heavy Rain | Strong Wind | Weather | 4 | 22 | 1038105 | 203659.8 | 40731.96 | 81463.92 | 122195.88 | 7.8474
139 | Weather | High Waves | Lightning | Marine Operations | 4 | 20 | 1111319 | 203537.85 | 40707.57 | 81415.14 | 122122.71 | 7.326
140 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 4 | 14 | 578056 | 200450.7 | 40090.14 | 80180.28 | 120270.42 | 13.8707
141 | Weather | Heavy Rain | High Waves | Weather | 3 | 12 | 771950 | 197260.95 | 39452.19 | 78904.38 | 118356.57 | 10.2214
142 | Drilling | Lost Circulation | Differential Sticking | Operator | 2 | 10 | 490013 | 196005.2 | 39201.04 | 78402.08 | 117603.12 | 16
143 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | 2 | 12 | 640857 | 192257.1 | 38451.42 | 76902.84 | 115354.26 | 12
144 | Weather | Heavy Rain | High Waves | Marine Operations | 4 | 16 | 890384 | 191736.075 | 38347.215 | 76694.43 | 115041.645 | 8.6136
145 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | 1 | 12 | 637608 | 191282.4 | 38256.48 | 76512.96 | 114769.44 | 12
146 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | 2 | 8 | 422889 | 190300.05 | 38060.01 | 76120.02 | 114180.03 | 18
147 | Weather | High Waves | Storm | Marine Operations | 4 | 20 | 1033811 | 189754.275 | 37950.855 | 75901.71 | 113852.565 | 7.3419
148 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | 2 | 12 | 621703 | 186510.9 | 37302.18 | 74604.36 | 111906.54 | 12
149 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | 2 | 10 | 531207 | 185922.45 | 37184.49 | 74368.98 | 111553.47 | 14
150 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | 2 | 14 | 616526 | 184957.8 | 36991.56 | 73983.12 | 110974.68 | 12
151 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | 1 | 8 | 405809 | 182614.05 | 36522.81 | 73045.62 | 109568.43 | 18
152 | Weather | Strong Wind | High Waves | Marine Operations | 4 | 18 | 927544 | 182324.25 | 36464.85 | 72929.7 | 109394.55 | 7.8627
153 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 6 | 302089 | 182298.825 | 36459.765 | 72919.53 | 109379.295 | 24.1384
154 | Personnel | Crew Change | Crew Rotation | Rig Management | 1 | 18 | 603804 | 181141.2 | 36228.24 | 72456.48 | 108684.72 | 12
155 | Weather | High Waves | Lightning | Weather | 4 | 22 | 1200954 | 180143.1 | 36028.62 | 72057.24 | 108085.86 | 6
156 | Weather | Lightning | Strong Wind | Weather | 2 | 24 | 1200103 | 180015.45 | 36003.09 | 72006.18 | 108009.27 | 6
157 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | 3 | 14 | 584802 | 175440.6 | 35088.12 | 70176.24 | 105264.36 | 12
158 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | 1 | 6 | 387813 | 174515.85 | 34903.17 | 69806.34 | 104709.51 | 18
159 | Weather | Poor Visibility | Lightning | Weather | 3 | 14 | 698883 | 173130.45 | 34626.09 | 69252.18 | 103878.27 | 9.909
160 | Weather | Lightning | High Waves | Marine Operations | 5 | 20 | 934313 | 167834.7 | 33566.94 | 67133.88 | 100700.82 | 7.1854
161 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | 2 | 8 | 395317 | 164887.35 | 32977.47 | 65954.94 | 98932.41 | 16.6841
162 | Weather | Strong Wind | Storm | Weather | 4 | 16 | 651975 | 163299.9 | 32659.98 | 65319.96 | 97979.94 | 10.0188
163 | Drilling | Bit Failure | Formation Instability | Directional Drilling | 3 | 12 | 501905 | 163119.125 | 32623.825 | 65247.65 | 97871.475 | 13
164 | Weather | Poor Visibility | Strong Wind | Weather | 5 | 24 | 1038046 | 161102.475 | 32220.495 | 64440.99 | 96661.485 | 6.2079
165 | Drilling | Bit Failure | Formation Instability | Mud Engineering | 3 | 10 | 364506 | 158385.825 | 31677.165 | 63354.33 | 95031.495 | 17.3809
166 | Drilling | Bit Failure | Differential Sticking | Operator | 1 | 6 | 393652 | 157460.8 | 31492.16 | 62984.32 | 94476.48 | 16
167 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | 1 | 6 | 348626 | 156881.7 | 31376.34 | 62752.68 | 94129.02 | 18
168 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | 2 | 6 | 199911 | 149336.55 | 29867.31 | 59734.62 | 89601.93 | 29.8806
169 | Logistics | Delayed Helicopter | Material Shortage | Procurement | 1 | 4 | 245667 | 147400.2 | 29480.04 | 58960.08 | 88440.12 | 24
170 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | 2 | 4 | 217220 | 146623.5 | 29324.7 | 58649.4 | 87974.1 | 27
171 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | 2 | 6 | 365852 | 146340.8 | 29268.16 | 58536.32 | 87804.48 | 16
172 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | 1 | 4 | 242362 | 145417.2 | 29083.44 | 58166.88 | 87250.32 | 24
173 | Weather | Lightning | Storm | Weather | 2 | 16 | 867402 | 144399.9 | 28879.98 | 57759.96 | 86639.94 | 6.659
174 | Weather | Lightning | Storm | Marine Operations | 3 | 16 | 777872 | 143023.05 | 28604.61 | 57209.22 | 85813.83 | 7.3546
175 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | 1 | 8 | 316114 | 142251.3 | 28450.26 | 56900.52 | 85350.78 | 18
176 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | 1 | 6 | 210610 | 142161.75 | 28432.35 | 56864.7 | 85297.05 | 27
177 | Logistics | Delayed Helicopter | Port Congestion | Procurement | 3 | 10 | 472968 | 141890.4 | 28378.08 | 56756.16 | 85134.24 | 12
178 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | 1 | 6 | 311670 | 140251.5 | 28050.3 | 56100.6 | 84150.9 | 18
179 | Logistics | Waiting on Materials | Customs Clearance | Procurement | 2 | 6 | 231473 | 138883.8 | 27776.76 | 55553.52 | 83330.28 | 24
180 | Drilling | Bit Failure | Bit Wear | Directional Drilling | 1 | 6 | 344964 | 137985.6 | 27597.12 | 55194.24 | 82791.36 | 16
181 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | 1 | 4 | 153062 | 137755.8 | 27551.16 | 55102.32 | 82653.48 | 36
182 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | 1 | 6 | 390679 | 136737.65 | 27347.53 | 54695.06 | 82042.59 | 14
183 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | 1 | 6 | 201020 | 135688.5 | 27137.7 | 54275.4 | 81413.1 | 27
184 | Drilling | Hole Cleaning | Formation Instability | Operator | 3 | 8 | 415395 | 135003.375 | 27000.675 | 54001.35 | 81002.025 | 13
185 | Personnel | Crew Change | Medical Emergency | Rig Management | 2 | 6 | 327936 | 132432.3 | 26486.46 | 52972.92 | 79459.38 | 16.1534
186 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | 1 | 6 | 292855 | 131784.75 | 26356.95 | 52713.9 | 79070.85 | 18
187 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | 2 | 10 | 431793 | 129537.9 | 25907.58 | 51815.16 | 77722.74 | 12
188 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | 1 | 4 | 280600 | 126270 | 25254 | 50508 | 75762 | 18
189 | Personnel | Safety Stand Down | Training Requirement | Medical Team | 2 | 6 | 280591 | 126265.95 | 25253.19 | 50506.38 | 75759.57 | 18
190 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | 1 | 6 | 415691 | 124707.3 | 24941.46 | 49882.92 | 74824.38 | 12
191 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | 1 | 4 | 137523 | 123770.7 | 24754.14 | 49508.28 | 74262.42 | 36
192 | Weather | Poor Visibility | Lightning | Marine Operations | 4 | 16 | 681032 | 121788.15 | 24357.63 | 48715.26 | 73072.89 | 7.1532
193 | Logistics | Waiting on Boat | Customs Clearance | Procurement | 2 | 6 | 402137 | 120641.1 | 24128.22 | 48256.44 | 72384.66 | 12
194 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | 2 | 6 | 370619 | 120451.175 | 24090.235 | 48180.47 | 72270.705 | 13
195 | Drilling | Well Control | Formation Instability | Directional Drilling | 1 | 6 | 368781 | 119853.825 | 23970.765 | 47941.53 | 71912.295 | 13
196 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | 1 | 4 | 167299 | 117109.3 | 23421.86 | 46843.72 | 70265.58 | 28
197 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | 1 | 6 | 380337 | 114101.1 | 22820.22 | 45640.44 | 68460.66 | 12
198 | Weather | Strong Wind | High Waves | Weather | 2 | 14 | 755738 | 113360.7 | 22672.14 | 45344.28 | 68016.42 | 6
199 | Logistics | Waiting on Boat | Port Congestion | Procurement | 1 | 6 | 377721 | 113316.3 | 22663.26 | 45326.52 | 67989.78 | 12
200 | Personnel | Medical Evacuation | Medical Emergency | HR | 1 | 6 | 376090 | 112827 | 22565.4 | 45130.8 | 67696.2 | 12
201 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | 1 | 2 | 120946 | 108851.4 | 21770.28 | 43540.56 | 65310.84 | 36
202 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | 1 | 6 | 238864 | 107488.8 | 21497.76 | 42995.52 | 64493.28 | 18
203 | Personnel | Crew Change | Medical Emergency | HR | 1 | 6 | 232452 | 104603.4 | 20920.68 | 41841.36 | 62762.04 | 18
204 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | 2 | 6 | 223728 | 103607.875 | 20721.575 | 41443.15 | 62164.725 | 18.5239
205 | Weather | Strong Wind | Heavy Rain | Weather | 2 | 18 | 671484 | 100722.6 | 20144.52 | 40289.04 | 60433.56 | 6
206 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | 1 | 4 | 223184 | 100432.8 | 20086.56 | 40173.12 | 60259.68 | 18
207 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | 2 | 6 | 217803 | 98011.35 | 19602.27 | 39204.54 | 58806.81 | 18
208 | Personnel | Training | Crew Rotation | Medical Team | 1 | 6 | 213210 | 95944.5 | 19188.9 | 38377.8 | 57566.7 | 18
209 | Drilling | Well Control | Unexpected Pressure | Operator | 2 | 8 | 294925 | 95850.625 | 19170.125 | 38340.25 | 57510.375 | 13
210 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | 1 | 4 | 234076 | 93630.4 | 18726.08 | 37452.16 | 56178.24 | 16
211 | Weather | High Waves | Heavy Rain | Weather | 2 | 10 | 477046 | 91679.925 | 18335.985 | 36671.97 | 55007.955 | 7.6873
212 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | 2 | 6 | 203658 | 91646.1 | 18329.22 | 36658.44 | 54987.66 | 18
213 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | 1 | 4 | 201829 | 90823.05 | 18164.61 | 36329.22 | 54493.83 | 18
214 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | 1 | 2 | 96310 | 86679 | 17335.8 | 34671.6 | 52007.4 | 36
215 | Weather | Heavy Rain | Lightning | Weather | 3 | 10 | 564611 | 84691.65 | 16938.33 | 33876.66 | 50814.99 | 6
216 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | 1 | 4 | 280384 | 84115.2 | 16823.04 | 33646.08 | 50469.12 | 12
217 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | 1 | 4 | 229210 | 80223.5 | 16044.7 | 32089.4 | 48134.1 | 14
218 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | 1 | 4 | 263601 | 79080.3 | 15816.06 | 31632.12 | 47448.18 | 12
219 | Weather | Poor Visibility | Storm | Weather | 3 | 12 | 500712 | 75106.8 | 15021.36 | 30042.72 | 45064.08 | 6
220 | Personnel | Medical Evacuation | Training Requirement | Medical Team | 2 | 4 | 250110 | 75033 | 15006.6 | 30013.2 | 45019.8 | 12
221 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | 1 | 2 | 82273 | 74045.7 | 14809.14 | 29618.28 | 44427.42 | 36
222 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | 1 | 6 | 226088 | 73478.6 | 14695.72 | 29391.44 | 44087.16 | 13
223 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | 1 | 4 | 159432 | 71744.4 | 14348.88 | 28697.76 | 43046.64 | 18
224 | Weather | Poor Visibility | High Waves | Marine Operations | 3 | 12 | 473431 | 71014.65 | 14202.93 | 28405.86 | 42608.79 | 6
225 | Weather | Strong Wind | Storm | Marine Operations | 2 | 8 | 344046 | 70674.75 | 14134.95 | 28269.9 | 42404.85 | 8.2169
226 | Weather | Heavy Rain | Heavy Rain | Marine Operations | 2 | 8 | 471076 | 70661.4 | 14132.28 | 28264.56 | 42396.84 | 6
227 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | 1 | 4 | 233679 | 70103.7 | 14020.74 | 28041.48 | 42062.22 | 12
228 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | 2 | 4 | 230664 | 69199.2 | 13839.84 | 27679.68 | 41519.52 | 12
229 | Weather | Poor Visibility | Storm | Marine Operations | 3 | 10 | 431632 | 64744.8 | 12948.96 | 25897.92 | 38846.88 | 6
230 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | 1 | 6 | 183652 | 64278.2 | 12855.64 | 25711.28 | 38566.92 | 14
231 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | 1 | 4 | 205597 | 61679.1 | 12335.82 | 24671.64 | 37007.46 | 12
232 | Drilling | Bit Failure | Formation Instability | Operator | 1 | 2 | 125034 | 60954.075 | 12190.815 | 24381.63 | 36572.445 | 19.5
233 | Weather | Heavy Rain | Storm | Marine Operations | 2 | 6 | 395085 | 59262.75 | 11852.55 | 23705.1 | 35557.65 | 6
234 | Drilling | Well Control | Differential Sticking | Operator | 1 | 4 | 146747 | 58698.8 | 11739.76 | 23479.52 | 35219.28 | 16
235 | Weather | Poor Visibility | High Waves | Weather | 1 | 6 | 256971 | 57818.475 | 11563.695 | 23127.39 | 34691.085 | 9
236 | Weather | Lightning | Strong Wind | Marine Operations | 2 | 8 | 383096 | 57464.4 | 11492.88 | 22985.76 | 34478.64 | 6
237 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | 1 | 4 | 171574 | 55761.55 | 11152.31 | 22304.62 | 33456.93 | 13
238 | Logistics | Waiting on Boat | Material Shortage | Procurement | 2 | 4 | 183397 | 55019.1 | 11003.82 | 22007.64 | 33011.46 | 12
239 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | 1 | 2 | 121900 | 54855 | 10971 | 21942 | 32913 | 18
240 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | 1 | 2 | 119766 | 53894.7 | 10778.94 | 21557.88 | 32336.82 | 18
241 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | 1 | 2 | 119555 | 53799.75 | 10759.95 | 21519.9 | 32279.85 | 18
242 | Drilling | Fishing Operation | Bit Wear | Operator | 1 | 2 | 88055 | 52833 | 10566.6 | 21133.2 | 31699.8 | 24
243 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | 1 | 4 | 148071 | 51824.85 | 10364.97 | 20729.94 | 31094.91 | 14
244 | Drilling | Well Control | Bit Wear | Operator | 1 | 2 | 125472 | 50188.8 | 10037.76 | 20075.52 | 30113.28 | 16
245 | Weather | Strong Wind | Heavy Rain | Marine Operations | 2 | 6 | 257065 | 49632.45 | 9926.49 | 19852.98 | 29779.47 | 7.7229
246 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | 2 | 4 | 163547 | 49064.1 | 9812.82 | 19625.64 | 29438.46 | 12
247 | Drilling | Lost Circulation | Unexpected Pressure | Operator | 1 | 2 | 100507 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975 | 19.5
248 | Personnel | Crew Change | Training Requirement | Rig Management | 1 | 4 | 156113 | 46833.9 | 9366.78 | 18733.56 | 28100.34 | 12
249 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | 1 | 2 | 101688 | 45759.6 | 9151.92 | 18303.84 | 27455.76 | 18
250 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | 1 | 2 | 97761 | 43992.45 | 8798.49 | 17596.98 | 26395.47 | 18
251 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | 1 | 4 | 146520 | 43956 | 8791.2 | 17582.4 | 26373.6 | 12
252 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | 1 | 4 | 142506 | 42751.8 | 8550.36 | 17100.72 | 25651.08 | 12
253 | Logistics | Waiting on Cement | Port Congestion | Procurement | 1 | 4 | 141854 | 42556.2 | 8511.24 | 17022.48 | 25533.72 | 12
254 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | 1 | 2 | 128171 | 38451.3 | 7690.26 | 15380.52 | 23070.78 | 12
255 | Personnel | Training | Training Requirement | Medical Team | 1 | 2 | 124993 | 37497.9 | 7499.58 | 14999.16 | 22498.74 | 12
256 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | 1 | 2 | 82480 | 37116 | 7423.2 | 14846.4 | 22269.6 | 18
257 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | 1 | 2 | 79500 | 35775 | 7155 | 14310 | 21465 | 18
258 | Weather | Strong Wind | Lightning | Marine Operations | 1 | 6 | 238339 | 35750.85 | 7150.17 | 14300.34 | 21450.51 | 6
259 | Weather | Lightning | Heavy Rain | Weather | 2 | 4 | 202029 | 35563.8 | 7112.76 | 14225.52 | 21338.28 | 7.0413
260 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | 1 | 2 | 73971 | 33286.95 | 6657.39 | 13314.78 | 19972.17 | 18
261 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | 1 | 2 | 108387 | 32516.1 | 6503.22 | 13006.44 | 19509.66 | 12
262 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | 1 | 2 | 89522 | 31332.7 | 6266.54 | 12533.08 | 18799.62 | 14
263 | Weather | High Waves | Storm | Weather | 1 | 4 | 191816 | 28772.4 | 5754.48 | 11508.96 | 17263.44 | 6
264 | Personnel | Safety Stand Down | Training Requirement | HR | 1 | 2 | 93981 | 28194.3 | 5638.86 | 11277.72 | 16916.58 | 12
265 | Drilling | Well Control | Differential Sticking | Mud Engineering | 1 | 2 | 70168 | 28067.2 | 5613.44 | 11226.88 | 16840.32 | 16
266 | Weather | High Waves | High Waves | Weather | 1 | 6 | 185319 | 27797.85 | 5559.57 | 11119.14 | 16678.71 | 6
267 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | 1 | 2 | 81540 | 24462 | 4892.4 | 9784.8 | 14677.2 | 12
268 | Personnel | Safety Stand Down | Medical Emergency | HR | 1 | 2 | 65522 | 19656.6 | 3931.32 | 7862.64 | 11793.96 | 12
269 | Weather | Strong Wind | Lightning | Weather | 1 | 2 | 84759 | 12713.85 | 2542.77 | 5085.54 | 7628.31 | 6

## Responsible_Party
Responsible_Party | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Target_Savings_USD
OEM Vendor | 59 | 376 | 18331322 | 10785282.15 | 4314112.86
Drilling Contractor | 65 | 368 | 19000514 | 9853357.8 | 3941343.12
Directional Drilling | 71 | 428 | 21180149 | 9561910.0375 | 3824764.015
Mud Engineering | 70 | 438 | 21226556 | 8633039.25 | 3453215.7
Maintenance Team | 47 | 308 | 14900279 | 8207573.175 | 3283029.27
Operator | 72 | 386 | 18655151 | 8112625.875 | 3245050.35
Marine Operations | 88 | 490 | 25000021 | 4628653.95 | 1851461.58
Supply Chain | 32 | 236 | 12321042 | 4562764.35 | 1825105.74
Weather | 73 | 452 | 21883982 | 3925373.85 | 1570149.54
Procurement | 36 | 180 | 9196062 | 3403995.15 | 1361598.06
Marine Logistics | 36 | 190 | 9511811 | 3024146.7 | 1209658.68
Rig Management | 9 | 66 | 2571074 | 945293.85 | 378117.54
Medical Team | 11 | 56 | 2864253 | 933346.05 | 373338.42
HR | 8 | 34 | 1507962 | 487256.4 | 194902.56

## Top_Opportunities
Priority_Rank | NPT_ID | Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Action_Status | Corrective_Action | Controllability | Addressability_Factor | Actionability_Factor | Duration_hr | Total_Impact_USD | Calculated_Addressable_Impact_USD | Calculated_Conservative_Savings_USD | Calculated_Target_Savings_USD | Calculated_Stretch_Savings_USD
1 | NPT00151 | W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Open | Preventive Maintenance | HIGH | 0.9 | 1 | 24 | 1549746 | 1394771.4 | 278954.28 | 557908.56 | 836862.84
2 | NPT00033 | W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Open | Adjust Drilling Parameters | HIGH | 0.8 | 1 | 18 | 1230862 | 984689.6 | 196937.92 | 393875.84 | 590813.76
3 | NPT00420 | W031 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | In Progress | Replace Equipment | HIGH | 0.9 | 0.75 | 24 | 1403802 | 947566.35 | 189513.27 | 379026.54 | 568539.81
4 | NPT00551 | W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Open | Preventive Maintenance | HIGH | 0.9 | 1 | 18 | 848296 | 763466.4 | 152693.28 | 305386.56 | 458079.84
5 | NPT00036 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Closed | OEM Inspection | HIGH | 0.9 | 0.5 | 24 | 1547580 | 696411 | 139282.2 | 278564.4 | 417846.6
6 | NPT00503 | W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | In Progress | Expedite Shipment | MEDIUM | 0.6 | 0.75 | 24 | 1223810 | 550714.5 | 110142.9 | 220285.8 | 330428.7
7 | NPT00356 | W027 | R002 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | In Progress | Adjust Drilling Parameters | HIGH | 0.8 | 0.75 | 18 | 910252 | 546151.2 | 109230.24 | 218460.48 | 327690.72
8 | NPT00096 | W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Closed | Replace Equipment | HIGH | 0.9 | 0.5 | 18 | 1199760 | 539892 | 107978.4 | 215956.8 | 323935.2
9 | NPT00233 | W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Open | Air Freight Materials | MEDIUM | 0.6 | 1 | 24 | 887460 | 532476 | 106495.2 | 212990.4 | 319485.6
10 | NPT00480 | W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Closed | Repair Component | HIGH | 0.9 | 0.5 | 18 | 1121256 | 504565.2 | 100913.04 | 201826.08 | 302739.12
11 | NPT00024 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Closed | Repair Component | HIGH | 0.9 | 0.5 | 18 | 1109300 | 499185 | 99837 | 199674 | 299511
12 | NPT00091 | W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Closed | Repair Component | HIGH | 0.9 | 0.5 | 18 | 1058312 | 476240.4 | 95248.08 | 190496.16 | 285744.24
13 | NPT00255 | W019 | R003 | Drilling | Well Control | Bit Wear | Mud Engineering | Closed | Adjust Drilling Parameters | HIGH | 0.8 | 0.5 | 18 | 1187467 | 474986.8 | 94997.36 | 189994.72 | 284992.08
14 | NPT00088 | W007 | R001 | Drilling | Well Control | Bit Wear | Directional Drilling | Closed | Condition Hole | HIGH | 0.8 | 0.5 | 18 | 1154940 | 461976 | 92395.2 | 184790.4 | 277185.6
15 | NPT00259 | W020 | R003 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | Closed | OEM Inspection | HIGH | 0.9 | 0.5 | 18 | 1023187 | 460434.15 | 92086.83 | 184173.66 | 276260.49
16 | NPT00614 | W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Closed | Air Freight Materials | MEDIUM | 0.6 | 0.5 | 24 | 1534504 | 460351.2 | 92070.24 | 184140.48 | 276210.72
17 | NPT00667 | W050 | R004 | Drilling | Lost Circulation | Bit Wear | Operator | Open | Run Fishing Tools | HIGH | 0.8 | 1 | 8 | 568521 | 454816.8 | 90963.36 | 181926.72 | 272890.08
18 | NPT00670 | W050 | R004 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Open | Mobilize Supply Vessel | MEDIUM | 0.6 | 1 | 12 | 757335 | 454401 | 90880.2 | 181760.4 | 272640.6
19 | NPT00565 | W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | In Progress | Condition Hole | HIGH | 0.8 | 0.75 | 18 | 735612 | 441367.2 | 88273.44 | 176546.88 | 264820.32
20 | NPT00317 | W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Open | Replace Equipment | HIGH | 0.9 | 1 | 8 | 488048 | 439243.2 | 87848.64 | 175697.28 | 263545.92
21 | NPT00032 | W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | In Progress | Repair Component | HIGH | 0.9 | 0.75 | 12 | 632370 | 426849.75 | 85369.95 | 170739.9 | 256109.85
22 | NPT00298 | W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Open | Replace Equipment | HIGH | 0.9 | 1 | 8 | 456648 | 410983.2 | 82196.64 | 164393.28 | 246589.92
23 | NPT00486 | W036 | R002 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Closed | Preventive Maintenance | HIGH | 0.9 | 0.5 | 18 | 871177 | 392029.65 | 78405.93 | 156811.86 | 235217.79
24 | NPT00359 | W027 | R002 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Open | Condition Hole | HIGH | 0.8 | 1 | 8 | 488768 | 391014.4 | 78202.88 | 156405.76 | 234608.64
25 | NPT00452 | W034 | R001 | Drilling | Fishing Operation | Formation Instability | Operator | Closed | Adjust Drilling Parameters | MEDIUM | 0.65 | 0.5 | 18 | 1178555 | 383030.375 | 76606.075 | 153212.15 | 229818.225

## Double_Counting_Check
Check | Value
Event-level Target Savings | 30825847.435
Root Cause grouped Target Savings | 30825847.435
Difference | 0
Duplicate NPT IDs | 0
Unique NPT IDs | 677
Total NPT Rows | 677

## Event_Level_Audit
NPT_ID | Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Duration_hr | Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Calculated_Total_Impact_USD | Economic_Reconciliation_Difference_USD | Addressability_Factor | Actionability_Factor | Calculated_Addressable_Impact_USD | Calculated_Conservative_Savings_USD | Calculated_Target_Savings_USD | Calculated_Stretch_Savings_USD
NPT00001 | W001 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 2 | 40833 | 101446 | 142279 | 142279 | 0 | 0.6 | 1 | 85367.4 | 17073.48 | 34146.96 | 51220.44
NPT00002 | W001 | R004 | Mechanical | BOP Repair | Electrical Failure | 2 | 40833 | 70917 | 111750 | 111750 | 0 | 0.9 | 1 | 100575 | 20115 | 40230 | 60345
NPT00003 | W001 | R004 | Logistics | Waiting on Cement | Material Shortage | 2 | 40833 | 60855 | 101688 | 101688 | 0 | 0.6 | 0.75 | 45759.6 | 9151.92 | 18303.84 | 27455.76
NPT00004 | W001 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 6 | 122500 | 251157 | 373657 | 373657 | 0 | 0.6 | 0.5 | 112097.1 | 22419.42 | 44838.84 | 67258.26
NPT00005 | W001 | R004 | Mechanical | Top Drive Failure | OEM Defect | 6 | 122500 | 128869 | 251369 | 251369 | 0 | 0.7 | 0.5 | 87979.15 | 17595.83 | 35191.66 | 52787.49
NPT00006 | W001 | R004 | Weather | High Waves | Strong Wind | 8 | 163333 | 105854 | 269187 | 269187 | 0 | 0.3 | 0.5 | 40378.05 | 8075.61 | 16151.22 | 24226.83
NPT00007 | W001 | R004 | Drilling | Fishing Operation | Differential Sticking | 4 | 81666 | 85703 | 167369 | 167369 | 0 | 0.8 | 0.5 | 66947.6 | 13389.52 | 26779.04 | 40168.56
NPT00008 | W001 | R004 | Drilling | Lost Circulation | Differential Sticking | 2 | 40833 | 94533 | 135366 | 135366 | 0 | 0.8 | 0.5 | 54146.4 | 10829.28 | 21658.56 | 32487.84
NPT00009 | W001 | R004 | Weather | Lightning | Storm | 4 | 81666 | 108862 | 190528 | 190528 | 0 | 0.3 | 0.75 | 42868.8 | 8573.76 | 17147.52 | 25721.28
NPT00010 | W001 | R004 | Weather | High Waves | High Waves | 4 | 81666 | 124254 | 205920 | 205920 | 0 | 0.3 | 1 | 61776 | 12355.2 | 24710.4 | 37065.6
NPT00011 | W001 | R004 | Weather | Heavy Rain | High Waves | 2 | 40833 | 78584 | 119417 | 119417 | 0 | 0.3 | 0.5 | 17912.55 | 3582.51 | 7165.02 | 10747.53
NPT00012 | W001 | R004 | Logistics | Waiting on Materials | Late Supply Vessel | 4 | 81666 | 152013 | 233679 | 233679 | 0 | 0.6 | 0.5 | 70103.7 | 14020.74 | 28041.48 | 42062.22
NPT00013 | W001 | R004 | Weather | High Waves | Lightning | 6 | 122500 | 139841 | 262341 | 262341 | 0 | 0.3 | 0.5 | 39351.15 | 7870.23 | 15740.46 | 23610.69
NPT00014 | W001 | R004 | Drilling | Well Control | Unexpected Pressure | 6 | 122500 | 230529 | 353029 | 353029 | 0 | 0.65 | 0.75 | 172101.6375 | 34420.3275 | 68840.655 | 103260.9825
NPT00015 | W001 | R004 | Weather | High Waves | Storm | 12 | 245000 | 394548 | 639548 | 639548 | 0 | 0.3 | 0.5 | 95932.2 | 19186.44 | 38372.88 | 57559.32
NPT00016 | W001 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 4 | 81666 | 185722 | 267388 | 267388 | 0 | 0.65 | 0.5 | 86901.1 | 17380.22 | 34760.44 | 52140.66
NPT00017 | W001 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 4 | 81666 | 90708 | 172374 | 172374 | 0 | 0.9 | 0.75 | 116352.45 | 23270.49 | 46540.98 | 69811.47
NPT00018 | W001 | R004 | Weather | Lightning | Heavy Rain | 6 | 122500 | 205768 | 328268 | 328268 | 0 | 0.3 | 0.75 | 73860.3 | 14772.06 | 29544.12 | 44316.18
NPT00019 | W001 | R004 | Logistics | Delayed Helicopter | Material Shortage | 4 | 81666 | 198718 | 280384 | 280384 | 0 | 0.6 | 0.5 | 84115.2 | 16823.04 | 33646.08 | 50469.12
NPT00020 | W002 | R001 | Drilling | Bit Failure | Bit Wear | 6 | 118750 | 226214 | 344964 | 344964 | 0 | 0.8 | 0.5 | 137985.6 | 27597.12 | 55194.24 | 82791.36
NPT00021 | W002 | R001 | Drilling | Bit Failure | Bit Wear | 6 | 118750 | 68245 | 186995 | 186995 | 0 | 0.8 | 1 | 149596 | 29919.2 | 59838.4 | 89757.6
NPT00022 | W002 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 39583 | 70254 | 109837 | 109837 | 0 | 0.65 | 0.5 | 35697.025 | 7139.405 | 14278.81 | 21418.215
NPT00023 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | 2 | 39583 | 76363 | 115946 | 115946 | 0 | 0.9 | 0.5 | 52175.7 | 10435.14 | 20870.28 | 31305.42
NPT00024 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | 18 | 356250 | 753050 | 1109300 | 1109300 | 0 | 0.9 | 0.5 | 499185 | 99837 | 199674 | 299511
NPT00025 | W002 | R001 | Logistics | Fuel Supply Delay | Material Shortage | 6 | 118750 | 98071 | 216821 | 216821 | 0 | 0.6 | 0.5 | 65046.3 | 13009.26 | 26018.52 | 39027.78
NPT00026 | W002 | R001 | Drilling | Stuck Pipe | Unexpected Pressure | 6 | 118750 | 188958 | 307708 | 307708 | 0 | 0.65 | 0.5 | 100005.1 | 20001.02 | 40002.04 | 60003.06
NPT00027 | W002 | R001 | Mechanical | Mud Pump Failure | OEM Defect | 6 | 118750 | 64902 | 183652 | 183652 | 0 | 0.7 | 0.5 | 64278.2 | 12855.64 | 25711.28 | 38566.92
NPT00028 | W002 | R001 | Drilling | Hole Cleaning | Bit Wear | 8 | 158333 | 316860 | 475193 | 475193 | 0 | 0.8 | 0.75 | 285115.8 | 57023.16 | 114046.32 | 171069.48
NPT00029 | W002 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 4 | 79166 | 173712 | 252878 | 252878 | 0 | 0.6 | 0.5 | 75863.4 | 15172.68 | 30345.36 | 45518.04
NPT00030 | W002 | R001 | Mechanical | Draw Works Failure | Equipment Wear | 8 | 158333 | 235732 | 394065 | 394065 | 0 | 0.9 | 1 | 354658.5 | 70931.7 | 141863.4 | 212795.1
NPT00031 | W002 | R001 | Weather | Poor Visibility | Heavy Rain | 4 | 79166 | 137466 | 216632 | 216632 | 0 | 0.3 | 0.5 | 32494.8 | 6498.96 | 12997.92 | 19496.88
NPT00032 | W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | 12 | 237500 | 394870 | 632370 | 632370 | 0 | 0.9 | 0.75 | 426849.75 | 85369.95 | 170739.9 | 256109.85
NPT00033 | W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | 18 | 367500 | 863362 | 1230862 | 1230862 | 0 | 0.8 | 1 | 984689.6 | 196937.92 | 393875.84 | 590813.76
NPT00034 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 6 | 122500 | 294100 | 416600 | 416600 | 0 | 0.9 | 0.75 | 281205 | 56241 | 112482 | 168723
NPT00035 | W003 | R004 | Personnel | Safety Stand Down | Training Requirement | 6 | 122500 | 101091 | 223591 | 223591 | 0 | 0.6 | 0.5 | 67077.3 | 13415.46 | 26830.92 | 40246.38
NPT00036 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 24 | 490000 | 1057580 | 1547580 | 1547580 | 0 | 0.9 | 0.5 | 696411 | 139282.2 | 278564.4 | 417846.6
NPT00037 | W003 | R004 | Mechanical | Power System Failure | Equipment Wear | 2 | 40833 | 94991 | 135824 | 135824 | 0 | 0.9 | 0.5 | 61120.8 | 12224.16 | 24448.32 | 36672.48
NPT00038 | W003 | R004 | Mechanical | Power System Failure | Hydraulic Failure | 4 | 81666 | 198934 | 280600 | 280600 | 0 | 0.9 | 0.5 | 126270 | 25254 | 50508 | 75762
NPT00039 | W003 | R004 | Logistics | Waiting on Boat | Customs Clearance | 4 | 81666 | 188346 | 270012 | 270012 | 0 | 0.6 | 0.5 | 81003.6 | 16200.72 | 32401.44 | 48602.16
NPT00040 | W003 | R004 | Logistics | Waiting on Boat | Material Shortage | 4 | 81666 | 64854 | 146520 | 146520 | 0 | 0.6 | 0.5 | 43956 | 8791.2 | 17582.4 | 26373.6
NPT00041 | W003 | R004 | Mechanical | Power System Failure | Electrical Failure | 6 | 122500 | 177370 | 299870 | 299870 | 0 | 0.9 | 0.5 | 134941.5 | 26988.3 | 53976.6 | 80964.9
NPT00042 | W003 | R004 | Mechanical | Draw Works Failure | Hydraulic Failure | 2 | 40833 | 50164 | 90997 | 90997 | 0 | 0.9 | 0.75 | 61422.975 | 12284.595 | 24569.19 | 36853.785
NPT00043 | W003 | R004 | Logistics | Waiting on Boat | Material Shortage | 2 | 40833 | 27318 | 68151 | 68151 | 0 | 0.6 | 0.5 | 20445.3 | 4089.06 | 8178.12 | 12267.18
NPT00044 | W003 | R004 | Mechanical | BOP Repair | Electrical Failure | 6 | 122500 | 191741 | 314241 | 314241 | 0 | 0.9 | 0.5 | 141408.45 | 28281.69 | 56563.38 | 84845.07
NPT00045 | W003 | R004 | Weather | Strong Wind | Strong Wind | 4 | 81666 | 119164 | 200830 | 200830 | 0 | 0.3 | 0.5 | 30124.5 | 6024.9 | 12049.8 | 18074.7
NPT00046 | W004 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 2 | 38333 | 23125 | 61458 | 61458 | 0 | 0.9 | 0.5 | 27656.1 | 5531.22 | 11062.44 | 16593.66
NPT00047 | W004 | R002 | Drilling | Bit Failure | Differential Sticking | 2 | 38333 | 82098 | 120431 | 120431 | 0 | 0.8 | 0.5 | 48172.4 | 9634.48 | 19268.96 | 28903.44
NPT00048 | W004 | R002 | Weather | Lightning | Lightning | 2 | 38333 | 95062 | 133395 | 133395 | 0 | 0.3 | 1 | 40018.5 | 8003.7 | 16007.4 | 24011.1
NPT00049 | W004 | R002 | Drilling | Stuck Pipe | Differential Sticking | 12 | 230000 | 495852 | 725852 | 725852 | 0 | 0.8 | 0.5 | 290340.8 | 58068.16 | 116136.32 | 174204.48
NPT00050 | W004 | R002 | Weather | Heavy Rain | Heavy Rain | 4 | 76666 | 120129 | 196795 | 196795 | 0 | 0.3 | 0.5 | 29519.25 | 5903.85 | 11807.7 | 17711.55
NPT00051 | W004 | R002 | Drilling | Lost Circulation | Formation Instability | 4 | 76666 | 57881 | 134547 | 134547 | 0 | 0.65 | 0.5 | 43727.775 | 8745.555 | 17491.11 | 26236.665
NPT00052 | W004 | R002 | Weather | Lightning | Lightning | 6 | 115000 | 137010 | 252010 | 252010 | 0 | 0.3 | 0.75 | 56702.25 | 11340.45 | 22680.9 | 34021.35
NPT00053 | W004 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 2 | 38333 | 24450 | 62783 | 62783 | 0 | 0.65 | 0.5 | 20404.475 | 4080.895 | 8161.79 | 12242.685
NPT00054 | W004 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 2 | 38333 | 89763 | 128096 | 128096 | 0 | 0.9 | 0.75 | 86464.8 | 17292.96 | 34585.92 | 51878.88
NPT00055 | W004 | R002 | Weather | Lightning | High Waves | 4 | 76666 | 91438 | 168104 | 168104 | 0 | 0.3 | 0.5 | 25215.6 | 5043.12 | 10086.24 | 15129.36
NPT00056 | W004 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 12 | 230000 | 121023 | 351023 | 351023 | 0 | 0.9 | 0.5 | 157960.35 | 31592.07 | 63184.14 | 94776.21
NPT00057 | W005 | R002 | Weather | Lightning | Lightning | 4 | 76666 | 160965 | 237631 | 237631 | 0 | 0.3 | 0.5 | 35644.65 | 7128.93 | 14257.86 | 21386.79
NPT00058 | W005 | R002 | Weather | Heavy Rain | Storm | 6 | 115000 | 222173 | 337173 | 337173 | 0 | 0.3 | 0.75 | 75863.925 | 15172.785 | 30345.57 | 45518.355
NPT00059 | W005 | R002 | Mechanical | Power System Failure | Electrical Failure | 6 | 115000 | 185545 | 300545 | 300545 | 0 | 0.9 | 0.5 | 135245.25 | 27049.05 | 54098.1 | 81147.15
NPT00060 | W005 | R002 | Weather | Strong Wind | Storm | 2 | 38333 | 51475 | 89808 | 89808 | 0 | 0.3 | 0.5 | 13471.2 | 2694.24 | 5388.48 | 8082.72
NPT00061 | W005 | R002 | Logistics | Waiting on Materials | Material Shortage | 4 | 76666 | 100056 | 176722 | 176722 | 0 | 0.6 | 0.5 | 53016.6 | 10603.32 | 21206.64 | 31809.96
NPT00062 | W005 | R002 | Personnel | Medical Evacuation | Training Requirement | 8 | 153333 | 97266 | 250599 | 250599 | 0 | 0.6 | 0.5 | 75179.7 | 15035.94 | 30071.88 | 45107.82
NPT00063 | W005 | R002 | Mechanical | BOP Repair | Equipment Wear | 8 | 153333 | 252476 | 405809 | 405809 | 0 | 0.9 | 0.5 | 182614.05 | 36522.81 | 73045.62 | 109568.43
NPT00064 | W005 | R002 | Drilling | Hole Cleaning | Formation Instability | 4 | 76666 | 183892 | 260558 | 260558 | 0 | 0.65 | 0.5 | 84681.35 | 16936.27 | 33872.54 | 50808.81
NPT00065 | W005 | R002 | Weather | Strong Wind | Strong Wind | 6 | 115000 | 134376 | 249376 | 249376 | 0 | 0.3 | 0.5 | 37406.4 | 7481.28 | 14962.56 | 22443.84
NPT00066 | W005 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 6 | 115000 | 241365 | 356365 | 356365 | 0 | 0.9 | 0.5 | 160364.25 | 32072.85 | 64145.7 | 96218.55
NPT00067 | W005 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 4 | 76666 | 150606 | 227272 | 227272 | 0 | 0.6 | 0.5 | 68181.6 | 13636.32 | 27272.64 | 40908.96
NPT00068 | W005 | R002 | Drilling | Stuck Pipe | Bit Wear | 4 | 76666 | 67864 | 144530 | 144530 | 0 | 0.8 | 0.5 | 57812 | 11562.4 | 23124.8 | 34687.2
NPT00069 | W005 | R002 | Weather | Poor Visibility | Storm | 2 | 38333 | 69012 | 107345 | 107345 | 0 | 0.3 | 0.5 | 16101.75 | 3220.35 | 6440.7 | 9661.05
NPT00070 | W006 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 2 | 38333 | 55949 | 94282 | 94282 | 0 | 0.9 | 1 | 84853.8 | 16970.76 | 33941.52 | 50912.28
NPT00071 | W006 | R002 | Weather | Lightning | Lightning | 2 | 38333 | 74025 | 112358 | 112358 | 0 | 0.3 | 0.5 | 16853.7 | 3370.74 | 6741.48 | 10112.22
NPT00072 | W006 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 8 | 153333 | 347820 | 501153 | 501153 | 0 | 0.9 | 0.5 | 225518.85 | 45103.77 | 90207.54 | 135311.31
NPT00073 | W006 | R002 | Weather | Poor Visibility | Lightning | 2 | 38333 | 92556 | 130889 | 130889 | 0 | 0.3 | 1 | 39266.7 | 7853.34 | 15706.68 | 23560.02
NPT00074 | W006 | R002 | Logistics | Delayed Helicopter | Material Shortage | 4 | 76666 | 169001 | 245667 | 245667 | 0 | 0.6 | 1 | 147400.2 | 29480.04 | 58960.08 | 88440.12
NPT00075 | W006 | R002 | Weather | High Waves | Lightning | 4 | 76666 | 45813 | 122479 | 122479 | 0 | 0.3 | 0.5 | 18371.85 | 3674.37 | 7348.74 | 11023.11
NPT00076 | W006 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 4 | 76666 | 142294 | 218960 | 218960 | 0 | 0.6 | 0.5 | 65688 | 13137.6 | 26275.2 | 39412.8
NPT00077 | W006 | R002 | Logistics | Waiting on Cement | Customs Clearance | 8 | 153333 | 232289 | 385622 | 385622 | 0 | 0.6 | 0.5 | 115686.6 | 23137.32 | 46274.64 | 69411.96
NPT00078 | W006 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 6 | 115000 | 236864 | 351864 | 351864 | 0 | 0.9 | 0.5 | 158338.8 | 31667.76 | 63335.52 | 95003.28
NPT00079 | W006 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 4 | 76666 | 64974 | 141640 | 141640 | 0 | 0.6 | 0.5 | 42492 | 8498.4 | 16996.8 | 25495.2
NPT00080 | W006 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 6 | 115000 | 145730 | 260730 | 260730 | 0 | 0.9 | 0.5 | 117328.5 | 23465.7 | 46931.4 | 70397.1
NPT00081 | W006 | R002 | Logistics | Waiting on Materials | Port Congestion | 4 | 76666 | 107545 | 184211 | 184211 | 0 | 0.6 | 0.5 | 55263.3 | 11052.66 | 22105.32 | 33157.98
NPT00082 | W006 | R002 | Drilling | Bit Failure | Bit Wear | 18 | 345000 | 462111 | 807111 | 807111 | 0 | 0.8 | 0.5 | 322844.4 | 64568.88 | 129137.76 | 193706.64
NPT00083 | W006 | R002 | Drilling | Fishing Operation | Differential Sticking | 4 | 76666 | 157410 | 234076 | 234076 | 0 | 0.8 | 0.5 | 93630.4 | 18726.08 | 37452.16 | 56178.24
NPT00084 | W006 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 8 | 153333 | 286906 | 440239 | 440239 | 0 | 0.9 | 0.75 | 297161.325 | 59432.265 | 118864.53 | 178296.795
NPT00085 | W007 | R001 | Drilling | Hole Cleaning | Differential Sticking | 4 | 79166 | 115572 | 194738 | 194738 | 0 | 0.8 | 0.5 | 77895.2 | 15579.04 | 31158.08 | 46737.12
NPT00086 | W007 | R001 | Drilling | Stuck Pipe | Formation Instability | 2 | 39583 | 64096 | 103679 | 103679 | 0 | 0.65 | 0.5 | 33695.675 | 6739.135 | 13478.27 | 20217.405
NPT00087 | W007 | R001 | Weather | Strong Wind | High Waves | 4 | 79166 | 60596 | 139762 | 139762 | 0 | 0.3 | 0.5 | 20964.3 | 4192.86 | 8385.72 | 12578.58
NPT00088 | W007 | R001 | Drilling | Well Control | Bit Wear | 18 | 356250 | 798690 | 1154940 | 1154940 | 0 | 0.8 | 0.5 | 461976 | 92395.2 | 184790.4 | 277185.6
NPT00089 | W007 | R001 | Logistics | Fuel Supply Delay | Material Shortage | 4 | 79166 | 52507 | 131673 | 131673 | 0 | 0.6 | 0.5 | 39501.9 | 7900.38 | 15800.76 | 23701.14
NPT00090 | W007 | R001 | Mechanical | Generator Failure | Equipment Wear | 2 | 39583 | 82308 | 121891 | 121891 | 0 | 0.9 | 0.75 | 82276.425 | 16455.285 | 32910.57 | 49365.855
NPT00091 | W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 18 | 356250 | 702062 | 1058312 | 1058312 | 0 | 0.9 | 0.5 | 476240.4 | 95248.08 | 190496.16 | 285744.24
NPT00092 | W007 | R001 | Weather | Lightning | Storm | 8 | 158333 | 192897 | 351230 | 351230 | 0 | 0.3 | 0.75 | 79026.75 | 15805.35 | 31610.7 | 47416.05
NPT00093 | W007 | R001 | Weather | Lightning | Lightning | 6 | 118750 | 152256 | 271006 | 271006 | 0 | 0.3 | 0.75 | 60976.35 | 12195.27 | 24390.54 | 36585.81
NPT00094 | W007 | R001 | Personnel | Training | Training Requirement | 2 | 39583 | 85410 | 124993 | 124993 | 0 | 0.6 | 0.5 | 37497.9 | 7499.58 | 14999.16 | 22498.74
NPT00095 | W007 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | 8 | 158333 | 144349 | 302682 | 302682 | 0 | 0.65 | 0.5 | 98371.65 | 19674.33 | 39348.66 | 59022.99
NPT00096 | W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | 18 | 356250 | 843510 | 1199760 | 1199760 | 0 | 0.9 | 0.5 | 539892 | 107978.4 | 215956.8 | 323935.2
NPT00097 | W007 | R001 | Mechanical | Generator Failure | Hydraulic Failure | 2 | 39583 | 39917 | 79500 | 79500 | 0 | 0.9 | 0.5 | 35775 | 7155 | 14310 | 21465
NPT00098 | W007 | R001 | Mechanical | Draw Works Failure | Hydraulic Failure | 6 | 118750 | 164765 | 283515 | 283515 | 0 | 0.9 | 0.5 | 127581.75 | 25516.35 | 51032.7 | 76549.05
NPT00099 | W007 | R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | 18 | 356250 | 426483 | 782733 | 782733 | 0 | 0.6 | 0.5 | 234819.9 | 46963.98 | 93927.96 | 140891.94
NPT00100 | W007 | R001 | Mechanical | BOP Repair | Poor Preventive Maintenance | 8 | 158333 | 357164 | 515497 | 515497 | 0 | 0.9 | 0.5 | 231973.65 | 46394.73 | 92789.46 | 139184.19
NPT00101 | W008 | R002 | Drilling | Bit Failure | Differential Sticking | 4 | 76666 | 111806 | 188472 | 188472 | 0 | 0.8 | 0.5 | 75388.8 | 15077.76 | 30155.52 | 45233.28
NPT00102 | W008 | R002 | Weather | Lightning | Lightning | 2 | 38333 | 76426 | 114759 | 114759 | 0 | 0.3 | 0.5 | 17213.85 | 3442.77 | 6885.54 | 10328.31
NPT00103 | W008 | R002 | Personnel | Safety Stand Down | Training Requirement | 2 | 38333 | 66496 | 104829 | 104829 | 0 | 0.6 | 0.75 | 47173.05 | 9434.61 | 18869.22 | 28303.83
NPT00104 | W008 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 2 | 38333 | 59428 | 97761 | 97761 | 0 | 0.6 | 0.75 | 43992.45 | 8798.49 | 17596.98 | 26395.47
NPT00105 | W008 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 8 | 153333 | 77458 | 230791 | 230791 | 0 | 0.65 | 0.75 | 112510.6125 | 22502.1225 | 45004.245 | 67506.3675
NPT00106 | W008 | R002 | Weather | Poor Visibility | High Waves | 4 | 76666 | 73637 | 150303 | 150303 | 0 | 0.3 | 0.5 | 22545.45 | 4509.09 | 9018.18 | 13527.27
NPT00107 | W008 | R002 | Mechanical | BOP Repair | OEM Defect | 4 | 76666 | 90633 | 167299 | 167299 | 0 | 0.7 | 1 | 117109.3 | 23421.86 | 46843.72 | 70265.58
NPT00108 | W008 | R002 | Drilling | Bit Failure | Unexpected Pressure | 6 | 115000 | 286152 | 401152 | 401152 | 0 | 0.65 | 0.5 | 130374.4 | 26074.88 | 52149.76 | 78224.64
NPT00109 | W008 | R002 | Drilling | Fishing Operation | Formation Instability | 6 | 115000 | 161085 | 276085 | 276085 | 0 | 0.65 | 1 | 179455.25 | 35891.05 | 71782.1 | 107673.15
NPT00110 | W008 | R002 | Logistics | Waiting on Boat | Late Supply Vessel | 2 | 38333 | 48369 | 86702 | 86702 | 0 | 0.6 | 0.5 | 26010.6 | 5202.12 | 10404.24 | 15606.36
NPT00111 | W009 | R001 | Weather | High Waves | Lightning | 2 | 39583 | 93632 | 133215 | 133215 | 0 | 0.3 | 0.5 | 19982.25 | 3996.45 | 7992.9 | 11989.35
NPT00112 | W009 | R001 | Drilling | Bit Failure | Formation Instability | 4 | 79166 | 43669 | 122835 | 122835 | 0 | 0.65 | 1 | 79842.75 | 15968.55 | 31937.1 | 47905.65
NPT00113 | W009 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 6 | 118750 | 110684 | 229434 | 229434 | 0 | 0.6 | 0.5 | 68830.2 | 13766.04 | 27532.08 | 41298.12
NPT00114 | W009 | R001 | Drilling | Lost Circulation | Formation Instability | 24 | 475000 | 464721 | 939721 | 939721 | 0 | 0.65 | 0.5 | 305409.325 | 61081.865 | 122163.73 | 183245.595
NPT00115 | W009 | R001 | Mechanical | Rotary Table Failure | Electrical Failure | 6 | 118750 | 114628 | 233378 | 233378 | 0 | 0.9 | 0.75 | 157530.15 | 31506.03 | 63012.06 | 94518.09
NPT00116 | W009 | R001 | Weather | Poor Visibility | Storm | 2 | 39583 | 69610 | 109193 | 109193 | 0 | 0.3 | 0.5 | 16378.95 | 3275.79 | 6551.58 | 9827.37
NPT00117 | W009 | R001 | Mechanical | Top Drive Failure | Electrical Failure | 6 | 118750 | 89584 | 208334 | 208334 | 0 | 0.9 | 0.75 | 140625.45 | 28125.09 | 56250.18 | 84375.27
NPT00118 | W009 | R001 | Mechanical | Top Drive Failure | Equipment Wear | 4 | 79166 | 182360 | 261526 | 261526 | 0 | 0.9 | 1 | 235373.4 | 47074.68 | 94149.36 | 141224.04
NPT00119 | W009 | R001 | Weather | Heavy Rain | Lightning | 4 | 79166 | 143929 | 223095 | 223095 | 0 | 0.3 | 0.5 | 33464.25 | 6692.85 | 13385.7 | 20078.55
NPT00120 | W009 | R001 | Mechanical | Draw Works Failure | OEM Defect | 4 | 79166 | 68905 | 148071 | 148071 | 0 | 0.7 | 0.5 | 51824.85 | 10364.97 | 20729.94 | 31094.91
NPT00121 | W009 | R001 | Drilling | Lost Circulation | Differential Sticking | 6 | 118750 | 291172 | 409922 | 409922 | 0 | 0.8 | 0.75 | 245953.2 | 49190.64 | 98381.28 | 147571.92
NPT00122 | W009 | R001 | Weather | Lightning | High Waves | 6 | 118750 | 128920 | 247670 | 247670 | 0 | 0.3 | 0.5 | 37150.5 | 7430.1 | 14860.2 | 22290.3
NPT00123 | W009 | R001 | Weather | Strong Wind | High Waves | 6 | 118750 | 279850 | 398600 | 398600 | 0 | 0.3 | 0.75 | 89685 | 17937 | 35874 | 53811
NPT00124 | W009 | R001 | Logistics | Waiting on Cement | Customs Clearance | 12 | 237500 | 223755 | 461255 | 461255 | 0 | 0.6 | 0.5 | 138376.5 | 27675.3 | 55350.6 | 83025.9
NPT00125 | W009 | R001 | Weather | Heavy Rain | High Waves | 8 | 158333 | 384790 | 543123 | 543123 | 0 | 0.3 | 1 | 162936.9 | 32587.38 | 65174.76 | 97762.14
NPT00126 | W010 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 8 | 153333 | 152314 | 305647 | 305647 | 0 | 0.9 | 1 | 275082.3 | 55016.46 | 110032.92 | 165049.38
NPT00127 | W010 | R002 | Weather | Strong Wind | Storm | 6 | 115000 | 139238 | 254238 | 254238 | 0 | 0.3 | 0.75 | 57203.55 | 11440.71 | 22881.42 | 34322.13
NPT00128 | W010 | R002 | Drilling | Bit Failure | Unexpected Pressure | 2 | 38333 | 30581 | 68914 | 68914 | 0 | 0.65 | 0.5 | 22397.05 | 4479.41 | 8958.82 | 13438.23
NPT00129 | W010 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 2 | 38333 | 24138 | 62471 | 62471 | 0 | 0.65 | 0.5 | 20303.075 | 4060.615 | 8121.23 | 12181.845
NPT00130 | W010 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 8 | 153333 | 121885 | 275218 | 275218 | 0 | 0.9 | 0.5 | 123848.1 | 24769.62 | 49539.24 | 74308.86
NPT00131 | W010 | R002 | Weather | Heavy Rain | Strong Wind | 24 | 460000 | 815283 | 1275283 | 1275283 | 0 | 0.3 | 0.5 | 191292.45 | 38258.49 | 76516.98 | 114775.47
NPT00132 | W010 | R002 | Weather | Lightning | Heavy Rain | 18 | 345000 | 286552 | 631552 | 631552 | 0 | 0.3 | 0.5 | 94732.8 | 18946.56 | 37893.12 | 56839.68
NPT00133 | W010 | R002 | Drilling | Lost Circulation | Bit Wear | 4 | 76666 | 146588 | 223254 | 223254 | 0 | 0.8 | 0.5 | 89301.6 | 17860.32 | 35720.64 | 53580.96
NPT00134 | W010 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | 2 | 38333 | 89900 | 128233 | 128233 | 0 | 0.6 | 0.5 | 38469.9 | 7693.98 | 15387.96 | 23081.94
NPT00135 | W010 | R002 | Weather | Strong Wind | Strong Wind | 4 | 76666 | 104095 | 180761 | 180761 | 0 | 0.3 | 0.5 | 27114.15 | 5422.83 | 10845.66 | 16268.49
NPT00136 | W010 | R002 | Drilling | Well Control | Formation Instability | 4 | 76666 | 150640 | 227306 | 227306 | 0 | 0.65 | 0.75 | 110811.675 | 22162.335 | 44324.67 | 66487.005
NPT00137 | W010 | R002 | Drilling | Hole Cleaning | Differential Sticking | 8 | 153333 | 121122 | 274455 | 274455 | 0 | 0.8 | 0.5 | 109782 | 21956.4 | 43912.8 | 65869.2
NPT00138 | W010 | R002 | Drilling | Lost Circulation | Formation Instability | 6 | 115000 | 223747 | 338747 | 338747 | 0 | 0.65 | 0.5 | 110092.775 | 22018.555 | 44037.11 | 66055.665
NPT00139 | W010 | R002 | Drilling | Stuck Pipe | Differential Sticking | 4 | 76666 | 168661 | 245327 | 245327 | 0 | 0.8 | 0.5 | 98130.8 | 19626.16 | 39252.32 | 58878.48
NPT00140 | W010 | R002 | Weather | Lightning | Heavy Rain | 2 | 38333 | 31793 | 70126 | 70126 | 0 | 0.3 | 0.75 | 15778.35 | 3155.67 | 6311.34 | 9467.01
NPT00141 | W010 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 4 | 76666 | 96663 | 173329 | 173329 | 0 | 0.9 | 0.5 | 77998.05 | 15599.61 | 31199.22 | 46798.83
NPT00142 | W011 | R004 | Weather | Poor Visibility | Strong Wind | 4 | 81666 | 60048 | 141714 | 141714 | 0 | 0.3 | 0.5 | 21257.1 | 4251.42 | 8502.84 | 12754.26
NPT00143 | W011 | R004 | Drilling | Lost Circulation | Unexpected Pressure | 4 | 81666 | 126974 | 208640 | 208640 | 0 | 0.65 | 0.5 | 67808 | 13561.6 | 27123.2 | 40684.8
NPT00144 | W011 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 8 | 163333 | 235581 | 398914 | 398914 | 0 | 0.65 | 0.5 | 129647.05 | 25929.41 | 51858.82 | 77788.23
NPT00145 | W011 | R004 | Weather | Lightning | Storm | 4 | 81666 | 98387 | 180053 | 180053 | 0 | 0.3 | 0.5 | 27007.95 | 5401.59 | 10803.18 | 16204.77
NPT00146 | W011 | R004 | Drilling | Lost Circulation | Bit Wear | 2 | 40833 | 26711 | 67544 | 67544 | 0 | 0.8 | 1 | 54035.2 | 10807.04 | 21614.08 | 32421.12
NPT00147 | W011 | R004 | Drilling | Hole Cleaning | Differential Sticking | 12 | 245000 | 250040 | 495040 | 495040 | 0 | 0.8 | 0.5 | 198016 | 39603.2 | 79206.4 | 118809.6
NPT00148 | W011 | R004 | Weather | Lightning | Lightning | 4 | 81666 | 47696 | 129362 | 129362 | 0 | 0.3 | 0.5 | 19404.3 | 3880.86 | 7761.72 | 11642.58
NPT00149 | W011 | R004 | Personnel | Training | Crew Rotation | 6 | 122500 | 90710 | 213210 | 213210 | 0 | 0.6 | 0.75 | 95944.5 | 19188.9 | 38377.8 | 57566.7
NPT00150 | W011 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 6 | 122500 | 73044 | 195544 | 195544 | 0 | 0.9 | 0.5 | 87994.8 | 17598.96 | 35197.92 | 52796.88
NPT00151 | W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 24 | 490000 | 1059746 | 1549746 | 1549746 | 0 | 0.9 | 1 | 1394771.4 | 278954.28 | 557908.56 | 836862.84
NPT00152 | W011 | R004 | Mechanical | Generator Failure | Equipment Wear | 2 | 40833 | 27130 | 67963 | 67963 | 0 | 0.9 | 0.5 | 30583.35 | 6116.67 | 12233.34 | 18350.01
NPT00153 | W011 | R004 | Weather | Lightning | Lightning | 6 | 122500 | 186779 | 309279 | 309279 | 0 | 0.3 | 0.75 | 69587.775 | 13917.555 | 27835.11 | 41752.665
NPT00154 | W011 | R004 | Weather | Poor Visibility | Heavy Rain | 4 | 81666 | 107304 | 188970 | 188970 | 0 | 0.3 | 0.75 | 42518.25 | 8503.65 | 17007.3 | 25510.95
NPT00155 | W011 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 2 | 40833 | 71255 | 112088 | 112088 | 0 | 0.9 | 0.5 | 50439.6 | 10087.92 | 20175.84 | 30263.76
NPT00156 | W011 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 4 | 81666 | 48082 | 129748 | 129748 | 0 | 0.6 | 0.5 | 38924.4 | 7784.88 | 15569.76 | 23354.64
NPT00157 | W011 | R004 | Drilling | Bit Failure | Bit Wear | 12 | 245000 | 554806 | 799806 | 799806 | 0 | 0.8 | 0.5 | 319922.4 | 63984.48 | 127968.96 | 191953.44
NPT00158 | W012 | R004 | Drilling | Stuck Pipe | Bit Wear | 2 | 40833 | 30300 | 71133 | 71133 | 0 | 0.8 | 0.5 | 28453.2 | 5690.64 | 11381.28 | 17071.92
NPT00159 | W012 | R004 | Mechanical | Power System Failure | Equipment Wear | 6 | 122500 | 63732 | 186232 | 186232 | 0 | 0.9 | 0.5 | 83804.4 | 16760.88 | 33521.76 | 50282.64
NPT00160 | W012 | R004 | Logistics | Waiting on Materials | Customs Clearance | 2 | 40833 | 67554 | 108387 | 108387 | 0 | 0.6 | 0.5 | 32516.1 | 6503.22 | 13006.44 | 19509.66
NPT00161 | W012 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 6 | 122500 | 226126 | 348626 | 348626 | 0 | 0.9 | 0.5 | 156881.7 | 31376.34 | 62752.68 | 94129.02
NPT00162 | W012 | R004 | Logistics | Waiting on Boat | Port Congestion | 6 | 122500 | 255221 | 377721 | 377721 | 0 | 0.6 | 0.5 | 113316.3 | 22663.26 | 45326.52 | 67989.78
NPT00163 | W012 | R004 | Logistics | Waiting on Cement | Customs Clearance | 2 | 40833 | 100241 | 141074 | 141074 | 0 | 0.6 | 0.75 | 63483.3 | 12696.66 | 25393.32 | 38089.98
NPT00164 | W012 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 4 | 81666 | 62073 | 143739 | 143739 | 0 | 0.9 | 0.5 | 64682.55 | 12936.51 | 25873.02 | 38809.53
NPT00165 | W012 | R004 | Drilling | Bit Failure | Unexpected Pressure | 18 | 367500 | 574959 | 942459 | 942459 | 0 | 0.65 | 0.5 | 306299.175 | 61259.835 | 122519.67 | 183779.505
NPT00166 | W012 | R004 | Logistics | Delayed Helicopter | Customs Clearance | 2 | 40833 | 57857 | 98690 | 98690 | 0 | 0.6 | 0.5 | 29607 | 5921.4 | 11842.8 | 17764.2
NPT00167 | W012 | R004 | Drilling | Fishing Operation | Formation Instability | 4 | 81666 | 116402 | 198068 | 198068 | 0 | 0.65 | 0.75 | 96558.15 | 19311.63 | 38623.26 | 57934.89
NPT00168 | W012 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 12 | 245000 | 372611 | 617611 | 617611 | 0 | 0.6 | 0.5 | 185283.3 | 37056.66 | 74113.32 | 111169.98
NPT00169 | W013 | R003 | Drilling | Hole Cleaning | Differential Sticking | 6 | 120000 | 253064 | 373064 | 373064 | 0 | 0.8 | 0.5 | 149225.6 | 29845.12 | 59690.24 | 89535.36
NPT00170 | W013 | R003 | Personnel | Safety Stand Down | Medical Emergency | 2 | 40000 | 25522 | 65522 | 65522 | 0 | 0.6 | 0.5 | 19656.6 | 3931.32 | 7862.64 | 11793.96
NPT00171 | W013 | R003 | Personnel | Safety Stand Down | Crew Rotation | 8 | 160000 | 104847 | 264847 | 264847 | 0 | 0.6 | 0.5 | 79454.1 | 15890.82 | 31781.64 | 47672.46
NPT00172 | W013 | R003 | Weather | Heavy Rain | Strong Wind | 6 | 120000 | 223619 | 343619 | 343619 | 0 | 0.3 | 0.5 | 51542.85 | 10308.57 | 20617.14 | 30925.71
NPT00173 | W013 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 2 | 40000 | 42480 | 82480 | 82480 | 0 | 0.6 | 0.75 | 37116 | 7423.2 | 14846.4 | 22269.6
NPT00174 | W013 | R003 | Logistics | Waiting on Cement | Material Shortage | 2 | 40000 | 64200 | 104200 | 104200 | 0 | 0.6 | 0.5 | 31260 | 6252 | 12504 | 18756
NPT00175 | W013 | R003 | Logistics | Waiting on Cement | Customs Clearance | 4 | 80000 | 159783 | 239783 | 239783 | 0 | 0.6 | 1 | 143869.8 | 28773.96 | 57547.92 | 86321.88
NPT00176 | W013 | R003 | Weather | Strong Wind | Storm | 8 | 160000 | 158983 | 318983 | 318983 | 0 | 0.3 | 1 | 95694.9 | 19138.98 | 38277.96 | 57416.94
NPT00177 | W013 | R003 | Weather | Heavy Rain | High Waves | 4 | 80000 | 185590 | 265590 | 265590 | 0 | 0.3 | 0.5 | 39838.5 | 7967.7 | 15935.4 | 23903.1
NPT00178 | W013 | R003 | Drilling | Lost Circulation | Formation Instability | 6 | 120000 | 231131 | 351131 | 351131 | 0 | 0.65 | 0.75 | 171176.3625 | 34235.2725 | 68470.545 | 102705.8175
NPT00179 | W013 | R003 | Drilling | Fishing Operation | Formation Instability | 4 | 80000 | 113231 | 193231 | 193231 | 0 | 0.65 | 0.5 | 62800.075 | 12560.015 | 25120.03 | 37680.045
NPT00180 | W013 | R003 | Drilling | Lost Circulation | Formation Instability | 12 | 240000 | 542475 | 782475 | 782475 | 0 | 0.65 | 0.5 | 254304.375 | 50860.875 | 101721.75 | 152582.625
NPT00181 | W013 | R003 | Drilling | Lost Circulation | Bit Wear | 2 | 40000 | 26827 | 66827 | 66827 | 0 | 0.8 | 0.5 | 26730.8 | 5346.16 | 10692.32 | 16038.48
NPT00182 | W013 | R003 | Drilling | Stuck Pipe | Differential Sticking | 6 | 120000 | 278656 | 398656 | 398656 | 0 | 0.8 | 0.75 | 239193.6 | 47838.72 | 95677.44 | 143516.16
NPT00183 | W013 | R003 | Drilling | Bit Failure | Formation Instability | 2 | 40000 | 74203 | 114203 | 114203 | 0 | 0.65 | 0.5 | 37115.975 | 7423.195 | 14846.39 | 22269.585
NPT00184 | W013 | R003 | Mechanical | BOP Repair | Equipment Wear | 4 | 80000 | 122873 | 202873 | 202873 | 0 | 0.9 | 0.5 | 91292.85 | 18258.57 | 36517.14 | 54775.71
NPT00185 | W013 | R003 | Weather | Lightning | Lightning | 6 | 120000 | 129874 | 249874 | 249874 | 0 | 0.3 | 0.5 | 37481.1 | 7496.22 | 14992.44 | 22488.66
NPT00186 | W013 | R003 | Drilling | Fishing Operation | Differential Sticking | 8 | 160000 | 104193 | 264193 | 264193 | 0 | 0.8 | 0.5 | 105677.2 | 21135.44 | 42270.88 | 63406.32
NPT00187 | W013 | R003 | Drilling | Lost Circulation | Bit Wear | 2 | 40000 | 73930 | 113930 | 113930 | 0 | 0.8 | 0.5 | 45572 | 9114.4 | 18228.8 | 27343.2
NPT00188 | W013 | R003 | Mechanical | Generator Failure | Poor Preventive Maintenance | 2 | 40000 | 48341 | 88341 | 88341 | 0 | 0.9 | 0.5 | 39753.45 | 7950.69 | 15901.38 | 23852.07
NPT00189 | W014 | R004 | Personnel | Medical Evacuation | Training Requirement | 2 | 40833 | 98245 | 139078 | 139078 | 0 | 0.6 | 0.5 | 41723.4 | 8344.68 | 16689.36 | 25034.04
NPT00190 | W014 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 4 | 81666 | 198783 | 280449 | 280449 | 0 | 0.9 | 0.5 | 126202.05 | 25240.41 | 50480.82 | 75721.23
NPT00191 | W014 | R004 | Logistics | Waiting on Cement | Port Congestion | 4 | 81666 | 60188 | 141854 | 141854 | 0 | 0.6 | 0.5 | 42556.2 | 8511.24 | 17022.48 | 25533.72
NPT00192 | W014 | R004 | Drilling | Stuck Pipe | Bit Wear | 12 | 245000 | 508399 | 753399 | 753399 | 0 | 0.8 | 0.5 | 301359.6 | 60271.92 | 120543.84 | 180815.76
NPT00193 | W014 | R004 | Weather | Heavy Rain | High Waves | 2 | 40833 | 98036 | 138869 | 138869 | 0 | 0.3 | 0.75 | 31245.525 | 6249.105 | 12498.21 | 18747.315
NPT00194 | W014 | R004 | Mechanical | Power System Failure | Electrical Failure | 4 | 81666 | 154123 | 235789 | 235789 | 0 | 0.9 | 0.5 | 106105.05 | 21221.01 | 42442.02 | 63663.03
NPT00195 | W014 | R004 | Mechanical | Rotary Table Failure | Equipment Wear | 4 | 81666 | 77766 | 159432 | 159432 | 0 | 0.9 | 0.5 | 71744.4 | 14348.88 | 28697.76 | 43046.64
NPT00196 | W014 | R004 | Drilling | Fishing Operation | Unexpected Pressure | 6 | 122500 | 135468 | 257968 | 257968 | 0 | 0.65 | 0.5 | 83839.6 | 16767.92 | 33535.84 | 50303.76
NPT00197 | W015 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 8 | 160000 | 164904 | 324904 | 324904 | 0 | 0.65 | 1 | 211187.6 | 42237.52 | 84475.04 | 126712.56
NPT00198 | W015 | R003 | Drilling | Stuck Pipe | Bit Wear | 4 | 80000 | 168562 | 248562 | 248562 | 0 | 0.8 | 1 | 198849.6 | 39769.92 | 79539.84 | 119309.76
NPT00199 | W015 | R003 | Mechanical | Generator Failure | Equipment Wear | 8 | 160000 | 393128 | 553128 | 553128 | 0 | 0.9 | 0.5 | 248907.6 | 49781.52 | 99563.04 | 149344.56
NPT00200 | W015 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | 4 | 80000 | 127428 | 207428 | 207428 | 0 | 0.6 | 0.5 | 62228.4 | 12445.68 | 24891.36 | 37337.04
NPT00201 | W015 | R003 | Drilling | Well Control | Unexpected Pressure | 2 | 40000 | 30537 | 70537 | 70537 | 0 | 0.65 | 0.5 | 22924.525 | 4584.905 | 9169.81 | 13754.715
NPT00202 | W015 | R003 | Drilling | Fishing Operation | Formation Instability | 4 | 80000 | 93447 | 173447 | 173447 | 0 | 0.65 | 0.5 | 56370.275 | 11274.055 | 22548.11 | 33822.165
NPT00203 | W015 | R003 | Logistics | Waiting on Cement | Customs Clearance | 6 | 120000 | 295691 | 415691 | 415691 | 0 | 0.6 | 0.5 | 124707.3 | 24941.46 | 49882.92 | 74824.38
NPT00204 | W015 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 18 | 360000 | 883515 | 1243515 | 1243515 | 0 | 0.6 | 0.5 | 373054.5 | 74610.9 | 149221.8 | 223832.7
NPT00205 | W015 | R003 | Drilling | Fishing Operation | Differential Sticking | 2 | 40000 | 25923 | 65923 | 65923 | 0 | 0.8 | 0.5 | 26369.2 | 5273.84 | 10547.68 | 15821.52
NPT00206 | W015 | R003 | Drilling | Well Control | Formation Instability | 2 | 40000 | 27367 | 67367 | 67367 | 0 | 0.65 | 0.5 | 21894.275 | 4378.855 | 8757.71 | 13136.565
NPT00207 | W015 | R003 | Mechanical | BOP Repair | Hydraulic Failure | 6 | 120000 | 245352 | 365352 | 365352 | 0 | 0.9 | 1 | 328816.8 | 65763.36 | 131526.72 | 197290.08
NPT00208 | W015 | R003 | Drilling | Hole Cleaning | Unexpected Pressure | 6 | 120000 | 208139 | 328139 | 328139 | 0 | 0.65 | 0.5 | 106645.175 | 21329.035 | 42658.07 | 63987.105
NPT00209 | W015 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 4 | 80000 | 147308 | 227308 | 227308 | 0 | 0.6 | 0.5 | 68192.4 | 13638.48 | 27276.96 | 40915.44
NPT00210 | W015 | R003 | Personnel | Safety Stand Down | Training Requirement | 2 | 40000 | 53981 | 93981 | 93981 | 0 | 0.6 | 0.5 | 28194.3 | 5638.86 | 11277.72 | 16916.58
NPT00211 | W016 | R004 | Logistics | Waiting on Cement | Late Supply Vessel | 6 | 122500 | 96624 | 219124 | 219124 | 0 | 0.6 | 0.5 | 65737.2 | 13147.44 | 26294.88 | 39442.32
NPT00212 | W016 | R004 | Mechanical | Top Drive Failure | Electrical Failure | 6 | 122500 | 78520 | 201020 | 201020 | 0 | 0.9 | 0.75 | 135688.5 | 27137.7 | 54275.4 | 81413.1
NPT00213 | W016 | R004 | Weather | Lightning | Strong Wind | 6 | 122500 | 264246 | 386746 | 386746 | 0 | 0.3 | 0.5 | 58011.9 | 11602.38 | 23204.76 | 34807.14
NPT00214 | W016 | R004 | Weather | Heavy Rain | Lightning | 2 | 40833 | 90548 | 131381 | 131381 | 0 | 0.3 | 0.5 | 19707.15 | 3941.43 | 7882.86 | 11824.29
NPT00215 | W016 | R004 | Mechanical | Generator Failure | Hydraulic Failure | 8 | 163333 | 216971 | 380304 | 380304 | 0 | 0.9 | 0.5 | 171136.8 | 34227.36 | 68454.72 | 102682.08
NPT00216 | W016 | R004 | Drilling | Well Control | Unexpected Pressure | 2 | 40833 | 42270 | 83103 | 83103 | 0 | 0.65 | 0.75 | 40512.7125 | 8102.5425 | 16205.085 | 24307.6275
NPT00217 | W016 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 4 | 81666 | 165749 | 247415 | 247415 | 0 | 0.6 | 0.75 | 111336.75 | 22267.35 | 44534.7 | 66802.05
NPT00218 | W016 | R004 | Weather | Poor Visibility | Heavy Rain | 4 | 81666 | 146635 | 228301 | 228301 | 0 | 0.3 | 0.5 | 34245.15 | 6849.03 | 13698.06 | 20547.09
NPT00219 | W016 | R004 | Weather | Strong Wind | Strong Wind | 8 | 163333 | 228822 | 392155 | 392155 | 0 | 0.3 | 0.5 | 58823.25 | 11764.65 | 23529.3 | 35293.95
NPT00220 | W016 | R004 | Weather | Heavy Rain | Heavy Rain | 4 | 81666 | 192615 | 274281 | 274281 | 0 | 0.3 | 0.5 | 41142.15 | 8228.43 | 16456.86 | 24685.29
NPT00221 | W017 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 6 | 118750 | 239519 | 358269 | 358269 | 0 | 0.9 | 0.5 | 161221.05 | 32244.21 | 64488.42 | 96732.63
NPT00222 | W017 | R001 | Mechanical | Draw Works Failure | OEM Defect | 6 | 118750 | 120704 | 239454 | 239454 | 0 | 0.7 | 0.75 | 125713.35 | 25142.67 | 50285.34 | 75428.01
NPT00223 | W017 | R001 | Weather | Strong Wind | High Waves | 6 | 118750 | 136446 | 255196 | 255196 | 0 | 0.3 | 0.5 | 38279.4 | 7655.88 | 15311.76 | 22967.64
NPT00224 | W017 | R001 | Drilling | Fishing Operation | Formation Instability | 4 | 79166 | 127827 | 206993 | 206993 | 0 | 0.65 | 0.75 | 100909.0875 | 20181.8175 | 40363.635 | 60545.4525
NPT00225 | W017 | R001 | Drilling | Bit Failure | Formation Instability | 6 | 118750 | 81777 | 200527 | 200527 | 0 | 0.65 | 0.5 | 65171.275 | 13034.255 | 26068.51 | 39102.765
NPT00226 | W017 | R001 | Drilling | Hole Cleaning | Formation Instability | 2 | 39583 | 44552 | 84135 | 84135 | 0 | 0.65 | 0.5 | 27343.875 | 5468.775 | 10937.55 | 16406.325
NPT00227 | W017 | R001 | Logistics | Waiting on Cement | Late Supply Vessel | 6 | 118750 | 154929 | 273679 | 273679 | 0 | 0.6 | 0.5 | 82103.7 | 16420.74 | 32841.48 | 49262.22
NPT00228 | W017 | R001 | Drilling | Well Control | Bit Wear | 2 | 39583 | 49805 | 89388 | 89388 | 0 | 0.8 | 0.5 | 35755.2 | 7151.04 | 14302.08 | 21453.12
NPT00229 | W017 | R001 | Personnel | Safety Stand Down | Crew Rotation | 6 | 118750 | 236976 | 355726 | 355726 | 0 | 0.6 | 0.5 | 106717.8 | 21343.56 | 42687.12 | 64030.68
NPT00230 | W017 | R001 | Drilling | Stuck Pipe | Formation Instability | 2 | 39583 | 55699 | 95282 | 95282 | 0 | 0.65 | 0.75 | 46449.975 | 9289.995 | 18579.99 | 27869.985
NPT00231 | W017 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 8 | 158333 | 274332 | 432665 | 432665 | 0 | 0.6 | 0.5 | 129799.5 | 25959.9 | 51919.8 | 77879.7
NPT00232 | W018 | R004 | Weather | Poor Visibility | Storm | 6 | 122500 | 92594 | 215094 | 215094 | 0 | 0.3 | 0.5 | 32264.1 | 6452.82 | 12905.64 | 19358.46
NPT00233 | W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | 24 | 490000 | 397460 | 887460 | 887460 | 0 | 0.6 | 1 | 532476 | 106495.2 | 212990.4 | 319485.6
NPT00234 | W018 | R004 | Drilling | Fishing Operation | Formation Instability | 2 | 40833 | 48398 | 89231 | 89231 | 0 | 0.65 | 0.75 | 43500.1125 | 8700.0225 | 17400.045 | 26100.0675
NPT00235 | W018 | R004 | Weather | Heavy Rain | Strong Wind | 2 | 40833 | 71375 | 112208 | 112208 | 0 | 0.3 | 0.75 | 25246.8 | 5049.36 | 10098.72 | 15148.08
NPT00236 | W018 | R004 | Weather | Strong Wind | High Waves | 4 | 81666 | 130214 | 211880 | 211880 | 0 | 0.3 | 0.5 | 31782 | 6356.4 | 12712.8 | 19069.2
NPT00237 | W018 | R004 | Mechanical | Generator Failure | Equipment Wear | 4 | 81666 | 121285 | 202951 | 202951 | 0 | 0.9 | 0.5 | 91327.95 | 18265.59 | 36531.18 | 54796.77
NPT00238 | W018 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 6 | 122500 | 117557 | 240057 | 240057 | 0 | 0.9 | 0.5 | 108025.65 | 21605.13 | 43210.26 | 64815.39
NPT00239 | W018 | R004 | Drilling | Fishing Operation | Formation Instability | 2 | 40833 | 96130 | 136963 | 136963 | 0 | 0.65 | 0.75 | 66769.4625 | 13353.8925 | 26707.785 | 40061.6775
NPT00240 | W018 | R004 | Weather | Heavy Rain | Storm | 4 | 81666 | 202290 | 283956 | 283956 | 0 | 0.3 | 0.5 | 42593.4 | 8518.68 | 17037.36 | 25556.04
NPT00241 | W018 | R004 | Weather | Poor Visibility | Storm | 6 | 122500 | 74361 | 196861 | 196861 | 0 | 0.3 | 0.5 | 29529.15 | 5905.83 | 11811.66 | 17717.49
NPT00242 | W018 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 8 | 163333 | 204429 | 367762 | 367762 | 0 | 0.65 | 0.5 | 119522.65 | 23904.53 | 47809.06 | 71713.59
NPT00243 | W018 | R004 | Drilling | Well Control | Unexpected Pressure | 4 | 81666 | 86316 | 167982 | 167982 | 0 | 0.65 | 0.5 | 54594.15 | 10918.83 | 21837.66 | 32756.49
NPT00244 | W018 | R004 | Drilling | Stuck Pipe | Formation Instability | 12 | 245000 | 278344 | 523344 | 523344 | 0 | 0.65 | 0.5 | 170086.8 | 34017.36 | 68034.72 | 102052.08
NPT00245 | W018 | R004 | Weather | Heavy Rain | Heavy Rain | 4 | 81666 | 138389 | 220055 | 220055 | 0 | 0.3 | 0.5 | 33008.25 | 6601.65 | 13203.3 | 19804.95
NPT00246 | W019 | R003 | Weather | Lightning | High Waves | 24 | 480000 | 674701 | 1154701 | 1154701 | 0 | 0.3 | 0.5 | 173205.15 | 34641.03 | 69282.06 | 103923.09
NPT00247 | W019 | R003 | Mechanical | Top Drive Failure | Hydraulic Failure | 12 | 240000 | 123301 | 363301 | 363301 | 0 | 0.9 | 1 | 326970.9 | 65394.18 | 130788.36 | 196182.54
NPT00248 | W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 80000 | 66304 | 146304 | 146304 | 0 | 0.65 | 0.5 | 47548.8 | 9509.76 | 19019.52 | 28529.28
NPT00249 | W019 | R003 | Drilling | Stuck Pipe | Bit Wear | 6 | 120000 | 217687 | 337687 | 337687 | 0 | 0.8 | 0.5 | 135074.8 | 27014.96 | 54029.92 | 81044.88
NPT00250 | W019 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 6 | 120000 | 111527 | 231527 | 231527 | 0 | 0.6 | 0.5 | 69458.1 | 13891.62 | 27783.24 | 41674.86
NPT00251 | W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | 12 | 240000 | 479117 | 719117 | 719117 | 0 | 0.65 | 0.5 | 233713.025 | 46742.605 | 93485.21 | 140227.815
NPT00252 | W019 | R003 | Drilling | Lost Circulation | Bit Wear | 2 | 40000 | 65954 | 105954 | 105954 | 0 | 0.8 | 0.5 | 42381.6 | 8476.32 | 16952.64 | 25428.96
NPT00253 | W019 | R003 | Drilling | Lost Circulation | Formation Instability | 2 | 40000 | 24142 | 64142 | 64142 | 0 | 0.65 | 0.75 | 31269.225 | 6253.845 | 12507.69 | 18761.535
NPT00254 | W019 | R003 | Drilling | Hole Cleaning | Bit Wear | 4 | 80000 | 52250 | 132250 | 132250 | 0 | 0.8 | 0.5 | 52900 | 10580 | 21160 | 31740
NPT00255 | W019 | R003 | Drilling | Well Control | Bit Wear | 18 | 360000 | 827467 | 1187467 | 1187467 | 0 | 0.8 | 0.5 | 474986.8 | 94997.36 | 189994.72 | 284992.08
NPT00256 | W019 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 8 | 160000 | 163949 | 323949 | 323949 | 0 | 0.6 | 0.5 | 97184.7 | 19436.94 | 38873.88 | 58310.82
NPT00257 | W019 | R003 | Drilling | Lost Circulation | Formation Instability | 4 | 80000 | 108553 | 188553 | 188553 | 0 | 0.65 | 0.5 | 61279.725 | 12255.945 | 24511.89 | 36767.835
NPT00258 | W019 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | 12 | 240000 | 366765 | 606765 | 606765 | 0 | 0.6 | 0.5 | 182029.5 | 36405.9 | 72811.8 | 109217.7
NPT00259 | W020 | R003 | Mechanical | BOP Repair | Electrical Failure | 18 | 360000 | 663187 | 1023187 | 1023187 | 0 | 0.9 | 0.5 | 460434.15 | 92086.83 | 184173.66 | 276260.49
NPT00260 | W020 | R003 | Drilling | Bit Failure | Formation Instability | 4 | 80000 | 107175 | 187175 | 187175 | 0 | 0.65 | 0.5 | 60831.875 | 12166.375 | 24332.75 | 36499.125
NPT00261 | W020 | R003 | Drilling | Stuck Pipe | Differential Sticking | 2 | 40000 | 72937 | 112937 | 112937 | 0 | 0.8 | 1 | 90349.6 | 18069.92 | 36139.84 | 54209.76
NPT00262 | W020 | R003 | Logistics | Delayed Helicopter | Port Congestion | 2 | 40000 | 24049 | 64049 | 64049 | 0 | 0.6 | 0.5 | 19214.7 | 3842.94 | 7685.88 | 11528.82
NPT00263 | W020 | R003 | Drilling | Lost Circulation | Bit Wear | 6 | 120000 | 69661 | 189661 | 189661 | 0 | 0.8 | 0.5 | 75864.4 | 15172.88 | 30345.76 | 45518.64
NPT00264 | W020 | R003 | Weather | Heavy Rain | High Waves | 4 | 80000 | 70919 | 150919 | 150919 | 0 | 0.3 | 1 | 45275.7 | 9055.14 | 18110.28 | 27165.42
NPT00265 | W020 | R003 | Drilling | Hole Cleaning | Differential Sticking | 4 | 80000 | 156404 | 236404 | 236404 | 0 | 0.8 | 0.5 | 94561.6 | 18912.32 | 37824.64 | 56736.96
NPT00266 | W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 4 | 80000 | 95170 | 175170 | 175170 | 0 | 0.9 | 0.5 | 78826.5 | 15765.3 | 31530.6 | 47295.9
NPT00267 | W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 8 | 160000 | 130021 | 290021 | 290021 | 0 | 0.9 | 0.5 | 130509.45 | 26101.89 | 52203.78 | 78305.67
NPT00268 | W020 | R003 | Personnel | Medical Evacuation | Training Requirement | 2 | 40000 | 71032 | 111032 | 111032 | 0 | 0.6 | 0.5 | 33309.6 | 6661.92 | 13323.84 | 19985.76
NPT00269 | W020 | R003 | Weather | High Waves | Heavy Rain | 8 | 160000 | 364772 | 524772 | 524772 | 0 | 0.3 | 1 | 157431.6 | 31486.32 | 62972.64 | 94458.96
NPT00270 | W020 | R003 | Mechanical | Mud Pump Failure | Electrical Failure | 2 | 40000 | 81266 | 121266 | 121266 | 0 | 0.9 | 0.5 | 54569.7 | 10913.94 | 21827.88 | 32741.82
NPT00271 | W020 | R003 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 2 | 40000 | 79766 | 119766 | 119766 | 0 | 0.9 | 0.5 | 53894.7 | 10778.94 | 21557.88 | 32336.82
NPT00272 | W020 | R003 | Mechanical | Rotary Table Failure | Equipment Wear | 2 | 40000 | 52909 | 92909 | 92909 | 0 | 0.9 | 0.5 | 41809.05 | 8361.81 | 16723.62 | 25085.43
NPT00273 | W020 | R003 | Mechanical | Mud Pump Failure | Equipment Wear | 2 | 40000 | 33971 | 73971 | 73971 | 0 | 0.9 | 0.5 | 33286.95 | 6657.39 | 13314.78 | 19972.17
NPT00274 | W020 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 6 | 120000 | 141830 | 261830 | 261830 | 0 | 0.6 | 0.5 | 78549 | 15709.8 | 31419.6 | 47129.4
NPT00275 | W020 | R003 | Drilling | Fishing Operation | Differential Sticking | 6 | 120000 | 223111 | 343111 | 343111 | 0 | 0.8 | 0.5 | 137244.4 | 27448.88 | 54897.76 | 82346.64
NPT00276 | W020 | R003 | Mechanical | BOP Repair | OEM Defect | 2 | 40000 | 92216 | 132216 | 132216 | 0 | 0.7 | 0.5 | 46275.6 | 9255.12 | 18510.24 | 27765.36
NPT00277 | W020 | R003 | Mechanical | Power System Failure | Poor Preventive Maintenance | 4 | 80000 | 143184 | 223184 | 223184 | 0 | 0.9 | 0.5 | 100432.8 | 20086.56 | 40173.12 | 60259.68
NPT00278 | W020 | R003 | Weather | Lightning | Heavy Rain | 2 | 40000 | 91903 | 131903 | 131903 | 0 | 0.3 | 0.5 | 19785.45 | 3957.09 | 7914.18 | 11871.27
NPT00279 | W021 | R002 | Mechanical | Power System Failure | Electrical Failure | 12 | 230000 | 265392 | 495392 | 495392 | 0 | 0.9 | 0.5 | 222926.4 | 44585.28 | 89170.56 | 133755.84
NPT00280 | W021 | R002 | Drilling | Well Control | Formation Instability | 6 | 115000 | 172490 | 287490 | 287490 | 0 | 0.65 | 0.5 | 93434.25 | 18686.85 | 37373.7 | 56060.55
NPT00281 | W021 | R002 | Mechanical | Draw Works Failure | OEM Defect | 2 | 38333 | 40806 | 79139 | 79139 | 0 | 0.7 | 0.5 | 27698.65 | 5539.73 | 11079.46 | 16619.19
NPT00282 | W021 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 6 | 115000 | 207678 | 322678 | 322678 | 0 | 0.9 | 0.5 | 145205.1 | 29041.02 | 58082.04 | 87123.06
NPT00283 | W021 | R002 | Logistics | Waiting on Materials | Port Congestion | 8 | 153333 | 239111 | 392444 | 392444 | 0 | 0.6 | 0.5 | 117733.2 | 23546.64 | 47093.28 | 70639.92
NPT00284 | W021 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 4 | 76666 | 173767 | 250433 | 250433 | 0 | 0.9 | 0.75 | 169042.275 | 33808.455 | 67616.91 | 101425.365
NPT00285 | W021 | R002 | Logistics | Waiting on Cement | Port Congestion | 18 | 345000 | 573898 | 918898 | 918898 | 0 | 0.6 | 0.5 | 275669.4 | 55133.88 | 110267.76 | 165401.64
NPT00286 | W021 | R002 | Weather | Strong Wind | Strong Wind | 6 | 115000 | 80176 | 195176 | 195176 | 0 | 0.3 | 0.5 | 29276.4 | 5855.28 | 11710.56 | 17565.84
NPT00287 | W021 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 6 | 115000 | 90497 | 205497 | 205497 | 0 | 0.9 | 0.75 | 138710.475 | 27742.095 | 55484.19 | 83226.285
NPT00288 | W021 | R002 | Personnel | Medical Evacuation | Training Requirement | 2 | 38333 | 79231 | 117564 | 117564 | 0 | 0.6 | 0.5 | 35269.2 | 7053.84 | 14107.68 | 21161.52
NPT00289 | W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 6 | 115000 | 286496 | 401496 | 401496 | 0 | 0.6 | 0.5 | 120448.8 | 24089.76 | 48179.52 | 72269.28
NPT00290 | W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 2 | 38333 | 40658 | 78991 | 78991 | 0 | 0.6 | 0.5 | 23697.3 | 4739.46 | 9478.92 | 14218.38
NPT00291 | W021 | R002 | Weather | Lightning | Lightning | 2 | 38333 | 88590 | 126923 | 126923 | 0 | 0.3 | 0.5 | 19038.45 | 3807.69 | 7615.38 | 11423.07
NPT00292 | W021 | R002 | Mechanical | Power System Failure | Hydraulic Failure | 6 | 115000 | 196670 | 311670 | 311670 | 0 | 0.9 | 0.5 | 140251.5 | 28050.3 | 56100.6 | 84150.9
NPT00293 | W021 | R002 | Drilling | Lost Circulation | Formation Instability | 6 | 115000 | 90381 | 205381 | 205381 | 0 | 0.65 | 1 | 133497.65 | 26699.53 | 53399.06 | 80098.59
NPT00294 | W021 | R002 | Mechanical | Power System Failure | OEM Defect | 2 | 38333 | 78798 | 117131 | 117131 | 0 | 0.7 | 0.5 | 40995.85 | 8199.17 | 16398.34 | 24597.51
NPT00295 | W022 | R001 | Drilling | Hole Cleaning | Bit Wear | 12 | 237500 | 199439 | 436939 | 436939 | 0 | 0.8 | 0.5 | 174775.6 | 34955.12 | 69910.24 | 104865.36
NPT00296 | W022 | R001 | Weather | High Waves | Strong Wind | 2 | 39583 | 63322 | 102905 | 102905 | 0 | 0.3 | 0.5 | 15435.75 | 3087.15 | 6174.3 | 9261.45
NPT00297 | W022 | R001 | Weather | Poor Visibility | High Waves | 6 | 118750 | 138221 | 256971 | 256971 | 0 | 0.3 | 0.75 | 57818.475 | 11563.695 | 23127.39 | 34691.085
NPT00298 | W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 8 | 158333 | 298315 | 456648 | 456648 | 0 | 0.9 | 1 | 410983.2 | 82196.64 | 164393.28 | 246589.92
NPT00299 | W022 | R001 | Weather | Poor Visibility | Strong Wind | 2 | 39583 | 32358 | 71941 | 71941 | 0 | 0.3 | 0.75 | 16186.725 | 3237.345 | 6474.69 | 9712.035
NPT00300 | W022 | R001 | Weather | Strong Wind | Strong Wind | 4 | 79166 | 120835 | 200001 | 200001 | 0 | 0.3 | 0.75 | 45000.225 | 9000.045 | 18000.09 | 27000.135
NPT00301 | W022 | R001 | Weather | Lightning | Lightning | 2 | 39583 | 52686 | 92269 | 92269 | 0 | 0.3 | 0.5 | 13840.35 | 2768.07 | 5536.14 | 8304.21
NPT00302 | W022 | R001 | Weather | Strong Wind | Heavy Rain | 4 | 79166 | 104081 | 183247 | 183247 | 0 | 0.3 | 0.5 | 27487.05 | 5497.41 | 10994.82 | 16492.23
NPT00303 | W022 | R001 | Logistics | Waiting on Materials | Material Shortage | 6 | 118750 | 120114 | 238864 | 238864 | 0 | 0.6 | 0.75 | 107488.8 | 21497.76 | 42995.52 | 64493.28
NPT00304 | W022 | R001 | Logistics | Waiting on Materials | Port Congestion | 8 | 158333 | 193285 | 351618 | 351618 | 0 | 0.6 | 1 | 210970.8 | 42194.16 | 84388.32 | 126582.48
NPT00305 | W022 | R001 | Drilling | Hole Cleaning | Bit Wear | 6 | 118750 | 59595 | 178345 | 178345 | 0 | 0.8 | 0.75 | 107007 | 21401.4 | 42802.8 | 64204.2
NPT00306 | W022 | R001 | Weather | Poor Visibility | Strong Wind | 12 | 237500 | 561306 | 798806 | 798806 | 0 | 0.3 | 0.5 | 119820.9 | 23964.18 | 47928.36 | 71892.54
NPT00307 | W022 | R001 | Weather | Strong Wind | Heavy Rain | 2 | 39583 | 34235 | 73818 | 73818 | 0 | 0.3 | 1 | 22145.4 | 4429.08 | 8858.16 | 13287.24
NPT00308 | W023 | R004 | Mechanical | Draw Works Failure | OEM Defect | 4 | 81666 | 189343 | 271009 | 271009 | 0 | 0.7 | 0.5 | 94853.15 | 18970.63 | 37941.26 | 56911.89
NPT00309 | W023 | R004 | Drilling | Well Control | Unexpected Pressure | 6 | 122500 | 274722 | 397222 | 397222 | 0 | 0.65 | 0.5 | 129097.15 | 25819.43 | 51638.86 | 77458.29
NPT00310 | W023 | R004 | Logistics | Waiting on Boat | Port Congestion | 6 | 122500 | 257837 | 380337 | 380337 | 0 | 0.6 | 0.5 | 114101.1 | 22820.22 | 45640.44 | 68460.66
NPT00311 | W023 | R004 | Personnel | Crew Change | Medical Emergency | 18 | 367500 | 774135 | 1141635 | 1141635 | 0 | 0.6 | 0.5 | 342490.5 | 68498.1 | 136996.2 | 205494.3
NPT00312 | W023 | R004 | Drilling | Well Control | Bit Wear | 4 | 81666 | 55231 | 136897 | 136897 | 0 | 0.8 | 0.75 | 82138.2 | 16427.64 | 32855.28 | 49282.92
NPT00313 | W023 | R004 | Weather | Lightning | Storm | 12 | 245000 | 431874 | 676874 | 676874 | 0 | 0.3 | 0.5 | 101531.1 | 20306.22 | 40612.44 | 60918.66
NPT00314 | W023 | R004 | Mechanical | Top Drive Failure | OEM Defect | 4 | 81666 | 112807 | 194473 | 194473 | 0 | 0.7 | 0.5 | 68065.55 | 13613.11 | 27226.22 | 40839.33
NPT00315 | W023 | R004 | Personnel | Medical Evacuation | Medical Emergency | 6 | 122500 | 253590 | 376090 | 376090 | 0 | 0.6 | 0.5 | 112827 | 22565.4 | 45130.8 | 67696.2
NPT00316 | W023 | R004 | Mechanical | Generator Failure | Hydraulic Failure | 2 | 40833 | 34121 | 74954 | 74954 | 0 | 0.9 | 0.5 | 33729.3 | 6745.86 | 13491.72 | 20237.58
NPT00317 | W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | 8 | 163333 | 324715 | 488048 | 488048 | 0 | 0.9 | 1 | 439243.2 | 87848.64 | 175697.28 | 263545.92
NPT00318 | W023 | R004 | Mechanical | Mud Pump Failure | Hydraulic Failure | 2 | 40833 | 86980 | 127813 | 127813 | 0 | 0.9 | 0.5 | 57515.85 | 11503.17 | 23006.34 | 34509.51
NPT00319 | W023 | R004 | Drilling | Fishing Operation | Bit Wear | 4 | 81666 | 185627 | 267293 | 267293 | 0 | 0.8 | 0.5 | 106917.2 | 21383.44 | 42766.88 | 64150.32
NPT00320 | W023 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 4 | 81666 | 71396 | 153062 | 153062 | 0 | 0.9 | 1 | 137755.8 | 27551.16 | 55102.32 | 82653.48
NPT00321 | W023 | R004 | Personnel | Safety Stand Down | Medical Emergency | 4 | 81666 | 60840 | 142506 | 142506 | 0 | 0.6 | 0.5 | 42751.8 | 8550.36 | 17100.72 | 25651.08
NPT00322 | W024 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 8 | 153333 | 152401 | 305734 | 305734 | 0 | 0.9 | 0.5 | 137580.3 | 27516.06 | 55032.12 | 82548.18
NPT00323 | W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 12 | 230000 | 245724 | 475724 | 475724 | 0 | 0.65 | 0.75 | 231915.45 | 46383.09 | 92766.18 | 139149.27
NPT00324 | W024 | R002 | Weather | Poor Visibility | High Waves | 4 | 76666 | 44941 | 121607 | 121607 | 0 | 0.3 | 0.5 | 18241.05 | 3648.21 | 7296.42 | 10944.63
NPT00325 | W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 76666 | 67775 | 144441 | 144441 | 0 | 0.65 | 0.5 | 46943.325 | 9388.665 | 18777.33 | 28165.995
NPT00326 | W024 | R002 | Logistics | Waiting on Materials | Material Shortage | 12 | 230000 | 541101 | 771101 | 771101 | 0 | 0.6 | 0.5 | 231330.3 | 46266.06 | 92532.12 | 138798.18
NPT00327 | W024 | R002 | Drilling | Well Control | Differential Sticking | 4 | 76666 | 70081 | 146747 | 146747 | 0 | 0.8 | 0.5 | 58698.8 | 11739.76 | 23479.52 | 35219.28
NPT00328 | W024 | R002 | Drilling | Bit Failure | Unexpected Pressure | 2 | 38333 | 86372 | 124705 | 124705 | 0 | 0.65 | 1 | 81058.25 | 16211.65 | 32423.3 | 48634.95
NPT00329 | W024 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 2 | 38333 | 86067 | 124400 | 124400 | 0 | 0.9 | 0.75 | 83970 | 16794 | 33588 | 50382
NPT00330 | W024 | R002 | Drilling | Lost Circulation | Differential Sticking | 6 | 115000 | 184818 | 299818 | 299818 | 0 | 0.8 | 0.5 | 119927.2 | 23985.44 | 47970.88 | 71956.32
NPT00331 | W024 | R002 | Drilling | Stuck Pipe | Formation Instability | 2 | 38333 | 66638 | 104971 | 104971 | 0 | 0.65 | 0.5 | 34115.575 | 6823.115 | 13646.23 | 20469.345
NPT00332 | W024 | R002 | Drilling | Stuck Pipe | Differential Sticking | 4 | 76666 | 132348 | 209014 | 209014 | 0 | 0.8 | 0.5 | 83605.6 | 16721.12 | 33442.24 | 50163.36
NPT00333 | W024 | R002 | Mechanical | Power System Failure | OEM Defect | 8 | 153333 | 260743 | 414076 | 414076 | 0 | 0.7 | 0.5 | 144926.6 | 28985.32 | 57970.64 | 86955.96
NPT00334 | W025 | R004 | Drilling | Bit Failure | Differential Sticking | 6 | 122500 | 144551 | 267051 | 267051 | 0 | 0.8 | 0.5 | 106820.4 | 21364.08 | 42728.16 | 64092.24
NPT00335 | W025 | R004 | Drilling | Well Control | Formation Instability | 4 | 81666 | 144601 | 226267 | 226267 | 0 | 0.65 | 0.5 | 73536.775 | 14707.355 | 29414.71 | 44122.065
NPT00336 | W025 | R004 | Weather | Heavy Rain | Storm | 4 | 81666 | 127004 | 208670 | 208670 | 0 | 0.3 | 0.5 | 31300.5 | 6260.1 | 12520.2 | 18780.3
NPT00337 | W025 | R004 | Drilling | Stuck Pipe | Bit Wear | 6 | 122500 | 154285 | 276785 | 276785 | 0 | 0.8 | 0.75 | 166071 | 33214.2 | 66428.4 | 99642.6
NPT00338 | W025 | R004 | Weather | Strong Wind | Lightning | 2 | 40833 | 43926 | 84759 | 84759 | 0 | 0.3 | 0.5 | 12713.85 | 2542.77 | 5085.54 | 7628.31
NPT00339 | W025 | R004 | Mechanical | BOP Repair | Hydraulic Failure | 4 | 81666 | 86786 | 168452 | 168452 | 0 | 0.9 | 0.75 | 113705.1 | 22741.02 | 45482.04 | 68223.06
NPT00340 | W025 | R004 | Weather | High Waves | Strong Wind | 6 | 122500 | 265620 | 388120 | 388120 | 0 | 0.3 | 1 | 116436 | 23287.2 | 46574.4 | 69861.6
NPT00341 | W025 | R004 | Mechanical | Top Drive Failure | OEM Defect | 2 | 40833 | 48689 | 89522 | 89522 | 0 | 0.7 | 0.5 | 31332.7 | 6266.54 | 12533.08 | 18799.62
NPT00342 | W025 | R004 | Weather | High Waves | Storm | 2 | 40833 | 62499 | 103332 | 103332 | 0 | 0.3 | 0.75 | 23249.7 | 4649.94 | 9299.88 | 13949.82
NPT00343 | W025 | R004 | Drilling | Lost Circulation | Bit Wear | 12 | 245000 | 539466 | 784466 | 784466 | 0 | 0.8 | 0.5 | 313786.4 | 62757.28 | 125514.56 | 188271.84
NPT00344 | W025 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 6 | 122500 | 138722 | 261222 | 261222 | 0 | 0.65 | 0.75 | 127345.725 | 25469.145 | 50938.29 | 76407.435
NPT00345 | W026 | R004 | Weather | High Waves | Strong Wind | 12 | 245000 | 580843 | 825843 | 825843 | 0 | 0.3 | 0.75 | 185814.675 | 37162.935 | 74325.87 | 111488.805
NPT00346 | W026 | R004 | Weather | Heavy Rain | Storm | 24 | 490000 | 614657 | 1104657 | 1104657 | 0 | 0.3 | 0.5 | 165698.55 | 33139.71 | 66279.42 | 99419.13
NPT00347 | W026 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | 4 | 81666 | 185274 | 266940 | 266940 | 0 | 0.9 | 0.5 | 120123 | 24024.6 | 48049.2 | 72073.8
NPT00348 | W026 | R004 | Drilling | Bit Failure | Bit Wear | 8 | 163333 | 234179 | 397512 | 397512 | 0 | 0.8 | 0.5 | 159004.8 | 31800.96 | 63601.92 | 95402.88
NPT00349 | W026 | R004 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 8 | 163333 | 249120 | 412453 | 412453 | 0 | 0.9 | 0.5 | 185603.85 | 37120.77 | 74241.54 | 111362.31
NPT00350 | W026 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 2 | 40833 | 48430 | 89263 | 89263 | 0 | 0.9 | 0.5 | 40168.35 | 8033.67 | 16067.34 | 24101.01
NPT00351 | W026 | R004 | Mechanical | Draw Works Failure | Equipment Wear | 2 | 40833 | 31395 | 72228 | 72228 | 0 | 0.9 | 0.5 | 32502.6 | 6500.52 | 13001.04 | 19501.56
NPT00352 | W026 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 6 | 122500 | 186115 | 308615 | 308615 | 0 | 0.6 | 0.75 | 138876.75 | 27775.35 | 55550.7 | 83326.05
NPT00353 | W026 | R004 | Personnel | Safety Stand Down | Medical Emergency | 18 | 367500 | 388821 | 756321 | 756321 | 0 | 0.6 | 0.75 | 340344.45 | 68068.89 | 136137.78 | 204206.67
NPT00354 | W026 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 81666 | 55037 | 136703 | 136703 | 0 | 0.65 | 0.5 | 44428.475 | 8885.695 | 17771.39 | 26657.085
NPT00355 | W026 | R004 | Logistics | Waiting on Materials | Customs Clearance | 2 | 40833 | 41456 | 82289 | 82289 | 0 | 0.6 | 1 | 49373.4 | 9874.68 | 19749.36 | 29624.04
NPT00356 | W027 | R002 | Drilling | Fishing Operation | Differential Sticking | 18 | 345000 | 565252 | 910252 | 910252 | 0 | 0.8 | 0.75 | 546151.2 | 109230.24 | 218460.48 | 327690.72
NPT00357 | W027 | R002 | Weather | High Waves | Heavy Rain | 2 | 38333 | 72075 | 110408 | 110408 | 0 | 0.3 | 0.5 | 16561.2 | 3312.24 | 6624.48 | 9936.72
NPT00358 | W027 | R002 | Weather | Lightning | High Waves | 4 | 76666 | 85784 | 162450 | 162450 | 0 | 0.3 | 0.75 | 36551.25 | 7310.25 | 14620.5 | 21930.75
NPT00359 | W027 | R002 | Drilling | Bit Failure | Differential Sticking | 8 | 153333 | 335435 | 488768 | 488768 | 0 | 0.8 | 1 | 391014.4 | 78202.88 | 156405.76 | 234608.64
NPT00360 | W027 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | 6 | 115000 | 112412 | 227412 | 227412 | 0 | 0.6 | 0.75 | 102335.4 | 20467.08 | 40934.16 | 61401.24
NPT00361 | W027 | R002 | Weather | Lightning | High Waves | 12 | 230000 | 258903 | 488903 | 488903 | 0 | 0.3 | 0.5 | 73335.45 | 14667.09 | 29334.18 | 44001.27
NPT00362 | W027 | R002 | Drilling | Stuck Pipe | Formation Instability | 2 | 38333 | 85268 | 123601 | 123601 | 0 | 0.65 | 0.75 | 60255.4875 | 12051.0975 | 24102.195 | 36153.2925
NPT00363 | W027 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 4 | 76666 | 38651 | 115317 | 115317 | 0 | 0.9 | 0.5 | 51892.65 | 10378.53 | 20757.06 | 31135.59
NPT00364 | W027 | R002 | Weather | Poor Visibility | Storm | 2 | 38333 | 61637 | 99970 | 99970 | 0 | 0.3 | 0.5 | 14995.5 | 2999.1 | 5998.2 | 8997.3
NPT00365 | W027 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 8 | 153333 | 342295 | 495628 | 495628 | 0 | 0.65 | 1 | 322158.2 | 64431.64 | 128863.28 | 193294.92
NPT00366 | W028 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 6 | 115000 | 87189 | 202189 | 202189 | 0 | 0.65 | 0.5 | 65711.425 | 13142.285 | 26284.57 | 39426.855
NPT00367 | W028 | R002 | Weather | Lightning | Storm | 4 | 76666 | 169923 | 246589 | 246589 | 0 | 0.3 | 0.5 | 36988.35 | 7397.67 | 14795.34 | 22193.01
NPT00368 | W028 | R002 | Mechanical | Power System Failure | Hydraulic Failure | 8 | 153333 | 276056 | 429389 | 429389 | 0 | 0.9 | 0.75 | 289837.575 | 57967.515 | 115935.03 | 173902.545
NPT00369 | W028 | R002 | Weather | Strong Wind | Strong Wind | 2 | 38333 | 68316 | 106649 | 106649 | 0 | 0.3 | 0.5 | 15997.35 | 3199.47 | 6398.94 | 9598.41
NPT00370 | W028 | R002 | Personnel | Crew Change | Training Requirement | 4 | 76666 | 79447 | 156113 | 156113 | 0 | 0.6 | 0.5 | 46833.9 | 9366.78 | 18733.56 | 28100.34
NPT00371 | W028 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 12 | 230000 | 150405 | 380405 | 380405 | 0 | 0.65 | 0.5 | 123631.625 | 24726.325 | 49452.65 | 74178.975
NPT00372 | W028 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 4 | 76666 | 154351 | 231017 | 231017 | 0 | 0.6 | 1 | 138610.2 | 27722.04 | 55444.08 | 83166.12
NPT00373 | W028 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 38333 | 40944 | 79277 | 79277 | 0 | 0.65 | 0.5 | 25765.025 | 5153.005 | 10306.01 | 15459.015
NPT00374 | W028 | R002 | Weather | High Waves | Lightning | 6 | 115000 | 249425 | 364425 | 364425 | 0 | 0.3 | 0.5 | 54663.75 | 10932.75 | 21865.5 | 32798.25
NPT00375 | W028 | R002 | Drilling | Fishing Operation | Formation Instability | 4 | 76666 | 159300 | 235966 | 235966 | 0 | 0.65 | 0.75 | 115033.425 | 23006.685 | 46013.37 | 69020.055
NPT00376 | W028 | R002 | Weather | Strong Wind | Heavy Rain | 6 | 115000 | 194047 | 309047 | 309047 | 0 | 0.3 | 0.5 | 46357.05 | 9271.41 | 18542.82 | 27814.23
NPT00377 | W028 | R002 | Drilling | Stuck Pipe | Bit Wear | 18 | 345000 | 380594 | 725594 | 725594 | 0 | 0.8 | 0.5 | 290237.6 | 58047.52 | 116095.04 | 174142.56
NPT00378 | W028 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | 2 | 38333 | 83567 | 121900 | 121900 | 0 | 0.9 | 0.5 | 54855 | 10971 | 21942 | 32913
NPT00379 | W028 | R002 | Weather | Strong Wind | Storm | 4 | 76666 | 41042 | 117708 | 117708 | 0 | 0.3 | 1 | 35312.4 | 7062.48 | 14124.96 | 21187.44
NPT00380 | W028 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 8 | 153333 | 283449 | 436782 | 436782 | 0 | 0.9 | 0.5 | 196551.9 | 39310.38 | 78620.76 | 117931.14
NPT00381 | W029 | R002 | Drilling | Hole Cleaning | Differential Sticking | 2 | 38333 | 53610 | 91943 | 91943 | 0 | 0.8 | 1 | 73554.4 | 14710.88 | 29421.76 | 44132.64
NPT00382 | W029 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | 4 | 76666 | 74370 | 151036 | 151036 | 0 | 0.9 | 0.5 | 67966.2 | 13593.24 | 27186.48 | 40779.72
NPT00383 | W029 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 8 | 153333 | 279943 | 433276 | 433276 | 0 | 0.9 | 0.75 | 292461.3 | 58492.26 | 116984.52 | 175476.78
NPT00384 | W029 | R002 | Personnel | Crew Change | Medical Emergency | 6 | 115000 | 117452 | 232452 | 232452 | 0 | 0.6 | 0.75 | 104603.4 | 20920.68 | 41841.36 | 62762.04
NPT00385 | W029 | R002 | Weather | Heavy Rain | Strong Wind | 2 | 38333 | 24538 | 62871 | 62871 | 0 | 0.3 | 0.75 | 14145.975 | 2829.195 | 5658.39 | 8487.585
NPT00386 | W029 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 8 | 153333 | 130015 | 283348 | 283348 | 0 | 0.9 | 0.5 | 127506.6 | 25501.32 | 51002.64 | 76503.96
NPT00387 | W029 | R002 | Weather | Heavy Rain | Lightning | 6 | 115000 | 262434 | 377434 | 377434 | 0 | 0.3 | 0.5 | 56615.1 | 11323.02 | 22646.04 | 33969.06
NPT00388 | W029 | R002 | Drilling | Hole Cleaning | Bit Wear | 4 | 76666 | 185391 | 262057 | 262057 | 0 | 0.8 | 0.5 | 104822.8 | 20964.56 | 41929.12 | 62893.68
NPT00389 | W029 | R002 | Drilling | Well Control | Unexpected Pressure | 4 | 76666 | 148435 | 225101 | 225101 | 0 | 0.65 | 0.5 | 73157.825 | 14631.565 | 29263.13 | 43894.695
NPT00390 | W029 | R002 | Weather | Strong Wind | High Waves | 4 | 76666 | 100636 | 177302 | 177302 | 0 | 0.3 | 0.75 | 39892.95 | 7978.59 | 15957.18 | 23935.77
NPT00391 | W029 | R002 | Personnel | Medical Evacuation | Training Requirement | 2 | 38333 | 37984 | 76317 | 76317 | 0 | 0.6 | 0.5 | 22895.1 | 4579.02 | 9158.04 | 13737.06
NPT00392 | W029 | R002 | Weather | Poor Visibility | Heavy Rain | 6 | 115000 | 152059 | 267059 | 267059 | 0 | 0.3 | 0.75 | 60088.275 | 12017.655 | 24035.31 | 36052.965
NPT00393 | W029 | R002 | Logistics | Waiting on Materials | Material Shortage | 6 | 115000 | 239219 | 354219 | 354219 | 0 | 0.6 | 0.75 | 159398.55 | 31879.71 | 63759.42 | 95639.13
NPT00394 | W029 | R002 | Drilling | Lost Circulation | Differential Sticking | 8 | 153333 | 201314 | 354647 | 354647 | 0 | 0.8 | 0.5 | 141858.8 | 28371.76 | 56743.52 | 85115.28
NPT00395 | W030 | R002 | Personnel | Safety Stand Down | Training Requirement | 8 | 153333 | 91956 | 245289 | 245289 | 0 | 0.6 | 0.5 | 73586.7 | 14717.34 | 29434.68 | 44152.02
NPT00396 | W030 | R002 | Drilling | Stuck Pipe | Bit Wear | 2 | 38333 | 20240 | 58573 | 58573 | 0 | 0.8 | 0.75 | 35143.8 | 7028.76 | 14057.52 | 21086.28
NPT00397 | W030 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 38333 | 56371 | 94704 | 94704 | 0 | 0.65 | 0.5 | 30778.8 | 6155.76 | 12311.52 | 18467.28
NPT00398 | W030 | R002 | Drilling | Well Control | Formation Instability | 6 | 115000 | 74266 | 189266 | 189266 | 0 | 0.65 | 0.5 | 61511.45 | 12302.29 | 24604.58 | 36906.87
NPT00399 | W030 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 4 | 76666 | 52243 | 128909 | 128909 | 0 | 0.65 | 1 | 83790.85 | 16758.17 | 33516.34 | 50274.51
NPT00400 | W030 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 6 | 115000 | 233024 | 348024 | 348024 | 0 | 0.6 | 0.5 | 104407.2 | 20881.44 | 41762.88 | 62644.32
NPT00401 | W030 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 8 | 153333 | 363755 | 517088 | 517088 | 0 | 0.9 | 0.5 | 232689.6 | 46537.92 | 93075.84 | 139613.76
NPT00402 | W030 | R002 | Mechanical | Generator Failure | Electrical Failure | 2 | 38333 | 43940 | 82273 | 82273 | 0 | 0.9 | 1 | 74045.7 | 14809.14 | 29618.28 | 44427.42
NPT00403 | W030 | R002 | Weather | High Waves | High Waves | 12 | 230000 | 429330 | 659330 | 659330 | 0 | 0.3 | 0.5 | 98899.5 | 19779.9 | 39559.8 | 59339.7
NPT00404 | W030 | R002 | Mechanical | Power System Failure | Electrical Failure | 12 | 230000 | 418094 | 648094 | 648094 | 0 | 0.9 | 0.5 | 291642.3 | 58328.46 | 116656.92 | 174985.38
NPT00405 | W030 | R002 | Mechanical | BOP Repair | Electrical Failure | 8 | 153333 | 123054 | 276387 | 276387 | 0 | 0.9 | 0.5 | 124374.15 | 24874.83 | 49749.66 | 74624.49
NPT00406 | W030 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 2 | 38333 | 94383 | 132716 | 132716 | 0 | 0.9 | 0.5 | 59722.2 | 11944.44 | 23888.88 | 35833.32
NPT00407 | W030 | R002 | Logistics | Waiting on Cement | Material Shortage | 6 | 115000 | 69074 | 184074 | 184074 | 0 | 0.6 | 0.5 | 55222.2 | 11044.44 | 22088.88 | 33133.32
NPT00408 | W030 | R002 | Mechanical | Power System Failure | Equipment Wear | 8 | 153333 | 169026 | 322359 | 322359 | 0 | 0.9 | 0.75 | 217592.325 | 43518.465 | 87036.93 | 130555.395
NPT00409 | W030 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 4 | 76666 | 173634 | 250300 | 250300 | 0 | 0.9 | 1 | 225270 | 45054 | 90108 | 135162
NPT00410 | W031 | R002 | Weather | High Waves | Heavy Rain | 4 | 76666 | 191641 | 268307 | 268307 | 0 | 0.3 | 0.75 | 60369.075 | 12073.815 | 24147.63 | 36221.445
NPT00411 | W031 | R002 | Drilling | Stuck Pipe | Differential Sticking | 2 | 38333 | 69018 | 107351 | 107351 | 0 | 0.8 | 0.5 | 42940.4 | 8588.08 | 17176.16 | 25764.24
NPT00412 | W031 | R002 | Personnel | Safety Stand Down | Training Requirement | 4 | 76666 | 99814 | 176480 | 176480 | 0 | 0.6 | 0.75 | 79416 | 15883.2 | 31766.4 | 47649.6
NPT00413 | W031 | R002 | Drilling | Lost Circulation | Differential Sticking | 4 | 76666 | 115177 | 191843 | 191843 | 0 | 0.8 | 1 | 153474.4 | 30694.88 | 61389.76 | 92084.64
NPT00414 | W031 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 4 | 76666 | 44040 | 120706 | 120706 | 0 | 0.9 | 0.5 | 54317.7 | 10863.54 | 21727.08 | 32590.62
NPT00415 | W031 | R002 | Logistics | Waiting on Materials | Customs Clearance | 4 | 76666 | 128931 | 205597 | 205597 | 0 | 0.6 | 0.5 | 61679.1 | 12335.82 | 24671.64 | 37007.46
NPT00416 | W031 | R002 | Weather | Poor Visibility | Strong Wind | 4 | 76666 | 41049 | 117715 | 117715 | 0 | 0.3 | 0.5 | 17657.25 | 3531.45 | 7062.9 | 10594.35
NPT00417 | W031 | R002 | Drilling | Bit Failure | Differential Sticking | 4 | 76666 | 93803 | 170469 | 170469 | 0 | 0.8 | 0.5 | 68187.6 | 13637.52 | 27275.04 | 40912.56
NPT00418 | W031 | R002 | Drilling | Stuck Pipe | Formation Instability | 4 | 76666 | 100999 | 177665 | 177665 | 0 | 0.65 | 0.5 | 57741.125 | 11548.225 | 23096.45 | 34644.675
NPT00419 | W031 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 2 | 38333 | 54487 | 92820 | 92820 | 0 | 0.9 | 0.75 | 62653.5 | 12530.7 | 25061.4 | 37592.1
NPT00420 | W031 | R002 | Mechanical | BOP Repair | Equipment Wear | 24 | 460000 | 943802 | 1403802 | 1403802 | 0 | 0.9 | 0.75 | 947566.35 | 189513.27 | 379026.54 | 568539.81
NPT00421 | W032 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | 2 | 40833 | 99458 | 140291 | 140291 | 0 | 0.6 | 0.5 | 42087.3 | 8417.46 | 16834.92 | 25252.38
NPT00422 | W032 | R004 | Weather | Heavy Rain | Lightning | 8 | 163333 | 288692 | 452025 | 452025 | 0 | 0.3 | 0.5 | 67803.75 | 13560.75 | 27121.5 | 40682.25
NPT00423 | W032 | R004 | Weather | Heavy Rain | Strong Wind | 6 | 122500 | 75891 | 198391 | 198391 | 0 | 0.3 | 0.5 | 29758.65 | 5951.73 | 11903.46 | 17855.19
NPT00424 | W032 | R004 | Weather | Lightning | High Waves | 4 | 81666 | 171063 | 252729 | 252729 | 0 | 0.3 | 0.5 | 37909.35 | 7581.87 | 15163.74 | 22745.61
NPT00425 | W032 | R004 | Weather | High Waves | Lightning | 4 | 81666 | 184832 | 266498 | 266498 | 0 | 0.3 | 0.5 | 39974.7 | 7994.94 | 15989.88 | 23984.82
NPT00426 | W032 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 6 | 122500 | 76832 | 199332 | 199332 | 0 | 0.9 | 0.5 | 89699.4 | 17939.88 | 35879.76 | 53819.64
NPT00427 | W032 | R004 | Weather | Lightning | Strong Wind | 18 | 367500 | 445857 | 813357 | 813357 | 0 | 0.3 | 0.5 | 122003.55 | 24400.71 | 48801.42 | 73202.13
NPT00428 | W032 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 8 | 163333 | 152781 | 316114 | 316114 | 0 | 0.9 | 0.5 | 142251.3 | 28450.26 | 56900.52 | 85350.78
NPT00429 | W032 | R004 | Weather | High Waves | Storm | 2 | 40833 | 27339 | 68172 | 68172 | 0 | 0.3 | 1 | 20451.6 | 4090.32 | 8180.64 | 12270.96
NPT00430 | W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 6 | 122500 | 301536 | 424036 | 424036 | 0 | 0.6 | 0.5 | 127210.8 | 25442.16 | 50884.32 | 76326.48
NPT00431 | W032 | R004 | Personnel | Safety Stand Down | Training Requirement | 4 | 81666 | 94096 | 175762 | 175762 | 0 | 0.6 | 0.75 | 79092.9 | 15818.58 | 31637.16 | 47455.74
NPT00432 | W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 6 | 122500 | 231858 | 354358 | 354358 | 0 | 0.6 | 0.5 | 106307.4 | 21261.48 | 42522.96 | 63784.44
NPT00433 | W032 | R004 | Mechanical | Top Drive Failure | OEM Defect | 2 | 40833 | 33061 | 73894 | 73894 | 0 | 0.7 | 0.5 | 25862.9 | 5172.58 | 10345.16 | 15517.74
NPT00434 | W032 | R004 | Mechanical | Draw Works Failure | Equipment Wear | 8 | 163333 | 267513 | 430846 | 430846 | 0 | 0.9 | 0.5 | 193880.7 | 38776.14 | 77552.28 | 116328.42
NPT00435 | W032 | R004 | Drilling | Bit Failure | Formation Instability | 2 | 40833 | 45052 | 85885 | 85885 | 0 | 0.65 | 0.5 | 27912.625 | 5582.525 | 11165.05 | 16747.575
NPT00436 | W033 | R002 | Mechanical | Generator Failure | Electrical Failure | 6 | 115000 | 177855 | 292855 | 292855 | 0 | 0.9 | 0.5 | 131784.75 | 26356.95 | 52713.9 | 79070.85
NPT00437 | W033 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 12 | 230000 | 161849 | 391849 | 391849 | 0 | 0.9 | 1 | 352664.1 | 70532.82 | 141065.64 | 211598.46
NPT00438 | W033 | R002 | Weather | Heavy Rain | Storm | 2 | 38333 | 72796 | 111129 | 111129 | 0 | 0.3 | 0.5 | 16669.35 | 3333.87 | 6667.74 | 10001.61
NPT00439 | W033 | R002 | Drilling | Lost Circulation | Formation Instability | 4 | 76666 | 107302 | 183968 | 183968 | 0 | 0.65 | 1 | 119579.2 | 23915.84 | 47831.68 | 71747.52
NPT00440 | W033 | R002 | Drilling | Fishing Operation | Formation Instability | 6 | 115000 | 225265 | 340265 | 340265 | 0 | 0.65 | 1 | 221172.25 | 44234.45 | 88468.9 | 132703.35
NPT00441 | W033 | R002 | Logistics | Fuel Supply Delay | Material Shortage | 4 | 76666 | 165696 | 242362 | 242362 | 0 | 0.6 | 1 | 145417.2 | 29083.44 | 58166.88 | 87250.32
NPT00442 | W033 | R002 | Weather | High Waves | High Waves | 2 | 38333 | 41966 | 80299 | 80299 | 0 | 0.3 | 0.5 | 12044.85 | 2408.97 | 4817.94 | 7226.91
NPT00443 | W033 | R002 | Mechanical | BOP Repair | Equipment Wear | 12 | 230000 | 219568 | 449568 | 449568 | 0 | 0.9 | 0.75 | 303458.4 | 60691.68 | 121383.36 | 182075.04
NPT00444 | W033 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 2 | 38333 | 82613 | 120946 | 120946 | 0 | 0.9 | 1 | 108851.4 | 21770.28 | 43540.56 | 65310.84
NPT00445 | W033 | R002 | Weather | Poor Visibility | Lightning | 8 | 153333 | 182342 | 335675 | 335675 | 0 | 0.3 | 0.5 | 50351.25 | 10070.25 | 20140.5 | 30210.75
NPT00446 | W033 | R002 | Weather | Strong Wind | High Waves | 8 | 153333 | 347209 | 500542 | 500542 | 0 | 0.3 | 0.5 | 75081.3 | 15016.26 | 30032.52 | 45048.78
NPT00447 | W033 | R002 | Weather | Lightning | High Waves | 2 | 38333 | 65027 | 103360 | 103360 | 0 | 0.3 | 1 | 31008 | 6201.6 | 12403.2 | 18604.8
NPT00448 | W033 | R002 | Logistics | Delayed Helicopter | Material Shortage | 12 | 230000 | 407608 | 637608 | 637608 | 0 | 0.6 | 0.5 | 191282.4 | 38256.48 | 76512.96 | 114769.44
NPT00449 | W033 | R002 | Weather | Poor Visibility | High Waves | 4 | 76666 | 124855 | 201521 | 201521 | 0 | 0.3 | 0.5 | 30228.15 | 6045.63 | 12091.26 | 18136.89
NPT00450 | W033 | R002 | Mechanical | Generator Failure | Equipment Wear | 4 | 76666 | 55282 | 131948 | 131948 | 0 | 0.9 | 1 | 118753.2 | 23750.64 | 47501.28 | 71251.92
NPT00451 | W033 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 2 | 38333 | 81222 | 119555 | 119555 | 0 | 0.9 | 0.5 | 53799.75 | 10759.95 | 21519.9 | 32279.85
NPT00452 | W034 | R001 | Drilling | Fishing Operation | Formation Instability | 18 | 356250 | 822305 | 1178555 | 1178555 | 0 | 0.65 | 0.5 | 383030.375 | 76606.075 | 153212.15 | 229818.225
NPT00453 | W034 | R001 | Mechanical | Top Drive Failure | Electrical Failure | 4 | 79166 | 107969 | 187135 | 187135 | 0 | 0.9 | 0.5 | 84210.75 | 16842.15 | 33684.3 | 50526.45
NPT00454 | W034 | R001 | Drilling | Bit Failure | Formation Instability | 4 | 79166 | 76620 | 155786 | 155786 | 0 | 0.65 | 0.5 | 50630.45 | 10126.09 | 20252.18 | 30378.27
NPT00455 | W034 | R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 18 | 356250 | 284572 | 640822 | 640822 | 0 | 0.9 | 0.5 | 288369.9 | 57673.98 | 115347.96 | 173021.94
NPT00456 | W034 | R001 | Weather | High Waves | Lightning | 8 | 158333 | 332867 | 491200 | 491200 | 0 | 0.3 | 0.75 | 110520 | 22104 | 44208 | 66312
NPT00457 | W034 | R001 | Mechanical | Draw Works Failure | Electrical Failure | 4 | 79166 | 55237 | 134403 | 134403 | 0 | 0.9 | 0.5 | 60481.35 | 12096.27 | 24192.54 | 36288.81
NPT00458 | W034 | R001 | Weather | Poor Visibility | Storm | 4 | 79166 | 124715 | 203881 | 203881 | 0 | 0.3 | 0.5 | 30582.15 | 6116.43 | 12232.86 | 18349.29
NPT00459 | W034 | R001 | Mechanical | Top Drive Failure | Equipment Wear | 2 | 39583 | 57298 | 96881 | 96881 | 0 | 0.9 | 0.5 | 43596.45 | 8719.29 | 17438.58 | 26157.87
NPT00460 | W034 | R001 | Logistics | Waiting on Materials | Late Supply Vessel | 4 | 79166 | 187319 | 266485 | 266485 | 0 | 0.6 | 0.5 | 79945.5 | 15989.1 | 31978.2 | 47967.3
NPT00461 | W034 | R001 | Mechanical | Rotary Table Failure | Equipment Wear | 4 | 79166 | 45728 | 124894 | 124894 | 0 | 0.9 | 0.5 | 56202.3 | 11240.46 | 22480.92 | 33721.38
NPT00462 | W034 | R001 | Logistics | Waiting on Boat | Material Shortage | 2 | 39583 | 75663 | 115246 | 115246 | 0 | 0.6 | 0.5 | 34573.8 | 6914.76 | 13829.52 | 20744.28
NPT00463 | W034 | R001 | Drilling | Hole Cleaning | Bit Wear | 2 | 39583 | 22675 | 62258 | 62258 | 0 | 0.8 | 1 | 49806.4 | 9961.28 | 19922.56 | 29883.84
NPT00464 | W035 | R003 | Drilling | Stuck Pipe | Differential Sticking | 18 | 360000 | 208849 | 568849 | 568849 | 0 | 0.8 | 0.5 | 227539.6 | 45507.92 | 91015.84 | 136523.76
NPT00465 | W035 | R003 | Weather | High Waves | Heavy Rain | 6 | 120000 | 88739 | 208739 | 208739 | 0 | 0.3 | 0.5 | 31310.85 | 6262.17 | 12524.34 | 18786.51
NPT00466 | W035 | R003 | Drilling | Well Control | Unexpected Pressure | 2 | 40000 | 69853 | 109853 | 109853 | 0 | 0.65 | 0.5 | 35702.225 | 7140.445 | 14280.89 | 21421.335
NPT00467 | W035 | R003 | Weather | High Waves | Strong Wind | 6 | 120000 | 243625 | 363625 | 363625 | 0 | 0.3 | 0.5 | 54543.75 | 10908.75 | 21817.5 | 32726.25
NPT00468 | W035 | R003 | Drilling | Well Control | Differential Sticking | 2 | 40000 | 30168 | 70168 | 70168 | 0 | 0.8 | 0.5 | 28067.2 | 5613.44 | 11226.88 | 16840.32
NPT00469 | W035 | R003 | Weather | High Waves | Strong Wind | 18 | 360000 | 200297 | 560297 | 560297 | 0 | 0.3 | 1 | 168089.1 | 33617.82 | 67235.64 | 100853.46
NPT00470 | W035 | R003 | Drilling | Fishing Operation | Bit Wear | 2 | 40000 | 58559 | 98559 | 98559 | 0 | 0.8 | 0.5 | 39423.6 | 7884.72 | 15769.44 | 23654.16
NPT00471 | W035 | R003 | Weather | Strong Wind | Heavy Rain | 12 | 240000 | 122437 | 362437 | 362437 | 0 | 0.3 | 0.5 | 54365.55 | 10873.11 | 21746.22 | 32619.33
NPT00472 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | 6 | 120000 | 273652 | 393652 | 393652 | 0 | 0.8 | 0.5 | 157460.8 | 31492.16 | 62984.32 | 94476.48
NPT00473 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | 12 | 240000 | 291067 | 531067 | 531067 | 0 | 0.8 | 0.5 | 212426.8 | 42485.36 | 84970.72 | 127456.08
NPT00474 | W035 | R003 | Logistics | Waiting on Cement | Customs Clearance | 2 | 40000 | 38248 | 78248 | 78248 | 0 | 0.6 | 0.5 | 23474.4 | 4694.88 | 9389.76 | 14084.64
NPT00475 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | 6 | 120000 | 130403 | 250403 | 250403 | 0 | 0.8 | 0.5 | 100161.2 | 20032.24 | 40064.48 | 60096.72
NPT00476 | W036 | R002 | Logistics | Waiting on Boat | Customs Clearance | 2 | 38333 | 93792 | 132125 | 132125 | 0 | 0.6 | 0.5 | 39637.5 | 7927.5 | 15855 | 23782.5
NPT00477 | W036 | R002 | Drilling | Lost Circulation | Formation Instability | 4 | 76666 | 153896 | 230562 | 230562 | 0 | 0.65 | 0.75 | 112398.975 | 22479.795 | 44959.59 | 67439.385
NPT00478 | W036 | R002 | Drilling | Well Control | Formation Instability | 6 | 115000 | 253781 | 368781 | 368781 | 0 | 0.65 | 0.5 | 119853.825 | 23970.765 | 47941.53 | 71912.295
NPT00479 | W036 | R002 | Mechanical | Generator Failure | OEM Defect | 4 | 76666 | 152544 | 229210 | 229210 | 0 | 0.7 | 0.5 | 80223.5 | 16044.7 | 32089.4 | 48134.1
NPT00480 | W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 18 | 345000 | 776256 | 1121256 | 1121256 | 0 | 0.9 | 0.5 | 504565.2 | 100913.04 | 201826.08 | 302739.12
NPT00481 | W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | 2 | 38333 | 84839 | 123172 | 123172 | 0 | 0.8 | 0.5 | 49268.8 | 9853.76 | 19707.52 | 29561.28
NPT00482 | W036 | R002 | Drilling | Lost Circulation | Differential Sticking | 6 | 115000 | 202496 | 317496 | 317496 | 0 | 0.8 | 0.5 | 126998.4 | 25399.68 | 50799.36 | 76199.04
NPT00483 | W036 | R002 | Mechanical | BOP Repair | Equipment Wear | 4 | 76666 | 78814 | 155480 | 155480 | 0 | 0.9 | 0.5 | 69966 | 13993.2 | 27986.4 | 41979.6
NPT00484 | W036 | R002 | Drilling | Bit Failure | Unexpected Pressure | 4 | 76666 | 112293 | 188959 | 188959 | 0 | 0.65 | 0.5 | 61411.675 | 12282.335 | 24564.67 | 36847.005
NPT00485 | W036 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 2 | 38333 | 91400 | 129733 | 129733 | 0 | 0.7 | 0.5 | 45406.55 | 9081.31 | 18162.62 | 27243.93
NPT00486 | W036 | R002 | Mechanical | Power System Failure | Equipment Wear | 18 | 345000 | 526177 | 871177 | 871177 | 0 | 0.9 | 0.5 | 392029.65 | 78405.93 | 156811.86 | 235217.79
NPT00487 | W036 | R002 | Drilling | Hole Cleaning | Differential Sticking | 6 | 115000 | 111365 | 226365 | 226365 | 0 | 0.8 | 0.5 | 90546 | 18109.2 | 36218.4 | 54327.6
NPT00488 | W036 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 6 | 115000 | 150140 | 265140 | 265140 | 0 | 0.65 | 0.5 | 86170.5 | 17234.1 | 34468.2 | 51702.3
NPT00489 | W036 | R002 | Weather | Strong Wind | Lightning | 6 | 115000 | 123339 | 238339 | 238339 | 0 | 0.3 | 0.5 | 35750.85 | 7150.17 | 14300.34 | 21450.51
NPT00490 | W036 | R002 | Logistics | Fuel Supply Delay | Late Supply Vessel | 2 | 38333 | 67158 | 105491 | 105491 | 0 | 0.6 | 0.5 | 31647.3 | 6329.46 | 12658.92 | 18988.38
NPT00491 | W036 | R002 | Mechanical | Draw Works Failure | OEM Defect | 4 | 76666 | 67923 | 144589 | 144589 | 0 | 0.7 | 0.75 | 75909.225 | 15181.845 | 30363.69 | 45545.535
NPT00492 | W036 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 4 | 76666 | 85809 | 162475 | 162475 | 0 | 0.65 | 0.75 | 79206.5625 | 15841.3125 | 31682.625 | 47523.9375
NPT00493 | W036 | R002 | Logistics | Delayed Helicopter | Port Congestion | 4 | 76666 | 58910 | 135576 | 135576 | 0 | 0.6 | 1 | 81345.6 | 16269.12 | 32538.24 | 48807.36
NPT00494 | W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | 6 | 115000 | 150582 | 265582 | 265582 | 0 | 0.8 | 0.5 | 106232.8 | 21246.56 | 42493.12 | 63739.68
NPT00495 | W037 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 76666 | 106832 | 183498 | 183498 | 0 | 0.65 | 0.5 | 59636.85 | 11927.37 | 23854.74 | 35782.11
NPT00496 | W037 | R002 | Weather | Poor Visibility | Lightning | 4 | 76666 | 55100 | 131766 | 131766 | 0 | 0.3 | 0.5 | 19764.9 | 3952.98 | 7905.96 | 11858.94
NPT00497 | W037 | R002 | Mechanical | Generator Failure | Equipment Wear | 4 | 76666 | 159831 | 236497 | 236497 | 0 | 0.9 | 0.75 | 159635.475 | 31927.095 | 63854.19 | 95781.285
NPT00498 | W037 | R002 | Weather | Poor Visibility | Strong Wind | 8 | 153333 | 204824 | 358157 | 358157 | 0 | 0.3 | 0.5 | 53723.55 | 10744.71 | 21489.42 | 32234.13
NPT00499 | W037 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 4 | 76666 | 126288 | 202954 | 202954 | 0 | 0.65 | 0.75 | 98940.075 | 19788.015 | 39576.03 | 59364.045
NPT00500 | W037 | R002 | Drilling | Stuck Pipe | Bit Wear | 12 | 230000 | 132340 | 362340 | 362340 | 0 | 0.8 | 0.5 | 144936 | 28987.2 | 57974.4 | 86961.6
NPT00501 | W037 | R002 | Drilling | Bit Failure | Unexpected Pressure | 8 | 153333 | 197597 | 350930 | 350930 | 0 | 0.65 | 0.5 | 114052.25 | 22810.45 | 45620.9 | 68431.35
NPT00502 | W037 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 4 | 76666 | 67775 | 144441 | 144441 | 0 | 0.9 | 1 | 129996.9 | 25999.38 | 51998.76 | 77998.14
NPT00503 | W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 24 | 460000 | 763810 | 1223810 | 1223810 | 0 | 0.6 | 0.75 | 550714.5 | 110142.9 | 220285.8 | 330428.7
NPT00504 | W038 | R004 | Weather | Poor Visibility | Lightning | 2 | 40833 | 41869 | 82702 | 82702 | 0 | 0.3 | 0.5 | 12405.3 | 2481.06 | 4962.12 | 7443.18
NPT00505 | W038 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 8 | 163333 | 237483 | 400816 | 400816 | 0 | 0.9 | 0.5 | 180367.2 | 36073.44 | 72146.88 | 108220.32
NPT00506 | W038 | R004 | Drilling | Hole Cleaning | Formation Instability | 4 | 81666 | 183089 | 264755 | 264755 | 0 | 0.65 | 0.5 | 86045.375 | 17209.075 | 34418.15 | 51627.225
NPT00507 | W038 | R004 | Mechanical | BOP Repair | Electrical Failure | 6 | 122500 | 244320 | 366820 | 366820 | 0 | 0.9 | 0.5 | 165069 | 33013.8 | 66027.6 | 99041.4
NPT00508 | W038 | R004 | Logistics | Waiting on Materials | Port Congestion | 2 | 40833 | 42029 | 82862 | 82862 | 0 | 0.6 | 0.5 | 24858.6 | 4971.72 | 9943.44 | 14915.16
NPT00509 | W038 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 4 | 81666 | 55857 | 137523 | 137523 | 0 | 0.9 | 1 | 123770.7 | 24754.14 | 49508.28 | 74262.42
NPT00510 | W038 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 6 | 122500 | 88110 | 210610 | 210610 | 0 | 0.9 | 0.75 | 142161.75 | 28432.35 | 56864.7 | 85297.05
NPT00511 | W038 | R004 | Weather | High Waves | Heavy Rain | 2 | 40833 | 72180 | 113013 | 113013 | 0 | 0.3 | 1 | 33903.9 | 6780.78 | 13561.56 | 20342.34
NPT00512 | W038 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 4 | 81666 | 161966 | 243632 | 243632 | 0 | 0.65 | 0.75 | 118770.6 | 23754.12 | 47508.24 | 71262.36
NPT00513 | W038 | R004 | Weather | High Waves | Storm | 4 | 81666 | 141093 | 222759 | 222759 | 0 | 0.3 | 0.75 | 50120.775 | 10024.155 | 20048.31 | 30072.465
NPT00514 | W038 | R004 | Weather | Lightning | Lightning | 6 | 122500 | 237410 | 359910 | 359910 | 0 | 0.3 | 0.75 | 80979.75 | 16195.95 | 32391.9 | 48587.85
NPT00515 | W038 | R004 | Weather | Heavy Rain | Lightning | 4 | 81666 | 195140 | 276806 | 276806 | 0 | 0.3 | 1 | 83041.8 | 16608.36 | 33216.72 | 49825.08
NPT00516 | W038 | R004 | Drilling | Well Control | Formation Instability | 6 | 122500 | 270926 | 393426 | 393426 | 0 | 0.65 | 0.75 | 191795.175 | 38359.035 | 76718.07 | 115077.105
NPT00517 | W038 | R004 | Drilling | Lost Circulation | Formation Instability | 8 | 163333 | 141844 | 305177 | 305177 | 0 | 0.65 | 0.5 | 99182.525 | 19836.505 | 39673.01 | 59509.515
NPT00518 | W038 | R004 | Logistics | Delayed Helicopter | Port Congestion | 2 | 40833 | 53993 | 94826 | 94826 | 0 | 0.6 | 0.5 | 28447.8 | 5689.56 | 11379.12 | 17068.68
NPT00519 | W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 4 | 76666 | 145357 | 222023 | 222023 | 0 | 0.65 | 0.5 | 72157.475 | 14431.495 | 28862.99 | 43294.485
NPT00520 | W039 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 6 | 115000 | 137040 | 252040 | 252040 | 0 | 0.9 | 0.75 | 170127 | 34025.4 | 68050.8 | 102076.2
NPT00521 | W039 | R002 | Logistics | Waiting on Materials | Port Congestion | 6 | 115000 | 109082 | 224082 | 224082 | 0 | 0.6 | 0.5 | 67224.6 | 13444.92 | 26889.84 | 40334.76
NPT00522 | W039 | R002 | Weather | Heavy Rain | Lightning | 2 | 38333 | 30704 | 69037 | 69037 | 0 | 0.3 | 0.5 | 10355.55 | 2071.11 | 4142.22 | 6213.33
NPT00523 | W039 | R002 | Personnel | Safety Stand Down | Crew Rotation | 2 | 38333 | 52302 | 90635 | 90635 | 0 | 0.6 | 0.5 | 27190.5 | 5438.1 | 10876.2 | 16314.3
NPT00524 | W039 | R002 | Weather | Lightning | Heavy Rain | 12 | 230000 | 493028 | 723028 | 723028 | 0 | 0.3 | 0.75 | 162681.3 | 32536.26 | 65072.52 | 97608.78
NPT00525 | W039 | R002 | Weather | Poor Visibility | Lightning | 4 | 76666 | 63467 | 140133 | 140133 | 0 | 0.3 | 0.5 | 21019.95 | 4203.99 | 8407.98 | 12611.97
NPT00526 | W039 | R002 | Drilling | Bit Failure | Differential Sticking | 4 | 76666 | 47093 | 123759 | 123759 | 0 | 0.8 | 0.5 | 49503.6 | 9900.72 | 19801.44 | 29702.16
NPT00527 | W039 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 2 | 38333 | 90911 | 129244 | 129244 | 0 | 0.6 | 0.5 | 38773.2 | 7754.64 | 15509.28 | 23263.92
NPT00528 | W039 | R002 | Weather | Heavy Rain | Heavy Rain | 12 | 230000 | 239440 | 469440 | 469440 | 0 | 0.3 | 1 | 140832 | 28166.4 | 56332.8 | 84499.2
NPT00529 | W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 6 | 115000 | 124749 | 239749 | 239749 | 0 | 0.65 | 0.75 | 116877.6375 | 23375.5275 | 46751.055 | 70126.5825
NPT00530 | W039 | R002 | Weather | Lightning | Strong Wind | 6 | 115000 | 203939 | 318939 | 318939 | 0 | 0.3 | 0.5 | 47840.85 | 9568.17 | 19136.34 | 28704.51
NPT00531 | W039 | R002 | Logistics | Waiting on Materials | Material Shortage | 4 | 76666 | 44616 | 121282 | 121282 | 0 | 0.6 | 0.75 | 54576.9 | 10915.38 | 21830.76 | 32746.14
NPT00532 | W040 | R002 | Drilling | Well Control | Formation Instability | 2 | 38333 | 80604 | 118937 | 118937 | 0 | 0.65 | 0.5 | 38654.525 | 7730.905 | 15461.81 | 23192.715
NPT00533 | W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 6 | 115000 | 215251 | 330251 | 330251 | 0 | 0.65 | 0.5 | 107331.575 | 21466.315 | 42932.63 | 64398.945
NPT00534 | W040 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 4 | 76666 | 95465 | 172131 | 172131 | 0 | 0.9 | 0.75 | 116188.425 | 23237.685 | 46475.37 | 69713.055
NPT00535 | W040 | R002 | Weather | Heavy Rain | Strong Wind | 8 | 153333 | 310650 | 463983 | 463983 | 0 | 0.3 | 0.5 | 69597.45 | 13919.49 | 27838.98 | 41758.47
NPT00536 | W040 | R002 | Drilling | Lost Circulation | Formation Instability | 4 | 76666 | 129558 | 206224 | 206224 | 0 | 0.65 | 0.5 | 67022.8 | 13404.56 | 26809.12 | 40213.68
NPT00537 | W040 | R002 | Weather | Poor Visibility | Heavy Rain | 12 | 230000 | 561616 | 791616 | 791616 | 0 | 0.3 | 0.5 | 118742.4 | 23748.48 | 47496.96 | 71245.44
NPT00538 | W040 | R002 | Weather | High Waves | Lightning | 4 | 76666 | 95669 | 172335 | 172335 | 0 | 0.3 | 0.5 | 25850.25 | 5170.05 | 10340.1 | 15510.15
NPT00539 | W040 | R002 | Weather | Heavy Rain | High Waves | 6 | 115000 | 220006 | 335006 | 335006 | 0 | 0.3 | 0.75 | 75376.35 | 15075.27 | 30150.54 | 45225.81
NPT00540 | W040 | R002 | Drilling | Well Control | Formation Instability | 4 | 76666 | 41323 | 117989 | 117989 | 0 | 0.65 | 1 | 76692.85 | 15338.57 | 30677.14 | 46015.71
NPT00541 | W040 | R002 | Personnel | Crew Change | Medical Emergency | 4 | 76666 | 150344 | 227010 | 227010 | 0 | 0.6 | 0.75 | 102154.5 | 20430.9 | 40861.8 | 61292.7
NPT00542 | W040 | R002 | Mechanical | Power System Failure | Equipment Wear | 2 | 38333 | 34861 | 73194 | 73194 | 0 | 0.9 | 0.5 | 32937.3 | 6587.46 | 13174.92 | 19762.38
NPT00543 | W040 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 2 | 38333 | 71989 | 110322 | 110322 | 0 | 0.7 | 0.5 | 38612.7 | 7722.54 | 15445.08 | 23167.62
NPT00544 | W040 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 8 | 153333 | 344980 | 498313 | 498313 | 0 | 0.6 | 0.5 | 149493.9 | 29898.78 | 59797.56 | 89696.34
NPT00545 | W040 | R002 | Drilling | Fishing Operation | Formation Instability | 12 | 230000 | 275951 | 505951 | 505951 | 0 | 0.65 | 0.5 | 164434.075 | 32886.815 | 65773.63 | 98660.445
NPT00546 | W040 | R002 | Drilling | Bit Failure | Unexpected Pressure | 4 | 76666 | 122362 | 199028 | 199028 | 0 | 0.65 | 1 | 129368.2 | 25873.64 | 51747.28 | 77620.92
NPT00547 | W040 | R002 | Weather | Poor Visibility | Heavy Rain | 6 | 115000 | 282556 | 397556 | 397556 | 0 | 0.3 | 0.5 | 59633.4 | 11926.68 | 23853.36 | 35780.04
NPT00548 | W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 76666 | 51458 | 128124 | 128124 | 0 | 0.65 | 0.5 | 41640.3 | 8328.06 | 16656.12 | 24984.18
NPT00549 | W040 | R002 | Logistics | Waiting on Cement | Port Congestion | 6 | 115000 | 192955 | 307955 | 307955 | 0 | 0.6 | 1 | 184773 | 36954.6 | 73909.2 | 110863.8
NPT00550 | W040 | R002 | Weather | High Waves | Heavy Rain | 6 | 115000 | 74637 | 189637 | 189637 | 0 | 0.3 | 1 | 56891.1 | 11378.22 | 22756.44 | 34134.66
NPT00551 | W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 18 | 345000 | 503296 | 848296 | 848296 | 0 | 0.9 | 1 | 763466.4 | 152693.28 | 305386.56 | 458079.84
NPT00552 | W040 | R002 | Drilling | Bit Failure | Differential Sticking | 8 | 153333 | 272919 | 426252 | 426252 | 0 | 0.8 | 0.5 | 170500.8 | 34100.16 | 68200.32 | 102300.48
NPT00553 | W041 | R002 | Mechanical | Power System Failure | Electrical Failure | 6 | 115000 | 247320 | 362320 | 362320 | 0 | 0.9 | 1 | 326088 | 65217.6 | 130435.2 | 195652.8
NPT00554 | W041 | R002 | Logistics | Fuel Supply Delay | Customs Clearance | 8 | 153333 | 317647 | 470980 | 470980 | 0 | 0.6 | 0.5 | 141294 | 28258.8 | 56517.6 | 84776.4
NPT00555 | W041 | R002 | Weather | Lightning | Lightning | 8 | 153333 | 183394 | 336727 | 336727 | 0 | 0.3 | 0.5 | 50509.05 | 10101.81 | 20203.62 | 30305.43
NPT00556 | W041 | R002 | Drilling | Fishing Operation | Differential Sticking | 8 | 153333 | 210689 | 364022 | 364022 | 0 | 0.8 | 0.75 | 218413.2 | 43682.64 | 87365.28 | 131047.92
NPT00557 | W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | 8 | 153333 | 214639 | 367972 | 367972 | 0 | 0.65 | 0.5 | 119590.9 | 23918.18 | 47836.36 | 71754.54
NPT00558 | W041 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 4 | 76666 | 58805 | 135471 | 135471 | 0 | 0.9 | 0.5 | 60961.95 | 12192.39 | 24384.78 | 36577.17
NPT00559 | W041 | R002 | Drilling | Well Control | Unexpected Pressure | 4 | 76666 | 102592 | 179258 | 179258 | 0 | 0.65 | 0.5 | 58258.85 | 11651.77 | 23303.54 | 34955.31
NPT00560 | W041 | R002 | Logistics | Delayed Helicopter | Port Congestion | 2 | 38333 | 33873 | 72206 | 72206 | 0 | 0.6 | 0.5 | 21661.8 | 4332.36 | 8664.72 | 12997.08
NPT00561 | W041 | R002 | Drilling | Hole Cleaning | Formation Instability | 2 | 38333 | 28172 | 66505 | 66505 | 0 | 0.65 | 0.5 | 21614.125 | 4322.825 | 8645.65 | 12968.475
NPT00562 | W041 | R002 | Drilling | Hole Cleaning | Formation Instability | 2 | 38333 | 71728 | 110061 | 110061 | 0 | 0.65 | 0.5 | 35769.825 | 7153.965 | 14307.93 | 21461.895
NPT00563 | W041 | R002 | Weather | Heavy Rain | High Waves | 2 | 38333 | 71077 | 109410 | 109410 | 0 | 0.3 | 0.5 | 16411.5 | 3282.3 | 6564.6 | 9846.9
NPT00564 | W041 | R002 | Weather | Lightning | Lightning | 2 | 38333 | 81289 | 119622 | 119622 | 0 | 0.3 | 0.75 | 26914.95 | 5382.99 | 10765.98 | 16148.97
NPT00565 | W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | 18 | 345000 | 390612 | 735612 | 735612 | 0 | 0.8 | 0.75 | 441367.2 | 88273.44 | 176546.88 | 264820.32
NPT00566 | W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | 2 | 38333 | 43647 | 81980 | 81980 | 0 | 0.65 | 0.5 | 26643.5 | 5328.7 | 10657.4 | 15986.1
NPT00567 | W042 | R004 | Weather | Lightning | Lightning | 6 | 122500 | 254150 | 376650 | 376650 | 0 | 0.3 | 0.5 | 56497.5 | 11299.5 | 22599 | 33898.5
NPT00568 | W042 | R004 | Drilling | Fishing Operation | Differential Sticking | 8 | 163333 | 191207 | 354540 | 354540 | 0 | 0.8 | 0.5 | 141816 | 28363.2 | 56726.4 | 85089.6
NPT00569 | W042 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | 2 | 40833 | 49540 | 90373 | 90373 | 0 | 0.6 | 0.5 | 27111.9 | 5422.38 | 10844.76 | 16267.14
NPT00570 | W042 | R004 | Weather | Poor Visibility | Heavy Rain | 18 | 367500 | 390071 | 757571 | 757571 | 0 | 0.3 | 0.75 | 170453.475 | 34090.695 | 68181.39 | 102272.085
NPT00571 | W042 | R004 | Mechanical | Top Drive Failure | Hydraulic Failure | 6 | 122500 | 159958 | 282458 | 282458 | 0 | 0.9 | 1 | 254212.2 | 50842.44 | 101684.88 | 152527.32
NPT00572 | W042 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 6 | 122500 | 203927 | 326427 | 326427 | 0 | 0.9 | 0.5 | 146892.15 | 29378.43 | 58756.86 | 88135.29
NPT00573 | W042 | R004 | Weather | Lightning | Strong Wind | 2 | 40833 | 23324 | 64157 | 64157 | 0 | 0.3 | 0.5 | 9623.55 | 1924.71 | 3849.42 | 5774.13
NPT00574 | W042 | R004 | Drilling | Lost Circulation | Bit Wear | 4 | 81666 | 64325 | 145991 | 145991 | 0 | 0.8 | 0.5 | 58396.4 | 11679.28 | 23358.56 | 35037.84
NPT00575 | W043 | R002 | Logistics | Waiting on Materials | Customs Clearance | 4 | 76666 | 72518 | 149184 | 149184 | 0 | 0.6 | 1 | 89510.4 | 17902.08 | 35804.16 | 53706.24
NPT00576 | W043 | R002 | Drilling | Stuck Pipe | Differential Sticking | 6 | 115000 | 248026 | 363026 | 363026 | 0 | 0.8 | 0.5 | 145210.4 | 29042.08 | 58084.16 | 87126.24
NPT00577 | W043 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 8 | 153333 | 86363 | 239696 | 239696 | 0 | 0.65 | 1 | 155802.4 | 31160.48 | 62320.96 | 93481.44
NPT00578 | W043 | R002 | Weather | Lightning | Heavy Rain | 4 | 76666 | 61263 | 137929 | 137929 | 0 | 0.3 | 0.5 | 20689.35 | 4137.87 | 8275.74 | 12413.61
NPT00579 | W043 | R002 | Mechanical | Power System Failure | Electrical Failure | 2 | 38333 | 84686 | 123019 | 123019 | 0 | 0.9 | 0.5 | 55358.55 | 11071.71 | 22143.42 | 33215.13
NPT00580 | W043 | R002 | Drilling | Fishing Operation | Bit Wear | 2 | 38333 | 49722 | 88055 | 88055 | 0 | 0.8 | 0.75 | 52833 | 10566.6 | 21133.2 | 31699.8
NPT00581 | W043 | R002 | Personnel | Crew Change | Medical Emergency | 2 | 38333 | 62593 | 100926 | 100926 | 0 | 0.6 | 0.5 | 30277.8 | 6055.56 | 12111.12 | 18166.68
NPT00582 | W043 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 38333 | 29667 | 68000 | 68000 | 0 | 0.65 | 0.5 | 22100 | 4420 | 8840 | 13260
NPT00583 | W043 | R002 | Drilling | Well Control | Unexpected Pressure | 2 | 38333 | 35940 | 74273 | 74273 | 0 | 0.65 | 0.75 | 36208.0875 | 7241.6175 | 14483.235 | 21724.8525
NPT00584 | W043 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 2 | 38333 | 37321 | 75654 | 75654 | 0 | 0.9 | 0.5 | 34044.3 | 6808.86 | 13617.72 | 20426.58
NPT00585 | W043 | R002 | Weather | Poor Visibility | Lightning | 6 | 115000 | 236890 | 351890 | 351890 | 0 | 0.3 | 1 | 105567 | 21113.4 | 42226.8 | 63340.2
NPT00586 | W043 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 6 | 115000 | 178383 | 293383 | 293383 | 0 | 0.9 | 1 | 264044.7 | 52808.94 | 105617.88 | 158426.82
NPT00587 | W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | 6 | 115000 | 199093 | 314093 | 314093 | 0 | 0.6 | 0.5 | 94227.9 | 18845.58 | 37691.16 | 56536.74
NPT00588 | W043 | R002 | Drilling | Well Control | Unexpected Pressure | 4 | 76666 | 39001 | 115667 | 115667 | 0 | 0.65 | 0.5 | 37591.775 | 7518.355 | 15036.71 | 22555.065
NPT00589 | W043 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 18 | 345000 | 418285 | 763285 | 763285 | 0 | 0.7 | 0.5 | 267149.75 | 53429.95 | 106859.9 | 160289.85
NPT00590 | W043 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 2 | 38333 | 57717 | 96050 | 96050 | 0 | 0.9 | 0.5 | 43222.5 | 8644.5 | 17289 | 25933.5
NPT00591 | W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | 12 | 230000 | 403320 | 633320 | 633320 | 0 | 0.6 | 0.5 | 189996 | 37999.2 | 75998.4 | 113997.6
NPT00592 | W043 | R002 | Drilling | Stuck Pipe | Formation Instability | 6 | 115000 | 247949 | 362949 | 362949 | 0 | 0.65 | 0.5 | 117958.425 | 23591.685 | 47183.37 | 70775.055
NPT00593 | W044 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 2 | 40000 | 25031 | 65031 | 65031 | 0 | 0.6 | 0.5 | 19509.3 | 3901.86 | 7803.72 | 11705.58
NPT00594 | W044 | R003 | Weather | Poor Visibility | Heavy Rain | 18 | 360000 | 773348 | 1133348 | 1133348 | 0 | 0.3 | 0.75 | 255003.3 | 51000.66 | 102001.32 | 153001.98
NPT00595 | W044 | R003 | Drilling | Hole Cleaning | Formation Instability | 6 | 120000 | 106088 | 226088 | 226088 | 0 | 0.65 | 0.5 | 73478.6 | 14695.72 | 29391.44 | 44087.16
NPT00596 | W044 | R003 | Logistics | Delayed Helicopter | Late Supply Vessel | 2 | 40000 | 88171 | 128171 | 128171 | 0 | 0.6 | 0.5 | 38451.3 | 7690.26 | 15380.52 | 23070.78
NPT00597 | W044 | R003 | Drilling | Bit Failure | Formation Instability | 2 | 40000 | 85034 | 125034 | 125034 | 0 | 0.65 | 0.75 | 60954.075 | 12190.815 | 24381.63 | 36572.445
NPT00598 | W044 | R003 | Drilling | Well Control | Bit Wear | 4 | 80000 | 130288 | 210288 | 210288 | 0 | 0.8 | 0.5 | 84115.2 | 16823.04 | 33646.08 | 50469.12
NPT00599 | W044 | R003 | Logistics | Delayed Helicopter | Port Congestion | 2 | 40000 | 51341 | 91341 | 91341 | 0 | 0.6 | 0.5 | 27402.3 | 5480.46 | 10960.92 | 16441.38
NPT00600 | W044 | R003 | Weather | Strong Wind | Storm | 2 | 40000 | 61338 | 101338 | 101338 | 0 | 0.3 | 0.5 | 15200.7 | 3040.14 | 6080.28 | 9120.42
NPT00601 | W044 | R003 | Weather | High Waves | Lightning | 8 | 160000 | 339780 | 499780 | 499780 | 0 | 0.3 | 0.5 | 74967 | 14993.4 | 29986.8 | 44980.2
NPT00602 | W044 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 8 | 160000 | 185853 | 345853 | 345853 | 0 | 0.65 | 0.5 | 112402.225 | 22480.445 | 44960.89 | 67441.335
NPT00603 | W044 | R003 | Weather | Poor Visibility | Strong Wind | 6 | 120000 | 228519 | 348519 | 348519 | 0 | 0.3 | 0.5 | 52277.85 | 10455.57 | 20911.14 | 31366.71
NPT00604 | W044 | R003 | Logistics | Fuel Supply Delay | Material Shortage | 4 | 80000 | 63153 | 143153 | 143153 | 0 | 0.6 | 0.75 | 64418.85 | 12883.77 | 25767.54 | 38651.31
NPT00605 | W045 | R004 | Weather | Poor Visibility | Strong Wind | 18 | 367500 | 851850 | 1219350 | 1219350 | 0 | 0.3 | 0.5 | 182902.5 | 36580.5 | 73161 | 109741.5
NPT00606 | W045 | R004 | Mechanical | Generator Failure | Poor Preventive Maintenance | 2 | 40833 | 55477 | 96310 | 96310 | 0 | 0.9 | 1 | 86679 | 17335.8 | 34671.6 | 52007.4
NPT00607 | W045 | R004 | Drilling | Lost Circulation | Formation Instability | 8 | 163333 | 376966 | 540299 | 540299 | 0 | 0.65 | 0.5 | 175597.175 | 35119.435 | 70238.87 | 105358.305
NPT00608 | W045 | R004 | Logistics | Fuel Supply Delay | Late Supply Vessel | 2 | 40833 | 67011 | 107844 | 107844 | 0 | 0.6 | 0.5 | 32353.2 | 6470.64 | 12941.28 | 19411.92
NPT00609 | W045 | R004 | Weather | Heavy Rain | Heavy Rain | 12 | 245000 | 133994 | 378994 | 378994 | 0 | 0.3 | 0.5 | 56849.1 | 11369.82 | 22739.64 | 34109.46
NPT00610 | W045 | R004 | Mechanical | BOP Repair | Poor Preventive Maintenance | 4 | 81666 | 186247 | 267913 | 267913 | 0 | 0.9 | 0.5 | 120560.85 | 24112.17 | 48224.34 | 72336.51
NPT00611 | W045 | R004 | Logistics | Waiting on Materials | Material Shortage | 6 | 122500 | 64878 | 187378 | 187378 | 0 | 0.6 | 0.5 | 56213.4 | 11242.68 | 22485.36 | 33728.04
NPT00612 | W045 | R004 | Weather | Lightning | Lightning | 2 | 40833 | 40713 | 81546 | 81546 | 0 | 0.3 | 0.5 | 12231.9 | 2446.38 | 4892.76 | 7339.14
NPT00613 | W045 | R004 | Weather | Heavy Rain | Heavy Rain | 2 | 40833 | 98596 | 139429 | 139429 | 0 | 0.3 | 0.5 | 20914.35 | 4182.87 | 8365.74 | 12548.61
NPT00614 | W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 24 | 490000 | 1044504 | 1534504 | 1534504 | 0 | 0.6 | 0.5 | 460351.2 | 92070.24 | 184140.48 | 276210.72
NPT00615 | W046 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 8 | 160000 | 137440 | 297440 | 297440 | 0 | 0.65 | 1 | 193336 | 38667.2 | 77334.4 | 116001.6
NPT00616 | W046 | R003 | Logistics | Waiting on Materials | Port Congestion | 12 | 240000 | 374455 | 614455 | 614455 | 0 | 0.6 | 0.5 | 184336.5 | 36867.3 | 73734.6 | 110601.9
NPT00617 | W046 | R003 | Weather | Poor Visibility | Strong Wind | 4 | 80000 | 174948 | 254948 | 254948 | 0 | 0.3 | 0.5 | 38242.2 | 7648.44 | 15296.88 | 22945.32
NPT00618 | W046 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 6 | 120000 | 270341 | 390341 | 390341 | 0 | 0.6 | 0.5 | 117102.3 | 23420.46 | 46840.92 | 70261.38
NPT00619 | W046 | R003 | Drilling | Fishing Operation | Bit Wear | 8 | 160000 | 306975 | 466975 | 466975 | 0 | 0.8 | 0.5 | 186790 | 37358 | 74716 | 112074
NPT00620 | W046 | R003 | Mechanical | Mud Pump Failure | Hydraulic Failure | 8 | 160000 | 96020 | 256020 | 256020 | 0 | 0.9 | 0.75 | 172813.5 | 34562.7 | 69125.4 | 103688.1
NPT00621 | W046 | R003 | Weather | Heavy Rain | Heavy Rain | 12 | 240000 | 397476 | 637476 | 637476 | 0 | 0.3 | 0.5 | 95621.4 | 19124.28 | 38248.56 | 57372.84
NPT00622 | W046 | R003 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 4 | 80000 | 89940 | 169940 | 169940 | 0 | 0.9 | 1 | 152946 | 30589.2 | 61178.4 | 91767.6
NPT00623 | W046 | R003 | Mechanical | Top Drive Failure | OEM Defect | 6 | 120000 | 86494 | 206494 | 206494 | 0 | 0.7 | 0.5 | 72272.9 | 14454.58 | 28909.16 | 43363.74
NPT00624 | W046 | R003 | Drilling | Bit Failure | Differential Sticking | 2 | 40000 | 98735 | 138735 | 138735 | 0 | 0.8 | 0.5 | 55494 | 11098.8 | 22197.6 | 33296.4
NPT00625 | W046 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 4 | 80000 | 199919 | 279919 | 279919 | 0 | 0.6 | 0.5 | 83975.7 | 16795.14 | 33590.28 | 50385.42
NPT00626 | W046 | R003 | Weather | Strong Wind | Strong Wind | 6 | 120000 | 250242 | 370242 | 370242 | 0 | 0.3 | 0.75 | 83304.45 | 16660.89 | 33321.78 | 49982.67
NPT00627 | W046 | R003 | Drilling | Hole Cleaning | Bit Wear | 4 | 80000 | 117922 | 197922 | 197922 | 0 | 0.8 | 0.5 | 79168.8 | 15833.76 | 31667.52 | 47501.28
NPT00628 | W046 | R003 | Mechanical | Draw Works Failure | Hydraulic Failure | 8 | 160000 | 218432 | 378432 | 378432 | 0 | 0.9 | 1 | 340588.8 | 68117.76 | 136235.52 | 204353.28
NPT00629 | W046 | R003 | Weather | Poor Visibility | Heavy Rain | 6 | 120000 | 81245 | 201245 | 201245 | 0 | 0.3 | 0.5 | 30186.75 | 6037.35 | 12074.7 | 18112.05
NPT00630 | W046 | R003 | Drilling | Stuck Pipe | Formation Instability | 4 | 80000 | 91574 | 171574 | 171574 | 0 | 0.65 | 0.5 | 55761.55 | 11152.31 | 22304.62 | 33456.93
NPT00631 | W047 | R004 | Drilling | Fishing Operation | Unexpected Pressure | 4 | 81666 | 77971 | 159637 | 159637 | 0 | 0.65 | 0.75 | 77823.0375 | 15564.6075 | 31129.215 | 46693.8225
NPT00632 | W047 | R004 | Drilling | Bit Failure | Bit Wear | 2 | 40833 | 84650 | 125483 | 125483 | 0 | 0.8 | 0.75 | 75289.8 | 15057.96 | 30115.92 | 45173.88
NPT00633 | W047 | R004 | Weather | Strong Wind | Storm | 2 | 40833 | 73113 | 113946 | 113946 | 0 | 0.3 | 0.5 | 17091.9 | 3418.38 | 6836.76 | 10255.14
NPT00634 | W047 | R004 | Drilling | Hole Cleaning | Differential Sticking | 8 | 163333 | 205525 | 368858 | 368858 | 0 | 0.8 | 0.5 | 147543.2 | 29508.64 | 59017.28 | 88525.92
NPT00635 | W047 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 8 | 163333 | 392949 | 556282 | 556282 | 0 | 0.9 | 0.75 | 375490.35 | 75098.07 | 150196.14 | 225294.21
NPT00636 | W047 | R004 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 4 | 81666 | 77527 | 159193 | 159193 | 0 | 0.9 | 0.5 | 71636.85 | 14327.37 | 28654.74 | 42982.11
NPT00637 | W047 | R004 | Mechanical | BOP Repair | OEM Defect | 8 | 163333 | 334485 | 497818 | 497818 | 0 | 0.7 | 0.5 | 174236.3 | 34847.26 | 69694.52 | 104541.78
NPT00638 | W047 | R004 | Personnel | Crew Change | Crew Rotation | 18 | 367500 | 236304 | 603804 | 603804 | 0 | 0.6 | 0.5 | 181141.2 | 36228.24 | 72456.48 | 108684.72
NPT00639 | W047 | R004 | Weather | Heavy Rain | Lightning | 4 | 81666 | 190813 | 272479 | 272479 | 0 | 0.3 | 0.5 | 40871.85 | 8174.37 | 16348.74 | 24523.11
NPT00640 | W047 | R004 | Drilling | Lost Circulation | Formation Instability | 8 | 163333 | 248690 | 412023 | 412023 | 0 | 0.65 | 0.5 | 133907.475 | 26781.495 | 53562.99 | 80344.485
NPT00641 | W047 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 4 | 81666 | 146922 | 228588 | 228588 | 0 | 0.9 | 0.5 | 102864.6 | 20572.92 | 41145.84 | 61718.76
NPT00642 | W047 | R004 | Drilling | Well Control | Bit Wear | 6 | 122500 | 196965 | 319465 | 319465 | 0 | 0.8 | 0.5 | 127786 | 25557.2 | 51114.4 | 76671.6
NPT00643 | W047 | R004 | Drilling | Lost Circulation | Unexpected Pressure | 2 | 40833 | 59674 | 100507 | 100507 | 0 | 0.65 | 0.75 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975
NPT00644 | W048 | R002 | Personnel | Safety Stand Down | Crew Rotation | 2 | 38333 | 43207 | 81540 | 81540 | 0 | 0.6 | 0.5 | 24462 | 4892.4 | 9784.8 | 14677.2
NPT00645 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 2 | 38333 | 46414 | 84747 | 84747 | 0 | 0.9 | 0.5 | 38136.15 | 7627.23 | 15254.46 | 22881.69
NPT00646 | W048 | R002 | Drilling | Well Control | Unexpected Pressure | 4 | 76666 | 109609 | 186275 | 186275 | 0 | 0.65 | 0.5 | 60539.375 | 12107.875 | 24215.75 | 36323.625
NPT00647 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 8 | 153333 | 295021 | 448354 | 448354 | 0 | 0.9 | 0.5 | 201759.3 | 40351.86 | 80703.72 | 121055.58
NPT00648 | W048 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 4 | 76666 | 129373 | 206039 | 206039 | 0 | 0.9 | 0.75 | 139076.325 | 27815.265 | 55630.53 | 83445.795
NPT00649 | W048 | R002 | Mechanical | Rotary Table Failure | Hydraulic Failure | 18 | 345000 | 423942 | 768942 | 768942 | 0 | 0.9 | 0.5 | 346023.9 | 69204.78 | 138409.56 | 207614.34
NPT00650 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 8 | 153333 | 294473 | 447806 | 447806 | 0 | 0.9 | 0.75 | 302269.05 | 60453.81 | 120907.62 | 181361.43
NPT00651 | W048 | R002 | Weather | High Waves | High Waves | 6 | 115000 | 70319 | 185319 | 185319 | 0 | 0.3 | 0.5 | 27797.85 | 5559.57 | 11119.14 | 16678.71
NPT00652 | W048 | R002 | Drilling | Hole Cleaning | Bit Wear | 8 | 153333 | 289177 | 442510 | 442510 | 0 | 0.8 | 0.5 | 177004 | 35400.8 | 70801.6 | 106202.4
NPT00653 | W048 | R002 | Weather | Poor Visibility | Lightning | 4 | 76666 | 130194 | 206860 | 206860 | 0 | 0.3 | 0.75 | 46543.5 | 9308.7 | 18617.4 | 27926.1
NPT00654 | W048 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 6 | 115000 | 272813 | 387813 | 387813 | 0 | 0.9 | 0.5 | 174515.85 | 34903.17 | 69806.34 | 104709.51
NPT00655 | W048 | R002 | Drilling | Lost Circulation | Bit Wear | 6 | 115000 | 241901 | 356901 | 356901 | 0 | 0.8 | 0.5 | 142760.4 | 28552.08 | 57104.16 | 85656.24
NPT00656 | W048 | R002 | Mechanical | BOP Repair | Equipment Wear | 4 | 76666 | 85043 | 161709 | 161709 | 0 | 0.9 | 0.5 | 72769.05 | 14553.81 | 29107.62 | 43661.43
NPT00657 | W048 | R002 | Drilling | Stuck Pipe | Differential Sticking | 6 | 115000 | 129108 | 244108 | 244108 | 0 | 0.8 | 0.5 | 97643.2 | 19528.64 | 39057.28 | 58585.92
NPT00658 | W049 | R003 | Logistics | Waiting on Boat | Customs Clearance | 4 | 80000 | 121829 | 201829 | 201829 | 0 | 0.6 | 0.75 | 90823.05 | 18164.61 | 36329.22 | 54493.83
NPT00659 | W049 | R003 | Drilling | Hole Cleaning | Differential Sticking | 18 | 360000 | 314096 | 674096 | 674096 | 0 | 0.8 | 0.5 | 269638.4 | 53927.68 | 107855.36 | 161783.04
NPT00660 | W049 | R003 | Logistics | Waiting on Boat | Port Congestion | 4 | 80000 | 183601 | 263601 | 263601 | 0 | 0.6 | 0.5 | 79080.3 | 15816.06 | 31632.12 | 47448.18
NPT00661 | W049 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 8 | 160000 | 279871 | 439871 | 439871 | 0 | 0.65 | 1 | 285916.15 | 57183.23 | 114366.46 | 171549.69
NPT00662 | W049 | R003 | Mechanical | Top Drive Failure | OEM Defect | 6 | 120000 | 270679 | 390679 | 390679 | 0 | 0.7 | 0.5 | 136737.65 | 27347.53 | 54695.06 | 82042.59
NPT00663 | W049 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 6 | 120000 | 60226 | 180226 | 180226 | 0 | 0.6 | 0.75 | 81101.7 | 16220.34 | 32440.68 | 48661.02
NPT00664 | W049 | R003 | Drilling | Well Control | Bit Wear | 2 | 40000 | 85472 | 125472 | 125472 | 0 | 0.8 | 0.5 | 50188.8 | 10037.76 | 20075.52 | 30113.28
NPT00665 | W049 | R003 | Weather | Heavy Rain | Strong Wind | 6 | 120000 | 143523 | 263523 | 263523 | 0 | 0.3 | 1 | 79056.9 | 15811.38 | 31622.76 | 47434.14
NPT00666 | W049 | R003 | Drilling | Fishing Operation | Bit Wear | 6 | 120000 | 294858 | 414858 | 414858 | 0 | 0.8 | 0.5 | 165943.2 | 33188.64 | 66377.28 | 99565.92
NPT00667 | W050 | R004 | Drilling | Lost Circulation | Bit Wear | 8 | 163333 | 405188 | 568521 | 568521 | 0 | 0.8 | 1 | 454816.8 | 90963.36 | 181926.72 | 272890.08
NPT00668 | W050 | R004 | Logistics | Waiting on Cement | Material Shortage | 6 | 122500 | 174028 | 296528 | 296528 | 0 | 0.6 | 0.5 | 88958.4 | 17791.68 | 35583.36 | 53375.04
NPT00669 | W050 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 2 | 40833 | 91284 | 132117 | 132117 | 0 | 0.9 | 0.5 | 59452.65 | 11890.53 | 23781.06 | 35671.59
NPT00670 | W050 | R004 | Logistics | Waiting on Cement | Port Congestion | 12 | 245000 | 512335 | 757335 | 757335 | 0 | 0.6 | 1 | 454401 | 90880.2 | 181760.4 | 272640.6
NPT00671 | W050 | R004 | Weather | High Waves | Storm | 4 | 81666 | 110150 | 191816 | 191816 | 0 | 0.3 | 0.5 | 28772.4 | 5754.48 | 11508.96 | 17263.44
NPT00672 | W050 | R004 | Mechanical | Power System Failure | Equipment Wear | 6 | 122500 | 116840 | 239340 | 239340 | 0 | 0.9 | 0.5 | 107703 | 21540.6 | 43081.2 | 64621.8
NPT00673 | W050 | R004 | Drilling | Stuck Pipe | Differential Sticking | 12 | 245000 | 368627 | 613627 | 613627 | 0 | 0.8 | 0.5 | 245450.8 | 49090.16 | 98180.32 | 147270.48
NPT00674 | W050 | R004 | Weather | High Waves | High Waves | 6 | 122500 | 126592 | 249092 | 249092 | 0 | 0.3 | 0.5 | 37363.8 | 7472.76 | 14945.52 | 22418.28
NPT00675 | W050 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 4 | 81666 | 122727 | 204393 | 204393 | 0 | 0.65 | 0.5 | 66427.725 | 13285.545 | 26571.09 | 39856.635
NPT00676 | W050 | R004 | Drilling | Stuck Pipe | Formation Instability | 8 | 163333 | 182981 | 346314 | 346314 | 0 | 0.65 | 0.5 | 112552.05 | 22510.41 | 45020.82 | 67531.23
NPT00677 | W050 | R004 | Personnel | Medical Evacuation | Training Requirement | 6 | 122500 | 172937 | 295437 | 295437 | 0 | 0.6 | 0.5 | 88631.1 | 17726.22 | 35452.44 | 53178.66