## Executive_Summary
Metric | Value
Total NPT Events | 677
Total NPT Hours | 4008
Direct NPT Cost USD | 79204408
Deferred Cost USD | 118945770
Total Impact USD | 198150178
Addressable Impact USD | 77064618.5875
Addressable Impact % of Total | 38.892
Conservative Savings USD | 15412923.7175
Target Savings USD | 30825847.435
Stretch Savings USD | 46238771.1525
Conservative Savings % of Total Impact | 7.7784
Target Savings % of Total Impact | 15.5568
Stretch Savings % of Total Impact | 23.3352
Unique Wells | 50
Unique Rigs | 4
Unique Root Causes | 21
High / Critical Root Cause Opportunities | 68

## Root_Cause_Scenarios
Priority_Rank | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Controllability | NPT_Events | NPT_Hours | Direct_NPT_Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | Target_Savings_Pct_of_Impact
1 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 4 | 44 | 876666 | 1780955 | 2657621 | 1969788.15 | 393957.63 | 787915.26 | 1181872.89 | 29.6474
2 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | HIGH | 5 | 48 | 923332 | 1450100 | 2373432 | 1485052.65 | 297010.53 | 594021.06 | 891031.59 | 25.0279
3 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | HIGH | 3 | 38 | 765833 | 1234524 | 2000357 | 1292487.6 | 258497.52 | 516995.04 | 775492.56 | 25.8451
4 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | HIGH | 4 | 34 | 660833 | 1223235 | 1884068 | 1170621.675 | 234124.335 | 468248.67 | 702373.005 | 24.8531
5 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | HIGH | 7 | 38 | 753332 | 1249861 | 2003193 | 1112858.55 | 222571.71 | 445143.42 | 667715.13 | 22.2217
6 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | HIGH | 3 | 30 | 601249 | 1353499 | 1954748 | 1099258.2 | 219851.64 | 439703.28 | 659554.92 | 22.4941
7 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | HIGH | 3 | 34 | 682916 | 1409351 | 2092267 | 1042276.5 | 208455.3 | 416910.6 | 625365.9 | 19.9263
8 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | HIGH | 5 | 50 | 984166 | 1229748 | 2213914 | 1032688 | 206537.6 | 413075.2 | 619612.8 | 18.6581
9 | Drilling | Fishing Operation | Formation Instability | Operator | MEDIUM | 7 | 42 | 829581 | 1528764 | 2358345 | 974856.675 | 194971.335 | 389942.67 | 584914.005 | 16.5346
10 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | HIGH | 3 | 32 | 618333 | 999052 | 1617385 | 901808.8 | 180361.76 | 360723.52 | 541085.28 | 22.3029
11 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | HIGH | 2 | 26 | 498333 | 625181 | 1123514 | 887314.5 | 177462.9 | 354925.8 | 532388.7 | 31.5907
12 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | HIGH | 5 | 42 | 820000 | 1392195 | 2212195 | 884878 | 176975.6 | 353951.2 | 530926.8 | 16
13 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | MEDIUM | 6 | 50 | 1009582 | 1789153 | 2798735 | 839620.5 | 167924.1 | 335848.2 | 503772.3 | 12
14 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | HIGH | 5 | 30 | 586665 | 930846 | 1517511 | 802511.6 | 160502.32 | 321004.64 | 481506.96 | 21.1534
15 | Drilling | Bit Failure | Bit Wear | Mud Engineering | HIGH | 3 | 38 | 753333 | 1251096 | 2004429 | 801771.6 | 160354.32 | 320708.64 | 481062.96 | 16
16 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | HIGH | 3 | 28 | 551666 | 1009356 | 1561022 | 767458.35 | 153491.67 | 306983.34 | 460475.01 | 19.6655
17 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | MEDIUM | 5 | 48 | 954998 | 1220391 | 2175389 | 766791.025 | 153358.205 | 306716.41 | 460074.615 | 14.0994
18 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 3 | 28 | 543333 | 444184 | 987517 | 758255.85 | 151651.17 | 303302.34 | 454953.51 | 30.7136
19 | Drilling | Hole Cleaning | Bit Wear | Operator | HIGH | 6 | 36 | 714166 | 768741 | 1482907 | 748773.6 | 149754.72 | 299509.44 | 449264.16 | 20.1975
20 | Drilling | Lost Circulation | Bit Wear | Operator | HIGH | 4 | 20 | 399999 | 695367 | 1095366 | 665554.8 | 133110.96 | 266221.92 | 399332.88 | 24.3044
21 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | HIGH | 4 | 26 | 508332 | 667160 | 1175492 | 654134.85 | 130826.97 | 261653.94 | 392480.91 | 22.2591
22 | Drilling | Well Control | Bit Wear | Mud Engineering | HIGH | 3 | 26 | 521666 | 1012986 | 1534652 | 641240.2 | 128248.04 | 256496.08 | 384744.12 | 16.7136
23 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | MEDIUM | 2 | 18 | 360000 | 705290 | 1065290 | 639174 | 127834.8 | 255669.6 | 383504.4 | 24
24 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | HIGH | 5 | 20 | 397498 | 832915 | 1230413 | 634323.15 | 126864.63 | 253729.26 | 380593.89 | 20.6215
25 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | HIGH | 3 | 22 | 441666 | 645962 | 1087628 | 631715.85 | 126343.17 | 252686.34 | 379029.51 | 23.2328
26 | Drilling | Well Control | Bit Wear | Directional Drilling | HIGH | 3 | 26 | 518333 | 1045460 | 1563793 | 625517.2 | 125103.44 | 250206.88 | 375310.32 | 16
27 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | HIGH | 3 | 28 | 541666 | 837609 | 1379275 | 620673.75 | 124134.75 | 248269.5 | 372404.25 | 18
28 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | MEDIUM | 4 | 30 | 579999 | 830678 | 1410677 | 619549.125 | 123909.825 | 247819.65 | 371729.475 | 17.5674
29 | Drilling | Fishing Operation | Unexpected Pressure | Operator | MEDIUM | 5 | 24 | 473332 | 592187 | 1065519 | 618899.775 | 123779.955 | 247559.91 | 371339.865 | 23.2337
30 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 2 | 16 | 321666 | 547435 | 869101 | 596587.05 | 119317.41 | 238634.82 | 357952.23 | 27.4577
31 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | MEDIUM | 2 | 26 | 498333 | 854721 | 1353054 | 589487.7 | 117897.54 | 235795.08 | 353692.62 | 17.4269
32 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | HIGH | 3 | 36 | 695000 | 730621 | 1425621 | 570248.4 | 114049.68 | 228099.36 | 342149.04 | 16
33 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | MEDIUM | 6 | 30 | 586665 | 798737 | 1385402 | 564893.875 | 112978.775 | 225957.55 | 338936.325 | 16.3099
34 | Logistics | Waiting on Materials | Material Shortage | Procurement | MEDIUM | 5 | 32 | 620832 | 989870 | 1610702 | 554535.75 | 110907.15 | 221814.3 | 332721.45 | 13.7713
35 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | MEDIUM | 5 | 32 | 639582 | 929609 | 1569191 | 552435.65 | 110487.13 | 220974.26 | 331461.39 | 14.082
36 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | MEDIUM | 6 | 30 | 594998 | 924767 | 1519765 | 532882.8375 | 106576.5675 | 213153.135 | 319729.7025 | 14.0254
37 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | MEDIUM | 1 | 24 | 490000 | 397460 | 887460 | 532476 | 106495.2 | 212990.4 | 319485.6 | 24
38 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | HIGH | 4 | 22 | 439166 | 630032 | 1069198 | 531426.6 | 106285.32 | 212570.64 | 318855.96 | 19.8813
39 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | MEDIUM | 4 | 24 | 465833 | 710577 | 1176410 | 515175.8625 | 103035.1725 | 206070.345 | 309105.5175 | 17.5169
40 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | HIGH | 3 | 26 | 505833 | 624770 | 1130603 | 508771.35 | 101754.27 | 203508.54 | 305262.81 | 18
41 | Weather | Poor Visibility | Heavy Rain | Weather | LOW | 5 | 46 | 906666 | 1675572 | 2582238 | 506538.975 | 101307.795 | 202615.59 | 303923.385 | 7.8465
42 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | HIGH | 3 | 14 | 275832 | 362592 | 638424 | 503349.525 | 100669.905 | 201339.81 | 302009.715 | 31.537
43 | Drilling | Stuck Pipe | Bit Wear | Operator | HIGH | 2 | 16 | 325000 | 676961 | 1001961 | 500209.2 | 100041.84 | 200083.68 | 300125.52 | 19.9692
44 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | HIGH | 1 | 18 | 356250 | 753050 | 1109300 | 499185 | 99837 | 199674 | 299511 | 18
45 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | MEDIUM | 6 | 34 | 672499 | 982945 | 1655444 | 496633.2 | 99326.64 | 198653.28 | 297979.92 | 12
46 | Drilling | Lost Circulation | Formation Instability | Operator | MEDIUM | 3 | 22 | 440000 | 882159 | 1322159 | 486760.4625 | 97352.0925 | 194704.185 | 292056.2775 | 14.7262
47 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | HIGH | 5 | 26 | 510832 | 677064 | 1187896 | 475158.4 | 95031.68 | 190063.36 | 285095.04 | 16
48 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | HIGH | 2 | 14 | 273333 | 397753 | 671086 | 466397.1 | 93279.42 | 186558.84 | 279838.26 | 27.7995
49 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | HIGH | 2 | 12 | 230000 | 432865 | 662865 | 461333.25 | 92266.65 | 184533.3 | 276799.95 | 27.8387
50 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | HIGH | 1 | 18 | 360000 | 663187 | 1023187 | 460434.15 | 92086.83 | 184173.66 | 276260.49 | 18
51 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | MEDIUM | 2 | 24 | 480000 | 995042 | 1475042 | 442512.6 | 88502.52 | 177005.04 | 265507.56 | 12
52 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | HIGH | 2 | 14 | 268333 | 377403 | 645736 | 435871.8 | 87174.36 | 174348.72 | 261523.08 | 27
53 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | HIGH | 5 | 18 | 363332 | 504214 | 867546 | 429179.85 | 85835.97 | 171671.94 | 257507.91 | 19.7882
54 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | HIGH | 3 | 12 | 236666 | 520254 | 756920 | 427674 | 85534.8 | 171069.6 | 256604.4 | 22.6008
55 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | HIGH | 3 | 18 | 354999 | 571010 | 926009 | 416704.05 | 83340.81 | 166681.62 | 250022.43 | 18
56 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | MEDIUM | 3 | 22 | 435000 | 500897 | 935897 | 409760.325 | 81952.065 | 163904.13 | 245856.195 | 17.5131
57 | Drilling | Stuck Pipe | Differential Sticking | Operator | HIGH | 4 | 26 | 513332 | 495054 | 1008386 | 403354.4 | 80670.88 | 161341.76 | 242012.64 | 16
58 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | MEDIUM | 4 | 26 | 503332 | 377984 | 881316 | 401832.4375 | 80366.4875 | 160732.975 | 241099.4625 | 18.2378
59 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | MEDIUM | 7 | 22 | 434998 | 711366 | 1146364 | 398141.9 | 79628.38 | 159256.76 | 238885.14 | 13.8923
60 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | HIGH | 2 | 20 | 385833 | 495197 | 881030 | 396463.5 | 79292.7 | 158585.4 | 237878.1 | 18
61 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | HIGH | 3 | 16 | 316666 | 380857 | 697523 | 386416.125 | 77283.225 | 154566.45 | 231849.675 | 22.1593
62 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | MEDIUM | 4 | 24 | 463332 | 470318 | 933650 | 380741.4 | 76148.28 | 152296.56 | 228444.84 | 16.312
63 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | HIGH | 2 | 12 | 233750 | 493668 | 727418 | 372951.6 | 74590.32 | 149180.64 | 223770.96 | 20.5082
64 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | HIGH | 2 | 10 | 195416 | 263218 | 458634 | 365895.45 | 73179.09 | 146358.18 | 219537.27 | 31.9118
65 | Drilling | Well Control | Formation Instability | Operator | MEDIUM | 3 | 16 | 314166 | 495832 | 809998 | 364118.3 | 72823.66 | 145647.32 | 218470.98 | 17.9812
66 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | MEDIUM | 3 | 20 | 383332 | 534598 | 917930 | 363011.35 | 72602.27 | 145204.54 | 217806.81 | 15.8187
67 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 2 | 22 | 437916 | 362099 | 800015 | 360006.75 | 72001.35 | 144002.7 | 216004.05 | 18
68 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | MEDIUM | 3 | 18 | 352499 | 693425 | 1045924 | 356460.9 | 71292.18 | 142584.36 | 213876.54 | 13.6324
69 | Drilling | Stuck Pipe | Formation Instability | Operator | MEDIUM | 5 | 22 | 432915 | 662663 | 1095578 | 356062.85 | 71212.57 | 142425.14 | 213637.71 | 13
70 | Drilling | Bit Failure | Unexpected Pressure | Operator | MEDIUM | 3 | 22 | 444166 | 649187 | 1093353 | 355339.725 | 71067.945 | 142135.89 | 213203.835 | 13
71 | Weather | High Waves | Strong Wind | Marine Operations | LOW | 2 | 30 | 605000 | 781140 | 1386140 | 353903.775 | 70780.755 | 141561.51 | 212342.265 | 10.2126
72 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | HIGH | 2 | 14 | 280000 | 601833 | 881833 | 352733.2 | 70546.64 | 141093.28 | 211639.92 | 16
73 | Weather | Lightning | Heavy Rain | Marine Operations | LOW | 4 | 40 | 774166 | 1046611 | 1820777 | 351963.75 | 70392.75 | 140785.5 | 211178.25 | 7.7322
74 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | MEDIUM | 3 | 22 | 421666 | 581674 | 1003340 | 351169 | 70233.8 | 140467.6 | 210701.4 | 14
75 | Weather | Heavy Rain | Heavy Rain | Weather | LOW | 5 | 42 | 837499 | 1007895 | 1845394 | 347225.1 | 69445.02 | 138890.04 | 208335.06 | 7.5263
76 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | HIGH | 2 | 12 | 234999 | 450541 | 685540 | 346394.7 | 69278.94 | 138557.88 | 207836.82 | 20.2115
77 | Personnel | Crew Change | Medical Emergency | Medical Team | MEDIUM | 1 | 18 | 367500 | 774135 | 1141635 | 342490.5 | 68498.1 | 136996.2 | 205494.3 | 12
78 | Weather | Poor Visibility | Strong Wind | Marine Operations | LOW | 3 | 34 | 685000 | 1588104 | 2273104 | 340965.6 | 68193.12 | 136386.24 | 204579.36 | 6
79 | Drilling | Fishing Operation | Differential Sticking | Operator | HIGH | 4 | 22 | 444999 | 407026 | 852025 | 340810 | 68162 | 136324 | 204486 | 16
80 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | HIGH | 2 | 14 | 285000 | 566293 | 851293 | 340517.2 | 68103.44 | 136206.88 | 204310.32 | 16
81 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | MEDIUM | 1 | 18 | 367500 | 388821 | 756321 | 340344.45 | 68068.89 | 136137.78 | 204206.67 | 18
82 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | HIGH | 4 | 14 | 283331 | 449372 | 732703 | 329716.35 | 65943.27 | 131886.54 | 197829.81 | 18
83 | Weather | Strong Wind | Strong Wind | Marine Operations | LOW | 8 | 40 | 789164 | 1106026 | 1895190 | 327046.725 | 65409.345 | 130818.69 | 196228.035 | 6.9027
84 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | HIGH | 1 | 12 | 240000 | 123301 | 363301 | 326970.9 | 65394.18 | 130788.36 | 196182.54 | 36
85 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | MEDIUM | 4 | 20 | 404166 | 598675 | 1002841 | 322325.25 | 64465.05 | 128930.1 | 193395.15 | 12.8565
86 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | HIGH | 2 | 10 | 199166 | 234328 | 433494 | 322178.4 | 64435.68 | 128871.36 | 193307.04 | 29.7285
87 | Weather | Lightning | Lightning | Marine Operations | LOW | 7 | 30 | 598749 | 1024066 | 1622815 | 319721.85 | 63944.37 | 127888.74 | 191833.11 | 7.8807
88 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | HIGH | 3 | 16 | 322916 | 253533 | 576449 | 311912.1 | 62382.42 | 124764.84 | 187147.26 | 21.6437
89 | Drilling | Hole Cleaning | Differential Sticking | Operator | HIGH | 3 | 16 | 316666 | 370500 | 687166 | 311643.6 | 62328.72 | 124657.44 | 186986.16 | 18.1408
90 | Drilling | Well Control | Formation Instability | Mud Engineering | MEDIUM | 5 | 18 | 351665 | 466385 | 818050 | 304212.675 | 60842.535 | 121685.07 | 182527.605 | 14.875
91 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | HIGH | 4 | 14 | 277499 | 398891 | 676390 | 297573.6 | 59514.72 | 119029.44 | 178544.16 | 17.5978
92 | Weather | Poor Visibility | Heavy Rain | Marine Operations | LOW | 4 | 32 | 643332 | 956728 | 1600060 | 296826.825 | 59365.365 | 118730.73 | 178096.095 | 7.4204
93 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | MEDIUM | 2 | 16 | 326666 | 538360 | 865026 | 296620.05 | 59324.01 | 118648.02 | 177972.03 | 13.7161
94 | Weather | Lightning | Lightning | Weather | LOW | 9 | 36 | 706247 | 974259 | 1680506 | 294172.575 | 58834.515 | 117669.03 | 176503.545 | 7.002
95 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | HIGH | 1 | 8 | 153333 | 279943 | 433276 | 292461.3 | 58492.26 | 116984.52 | 175476.78 | 27
96 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | HIGH | 2 | 14 | 275000 | 241750 | 516750 | 290142 | 58028.4 | 116056.8 | 174085.2 | 22.459
97 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | HIGH | 1 | 8 | 153333 | 276056 | 429389 | 289837.575 | 57967.515 | 115935.03 | 173902.545 | 27
98 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | HIGH | 2 | 8 | 158332 | 360014 | 518346 | 289603.125 | 57920.625 | 115841.25 | 173761.875 | 22.3482
99 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | HIGH | 4 | 14 | 278332 | 272689 | 551021 | 287480 | 57496 | 114992 | 172488 | 20.8689
100 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | MEDIUM | 4 | 20 | 399582 | 479851 | 879433 | 285815.725 | 57163.145 | 114326.29 | 171489.435 | 13
101 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | HIGH | 3 | 10 | 193333 | 344893 | 538226 | 284628.6 | 56925.72 | 113851.44 | 170777.16 | 21.1531
102 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | MEDIUM | 3 | 16 | 306665 | 637880 | 944545 | 283363.5 | 56672.7 | 113345.4 | 170018.1 | 12
103 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | HIGH | 2 | 12 | 229999 | 474568 | 704567 | 281826.8 | 56365.36 | 112730.72 | 169096.08 | 16
104 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | MEDIUM | 3 | 16 | 322916 | 419311 | 742227 | 276792.2625 | 55358.4525 | 110716.905 | 166075.3575 | 14.9169
105 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | MEDIUM | 1 | 18 | 345000 | 573898 | 918898 | 275669.4 | 55133.88 | 110267.76 | 165401.64 | 12
106 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | HIGH | 2 | 10 | 191666 | 299995 | 491661 | 273401.6 | 54680.32 | 109360.64 | 164040.96 | 22.2431
107 | Weather | Heavy Rain | Storm | Weather | LOW | 3 | 34 | 686666 | 963834 | 1650500 | 272862.975 | 54572.595 | 109145.19 | 163717.785 | 6.6129
108 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | MEDIUM | 3 | 12 | 229999 | 484817 | 714816 | 272844.325 | 54568.865 | 109137.73 | 163706.595 | 15.2679
109 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | MEDIUM | 2 | 16 | 306666 | 462230 | 768896 | 271341.6 | 54268.32 | 108536.64 | 162804.96 | 14.1159
110 | Weather | High Waves | Heavy Rain | Marine Operations | LOW | 4 | 18 | 354166 | 583664 | 937830 | 264787.8 | 52957.56 | 105915.12 | 158872.68 | 11.2936
111 | Logistics | Waiting on Cement | Customs Clearance | Procurement | MEDIUM | 2 | 12 | 233333 | 392072 | 625405 | 259556.4 | 51911.28 | 103822.56 | 155733.84 | 16.6009
112 | Weather | Heavy Rain | Strong Wind | Marine Operations | LOW | 3 | 32 | 618333 | 1063440 | 1681773 | 256981.275 | 51396.255 | 102792.51 | 154188.765 | 6.1122
113 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | HIGH | 2 | 14 | 272083 | 294780 | 566863 | 255088.35 | 51017.67 | 102035.34 | 153053.01 | 18
114 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | MEDIUM | 4 | 18 | 364999 | 361231 | 726230 | 254180.5 | 50836.1 | 101672.2 | 152508.3 | 14
115 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | MEDIUM | 3 | 10 | 197499 | 412127 | 609626 | 252192.9 | 50438.58 | 100877.16 | 151315.74 | 16.5474
116 | Weather | Lightning | High Waves | Weather | LOW | 2 | 36 | 710000 | 933604 | 1643604 | 246540.6 | 49308.12 | 98616.24 | 147924.36 | 6
117 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | MEDIUM | 3 | 14 | 280832 | 265682 | 546514 | 245453.4875 | 49090.6975 | 98181.395 | 147272.0925 | 17.965
118 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | MEDIUM | 2 | 16 | 316666 | 482000 | 798666 | 239599.8 | 47919.96 | 95839.92 | 143759.88 | 12
119 | Logistics | Waiting on Materials | Port Congestion | Procurement | MEDIUM | 2 | 10 | 199166 | 235314 | 434480 | 235829.4 | 47165.88 | 94331.76 | 141497.64 | 21.7114
120 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | MEDIUM | 1 | 18 | 356250 | 426483 | 782733 | 234819.9 | 46963.98 | 93927.96 | 140891.94 | 12
121 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | HIGH | 1 | 8 | 158333 | 357164 | 515497 | 231973.65 | 46394.73 | 92789.46 | 139184.19 | 18
122 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | HIGH | 2 | 10 | 201666 | 304834 | 506500 | 227925 | 45585 | 91170 | 136755 | 18
123 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | HIGH | 2 | 8 | 155833 | 224020 | 379853 | 227642.85 | 45528.57 | 91057.14 | 136585.71 | 23.9717
124 | Weather | Heavy Rain | Lightning | Marine Operations | LOW | 4 | 20 | 400832 | 836814 | 1237646 | 227167.8 | 45433.56 | 90867.12 | 136300.68 | 7.3419
125 | Weather | High Waves | Strong Wind | Weather | LOW | 4 | 22 | 445416 | 678421 | 1123837 | 226793.55 | 45358.71 | 90717.42 | 136076.13 | 8.0721
126 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | MEDIUM | 2 | 10 | 204166 | 316845 | 521011 | 226695.7875 | 45339.1575 | 90678.315 | 136017.4725 | 17.4043
127 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | MEDIUM | 3 | 16 | 318333 | 362244 | 680577 | 225334.2 | 45066.84 | 90133.68 | 135200.52 | 13.2437
128 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | HIGH | 3 | 10 | 194165 | 241772 | 435937 | 224993.25 | 44998.65 | 89997.3 | 134995.95 | 20.6446
129 | Drilling | Bit Failure | Bit Wear | Operator | HIGH | 2 | 8 | 159583 | 152895 | 312478 | 224885.8 | 44977.16 | 89954.32 | 134931.48 | 28.7874
130 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | MEDIUM | 3 | 10 | 196665 | 288719 | 485384 | 223742.1875 | 44748.4375 | 89496.875 | 134245.3125 | 18.4384
131 | Personnel | Medical Evacuation | Training Requirement | HR | MEDIUM | 4 | 18 | 352499 | 387418 | 739917 | 221975.1 | 44395.02 | 88790.04 | 133185.06 | 12
132 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | MEDIUM | 3 | 12 | 232499 | 389631 | 622130 | 220750.8 | 44150.16 | 88300.32 | 132450.48 | 14.1932
133 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | MEDIUM | 2 | 10 | 200416 | 310047 | 510463 | 220566.5 | 44113.3 | 88226.6 | 132339.9 | 17.2836
134 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | MEDIUM | 2 | 10 | 203333 | 426701 | 630034 | 220511.9 | 44102.38 | 88204.76 | 132307.14 | 14
135 | Personnel | Safety Stand Down | Training Requirement | Rig Management | MEDIUM | 3 | 18 | 352499 | 292861 | 645360 | 220080 | 44016 | 88032 | 132048 | 13.6408
136 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | MEDIUM | 3 | 16 | 317083 | 394125 | 711208 | 213362.4 | 42672.48 | 85344.96 | 128017.44 | 12
137 | Weather | High Waves | High Waves | Marine Operations | LOW | 4 | 24 | 472499 | 722142 | 1194641 | 210084.15 | 42016.83 | 84033.66 | 126050.49 | 7.0342
138 | Weather | Heavy Rain | Strong Wind | Weather | LOW | 4 | 22 | 436666 | 601439 | 1038105 | 203659.8 | 40731.96 | 81463.92 | 122195.88 | 7.8474
139 | Weather | High Waves | Lightning | Marine Operations | LOW | 4 | 20 | 389582 | 721737 | 1111319 | 203537.85 | 40707.57 | 81415.14 | 122122.71 | 7.326
140 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | MEDIUM | 4 | 14 | 278333 | 299723 | 578056 | 200450.7 | 40090.14 | 80180.28 | 120270.42 | 13.8707
141 | Weather | Heavy Rain | High Waves | Weather | LOW | 3 | 12 | 237499 | 534451 | 771950 | 197260.95 | 39452.19 | 78904.38 | 118356.57 | 10.2214
142 | Drilling | Lost Circulation | Differential Sticking | Operator | HIGH | 2 | 10 | 194166 | 295847 | 490013 | 196005.2 | 39201.04 | 78402.08 | 117603.12 | 16
143 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | MEDIUM | 2 | 12 | 241250 | 399607 | 640857 | 192257.1 | 38451.42 | 76902.84 | 115354.26 | 12
144 | Weather | Heavy Rain | High Waves | Marine Operations | LOW | 4 | 16 | 315833 | 574551 | 890384 | 191736.075 | 38347.215 | 76694.43 | 115041.645 | 8.6136
145 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | MEDIUM | 1 | 12 | 230000 | 407608 | 637608 | 191282.4 | 38256.48 | 76512.96 | 114769.44 | 12
146 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | HIGH | 2 | 8 | 160833 | 262056 | 422889 | 190300.05 | 38060.01 | 76120.02 | 114180.03 | 18
147 | Weather | High Waves | Storm | Marine Operations | LOW | 4 | 20 | 408332 | 625479 | 1033811 | 189754.275 | 37950.855 | 75901.71 | 113852.565 | 7.3419
148 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | MEDIUM | 2 | 12 | 233750 | 387953 | 621703 | 186510.9 | 37302.18 | 74604.36 | 111906.54 | 12
149 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | MEDIUM | 2 | 10 | 191666 | 339541 | 531207 | 185922.45 | 37184.49 | 74368.98 | 111553.47 | 14
150 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | MEDIUM | 2 | 14 | 268333 | 348193 | 616526 | 184957.8 | 36991.56 | 73983.12 | 110974.68 | 12
151 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | HIGH | 1 | 8 | 153333 | 252476 | 405809 | 182614.05 | 36522.81 | 73045.62 | 109568.43 | 18
152 | Weather | Strong Wind | High Waves | Marine Operations | LOW | 4 | 18 | 356248 | 571296 | 927544 | 182324.25 | 36464.85 | 72929.7 | 109394.55 | 7.8627
153 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | HIGH | 2 | 6 | 114999 | 187090 | 302089 | 182298.825 | 36459.765 | 72919.53 | 109379.295 | 24.1384
154 | Personnel | Crew Change | Crew Rotation | Rig Management | MEDIUM | 1 | 18 | 367500 | 236304 | 603804 | 181141.2 | 36228.24 | 72456.48 | 108684.72 | 12
155 | Weather | High Waves | Lightning | Weather | LOW | 4 | 22 | 440832 | 760122 | 1200954 | 180143.1 | 36028.62 | 72057.24 | 108085.86 | 6
156 | Weather | Lightning | Strong Wind | Weather | LOW | 2 | 24 | 490000 | 710103 | 1200103 | 180015.45 | 36003.09 | 72006.18 | 108009.27 | 6
157 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | MEDIUM | 3 | 14 | 277500 | 307302 | 584802 | 175440.6 | 35088.12 | 70176.24 | 105264.36 | 12
158 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | HIGH | 1 | 6 | 115000 | 272813 | 387813 | 174515.85 | 34903.17 | 69806.34 | 104709.51 | 18
159 | Weather | Poor Visibility | Lightning | Weather | LOW | 3 | 14 | 268332 | 430551 | 698883 | 173130.45 | 34626.09 | 69252.18 | 103878.27 | 9.909
160 | Weather | Lightning | High Waves | Marine Operations | LOW | 5 | 20 | 392081 | 542232 | 934313 | 167834.7 | 33566.94 | 67133.88 | 100700.82 | 7.1854
161 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | MEDIUM | 2 | 8 | 160833 | 234484 | 395317 | 164887.35 | 32977.47 | 65954.94 | 98932.41 | 16.6841
162 | Weather | Strong Wind | Storm | Weather | LOW | 4 | 16 | 317499 | 334476 | 651975 | 163299.9 | 32659.98 | 65319.96 | 97979.94 | 10.0188
163 | Drilling | Bit Failure | Formation Instability | Directional Drilling | MEDIUM | 3 | 12 | 238750 | 263155 | 501905 | 163119.125 | 32623.825 | 65247.65 | 97871.475 | 13
164 | Weather | Poor Visibility | Strong Wind | Weather | LOW | 5 | 24 | 471248 | 566798 | 1038046 | 161102.475 | 32220.495 | 64440.99 | 96661.485 | 6.2079
165 | Drilling | Bit Failure | Formation Instability | Mud Engineering | MEDIUM | 3 | 10 | 199165 | 165341 | 364506 | 158385.825 | 31677.165 | 63354.33 | 95031.495 | 17.3809
166 | Drilling | Bit Failure | Differential Sticking | Operator | HIGH | 1 | 6 | 120000 | 273652 | 393652 | 157460.8 | 31492.16 | 62984.32 | 94476.48 | 16
167 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | HIGH | 1 | 6 | 122500 | 226126 | 348626 | 156881.7 | 31376.34 | 62752.68 | 94129.02 | 18
168 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | HIGH | 2 | 6 | 117499 | 82412 | 199911 | 149336.55 | 29867.31 | 59734.62 | 89601.93 | 29.8806
169 | Logistics | Delayed Helicopter | Material Shortage | Procurement | MEDIUM | 1 | 4 | 76666 | 169001 | 245667 | 147400.2 | 29480.04 | 58960.08 | 88440.12 | 24
170 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | HIGH | 2 | 4 | 76666 | 140554 | 217220 | 146623.5 | 29324.7 | 58649.4 | 87974.1 | 27
171 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | HIGH | 2 | 6 | 121666 | 244186 | 365852 | 146340.8 | 29268.16 | 58536.32 | 87804.48 | 16
172 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | MEDIUM | 1 | 4 | 76666 | 165696 | 242362 | 145417.2 | 29083.44 | 58166.88 | 87250.32 | 24
173 | Weather | Lightning | Storm | Weather | LOW | 2 | 16 | 326666 | 540736 | 867402 | 144399.9 | 28879.98 | 57759.96 | 86639.94 | 6.659
174 | Weather | Lightning | Storm | Marine Operations | LOW | 3 | 16 | 316665 | 461207 | 777872 | 143023.05 | 28604.61 | 57209.22 | 85813.83 | 7.3546
175 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | HIGH | 1 | 8 | 163333 | 152781 | 316114 | 142251.3 | 28450.26 | 56900.52 | 85350.78 | 18
176 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | HIGH | 1 | 6 | 122500 | 88110 | 210610 | 142161.75 | 28432.35 | 56864.7 | 85297.05 | 27
177 | Logistics | Delayed Helicopter | Port Congestion | Procurement | MEDIUM | 3 | 10 | 195833 | 277135 | 472968 | 141890.4 | 28378.08 | 56756.16 | 85134.24 | 12
178 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | HIGH | 1 | 6 | 115000 | 196670 | 311670 | 140251.5 | 28050.3 | 56100.6 | 84150.9 | 18
179 | Logistics | Waiting on Materials | Customs Clearance | Procurement | MEDIUM | 2 | 6 | 117499 | 113974 | 231473 | 138883.8 | 27776.76 | 55553.52 | 83330.28 | 24
180 | Drilling | Bit Failure | Bit Wear | Directional Drilling | HIGH | 1 | 6 | 118750 | 226214 | 344964 | 137985.6 | 27597.12 | 55194.24 | 82791.36 | 16
181 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | HIGH | 1 | 4 | 81666 | 71396 | 153062 | 137755.8 | 27551.16 | 55102.32 | 82653.48 | 36
182 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | MEDIUM | 1 | 6 | 120000 | 270679 | 390679 | 136737.65 | 27347.53 | 54695.06 | 82042.59 | 14
183 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | HIGH | 1 | 6 | 122500 | 78520 | 201020 | 135688.5 | 27137.7 | 54275.4 | 81413.1 | 27
184 | Drilling | Hole Cleaning | Formation Instability | Operator | MEDIUM | 3 | 8 | 159582 | 255813 | 415395 | 135003.375 | 27000.675 | 54001.35 | 81002.025 | 13
185 | Personnel | Crew Change | Medical Emergency | Rig Management | MEDIUM | 2 | 6 | 114999 | 212937 | 327936 | 132432.3 | 26486.46 | 52972.92 | 79459.38 | 16.1534
186 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | HIGH | 1 | 6 | 115000 | 177855 | 292855 | 131784.75 | 26356.95 | 52713.9 | 79070.85 | 18
187 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | MEDIUM | 2 | 10 | 200833 | 230960 | 431793 | 129537.9 | 25907.58 | 51815.16 | 77722.74 | 12
188 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | HIGH | 1 | 4 | 81666 | 198934 | 280600 | 126270 | 25254 | 50508 | 75762 | 18
189 | Personnel | Safety Stand Down | Training Requirement | Medical Team | MEDIUM | 2 | 6 | 119999 | 160592 | 280591 | 126265.95 | 25253.19 | 50506.38 | 75759.57 | 18
190 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | MEDIUM | 1 | 6 | 120000 | 295691 | 415691 | 124707.3 | 24941.46 | 49882.92 | 74824.38 | 12
191 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 1 | 4 | 81666 | 55857 | 137523 | 123770.7 | 24754.14 | 49508.28 | 74262.42 | 36
192 | Weather | Poor Visibility | Lightning | Marine Operations | LOW | 4 | 16 | 309165 | 371867 | 681032 | 121788.15 | 24357.63 | 48715.26 | 73072.89 | 7.1532
193 | Logistics | Waiting on Boat | Customs Clearance | Procurement | MEDIUM | 2 | 6 | 119999 | 282138 | 402137 | 120641.1 | 24128.22 | 48256.44 | 72384.66 | 12
194 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | MEDIUM | 2 | 6 | 114999 | 255620 | 370619 | 120451.175 | 24090.235 | 48180.47 | 72270.705 | 13
195 | Drilling | Well Control | Formation Instability | Directional Drilling | MEDIUM | 1 | 6 | 115000 | 253781 | 368781 | 119853.825 | 23970.765 | 47941.53 | 71912.295 | 13
196 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | MEDIUM | 1 | 4 | 76666 | 90633 | 167299 | 117109.3 | 23421.86 | 46843.72 | 70265.58 | 28
197 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | MEDIUM | 1 | 6 | 122500 | 257837 | 380337 | 114101.1 | 22820.22 | 45640.44 | 68460.66 | 12
198 | Weather | Strong Wind | High Waves | Weather | LOW | 2 | 14 | 272083 | 483655 | 755738 | 113360.7 | 22672.14 | 45344.28 | 68016.42 | 6
199 | Logistics | Waiting on Boat | Port Congestion | Procurement | MEDIUM | 1 | 6 | 122500 | 255221 | 377721 | 113316.3 | 22663.26 | 45326.52 | 67989.78 | 12
200 | Personnel | Medical Evacuation | Medical Emergency | HR | MEDIUM | 1 | 6 | 122500 | 253590 | 376090 | 112827 | 22565.4 | 45130.8 | 67696.2 | 12
201 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | HIGH | 1 | 2 | 38333 | 82613 | 120946 | 108851.4 | 21770.28 | 43540.56 | 65310.84 | 36
202 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | MEDIUM | 1 | 6 | 118750 | 120114 | 238864 | 107488.8 | 21497.76 | 42995.52 | 64493.28 | 18
203 | Personnel | Crew Change | Medical Emergency | HR | MEDIUM | 1 | 6 | 115000 | 117452 | 232452 | 104603.4 | 20920.68 | 41841.36 | 62762.04 | 18
204 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | MEDIUM | 2 | 6 | 114999 | 108729 | 223728 | 103607.875 | 20721.575 | 41443.15 | 62164.725 | 18.5239
205 | Weather | Strong Wind | Heavy Rain | Weather | LOW | 2 | 18 | 355000 | 316484 | 671484 | 100722.6 | 20144.52 | 40289.04 | 60433.56 | 6
206 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | HIGH | 1 | 4 | 80000 | 143184 | 223184 | 100432.8 | 20086.56 | 40173.12 | 60259.68 | 18
207 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | HIGH | 2 | 6 | 119166 | 98637 | 217803 | 98011.35 | 19602.27 | 39204.54 | 58806.81 | 18
208 | Personnel | Training | Crew Rotation | Medical Team | MEDIUM | 1 | 6 | 122500 | 90710 | 213210 | 95944.5 | 19188.9 | 38377.8 | 57566.7 | 18
209 | Drilling | Well Control | Unexpected Pressure | Operator | MEDIUM | 2 | 8 | 153332 | 141593 | 294925 | 95850.625 | 19170.125 | 38340.25 | 57510.375 | 13
210 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | HIGH | 1 | 4 | 76666 | 157410 | 234076 | 93630.4 | 18726.08 | 37452.16 | 56178.24 | 16
211 | Weather | High Waves | Heavy Rain | Weather | LOW | 2 | 10 | 196666 | 280380 | 477046 | 91679.925 | 18335.985 | 36671.97 | 55007.955 | 7.6873
212 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | HIGH | 2 | 6 | 116666 | 86992 | 203658 | 91646.1 | 18329.22 | 36658.44 | 54987.66 | 18
213 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | MEDIUM | 1 | 4 | 80000 | 121829 | 201829 | 90823.05 | 18164.61 | 36329.22 | 54493.83 | 18
214 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | HIGH | 1 | 2 | 40833 | 55477 | 96310 | 86679 | 17335.8 | 34671.6 | 52007.4 | 36
215 | Weather | Heavy Rain | Lightning | Weather | LOW | 3 | 10 | 199165 | 365446 | 564611 | 84691.65 | 16938.33 | 33876.66 | 50814.99 | 6
216 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | MEDIUM | 1 | 4 | 81666 | 198718 | 280384 | 84115.2 | 16823.04 | 33646.08 | 50469.12 | 12
217 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | MEDIUM | 1 | 4 | 76666 | 152544 | 229210 | 80223.5 | 16044.7 | 32089.4 | 48134.1 | 14
218 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | MEDIUM | 1 | 4 | 80000 | 183601 | 263601 | 79080.3 | 15816.06 | 31632.12 | 47448.18 | 12
219 | Weather | Poor Visibility | Storm | Weather | LOW | 3 | 12 | 239999 | 260713 | 500712 | 75106.8 | 15021.36 | 30042.72 | 45064.08 | 6
220 | Personnel | Medical Evacuation | Training Requirement | Medical Team | MEDIUM | 2 | 4 | 80833 | 169277 | 250110 | 75033 | 15006.6 | 30013.2 | 45019.8 | 12
221 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | HIGH | 1 | 2 | 38333 | 43940 | 82273 | 74045.7 | 14809.14 | 29618.28 | 44427.42 | 36
222 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | MEDIUM | 1 | 6 | 120000 | 106088 | 226088 | 73478.6 | 14695.72 | 29391.44 | 44087.16 | 13
223 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | HIGH | 1 | 4 | 81666 | 77766 | 159432 | 71744.4 | 14348.88 | 28697.76 | 43046.64 | 18
224 | Weather | Poor Visibility | High Waves | Marine Operations | LOW | 3 | 12 | 229998 | 243433 | 473431 | 71014.65 | 14202.93 | 28405.86 | 42608.79 | 6
225 | Weather | Strong Wind | Storm | Marine Operations | LOW | 2 | 8 | 153333 | 190713 | 344046 | 70674.75 | 14134.95 | 28269.9 | 42404.85 | 8.2169
226 | Weather | Heavy Rain | Heavy Rain | Marine Operations | LOW | 2 | 8 | 158332 | 312744 | 471076 | 70661.4 | 14132.28 | 28264.56 | 42396.84 | 6
227 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | MEDIUM | 1 | 4 | 81666 | 152013 | 233679 | 70103.7 | 14020.74 | 28041.48 | 42062.22 | 12
228 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | MEDIUM | 2 | 4 | 81666 | 148998 | 230664 | 69199.2 | 13839.84 | 27679.68 | 41519.52 | 12
229 | Weather | Poor Visibility | Storm | Marine Operations | LOW | 3 | 10 | 200416 | 231216 | 431632 | 64744.8 | 12948.96 | 25897.92 | 38846.88 | 6
230 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | MEDIUM | 1 | 6 | 118750 | 64902 | 183652 | 64278.2 | 12855.64 | 25711.28 | 38566.92 | 14
231 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | MEDIUM | 1 | 4 | 76666 | 128931 | 205597 | 61679.1 | 12335.82 | 24671.64 | 37007.46 | 12
232 | Drilling | Bit Failure | Formation Instability | Operator | MEDIUM | 1 | 2 | 40000 | 85034 | 125034 | 60954.075 | 12190.815 | 24381.63 | 36572.445 | 19.5
233 | Weather | Heavy Rain | Storm | Marine Operations | LOW | 2 | 6 | 119999 | 275086 | 395085 | 59262.75 | 11852.55 | 23705.1 | 35557.65 | 6
234 | Drilling | Well Control | Differential Sticking | Operator | HIGH | 1 | 4 | 76666 | 70081 | 146747 | 58698.8 | 11739.76 | 23479.52 | 35219.28 | 16
235 | Weather | Poor Visibility | High Waves | Weather | LOW | 1 | 6 | 118750 | 138221 | 256971 | 57818.475 | 11563.695 | 23127.39 | 34691.085 | 9
236 | Weather | Lightning | Strong Wind | Marine Operations | LOW | 2 | 8 | 155833 | 227263 | 383096 | 57464.4 | 11492.88 | 22985.76 | 34478.64 | 6
237 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | MEDIUM | 1 | 4 | 80000 | 91574 | 171574 | 55761.55 | 11152.31 | 22304.62 | 33456.93 | 13
238 | Logistics | Waiting on Boat | Material Shortage | Procurement | MEDIUM | 2 | 4 | 80416 | 102981 | 183397 | 55019.1 | 11003.82 | 22007.64 | 33011.46 | 12
239 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | HIGH | 1 | 2 | 38333 | 83567 | 121900 | 54855 | 10971 | 21942 | 32913 | 18
240 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | HIGH | 1 | 2 | 40000 | 79766 | 119766 | 53894.7 | 10778.94 | 21557.88 | 32336.82 | 18
241 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | HIGH | 1 | 2 | 38333 | 81222 | 119555 | 53799.75 | 10759.95 | 21519.9 | 32279.85 | 18
242 | Drilling | Fishing Operation | Bit Wear | Operator | HIGH | 1 | 2 | 38333 | 49722 | 88055 | 52833 | 10566.6 | 21133.2 | 31699.8 | 24
243 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | MEDIUM | 1 | 4 | 79166 | 68905 | 148071 | 51824.85 | 10364.97 | 20729.94 | 31094.91 | 14
244 | Drilling | Well Control | Bit Wear | Operator | HIGH | 1 | 2 | 40000 | 85472 | 125472 | 50188.8 | 10037.76 | 20075.52 | 30113.28 | 16
245 | Weather | Strong Wind | Heavy Rain | Marine Operations | LOW | 2 | 6 | 118749 | 138316 | 257065 | 49632.45 | 9926.49 | 19852.98 | 29779.47 | 7.7229
246 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | MEDIUM | 2 | 4 | 78333 | 85214 | 163547 | 49064.1 | 9812.82 | 19625.64 | 29438.46 | 12
247 | Drilling | Lost Circulation | Unexpected Pressure | Operator | MEDIUM | 1 | 2 | 40833 | 59674 | 100507 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975 | 19.5
248 | Personnel | Crew Change | Training Requirement | Rig Management | MEDIUM | 1 | 4 | 76666 | 79447 | 156113 | 46833.9 | 9366.78 | 18733.56 | 28100.34 | 12
249 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | MEDIUM | 1 | 2 | 40833 | 60855 | 101688 | 45759.6 | 9151.92 | 18303.84 | 27455.76 | 18
250 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | MEDIUM | 1 | 2 | 38333 | 59428 | 97761 | 43992.45 | 8798.49 | 17596.98 | 26395.47 | 18
251 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | MEDIUM | 1 | 4 | 81666 | 64854 | 146520 | 43956 | 8791.2 | 17582.4 | 26373.6 | 12
252 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | MEDIUM | 1 | 4 | 81666 | 60840 | 142506 | 42751.8 | 8550.36 | 17100.72 | 25651.08 | 12
253 | Logistics | Waiting on Cement | Port Congestion | Procurement | MEDIUM | 1 | 4 | 81666 | 60188 | 141854 | 42556.2 | 8511.24 | 17022.48 | 25533.72 | 12
254 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | MEDIUM | 1 | 2 | 40000 | 88171 | 128171 | 38451.3 | 7690.26 | 15380.52 | 23070.78 | 12
255 | Personnel | Training | Training Requirement | Medical Team | MEDIUM | 1 | 2 | 39583 | 85410 | 124993 | 37497.9 | 7499.58 | 14999.16 | 22498.74 | 12
256 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | MEDIUM | 1 | 2 | 40000 | 42480 | 82480 | 37116 | 7423.2 | 14846.4 | 22269.6 | 18
257 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | HIGH | 1 | 2 | 39583 | 39917 | 79500 | 35775 | 7155 | 14310 | 21465 | 18
258 | Weather | Strong Wind | Lightning | Marine Operations | LOW | 1 | 6 | 115000 | 123339 | 238339 | 35750.85 | 7150.17 | 14300.34 | 21450.51 | 6
259 | Weather | Lightning | Heavy Rain | Weather | LOW | 2 | 4 | 78333 | 123696 | 202029 | 35563.8 | 7112.76 | 14225.52 | 21338.28 | 7.0413
260 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | HIGH | 1 | 2 | 40000 | 33971 | 73971 | 33286.95 | 6657.39 | 13314.78 | 19972.17 | 18
261 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | MEDIUM | 1 | 2 | 40833 | 67554 | 108387 | 32516.1 | 6503.22 | 13006.44 | 19509.66 | 12
262 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | MEDIUM | 1 | 2 | 40833 | 48689 | 89522 | 31332.7 | 6266.54 | 12533.08 | 18799.62 | 14
263 | Weather | High Waves | Storm | Weather | LOW | 1 | 4 | 81666 | 110150 | 191816 | 28772.4 | 5754.48 | 11508.96 | 17263.44 | 6
264 | Personnel | Safety Stand Down | Training Requirement | HR | MEDIUM | 1 | 2 | 40000 | 53981 | 93981 | 28194.3 | 5638.86 | 11277.72 | 16916.58 | 12
265 | Drilling | Well Control | Differential Sticking | Mud Engineering | HIGH | 1 | 2 | 40000 | 30168 | 70168 | 28067.2 | 5613.44 | 11226.88 | 16840.32 | 16
266 | Weather | High Waves | High Waves | Weather | LOW | 1 | 6 | 115000 | 70319 | 185319 | 27797.85 | 5559.57 | 11119.14 | 16678.71 | 6
267 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | MEDIUM | 1 | 2 | 38333 | 43207 | 81540 | 24462 | 4892.4 | 9784.8 | 14677.2 | 12
268 | Personnel | Safety Stand Down | Medical Emergency | HR | MEDIUM | 1 | 2 | 40000 | 25522 | 65522 | 19656.6 | 3931.32 | 7862.64 | 11793.96 | 12
269 | Weather | Strong Wind | Lightning | Weather | LOW | 1 | 2 | 40833 | 43926 | 84759 | 12713.85 | 2542.77 | 5085.54 | 7628.31 | 6

## Rig_Scenarios
Priority_Rank | Rig_ID | Controllability | Wells_Affected | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD
1 | R002 | HIGH | 20 | 102 | 676 | 32231479 | 17293797.2 | 3458759.44 | 6917518.88 | 10376278.32
2 | R004 | HIGH | 16 | 69 | 418 | 22224686 | 12115541.125 | 2423108.225 | 4846216.45 | 7269324.675
3 | R002 | MEDIUM | 20 | 115 | 584 | 27555453 | 10679320.1125 | 2135864.0225 | 4271728.045 | 6407592.0675
4 | R004 | MEDIUM | 16 | 76 | 450 | 22944862 | 8334650.25 | 1666930.05 | 3333860.1 | 5000790.15
5 | R003 | HIGH | 8 | 44 | 262 | 12814531 | 6207252 | 1241450.4 | 2482900.8 | 3724351.2
6 | R001 | HIGH | 6 | 30 | 226 | 11746128 | 6191068.175 | 1238213.635 | 2476427.27 | 3714640.905
7 | R003 | MEDIUM | 8 | 51 | 260 | 13136049 | 4709052.9625 | 941810.5925 | 1883621.185 | 2825431.7775
8 | R002 | LOW | 20 | 65 | 350 | 16773513 | 2983178.7 | 596635.74 | 1193271.48 | 1789907.22
9 | R001 | MEDIUM | 6 | 29 | 190 | 8612987 | 2979908.9625 | 595981.7925 | 1191963.585 | 1787945.3775
10 | R004 | LOW | 15 | 54 | 318 | 16300851 | 2868247.575 | 573649.515 | 1147299.03 | 1720948.545
11 | R003 | LOW | 7 | 21 | 172 | 8445878 | 1652425.05 | 330485.01 | 660970.02 | 991455.03
12 | R001 | LOW | 6 | 21 | 102 | 5363761 | 1050176.475 | 210035.295 | 420070.59 | 630105.885

## Well_Scenarios
Priority_Rank | Well_ID | Rig_ID | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD
1 | W003 | R004 | 13 | 88 | 5225678 | 2730076.025 | 546015.205 | 1092030.41 | 1638045.615
2 | W011 | R004 | 16 | 104 | 5187621 | 2647862.075 | 529572.415 | 1059144.83 | 1588717.245
3 | W007 | R001 | 16 | 128 | 6815911 | 2638464.85 | 527692.97 | 1055385.94 | 1583078.91
4 | W040 | R002 | 21 | 130 | 6620110 | 2589362.3 | 517872.46 | 1035744.92 | 1553617.38
5 | W002 | R001 | 13 | 88 | 4546361 | 2278951.175 | 455790.235 | 911580.47 | 1367370.705
6 | W036 | R002 | 19 | 108 | 5411508 | 2188568.9125 | 437713.7825 | 875427.565 | 1313141.3475
7 | W033 | R002 | 16 | 90 | 4243450 | 1962145.55 | 392429.11 | 784858.22 | 1177287.33
8 | W046 | R003 | 16 | 102 | 5032158 | 1941940.85 | 388388.17 | 776776.34 | 1165164.51
9 | W019 | R003 | 13 | 114 | 5561717 | 1928002.325 | 385600.465 | 771200.93 | 1156801.395
10 | W015 | R003 | 14 | 76 | 4385282 | 1878341.95 | 375668.39 | 751336.78 | 1127005.17
11 | W023 | R004 | 14 | 84 | 4828213 | 1863016.9 | 372603.38 | 745206.76 | 1117810.14
12 | W048 | R002 | 14 | 86 | 4208923 | 1851299.95 | 370259.99 | 740519.98 | 1110779.97
13 | W020 | R003 | 20 | 90 | 4565483 | 1812456.825 | 362491.365 | 724982.73 | 1087474.095
14 | W006 | R002 | 15 | 84 | 4231281 | 1800698.425 | 360139.685 | 720279.37 | 1080419.055
15 | W009 | R001 | 15 | 100 | 4669372 | 1783363.675 | 356672.735 | 713345.47 | 1070018.205
16 | W030 | R002 | 15 | 90 | 4137386 | 1768676.775 | 353735.355 | 707470.71 | 1061206.065
17 | W043 | R002 | 18 | 94 | 4350399 | 1761792.3375 | 352358.4675 | 704716.935 | 1057075.4025
18 | W013 | R003 | 20 | 96 | 4883822 | 1758756.1375 | 351751.2275 | 703502.455 | 1055253.6825
19 | W050 | R004 | 11 | 74 | 3894520 | 1744529.725 | 348905.945 | 697811.89 | 1046717.835
20 | W021 | R002 | 16 | 94 | 4506303 | 1732894.9 | 346578.98 | 693157.96 | 1039736.94
21 | W027 | R002 | 10 | 66 | 3222709 | 1615250.7375 | 323050.1475 | 646100.295 | 969150.4425
22 | W031 | R002 | 11 | 60 | 3032755 | 1606002.5 | 321200.5 | 642401 | 963601.5
23 | W047 | R004 | 13 | 78 | 3918083 | 1574679.725 | 314935.945 | 629871.89 | 944807.835
24 | W041 | R002 | 14 | 76 | 3512146 | 1565498.85 | 313099.77 | 626199.54 | 939299.31
25 | W028 | R002 | 15 | 90 | 4143050 | 1536386.575 | 307277.315 | 614554.63 | 921831.945
26 | W010 | R002 | 16 | 106 | 4734861 | 1462338.625 | 292467.725 | 584935.45 | 877403.175
27 | W026 | R004 | 11 | 90 | 4452824 | 1461938.9 | 292387.78 | 584775.56 | 877163.34
28 | W001 | R004 | 19 | 88 | 4605541 | 1454525.3875 | 290905.0775 | 581810.155 | 872715.2325
29 | W038 | R004 | 15 | 68 | 3555637 | 1420920.25 | 284184.05 | 568368.1 | 852552.15
30 | W018 | R004 | 14 | 88 | 3855804 | 1380726.475 | 276145.295 | 552290.59 | 828435.885
31 | W029 | R002 | 14 | 70 | 3349062 | 1338967.275 | 267793.455 | 535586.91 | 803380.365
32 | W037 | R002 | 9 | 72 | 3194393 | 1331400.5 | 266280.1 | 532560.2 | 798840.3
33 | W022 | R001 | 13 | 74 | 3442372 | 1328960.275 | 265792.055 | 531584.11 | 797376.165
34 | W024 | R002 | 12 | 68 | 3242338 | 1272312.45 | 254462.49 | 508924.98 | 763387.47
35 | W034 | R001 | 12 | 74 | 3657546 | 1271949.425 | 254389.885 | 508779.77 | 763169.655
36 | W049 | R003 | 9 | 60 | 2954155 | 1238486.15 | 247697.23 | 495394.46 | 743091.69
37 | W045 | R004 | 10 | 80 | 4553567 | 1204652.675 | 240930.535 | 481861.07 | 722791.605
38 | W012 | R004 | 11 | 64 | 3233740 | 1160885.175 | 232177.035 | 464354.07 | 696531.105
39 | W032 | R004 | 15 | 86 | 4251690 | 1152206.925 | 230441.385 | 460882.77 | 691324.155
40 | W035 | R003 | 12 | 92 | 3595897 | 1132565.075 | 226513.015 | 453026.03 | 679539.045
41 | W025 | R004 | 11 | 54 | 2858646 | 1116298.15 | 223259.63 | 446519.26 | 669778.89
42 | W005 | R002 | 13 | 64 | 3143733 | 995582.725 | 199116.545 | 398233.09 | 597349.635
43 | W039 | R002 | 13 | 70 | 3123391 | 979160.5625 | 195832.1125 | 391664.225 | 587496.3375
44 | W017 | R001 | 11 | 54 | 2591314 | 919464.2125 | 183892.8425 | 367785.685 | 551678.5275
45 | W044 | R003 | 12 | 64 | 3417944 | 878180.7 | 175636.14 | 351272.28 | 526908.42
46 | W042 | R004 | 8 | 52 | 2398167 | 865003.175 | 173000.635 | 346001.27 | 519001.905
47 | W004 | R002 | 11 | 52 | 2334494 | 826182.3 | 165236.46 | 330472.92 | 495709.38
48 | W014 | R004 | 8 | 38 | 2106838 | 804775.825 | 160955.165 | 321910.33 | 482865.495
49 | W008 | R002 | 10 | 40 | 1818153 | 771773.7625 | 154354.7525 | 308709.505 | 463064.2575
50 | W016 | R004 | 10 | 50 | 2543830 | 736341.5625 | 147268.3125 | 294536.625 | 441804.9375

## Responsible_Party
Priority_Rank | Responsible_Party | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD
1 | OEM Vendor | 59 | 376 | 18331322 | 10785282.15 | 2157056.43 | 4314112.86 | 6471169.29
2 | Drilling Contractor | 65 | 368 | 19000514 | 9853357.8 | 1970671.56 | 3941343.12 | 5912014.68
3 | Directional Drilling | 71 | 428 | 21180149 | 9561910.0375 | 1912382.0075 | 3824764.015 | 5737146.0225
4 | Mud Engineering | 70 | 438 | 21226556 | 8633039.25 | 1726607.85 | 3453215.7 | 5179823.55
5 | Maintenance Team | 47 | 308 | 14900279 | 8207573.175 | 1641514.635 | 3283029.27 | 4924543.905
6 | Operator | 72 | 386 | 18655151 | 8112625.875 | 1622525.175 | 3245050.35 | 4867575.525
7 | Marine Operations | 88 | 490 | 25000021 | 4628653.95 | 925730.79 | 1851461.58 | 2777192.37
8 | Supply Chain | 32 | 236 | 12321042 | 4562764.35 | 912552.87 | 1825105.74 | 2737658.61
9 | Weather | 73 | 452 | 21883982 | 3925373.85 | 785074.77 | 1570149.54 | 2355224.31
10 | Procurement | 36 | 180 | 9196062 | 3403995.15 | 680799.03 | 1361598.06 | 2042397.09
11 | Marine Logistics | 36 | 190 | 9511811 | 3024146.7 | 604829.34 | 1209658.68 | 1814488.02
12 | Rig Management | 9 | 66 | 2571074 | 945293.85 | 189058.77 | 378117.54 | 567176.31
13 | Medical Team | 11 | 56 | 2864253 | 933346.05 | 186669.21 | 373338.42 | 560007.63
14 | HR | 8 | 34 | 1507962 | 487256.4 | 97451.28 | 194902.56 | 292353.84

## Top_Opportunities
Priority_Rank | Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Action_Status | Corrective_Action | Controllability | Addressability_Factor | NPT_Events | Duration_hr | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | Savings_Priority_Score | Priority
1 | W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Open | Preventive Maintenance | HIGH | 0.9 | 1 | 24 | 1549746 | 1394771.4 | 278954.28 | 557908.56 | 836862.84 | 100 | CRITICAL
2 | W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Open | Adjust Drilling Parameters | HIGH | 0.8 | 1 | 18 | 1230862 | 984689.6 | 196937.92 | 393875.84 | 590813.76 | 99.8523 | CRITICAL
3 | W031 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | In Progress | Replace Equipment | HIGH | 0.9 | 1 | 24 | 1403802 | 947566.35 | 189513.27 | 379026.54 | 568539.81 | 99.7046 | CRITICAL
4 | W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Open | Preventive Maintenance | HIGH | 0.9 | 1 | 18 | 848296 | 763466.4 | 152693.28 | 305386.56 | 458079.84 | 99.5569 | CRITICAL
5 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Closed | OEM Inspection | HIGH | 0.9 | 1 | 24 | 1547580 | 696411 | 139282.2 | 278564.4 | 417846.6 | 99.4092 | CRITICAL
6 | W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | In Progress | Expedite Shipment | MEDIUM | 0.6 | 1 | 24 | 1223810 | 550714.5 | 110142.9 | 220285.8 | 330428.7 | 99.2614 | CRITICAL
7 | W027 | R002 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | In Progress | Adjust Drilling Parameters | HIGH | 0.8 | 1 | 18 | 910252 | 546151.2 | 109230.24 | 218460.48 | 327690.72 | 99.1137 | CRITICAL
8 | W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Closed | Replace Equipment | HIGH | 0.9 | 1 | 18 | 1199760 | 539892 | 107978.4 | 215956.8 | 323935.2 | 98.966 | CRITICAL
9 | W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Open | Air Freight Materials | MEDIUM | 0.6 | 1 | 24 | 887460 | 532476 | 106495.2 | 212990.4 | 319485.6 | 98.8183 | CRITICAL
10 | W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Closed | Repair Component | HIGH | 0.9 | 1 | 18 | 1121256 | 504565.2 | 100913.04 | 201826.08 | 302739.12 | 98.6706 | CRITICAL
11 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Closed | Repair Component | HIGH | 0.9 | 1 | 18 | 1109300 | 499185 | 99837 | 199674 | 299511 | 98.5229 | CRITICAL
12 | W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Closed | Repair Component | HIGH | 0.9 | 1 | 18 | 1058312 | 476240.4 | 95248.08 | 190496.16 | 285744.24 | 98.3752 | CRITICAL
13 | W019 | R003 | Drilling | Well Control | Bit Wear | Mud Engineering | Closed | Adjust Drilling Parameters | HIGH | 0.8 | 1 | 18 | 1187467 | 474986.8 | 94997.36 | 189994.72 | 284992.08 | 98.2275 | CRITICAL
14 | W007 | R001 | Drilling | Well Control | Bit Wear | Directional Drilling | Closed | Condition Hole | HIGH | 0.8 | 1 | 18 | 1154940 | 461976 | 92395.2 | 184790.4 | 277185.6 | 98.0798 | CRITICAL
15 | W020 | R003 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | Closed | OEM Inspection | HIGH | 0.9 | 1 | 18 | 1023187 | 460434.15 | 92086.83 | 184173.66 | 276260.49 | 97.9321 | CRITICAL
16 | W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Closed | Air Freight Materials | MEDIUM | 0.6 | 1 | 24 | 1534504 | 460351.2 | 92070.24 | 184140.48 | 276210.72 | 97.7843 | CRITICAL
17 | W050 | R004 | Drilling | Lost Circulation | Bit Wear | Operator | Open | Run Fishing Tools | HIGH | 0.8 | 1 | 8 | 568521 | 454816.8 | 90963.36 | 181926.72 | 272890.08 | 97.6366 | CRITICAL
18 | W050 | R004 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Open | Mobilize Supply Vessel | MEDIUM | 0.6 | 1 | 12 | 757335 | 454401 | 90880.2 | 181760.4 | 272640.6 | 97.4889 | CRITICAL
19 | W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | In Progress | Condition Hole | HIGH | 0.8 | 1 | 18 | 735612 | 441367.2 | 88273.44 | 176546.88 | 264820.32 | 97.3412 | CRITICAL
20 | W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Open | Replace Equipment | HIGH | 0.9 | 1 | 8 | 488048 | 439243.2 | 87848.64 | 175697.28 | 263545.92 | 97.1935 | CRITICAL
21 | W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | In Progress | Repair Component | HIGH | 0.9 | 1 | 12 | 632370 | 426849.75 | 85369.95 | 170739.9 | 256109.85 | 97.0458 | CRITICAL
22 | W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Open | Replace Equipment | HIGH | 0.9 | 1 | 8 | 456648 | 410983.2 | 82196.64 | 164393.28 | 246589.92 | 96.8981 | CRITICAL
23 | W036 | R002 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Closed | Preventive Maintenance | HIGH | 0.9 | 1 | 18 | 871177 | 392029.65 | 78405.93 | 156811.86 | 235217.79 | 96.7504 | CRITICAL
24 | W027 | R002 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Open | Condition Hole | HIGH | 0.8 | 1 | 8 | 488768 | 391014.4 | 78202.88 | 156405.76 | 234608.64 | 96.6027 | CRITICAL
25 | W034 | R001 | Drilling | Fishing Operation | Formation Instability | Operator | Closed | Adjust Drilling Parameters | MEDIUM | 0.65 | 1 | 18 | 1178555 | 383030.375 | 76606.075 | 153212.15 | 229818.225 | 96.4549 | CRITICAL

## Controllability
Controllability | Addressability_Factor | NPT_Events | NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Target_Savings_USD
HIGH | 0.9 | 150 | 950 | 47398680 | 27028748.7 | 10811499.48
HIGH | 0.8 | 95 | 632 | 31618144 | 14778909.8 | 5911563.92
MEDIUM | 0.6 | 132 | 762 | 37972204 | 13356802.5 | 5342721
MEDIUM | 0.65 | 118 | 620 | 29443712 | 11528665.3625 | 4611466.145
LOW | 0.3 | 161 | 942 | 46884003 | 8554027.8 | 3421611.12
MEDIUM | 0.7 | 21 | 102 | 4833435 | 1817464.425 | 726985.77

## Scenario_Assumptions
Scenario | Savings_Rate_on_Addressable_Impact | Interpretation
Conservative | 0.2 | Limited improvement / cautious execution
Target | 0.4 | Realistic operational improvement program
Stretch | 0.6 | Aggressive improvement with strong execution

## Data_Quality
Check | Value
NPT rows | 677
Missing Root Cause | 0
Missing Responsible Party | 0
Missing Action Status | 0
Missing Corrective Action | 0
Negative Total Impact | 0
Negative Duration | 0
Total Impact Reconciliation | 0