## Executive_Summary
Metric | Value
NPT Events | 677
Strategic Actions | 502
Action Reduction | 175
NPT Hours | 4008
Total Economic Impact USD | 198150178
Target Savings USD | 33583985.43
Critical Strategic Actions | 4
High Strategic Actions | 6
Affected Wells | 50
Affected Rigs | 4

## Strategic_Action_Register
Strategic_Action_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Corrective_Action | NPT_Events | Affected_Wells | Affected_Rigs | Baseline_NPT_Hours | Direct_NPT_Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Avg_Duration_hr | Action_Status | Impact_Score | NPT_Hours_Score | Frequency_Score | Priority_Score | Priority | Addressability_Factor | Actionability_Factor | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | KPI | Target_NPT_Reduction_pct | Target_NPT_Hours | KPI_Baseline | KPI_Target | Implementation_Horizon | Monitoring_Frequency | Action_Rank
SA-0033 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 3 | 3 | 2 | 38 | 765833 | 1234524 | 2000357 | 12.6667 | Open | 98.7456 | 100 | 60 | 91.3728 | CRITICAL | 0.8 | 1 | 1600285.6 | 320057.12 | 640114.24 | 960171.36 | NPT Hours + ROP | 0.4 | 22.8 | 38 | 22.8 | 0-30 Days | Weekly | 1
SA-0108 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | 3 | 3 | 3 | 36 | 728750 | 1297018 | 2025768 | 12 | Closed | 100 | 94.7368 | 60 | 90.4211 | CRITICAL | 0.6 | 0.5 | 607730.4 | 121546.08 | 243092.16 | 364638.24 | Logistics NPT Hours | 0.4 | 21.6 | 36 | 21.6 | 0-30 Days | Weekly | 2
SA-0036 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | 2 | 2 | 2 | 32 | 643333 | 1352053 | 1995386 | 16 | In Progress | 98.5002 | 84.2105 | 40 | 82.5133 | CRITICAL | 0.9 | 0.75 | 1346885.55 | 269377.11 | 538754.22 | 808131.33 | Mechanical NPT Hours | 0.4 | 19.2 | 32 | 19.2 | 0-30 Days | Weekly | 3
SA-0135 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 32 | 643333 | 1343195 | 1986528 | 16 | Open | 98.063 | 84.2105 | 40 | 82.2946 | CRITICAL | 0.9 | 1 | 1787875.2 | 357575.04 | 715150.08 | 1072725.12 | Mechanical NPT Hours | 0.4 | 19.2 | 32 | 19.2 | 0-30 Days | Weekly | 4
SA-0426 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | 2 | 2 | 2 | 30 | 590000 | 1334964 | 1924964 | 15 | In Progress | 95.0239 | 78.9474 | 40 | 79.1962 | HIGH | 0.3 | 0.75 | 433116.9 | 86623.38 | 173246.76 | 259870.14 | Weather NPT Hours | 0.35 | 19.5 | 30 | 19.5 | 31-90 Days | Weekly | 5
SA-0275 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | 4 | 4 | 2 | 28 | 544166 | 889814 | 1433980 | 7 | In Progress | 70.787 | 73.6842 | 80 | 73.4988 | HIGH | 0.6 | 0.75 | 645291 | 129058.2 | 258116.4 | 387174.6 | Logistics NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 6
SA-0149 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 3 | 3 | 26 | 517916 | 1032154 | 1550070 | 8.6667 | In Progress | 76.5176 | 68.4211 | 60 | 70.7851 | HIGH | 0.65 | 0.75 | 755659.125 | 151131.825 | 302263.65 | 453395.475 | NPT Hours + ROP | 0.35 | 16.9 | 26 | 16.9 | 31-90 Days | Weekly | 7
SA-0092 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 2 | 2 | 26 | 519583 | 1168225 | 1687808 | 13 | Open | 83.3169 | 68.4211 | 40 | 70.1848 | HIGH | 0.9 | 1 | 1519027.2 | 303805.44 | 607610.88 | 911416.32 | Mechanical NPT Hours | 0.35 | 16.9 | 26 | 16.9 | 31-90 Days | Weekly | 8
SA-0164 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | 2 | 2 | 2 | 28 | 540000 | 1066675 | 1606675 | 14 | In Progress | 79.3119 | 73.6842 | 40 | 69.7612 | HIGH | 0.9 | 0.75 | 1084505.625 | 216901.125 | 433802.25 | 650703.375 | Mechanical NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 9
SA-0031 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | 3 | 3 | 3 | 28 | 561666 | 810093 | 1371759 | 9.3333 | In Progress | 67.7155 | 73.6842 | 60 | 67.963 | HIGH | 0.3 | 0.75 | 308645.775 | 61729.155 | 123458.31 | 185187.465 | Weather NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 10
SA-0048 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | 3 | 3 | 1 | 24 | 460000 | 872986 | 1332986 | 8 | Closed | 65.8015 | 63.1579 | 60 | 63.8481 | MEDIUM | 0.8 | 0.5 | 533194.4 | 106638.88 | 213277.76 | 319916.64 | NPT Hours + ROP | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 11
SA-0182 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 2 | 1 | 24 | 480000 | 995042 | 1475042 | 12 | Closed | 72.814 | 63.1579 | 40 | 63.3544 | MEDIUM | 0.6 | 0.5 | 442512.6 | 88502.52 | 177005.04 | 265507.56 | Logistics NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 12
SA-0423 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | 3 | 3 | 3 | 26 | 510833 | 735512 | 1246345 | 8.6667 | Open | 61.5246 | 68.4211 | 60 | 63.2886 | MEDIUM | 0.3 | 1 | 373903.5 | 74780.7 | 149561.4 | 224342.1 | Weather NPT Hours | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 13
SA-0160 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 2 | 1 | 22 | 440000 | 882159 | 1322159 | 7.3333 | In Progress | 65.267 | 57.8947 | 60 | 62.0019 | MEDIUM | 0.65 | 0.75 | 644552.5125 | 128910.5025 | 257821.005 | 386731.5075 | NPT Hours + ROP | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 14
SA-0088 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | 2 | 2 | 1 | 24 | 475000 | 941581 | 1416581 | 12 | Closed | 69.9281 | 63.1579 | 40 | 61.9114 | MEDIUM | 0.9 | 0.5 | 637461.45 | 127492.29 | 254984.58 | 382476.87 | Mechanical NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 15
SA-0122 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | 2 | 2 | 1 | 26 | 498333 | 839821 | 1338154 | 13 | In Progress | 66.0566 | 68.4211 | 40 | 61.5546 | MEDIUM | 0.3 | 0.75 | 301084.65 | 60216.93 | 120433.86 | 180650.79 | Weather NPT Hours | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 16
SA-0034 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | 4 | 4 | 2 | 22 | 446666 | 667061 | 1113727 | 5.5 | Open | 54.978 | 57.8947 | 80 | 60.8574 | MEDIUM | 0.9 | 1 | 1002354.3 | 200470.86 | 400941.72 | 601412.58 | Mechanical NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 17
SA-0222 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 1 | 22 | 440000 | 957755 | 1397755 | 11 | Closed | 68.9988 | 57.8947 | 40 | 59.8678 | MEDIUM | 0.8 | 0.5 | 559102 | 111820.4 | 223640.8 | 335461.2 | NPT Hours + ROP | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 18
SA-0109 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | 2 | 2 | 2 | 28 | 551666 | 594279 | 1145945 | 14 | Closed | 56.5684 | 73.6842 | 40 | 58.3895 | MEDIUM | 0.65 | 0.5 | 372432.125 | 74486.425 | 148972.85 | 223459.275 | NPT Hours + ROP | 0.25 | 21 | 28 | 21 | 91-180 Days | Weekly | 19
SA-0080 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | 2 | 2 | 2 | 26 | 508333 | 696290 | 1204623 | 13 | Closed | 59.465 | 68.4211 | 40 | 58.2588 | MEDIUM | 0.8 | 0.5 | 481849.2 | 96369.84 | 192739.68 | 289109.52 | NPT Hours + ROP | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 20
SA-0064 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | 4 | 4 | 2 | 22 | 426666 | 568889 | 995555 | 5.5 | In Progress | 49.1446 | 57.8947 | 80 | 57.9407 | MEDIUM | 0.3 | 0.75 | 223999.875 | 44799.975 | 89599.95 | 134399.925 | Weather NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 21
SA-0032 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 3 | 3 | 2 | 22 | 441666 | 645962 | 1087628 | 7.3333 | In Progress | 53.6897 | 57.8947 | 60 | 56.2133 | MEDIUM | 0.9 | 0.75 | 734148.9 | 146829.78 | 293659.56 | 440489.34 | Mechanical NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 22
SA-0042 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 2 | 2 | 2 | 20 | 385833 | 826420 | 1212253 | 10 | In Progress | 59.8417 | 52.6316 | 40 | 53.7103 | MEDIUM | 0.9 | 0.75 | 818270.775 | 163654.155 | 327308.31 | 490962.465 | Mechanical NPT Hours | 0.25 | 15 | 20 | 15 | 91-180 Days | Weekly | 23
SA-0056 | Weather | Lightning | Lightning | Weather | Suspend Operations | 5 | 5 | 3 | 16 | 317915 | 517569 | 835484 | 3.2 | In Progress | 41.2428 | 42.1053 | 100 | 53.253 | MEDIUM | 0.3 | 0.75 | 187983.9 | 37596.78 | 75193.56 | 112790.34 | Weather NPT Hours | 0.25 | 12 | 16 | 12 | 91-180 Days | Weekly | 24
SA-0404 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Expedite Shipment | 1 | 1 | 1 | 24 | 460000 | 763810 | 1223810 | 24 | In Progress | 60.4121 | 63.1579 | 20 | 53.1534 | MEDIUM | 0.6 | 0.75 | 550714.5 | 110142.9 | 220285.8 | 330428.7 | Logistics NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 25
SA-0214 | Weather | Lightning | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 24 | 480000 | 674701 | 1154701 | 24 | Closed | 57.0007 | 63.1579 | 20 | 51.4477 | MEDIUM | 0.3 | 0.5 | 173205.15 | 34641.03 | 69282.06 | 103923.09 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 26
SA-0018 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | 2 | 2 | 2 | 24 | 467500 | 492320 | 959820 | 12 | In Progress | 47.3805 | 63.1579 | 40 | 50.6376 | MEDIUM | 0.3 | 0.75 | 215959.5 | 43191.9 | 86383.8 | 129575.7 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 27
SA-0293 | Weather | Heavy Rain | Storm | Weather | Resume Operations | 1 | 1 | 1 | 24 | 490000 | 614657 | 1104657 | 24 | Closed | 54.5303 | 63.1579 | 20 | 50.2125 | MEDIUM | 0.3 | 0.5 | 165698.55 | 33139.71 | 66279.42 | 99419.13 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 28
SA-0147 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | 2 | 2 | 2 | 20 | 405833 | 618606 | 1024439 | 10 | Closed | 50.5704 | 52.6316 | 40 | 49.0747 | LOW | 0.65 | 0.5 | 332942.675 | 66588.535 | 133177.07 | 199765.605 | NPT Hours + ROP | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 29
SA-0104 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | 4 | 4 | 3 | 16 | 311665 | 496610 | 808275 | 4 | Open | 39.8997 | 42.1053 | 80 | 48.5814 | LOW | 0.65 | 1 | 525378.75 | 105075.75 | 210151.5 | 315227.25 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 30
SA-0431 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | 2 | 2 | 2 | 18 | 360000 | 705290 | 1065290 | 9 | Open | 52.587 | 47.3684 | 40 | 48.504 | LOW | 0.6 | 1 | 639174 | 127834.8 | 255669.6 | 383504.4 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 31
SA-0464 | Weather | Poor Visibility | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 18 | 367500 | 851850 | 1219350 | 18 | Closed | 60.192 | 47.3684 | 20 | 48.3065 | LOW | 0.3 | 0.5 | 182902.5 | 36580.5 | 73161 | 109741.5 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 32
SA-0066 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 3 | 3 | 1 | 16 | 306665 | 637880 | 944545 | 5.3333 | Closed | 46.6265 | 42.1053 | 60 | 47.9448 | LOW | 0.6 | 0.5 | 283363.5 | 56672.7 | 113345.4 | 170018.1 | Logistics NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 33
SA-0393 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 2 | 2 | 1 | 20 | 383333 | 561038 | 944371 | 10 | Closed | 46.6179 | 52.6316 | 40 | 47.0984 | LOW | 0.9 | 0.5 | 424966.95 | 84993.39 | 169986.78 | 254980.17 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 34
SA-0086 | Drilling | Well Control | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 18 | 356250 | 798690 | 1154940 | 18 | Closed | 57.0125 | 47.3684 | 20 | 46.7168 | LOW | 0.8 | 0.5 | 461976 | 92395.2 | 184790.4 | 277185.6 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 35
SA-0210 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 3 | 2 | 2 | 18 | 354999 | 474535 | 829534 | 6 | In Progress | 40.9491 | 47.3684 | 60 | 46.6851 | LOW | 0.8 | 0.75 | 497720.4 | 99544.08 | 199088.16 | 298632.24 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 36
SA-0260 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 16 | 317500 | 736254 | 1053754 | 8 | Closed | 52.0175 | 42.1053 | 40 | 46.6403 | LOW | 0.3 | 0.5 | 158063.1 | 31612.62 | 63225.24 | 94837.86 | Weather NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 37
SA-0065 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 3 | 2 | 1 | 16 | 306666 | 582800 | 889466 | 5.3333 | Closed | 43.9076 | 42.1053 | 60 | 46.5854 | LOW | 0.9 | 0.5 | 400259.7 | 80051.94 | 160103.88 | 240155.82 | Mechanical NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 38
SA-0264 | Personnel | Crew Change | Medical Emergency | Medical Team | Medical Clearance | 1 | 1 | 1 | 18 | 367500 | 774135 | 1141635 | 18 | Closed | 56.3557 | 47.3684 | 20 | 46.3884 | LOW | 0.6 | 0.5 | 342490.5 | 68498.1 | 136996.2 | 205494.3 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 39
SA-0024 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 1 | 1 | 18 | 356250 | 753050 | 1109300 | 18 | Closed | 54.7595 | 47.3684 | 20 | 45.5903 | LOW | 0.9 | 0.5 | 499185 | 99837 | 199674 | 299511 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 40
SA-0138 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 2 | 2 | 2 | 20 | 385833 | 495197 | 881030 | 10 | Closed | 43.4912 | 52.6316 | 40 | 45.5351 | LOW | 0.9 | 0.5 | 396463.5 | 79292.7 | 158585.4 | 237878.1 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 41
SA-0374 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 2 | 2 | 2 | 22 | 437916 | 362099 | 800015 | 11 | Closed | 39.4919 | 57.8947 | 40 | 45.1144 | LOW | 0.9 | 0.5 | 360006.75 | 72001.35 | 144002.7 | 216004.05 | Mechanical NPT Hours | 0.15 | 18.7 | 22 | 18.7 | >180 Days | Weekly | 42
SA-0203 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 24 | 490000 | 397460 | 887460 | 24 | Open | 43.8086 | 63.1579 | 20 | 44.8517 | LOW | 0.6 | 1 | 532476 | 106495.2 | 212990.4 | 319485.6 | Logistics NPT Hours | 0.15 | 20.4 | 24 | 20.4 | >180 Days | Weekly | 43
SA-0225 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 18 | 360000 | 663187 | 1023187 | 18 | Closed | 50.5086 | 47.3684 | 20 | 43.4648 | LOW | 0.9 | 0.5 | 460434.15 | 92086.83 | 184173.66 | 276260.49 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 44
SA-0304 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | 3 | 3 | 2 | 14 | 269999 | 527973 | 797972 | 4.6667 | Open | 39.3911 | 36.8421 | 60 | 42.7482 | LOW | 0.8 | 1 | 638377.6 | 127675.52 | 255351.04 | 383026.56 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 45
SA-0130 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 3 | 3 | 2 | 18 | 349999 | 300526 | 650525 | 6 | Open | 32.1125 | 47.3684 | 60 | 42.2668 | LOW | 0.65 | 1 | 422841.25 | 84568.25 | 169136.5 | 253704.75 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 46
SA-0150 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 2 | 2 | 1 | 16 | 326666 | 538360 | 865026 | 8 | In Progress | 42.7011 | 42.1053 | 40 | 41.9821 | LOW | 0.6 | 0.75 | 389261.7 | 77852.34 | 155704.68 | 233557.02 | Logistics NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 47
SA-0218 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 2 | 2 | 16 | 316666 | 546892 | 863558 | 8 | Closed | 42.6287 | 42.1053 | 40 | 41.9459 | LOW | 0.65 | 0.5 | 280656.35 | 56131.27 | 112262.54 | 168393.81 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 48
SA-0047 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | 3 | 3 | 3 | 14 | 280833 | 462346 | 743179 | 4.6667 | Open | 36.6863 | 36.8421 | 60 | 41.3958 | LOW | 0.3 | 1 | 222953.7 | 44590.74 | 89181.48 | 133772.22 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 49
SA-0050 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 3 | 1 | 16 | 306666 | 372009 | 678675 | 5.3333 | Open | 33.5021 | 42.1053 | 60 | 41.3826 | LOW | 0.65 | 1 | 441138.75 | 88227.75 | 176455.5 | 264683.25 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 50
SA-0246 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 18 | 345000 | 573898 | 918898 | 18 | Closed | 45.3605 | 47.3684 | 20 | 40.8908 | LOW | 0.6 | 0.5 | 275669.4 | 55133.88 | 110267.76 | 165401.64 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 51
SA-0378 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | 2 | 2 | 2 | 20 | 398333 | 293688 | 692021 | 10 | Closed | 34.1609 | 52.6316 | 40 | 40.8699 | LOW | 0.8 | 0.5 | 276808.4 | 55361.68 | 110723.36 | 166085.04 | NPT Hours + ROP | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 52
SA-0301 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 18 | 345000 | 565252 | 910252 | 18 | In Progress | 44.9337 | 47.3684 | 20 | 40.6774 | LOW | 0.8 | 0.75 | 546151.2 | 109230.24 | 218460.48 | 327690.72 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 53
SA-0229 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 20 | 390000 | 291870 | 681870 | 10 | Open | 33.6598 | 52.6316 | 40 | 40.6194 | LOW | 0.9 | 1 | 613683 | 122736.6 | 245473.2 | 368209.8 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 54
SA-0126 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | 3 | 3 | 2 | 12 | 236666 | 520254 | 756920 | 4 | Open | 37.3646 | 31.5789 | 60 | 40.156 | LOW | 0.8 | 1 | 605536 | 121107.2 | 242214.4 | 363321.6 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 55
SA-0432 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 18 | 345000 | 503296 | 848296 | 18 | Open | 41.8753 | 47.3684 | 20 | 39.1482 | LOW | 0.9 | 1 | 763466.4 | 152693.28 | 305386.56 | 458079.84 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 56
SA-0316 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | 2 | 2 | 2 | 18 | 355000 | 316484 | 671484 | 9 | Closed | 33.1471 | 47.3684 | 40 | 38.7841 | LOW | 0.3 | 0.5 | 100722.6 | 20144.52 | 40289.04 | 60433.56 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 57
SA-0179 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | 3 | 2 | 2 | 12 | 233333 | 454582 | 687915 | 4 | Closed | 33.9582 | 31.5789 | 60 | 38.4528 | LOW | 0.6 | 0.5 | 206374.5 | 41274.9 | 82549.8 | 123824.7 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 58
SA-0352 | Weather | Lightning | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 18 | 367500 | 445857 | 813357 | 18 | Closed | 40.1506 | 47.3684 | 20 | 38.2858 | LOW | 0.3 | 0.5 | 122003.55 | 24400.71 | 48801.42 | 73202.13 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 59
SA-0091 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | 2 | 2 | 2 | 16 | 321666 | 379930 | 701596 | 8 | Closed | 34.6336 | 42.1053 | 40 | 37.9484 | LOW | 0.8 | 0.5 | 280638.4 | 56127.68 | 112255.36 | 168383.04 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 60
SA-0161 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | 2 | 2 | 2 | 16 | 310000 | 389182 | 699182 | 8 | Closed | 34.5144 | 42.1053 | 40 | 37.8888 | LOW | 0.65 | 0.5 | 227234.15 | 45446.83 | 90893.66 | 136340.49 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 61
SA-0013 | Weather | High Waves | Lightning | Weather | Resume Operations | 2 | 2 | 2 | 14 | 282500 | 479621 | 762121 | 7 | Closed | 37.6213 | 36.8421 | 40 | 37.8633 | LOW | 0.3 | 0.5 | 114318.15 | 22863.63 | 45727.26 | 68590.89 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 62
SA-0095 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 18 | 356250 | 426483 | 782733 | 18 | Closed | 38.6388 | 47.3684 | 20 | 37.5299 | LOW | 0.6 | 0.5 | 234819.9 | 46963.98 | 93927.96 | 140891.94 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 63
SA-0453 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 18 | 345000 | 418285 | 763285 | 18 | Closed | 37.6788 | 47.3684 | 20 | 37.0499 | LOW | 0.7 | 0.5 | 267149.75 | 53429.95 | 106859.9 | 160289.85 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 64
SA-0299 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | Crew Replacement | 1 | 1 | 1 | 18 | 367500 | 388821 | 756321 | 18 | In Progress | 37.335 | 47.3684 | 20 | 36.878 | LOW | 0.6 | 0.75 | 340344.45 | 68068.89 | 136137.78 | 204206.67 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 65
SA-0115 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | 3 | 3 | 3 | 12 | 238749 | 365010 | 603759 | 4 | Open | 29.804 | 31.5789 | 60 | 36.3757 | LOW | 0.3 | 1 | 181127.7 | 36225.54 | 72451.08 | 108676.62 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 66
SA-0442 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Condition Hole | 1 | 1 | 1 | 18 | 345000 | 390612 | 735612 | 18 | In Progress | 36.3127 | 47.3684 | 20 | 36.3669 | LOW | 0.8 | 0.75 | 441367.2 | 88273.44 | 176546.88 | 264820.32 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 67
SA-0317 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 18 | 345000 | 380594 | 725594 | 18 | Closed | 35.8182 | 47.3684 | 20 | 36.1196 | LOW | 0.8 | 0.5 | 290237.6 | 58047.52 | 116095.04 | 174142.56 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 68
SA-0364 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | 2 | 2 | 1 | 16 | 306666 | 304611 | 611277 | 8 | In Progress | 30.1751 | 42.1053 | 40 | 35.7191 | LOW | 0.9 | 0.75 | 412611.975 | 82522.395 | 165044.79 | 247567.185 | Mechanical NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 69
SA-0132 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | 3 | 3 | 2 | 12 | 237499 | 332937 | 570436 | 4 | Open | 28.159 | 31.5789 | 60 | 35.5532 | LOW | 0.8 | 1 | 456348.8 | 91269.76 | 182539.52 | 273809.28 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 70
SA-0273 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 1 | 16 | 306666 | 297182 | 603848 | 8 | In Progress | 29.8083 | 42.1053 | 40 | 35.5358 | LOW | 0.65 | 0.75 | 294375.9 | 58875.18 | 117750.36 | 176625.54 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 71
SA-0350 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | 2 | 2 | 2 | 14 | 275833 | 386541 | 662374 | 7 | Closed | 32.6974 | 36.8421 | 40 | 35.4013 | LOW | 0.3 | 0.5 | 99356.1 | 19871.22 | 39742.44 | 59613.66 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 72
SA-0361 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 2 | 12 | 239999 | 484268 | 724267 | 6 | Open | 35.7527 | 31.5789 | 40 | 35.35 | LOW | 0.65 | 1 | 470773.55 | 94154.71 | 188309.42 | 282464.13 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 73
SA-0017 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 3 | 3 | 2 | 12 | 242499 | 317760 | 560259 | 4 | In Progress | 27.6566 | 31.5789 | 60 | 35.302 | LOW | 0.9 | 0.75 | 378174.825 | 75634.965 | 151269.93 | 226904.895 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 74
SA-0028 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | 2 | 2 | 1 | 14 | 277083 | 376455 | 653538 | 7 | In Progress | 32.2612 | 36.8421 | 40 | 35.1833 | LOW | 0.8 | 0.75 | 392122.8 | 78424.56 | 156849.12 | 235273.68 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 75
SA-0490 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 18 | 360000 | 314096 | 674096 | 18 | Closed | 33.2761 | 47.3684 | 20 | 34.8486 | LOW | 0.8 | 0.5 | 269638.4 | 53927.68 | 107855.36 | 161783.04 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 76
SA-0010 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | 3 | 3 | 2 | 12 | 242499 | 292812 | 535311 | 4 | Open | 26.4251 | 31.5789 | 60 | 34.6862 | LOW | 0.3 | 1 | 160593.3 | 32118.66 | 64237.32 | 96355.98 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 77
SA-0006 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | 2 | 2 | 2 | 14 | 283333 | 349479 | 632812 | 7 | Closed | 31.2381 | 36.8421 | 40 | 34.6717 | LOW | 0.3 | 0.5 | 94921.8 | 18984.36 | 37968.72 | 56953.08 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 78
SA-0153 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | 2 | 2 | 2 | 14 | 278750 | 341823 | 620573 | 7 | Closed | 30.634 | 36.8421 | 40 | 34.3696 | LOW | 0.6 | 0.5 | 186171.9 | 37234.38 | 74468.76 | 111703.14 | Personnel NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 79
SA-0005 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | 3 | 3 | 1 | 12 | 244999 | 274737 | 519736 | 4 | Closed | 25.6562 | 31.5789 | 60 | 34.3018 | LOW | 0.7 | 0.5 | 181907.6 | 36381.52 | 72763.04 | 109144.56 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 80
SA-0292 | Weather | High Waves | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 12 | 245000 | 580843 | 825843 | 12 | In Progress | 40.7669 | 31.5789 | 20 | 33.8571 | LOW | 0.3 | 0.75 | 185814.675 | 37162.935 | 74325.87 | 111488.805 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 81
SA-0058 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | 2 | 2 | 1 | 12 | 230000 | 432865 | 662865 | 6 | Open | 32.7217 | 31.5789 | 40 | 33.8345 | LOW | 0.9 | 1 | 596578.5 | 119315.7 | 238631.4 | 357947.1 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 82
SA-0044 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 14 | 275833 | 314795 | 590628 | 7 | Closed | 29.1558 | 36.8421 | 40 | 33.6305 | LOW | 0.9 | 0.5 | 265782.6 | 53156.52 | 106313.04 | 159469.56 | Mechanical NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 83
SA-0176 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 2 | 2 | 14 | 275000 | 315044 | 590044 | 7 | Open | 29.1269 | 36.8421 | 40 | 33.6161 | LOW | 0.65 | 1 | 383528.6 | 76705.72 | 153411.44 | 230117.16 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 84
SA-0051 | Weather | Lightning | Lightning | Weather | Wait on Weather | 2 | 2 | 1 | 14 | 268333 | 320404 | 588737 | 7 | In Progress | 29.0624 | 36.8421 | 40 | 33.5838 | LOW | 0.3 | 0.75 | 132465.825 | 26493.165 | 52986.33 | 79479.495 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 85
SA-0400 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | 2 | 2 | 2 | 12 | 236666 | 406159 | 642825 | 6 | Open | 31.7324 | 31.5789 | 40 | 33.3399 | LOW | 0.65 | 1 | 417836.25 | 83567.25 | 167134.5 | 250701.75 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 86
SA-0180 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 3 | 3 | 3 | 10 | 200833 | 341199 | 542032 | 3.3333 | In Progress | 26.7569 | 26.3158 | 60 | 33.2732 | LOW | 0.65 | 0.75 | 264240.6 | 52848.12 | 105696.24 | 158544.36 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 87
SA-0139 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 554806 | 799806 | 12 | Closed | 39.4816 | 31.5789 | 20 | 33.2145 | LOW | 0.8 | 0.5 | 319922.4 | 63984.48 | 127968.96 | 191953.44 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 88
SA-0481 | Personnel | Crew Change | Crew Rotation | Rig Management | Medical Clearance | 1 | 1 | 1 | 18 | 367500 | 236304 | 603804 | 18 | Closed | 29.8062 | 47.3684 | 20 | 33.1136 | LOW | 0.6 | 0.5 | 181141.2 | 36228.24 | 72456.48 | 108684.72 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 89
SA-0338 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 2 | 2 | 10 | 201666 | 487332 | 688998 | 5 | In Progress | 34.0117 | 26.3158 | 40 | 32.9006 | LOW | 0.9 | 0.75 | 465073.65 | 93014.73 | 186029.46 | 279044.19 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 90
SA-0290 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 539466 | 784466 | 12 | Closed | 38.7244 | 31.5789 | 20 | 32.8359 | LOW | 0.8 | 0.5 | 313786.4 | 62757.28 | 125514.56 | 188271.84 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 91
SA-0074 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | 2 | 2 | 2 | 12 | 234999 | 378680 | 613679 | 6 | In Progress | 30.2936 | 31.5789 | 40 | 32.6205 | LOW | 0.3 | 0.75 | 138077.775 | 27615.555 | 55231.11 | 82846.665 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 92
SA-0011 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | 2 | 2 | 2 | 10 | 199166 | 463374 | 662540 | 5 | Open | 32.7056 | 26.3158 | 40 | 32.2475 | LOW | 0.3 | 1 | 198762 | 39752.4 | 79504.8 | 119257.2 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 93
SA-0045 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | 2 | 2 | 1 | 12 | 244999 | 347986 | 592985 | 6 | Closed | 29.2721 | 31.5789 | 40 | 32.1097 | LOW | 0.3 | 0.5 | 88947.75 | 17789.55 | 35579.1 | 53368.65 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 94
SA-0171 | Drilling | Stuck Pipe | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 12 | 245000 | 508399 | 753399 | 12 | Closed | 37.1908 | 31.5789 | 20 | 32.0691 | LOW | 0.8 | 0.5 | 301359.6 | 60271.92 | 120543.84 | 180815.76 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 95
SA-0325 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 10 | 196666 | 457574 | 654240 | 5 | Open | 32.2959 | 26.3158 | 40 | 32.0427 | LOW | 0.3 | 1 | 196272 | 39254.4 | 78508.8 | 117763.2 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 96
SA-0382 | Weather | High Waves | Strong Wind | Marine Operations | Resume Operations | 1 | 1 | 1 | 18 | 360000 | 200297 | 560297 | 18 | Open | 27.6585 | 47.3684 | 20 | 32.0398 | LOW | 0.3 | 1 | 168089.1 | 33617.82 | 67235.64 | 100853.46 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 97
SA-0030 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 2 | 2 | 12 | 234999 | 331197 | 566196 | 6 | Open | 27.9497 | 31.5789 | 40 | 31.4485 | LOW | 0.9 | 1 | 509576.4 | 101915.28 | 203830.56 | 305745.84 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 98
SA-0237 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 10 | 203333 | 426701 | 630034 | 5 | Closed | 31.101 | 26.3158 | 40 | 31.4452 | LOW | 0.7 | 0.5 | 220511.9 | 44102.38 | 88204.76 | 132307.14 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 99
SA-0251 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | 2 | 2 | 1 | 14 | 277083 | 222114 | 499197 | 7 | Open | 24.6424 | 36.8421 | 40 | 31.3738 | LOW | 0.8 | 1 | 399357.6 | 79871.52 | 159743.04 | 239614.56 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 100
SA-0419 | Weather | Lightning | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 12 | 230000 | 493028 | 723028 | 12 | In Progress | 35.6916 | 31.5789 | 20 | 31.3195 | LOW | 0.3 | 0.75 | 162681.3 | 32536.26 | 65072.52 | 97608.78 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 101
SA-0125 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 199166 | 421566 | 620732 | 5 | In Progress | 30.6418 | 26.3158 | 40 | 31.2156 | LOW | 0.65 | 0.75 | 302606.85 | 60521.37 | 121042.74 | 181564.11 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 102
SA-0421 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | 2 | 2 | 1 | 12 | 229999 | 320012 | 550011 | 6 | Closed | 27.1507 | 31.5789 | 40 | 31.0491 | LOW | 0.8 | 0.5 | 220004.4 | 44000.88 | 88001.76 | 132002.64 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 103
SA-0402 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 1 | 12 | 229999 | 319959 | 549958 | 6 | Open | 27.1481 | 31.5789 | 40 | 31.0477 | LOW | 0.65 | 1 | 357472.7 | 71494.54 | 142989.08 | 214483.62 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 104
SA-0007 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | 2 | 2 | 1 | 12 | 244999 | 276910 | 521909 | 6 | Closed | 25.7635 | 31.5789 | 40 | 30.3554 | LOW | 0.8 | 0.5 | 208763.6 | 41752.72 | 83505.44 | 125258.16 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 105
SA-0266 | Weather | Lightning | Storm | Weather | Resume Operations | 1 | 1 | 1 | 12 | 245000 | 431874 | 676874 | 12 | Closed | 33.4132 | 31.5789 | 20 | 30.1803 | LOW | 0.3 | 0.5 | 101531.1 | 20306.22 | 40612.44 | 60918.66 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 106
SA-0302 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | 3 | 3 | 2 | 10 | 194166 | 218892 | 413058 | 3.3333 | Open | 20.3902 | 26.3158 | 60 | 30.0898 | LOW | 0.3 | 1 | 123917.4 | 24783.48 | 49566.96 | 74350.44 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 107
SA-0001 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | 2 | 2 | 2 | 10 | 199166 | 375778 | 574944 | 5 | Open | 28.3815 | 26.3158 | 40 | 30.0855 | LOW | 0.6 | 1 | 344966.4 | 68993.28 | 137986.56 | 206979.84 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 108
SA-0336 | Weather | High Waves | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 12 | 230000 | 429330 | 659330 | 12 | Closed | 32.5472 | 31.5789 | 20 | 29.7473 | LOW | 0.3 | 0.5 | 98899.5 | 19779.9 | 39559.8 | 59339.7 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 109
SA-0337 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 12 | 230000 | 418094 | 648094 | 12 | Closed | 31.9925 | 31.5789 | 20 | 29.4699 | LOW | 0.9 | 0.5 | 291642.3 | 58328.46 | 116656.92 | 174985.38 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 110
SA-0015 | Weather | High Waves | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 12 | 245000 | 394548 | 639548 | 12 | Closed | 31.5706 | 31.5789 | 20 | 29.259 | LOW | 0.3 | 0.5 | 95932.2 | 19186.44 | 38372.88 | 57559.32 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 111
SA-0368 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 12 | 230000 | 407608 | 637608 | 12 | Closed | 31.4749 | 31.5789 | 20 | 29.2111 | LOW | 0.6 | 0.5 | 191282.4 | 38256.48 | 76512.96 | 114769.44 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 112
SA-0455 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 12 | 230000 | 403320 | 633320 | 12 | Closed | 31.2632 | 31.5789 | 20 | 29.1053 | LOW | 0.6 | 0.5 | 189996 | 37999.2 | 75998.4 | 113997.6 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 113
SA-0425 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 196666 | 337978 | 534644 | 5 | Closed | 26.3922 | 26.3158 | 40 | 29.0908 | LOW | 0.65 | 0.5 | 173759.3 | 34751.86 | 69503.72 | 104255.58 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 114
SA-0366 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | 2 | 2 | 1 | 12 | 229999 | 237442 | 467441 | 6 | Closed | 23.0748 | 31.5789 | 40 | 29.0111 | LOW | 0.3 | 0.5 | 70116.15 | 14023.23 | 28046.46 | 42069.69 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 115
SA-0469 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 12 | 240000 | 374455 | 614455 | 12 | Closed | 30.332 | 31.5789 | 20 | 28.6397 | LOW | 0.6 | 0.5 | 184336.5 | 36867.3 | 73734.6 | 110601.9 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 116
SA-0501 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 12 | 245000 | 368627 | 613627 | 12 | Closed | 30.2911 | 31.5789 | 20 | 28.6192 | LOW | 0.8 | 0.5 | 245450.8 | 49090.16 | 98180.32 | 147270.48 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 117
SA-0224 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 12 | 240000 | 366765 | 606765 | 12 | Closed | 29.9523 | 31.5789 | 20 | 28.4499 | LOW | 0.6 | 0.5 | 182029.5 | 36405.9 | 72811.8 | 109217.7 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 118
SA-0004 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 10 | 201666 | 303664 | 505330 | 5 | Closed | 24.9451 | 26.3158 | 40 | 28.3673 | LOW | 0.6 | 0.5 | 151599 | 30319.8 | 60639.6 | 90959.4 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 119
SA-0129 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | 2 | 2 | 2 | 10 | 201666 | 288567 | 490233 | 5 | Closed | 24.1999 | 26.3158 | 40 | 27.9947 | LOW | 0.3 | 0.5 | 73534.95 | 14706.99 | 29413.98 | 44120.97 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 120
SA-0330 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | 2 | 2 | 1 | 12 | 229999 | 191770 | 421769 | 6 | In Progress | 20.8202 | 31.5789 | 40 | 27.8838 | LOW | 0.6 | 0.75 | 189796.05 | 37959.21 | 75918.42 | 113877.63 | Personnel NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 121
SA-0103 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 2 | 2 | 1 | 8 | 153333 | 372524 | 525857 | 4 | Open | 25.9584 | 21.0526 | 40 | 27.295 | LOW | 0.65 | 1 | 341807.05 | 68361.41 | 136722.82 | 205084.23 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 122
SA-0111 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 10 | 195416 | 263218 | 458634 | 5 | Open | 22.64 | 26.3158 | 40 | 27.2147 | LOW | 0.9 | 1 | 412770.6 | 82554.12 | 165108.24 | 247662.36 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 123
SA-0314 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 8 | 156666 | 354270 | 510936 | 4 | Open | 25.2218 | 21.0526 | 40 | 26.9267 | LOW | 0.6 | 1 | 306561.6 | 61312.32 | 122624.64 | 183936.96 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 124
SA-0106 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 154583 | 343057 | 497640 | 4 | Closed | 24.5655 | 21.0526 | 40 | 26.5985 | LOW | 0.3 | 0.5 | 74646 | 14929.2 | 29858.4 | 44787.6 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 125
SA-0385 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 12 | 240000 | 291067 | 531067 | 12 | Closed | 26.2156 | 31.5789 | 20 | 26.5815 | LOW | 0.8 | 0.5 | 212426.8 | 42485.36 | 84970.72 | 127456.08 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 126
SA-0441 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | 2 | 2 | 2 | 8 | 160833 | 335439 | 496272 | 4 | In Progress | 24.498 | 21.0526 | 40 | 26.5648 | LOW | 0.3 | 0.75 | 111661.2 | 22332.24 | 44664.48 | 66996.72 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 127
SA-0255 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | 2 | 2 | 2 | 10 | 192916 | 237182 | 430098 | 5 | In Progress | 21.2314 | 26.3158 | 40 | 26.5104 | LOW | 0.3 | 0.75 | 96772.05 | 19354.41 | 38708.82 | 58063.23 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 128
SA-0212 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 278344 | 523344 | 12 | Closed | 25.8344 | 31.5789 | 20 | 26.3909 | LOW | 0.65 | 0.5 | 170086.8 | 34017.36 | 68034.72 | 102052.08 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 129
SA-0184 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 2 | 2 | 8 | 154999 | 149294 | 304293 | 2.6667 | Open | 15.0211 | 21.0526 | 60 | 25.8263 | LOW | 0.65 | 1 | 197790.45 | 39558.09 | 79116.18 | 118674.27 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 130
SA-0291 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 2 | 1 | 10 | 204166 | 193759 | 397925 | 5 | In Progress | 19.6432 | 26.3158 | 40 | 25.7163 | LOW | 0.65 | 0.75 | 193988.4375 | 38797.6875 | 77595.375 | 116393.0625 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 131
SA-0240 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 12 | 230000 | 265392 | 495392 | 12 | Closed | 24.4545 | 31.5789 | 20 | 25.7009 | LOW | 0.9 | 0.5 | 222926.4 | 44585.28 | 89170.56 | 133755.84 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 132
SA-0306 | Weather | Lightning | High Waves | Weather | Suspend Operations | 1 | 1 | 1 | 12 | 230000 | 258903 | 488903 | 12 | Closed | 24.1342 | 31.5789 | 20 | 25.5408 | LOW | 0.3 | 0.5 | 73335.45 | 14667.09 | 29334.18 | 44001.27 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 133
SA-0137 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | 2 | 2 | 2 | 10 | 201666 | 188549 | 390215 | 5 | In Progress | 19.2626 | 26.3158 | 40 | 25.526 | LOW | 0.3 | 0.75 | 87798.375 | 17559.675 | 35119.35 | 52679.025 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 134
SA-0206 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 8 | 158332 | 281116 | 439448 | 4 | In Progress | 21.6929 | 21.0526 | 40 | 25.1622 | LOW | 0.9 | 0.75 | 296627.4 | 59325.48 | 118650.96 | 177976.44 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 135
SA-0083 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 2 | 8 | 159166 | 271976 | 431142 | 4 | Closed | 21.2829 | 21.0526 | 40 | 24.9572 | LOW | 0.8 | 0.5 | 172456.8 | 34491.36 | 68982.72 | 103474.08 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 136
SA-0117 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 12 | 237500 | 223755 | 461255 | 12 | Closed | 22.7694 | 31.5789 | 20 | 24.8584 | LOW | 0.6 | 0.5 | 138376.5 | 27675.3 | 55350.6 | 83025.9 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 137
SA-0131 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | 2 | 2 | 2 | 8 | 158332 | 268310 | 426642 | 4 | Closed | 21.0608 | 21.0526 | 40 | 24.8462 | LOW | 0.3 | 0.5 | 63996.3 | 12799.26 | 25598.52 | 38397.78 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 138
SA-0077 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | 2 | 2 | 2 | 10 | 199166 | 161598 | 360764 | 5 | Closed | 17.8088 | 26.3158 | 40 | 24.7991 | LOW | 0.6 | 0.5 | 108229.2 | 21645.84 | 43291.68 | 64937.52 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 139
SA-0052 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 198333 | 161890 | 360223 | 5 | Open | 17.782 | 26.3158 | 40 | 24.7858 | LOW | 0.65 | 1 | 234144.95 | 46828.99 | 93657.98 | 140486.97 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 140
SA-0041 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | 2 | 2 | 2 | 8 | 160833 | 262056 | 422889 | 4 | Closed | 20.8755 | 21.0526 | 40 | 24.7535 | LOW | 0.9 | 0.5 | 190300.05 | 38060.01 | 76120.02 | 114180.03 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 141
SA-0186 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 2 | 2 | 8 | 158333 | 264510 | 422843 | 4 | Closed | 20.8732 | 21.0526 | 40 | 24.7524 | LOW | 0.8 | 0.5 | 169137.2 | 33827.44 | 67654.88 | 101482.32 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 142
SA-0169 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 2 | 2 | 2 | 8 | 160832 | 254020 | 414852 | 4 | Closed | 20.4788 | 21.0526 | 40 | 24.5552 | LOW | 0.9 | 0.5 | 186683.4 | 37336.68 | 74673.36 | 112010.04 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 143
SA-0248 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | 2 | 2 | 2 | 8 | 160833 | 252168 | 413001 | 4 | Closed | 20.3874 | 21.0526 | 40 | 24.5095 | LOW | 0.6 | 0.5 | 123900.3 | 24780.06 | 49560.12 | 74340.18 | Personnel NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 144
SA-0146 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | 2 | 2 | 1 | 10 | 204166 | 138905 | 343071 | 5 | Closed | 16.9354 | 26.3158 | 40 | 24.3624 | LOW | 0.9 | 0.5 | 154381.95 | 30876.39 | 61752.78 | 92629.17 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 145
SA-0496 | Drilling | Lost Circulation | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 163333 | 405188 | 568521 | 8 | Open | 28.0645 | 21.0526 | 20 | 24.348 | LOW | 0.8 | 1 | 454816.8 | 90963.36 | 181926.72 | 272890.08 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 146
SA-0178 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 160000 | 393128 | 553128 | 8 | Closed | 27.3046 | 21.0526 | 20 | 23.9681 | LOW | 0.9 | 0.5 | 248907.6 | 49781.52 | 99563.04 | 149344.56 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 147
SA-0061 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | 2 | 2 | 1 | 10 | 191666 | 135250 | 326916 | 5 | Closed | 16.1379 | 26.3158 | 40 | 23.9637 | LOW | 0.6 | 0.5 | 98074.8 | 19614.96 | 39229.92 | 58844.88 | Personnel NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 148
SA-0070 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 157083 | 226281 | 383364 | 4 | In Progress | 18.9244 | 21.0526 | 40 | 23.778 | LOW | 0.3 | 0.75 | 86256.9 | 17251.38 | 34502.76 | 51754.14 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 149
SA-0424 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 155833 | 227263 | 383096 | 4 | Closed | 18.9111 | 21.0526 | 40 | 23.7714 | LOW | 0.3 | 0.5 | 57464.4 | 11492.88 | 22985.76 | 34478.64 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 150
SA-0029 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 2 | 2 | 8 | 160832 | 221794 | 382626 | 4 | Closed | 18.8879 | 21.0526 | 40 | 23.7598 | LOW | 0.6 | 0.5 | 114787.8 | 22957.56 | 45915.12 | 68872.68 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 151
SA-0046 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 2 | 8 | 158333 | 212501 | 370834 | 4 | Closed | 18.3058 | 21.0526 | 40 | 23.4687 | LOW | 0.8 | 0.5 | 148333.6 | 29666.72 | 59333.44 | 89000.16 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 152
SA-0231 | Weather | High Waves | Heavy Rain | Marine Operations | Suspend Operations | 1 | 1 | 1 | 8 | 160000 | 364772 | 524772 | 8 | Open | 25.9048 | 21.0526 | 20 | 23.2682 | LOW | 0.3 | 1 | 157431.6 | 31486.32 | 62972.64 | 94458.96 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 153
SA-0334 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 363755 | 517088 | 8 | Closed | 25.5255 | 21.0526 | 20 | 23.0786 | LOW | 0.9 | 0.5 | 232689.6 | 46537.92 | 93075.84 | 139613.76 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 154
SA-0096 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 158333 | 357164 | 515497 | 8 | Closed | 25.447 | 21.0526 | 20 | 23.0393 | LOW | 0.9 | 0.5 | 231973.65 | 46394.73 | 92789.46 | 139184.19 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 155
SA-0420 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | 2 | 2 | 1 | 8 | 153332 | 193661 | 346993 | 4 | In Progress | 17.129 | 21.0526 | 40 | 22.8803 | LOW | 0.3 | 0.75 | 78073.425 | 15614.685 | 31229.37 | 46844.055 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 156
SA-0313 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 12 | 230000 | 150405 | 380405 | 12 | Closed | 18.7783 | 31.5789 | 20 | 22.8628 | LOW | 0.65 | 0.5 | 123631.625 | 24726.325 | 49452.65 | 74178.975 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 157
SA-0467 | Weather | Heavy Rain | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 12 | 245000 | 133994 | 378994 | 12 | Closed | 18.7087 | 31.5789 | 20 | 22.828 | LOW | 0.3 | 0.5 | 56849.1 | 11369.82 | 22739.64 | 34109.46 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 158
SA-0059 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | 2 | 2 | 1 | 8 | 153333 | 190713 | 344046 | 4 | In Progress | 16.9835 | 21.0526 | 40 | 22.8075 | LOW | 0.3 | 0.75 | 77410.35 | 15482.07 | 30964.14 | 46446.21 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 159
SA-0071 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 347820 | 501153 | 8 | Closed | 24.7389 | 21.0526 | 20 | 22.6852 | LOW | 0.9 | 0.5 | 225518.85 | 45103.77 | 90207.54 | 135311.31 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 160
SA-0367 | Weather | Strong Wind | High Waves | Weather | Wait on Weather | 1 | 1 | 1 | 8 | 153333 | 347209 | 500542 | 8 | Closed | 24.7088 | 21.0526 | 20 | 22.6702 | LOW | 0.3 | 0.5 | 75081.3 | 15016.26 | 30032.52 | 45048.78 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 161
SA-0039 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | 2 | 2 | 2 | 6 | 119999 | 282138 | 402137 | 3 | Closed | 19.8511 | 15.7895 | 40 | 22.6624 | LOW | 0.6 | 0.5 | 120641.1 | 24128.22 | 48256.44 | 72384.66 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 162
SA-0310 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 153333 | 342295 | 495628 | 8 | Open | 24.4662 | 21.0526 | 20 | 22.5489 | LOW | 0.65 | 1 | 322158.2 | 64431.64 | 128863.28 | 193294.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 163
SA-0221 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | 2 | 2 | 1 | 8 | 160000 | 170172 | 330172 | 4 | Closed | 16.2986 | 21.0526 | 40 | 22.4651 | LOW | 0.8 | 0.5 | 132068.8 | 26413.76 | 52827.52 | 79241.28 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 164
SA-0216 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 2 | 2 | 8 | 156666 | 173136 | 329802 | 4 | Closed | 16.2803 | 21.0526 | 40 | 22.456 | LOW | 0.65 | 0.5 | 107185.65 | 21437.13 | 42874.26 | 64311.39 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 165
SA-0215 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 12 | 240000 | 123301 | 363301 | 12 | Open | 17.934 | 31.5789 | 20 | 22.4407 | LOW | 0.9 | 1 | 326970.9 | 65394.18 | 130788.36 | 196182.54 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 166
SA-0401 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 12 | 230000 | 132340 | 362340 | 12 | Closed | 17.8865 | 31.5789 | 20 | 22.417 | LOW | 0.8 | 0.5 | 144936 | 28987.2 | 57974.4 | 86961.6 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 167
SA-0085 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | 2 | 2 | 2 | 8 | 155832 | 161232 | 317064 | 4 | In Progress | 15.6515 | 21.0526 | 40 | 22.1416 | LOW | 0.3 | 0.75 | 71339.4 | 14267.88 | 28535.76 | 42803.64 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 168
SA-0055 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 12 | 230000 | 121023 | 351023 | 12 | Closed | 17.3279 | 31.5789 | 20 | 22.1376 | LOW | 0.9 | 0.5 | 157960.35 | 31592.07 | 63184.14 | 94776.21 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 169
SA-0433 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Air Freight Materials | 1 | 1 | 1 | 8 | 153333 | 317647 | 470980 | 8 | Closed | 23.2495 | 21.0526 | 20 | 21.9405 | LOW | 0.6 | 0.5 | 141294 | 28258.8 | 56517.6 | 84776.4 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 170
SA-0471 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 8 | 160000 | 306975 | 466975 | 8 | Closed | 23.0518 | 21.0526 | 20 | 21.8417 | LOW | 0.8 | 0.5 | 186790 | 37358 | 74716 | 112074 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 171
SA-0166 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | 2 | 2 | 1 | 8 | 160000 | 143591 | 303591 | 4 | Closed | 14.9865 | 21.0526 | 40 | 21.809 | LOW | 0.8 | 0.5 | 121436.4 | 24287.28 | 48574.56 | 72861.84 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 172
SA-0254 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 158333 | 298315 | 456648 | 8 | Open | 22.542 | 21.0526 | 20 | 21.5868 | LOW | 0.9 | 1 | 410983.2 | 82196.64 | 164393.28 | 246589.92 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 173
SA-0349 | Weather | Heavy Rain | Lightning | Marine Operations | Suspend Operations | 1 | 1 | 1 | 8 | 163333 | 288692 | 452025 | 8 | Closed | 22.3138 | 21.0526 | 20 | 21.4727 | LOW | 0.3 | 0.5 | 67803.75 | 13560.75 | 27121.5 | 40682.25 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 174
SA-0156 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 8 | 155000 | 133274 | 288274 | 4 | Closed | 14.2304 | 21.0526 | 40 | 21.431 | LOW | 0.6 | 0.5 | 86482.2 | 17296.44 | 34592.88 | 51889.32 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 175
SA-0487 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 8 | 153333 | 289177 | 442510 | 8 | Closed | 21.8441 | 21.0526 | 20 | 21.2378 | LOW | 0.8 | 0.5 | 177004 | 35400.8 | 70801.6 | 106202.4 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 176
SA-0082 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 286906 | 440239 | 8 | In Progress | 21.732 | 21.0526 | 20 | 21.1818 | LOW | 0.9 | 0.75 | 297161.325 | 59432.265 | 118864.53 | 178296.795 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 177
SA-0417 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | 2 | 2 | 2 | 6 | 119999 | 221517 | 341516 | 3 | Closed | 16.8586 | 15.7895 | 40 | 21.1661 | LOW | 0.3 | 0.5 | 51227.4 | 10245.48 | 20490.96 | 30736.44 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 178
SA-0322 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 279943 | 433276 | 8 | In Progress | 21.3882 | 21.0526 | 20 | 21.0099 | LOW | 0.9 | 0.75 | 292461.3 | 58492.26 | 116984.52 | 175476.78 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 179
SA-0357 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 163333 | 267513 | 430846 | 8 | Closed | 21.2683 | 21.0526 | 20 | 20.9499 | LOW | 0.9 | 0.5 | 193880.7 | 38776.14 | 77552.28 | 116328.42 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 180
SA-0311 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 276056 | 429389 | 8 | In Progress | 21.1964 | 21.0526 | 20 | 20.914 | LOW | 0.9 | 0.75 | 289837.575 | 57967.515 | 115935.03 | 173902.545 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 181
SA-0407 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | 2 | 2 | 2 | 6 | 119999 | 211261 | 331260 | 3 | Closed | 16.3523 | 15.7895 | 40 | 20.913 | LOW | 0.8 | 0.5 | 132504 | 26500.8 | 53001.6 | 79502.4 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 182
SA-0429 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | 2 | 2 | 1 | 6 | 114999 | 212937 | 327936 | 3 | In Progress | 16.1882 | 15.7895 | 40 | 20.831 | LOW | 0.6 | 0.75 | 147571.2 | 29514.24 | 59028.48 | 88542.72 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 183
SA-0296 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 2 | 1 | 6 | 122499 | 195352 | 317851 | 3 | Closed | 15.6904 | 15.7895 | 40 | 20.582 | LOW | 0.9 | 0.5 | 143032.95 | 28606.59 | 57213.18 | 85819.77 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 184
SA-0280 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 260743 | 414076 | 8 | Closed | 20.4404 | 21.0526 | 20 | 20.536 | LOW | 0.7 | 0.5 | 144926.6 | 28985.32 | 57970.64 | 86955.96 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 185
SA-0295 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 163333 | 249120 | 412453 | 8 | Closed | 20.3603 | 21.0526 | 20 | 20.496 | LOW | 0.9 | 0.5 | 185603.85 | 37120.77 | 74241.54 | 111362.31 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 186
SA-0482 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 8 | 163333 | 248690 | 412023 | 8 | Closed | 20.3391 | 21.0526 | 20 | 20.4853 | LOW | 0.65 | 0.5 | 133907.475 | 26781.495 | 53562.99 | 80344.485 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 187
SA-0457 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 2 | 1 | 8 | 160000 | 85257 | 245257 | 4 | In Progress | 12.1069 | 21.0526 | 40 | 20.3692 | LOW | 0.6 | 0.75 | 110365.65 | 22073.13 | 44146.26 | 66219.39 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 188
SA-0062 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 252476 | 405809 | 8 | Closed | 20.0324 | 21.0526 | 20 | 20.332 | LOW | 0.9 | 0.5 | 182614.05 | 36522.81 | 73045.62 | 109568.43 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 189
SA-0256 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 6 | 117499 | 189151 | 306650 | 3 | In Progress | 15.1375 | 15.7895 | 40 | 20.3056 | LOW | 0.3 | 0.75 | 68996.25 | 13799.25 | 27598.5 | 41397.75 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 190
SA-0309 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | 2 | 2 | 2 | 6 | 117499 | 186352 | 303851 | 3 | Closed | 14.9993 | 15.7895 | 40 | 20.2365 | LOW | 0.3 | 0.5 | 45577.65 | 9115.53 | 18231.06 | 27346.59 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 191
SA-0406 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 8 | 163333 | 237483 | 400816 | 8 | Closed | 19.7859 | 21.0526 | 20 | 20.2087 | LOW | 0.9 | 0.5 | 180367.2 | 36073.44 | 72146.88 | 108220.32 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 192
SA-0454 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 2 | 1 | 6 | 114999 | 187090 | 302089 | 3 | In Progress | 14.9123 | 15.7895 | 40 | 20.193 | LOW | 0.9 | 0.75 | 203910.075 | 40782.015 | 81564.03 | 122346.045 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 193
SA-0244 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 153333 | 239111 | 392444 | 8 | Closed | 19.3726 | 21.0526 | 20 | 20.0021 | LOW | 0.6 | 0.5 | 117733.2 | 23546.64 | 47093.28 | 70639.92 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 194
SA-0172 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | 2 | 2 | 2 | 6 | 120833 | 168955 | 289788 | 3 | Open | 14.3051 | 15.7895 | 40 | 19.8894 | LOW | 0.3 | 1 | 86936.4 | 17387.28 | 34774.56 | 52161.84 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 195
SA-0075 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 153333 | 232289 | 385622 | 8 | Closed | 19.0358 | 21.0526 | 20 | 19.8337 | LOW | 0.6 | 0.5 | 115686.6 | 23137.32 | 46274.64 | 69411.96 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 196
SA-0475 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 8 | 160000 | 218432 | 378432 | 8 | Open | 18.6809 | 21.0526 | 20 | 19.6562 | LOW | 0.9 | 1 | 340588.8 | 68117.76 | 136235.52 | 204353.28 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 197
SA-0480 | Drilling | Hole Cleaning | Differential Sticking | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 163333 | 205525 | 368858 | 8 | Closed | 18.2083 | 21.0526 | 20 | 19.4199 | LOW | 0.8 | 0.5 | 147543.2 | 29508.64 | 59017.28 | 88525.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 198
SA-0435 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 8 | 153333 | 214639 | 367972 | 8 | Closed | 18.1646 | 21.0526 | 20 | 19.3981 | LOW | 0.65 | 0.5 | 119590.9 | 23918.18 | 47836.36 | 71754.54 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 199
SA-0192 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 2 | 2 | 6 | 117499 | 151879 | 269378 | 3 | In Progress | 13.2976 | 15.7895 | 40 | 19.3856 | LOW | 0.65 | 0.75 | 131321.775 | 26264.355 | 52528.71 | 78793.065 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 200
SA-0434 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Condition Hole | 1 | 1 | 1 | 8 | 153333 | 210689 | 364022 | 8 | In Progress | 17.9696 | 21.0526 | 20 | 19.3006 | LOW | 0.8 | 0.75 | 218413.2 | 43682.64 | 87365.28 | 131047.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 201
SA-0354 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Air Freight Materials | 1 | 1 | 1 | 6 | 122500 | 301536 | 424036 | 6 | Closed | 20.9321 | 15.7895 | 20 | 19.2029 | LOW | 0.6 | 0.5 | 127210.8 | 25442.16 | 50884.32 | 76326.48 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 202
SA-0329 | Drilling | Lost Circulation | Differential Sticking | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 153333 | 201314 | 354647 | 8 | Closed | 17.5068 | 21.0526 | 20 | 19.0692 | LOW | 0.8 | 0.5 | 141858.8 | 28371.76 | 56743.52 | 85115.28 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 203
SA-0133 | Weather | Lightning | Lightning | Weather | Resume Operations | 2 | 2 | 2 | 6 | 119999 | 136286 | 256285 | 3 | Closed | 12.6513 | 15.7895 | 40 | 19.0625 | LOW | 0.3 | 0.5 | 38442.75 | 7688.55 | 15377.1 | 23065.65 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 204
SA-0181 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 6 | 120000 | 295691 | 415691 | 6 | Closed | 20.5202 | 15.7895 | 20 | 18.9969 | LOW | 0.6 | 0.5 | 124707.3 | 24941.46 | 49882.92 | 74824.38 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 205
SA-0259 | Logistics | Waiting on Materials | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 8 | 158333 | 193285 | 351618 | 8 | Open | 17.3573 | 21.0526 | 20 | 18.9944 | LOW | 0.6 | 1 | 210970.8 | 42194.16 | 84388.32 | 126582.48 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 206
SA-0089 | Weather | Lightning | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 8 | 158333 | 192897 | 351230 | 8 | In Progress | 17.3381 | 21.0526 | 20 | 18.9848 | LOW | 0.3 | 0.75 | 79026.75 | 15805.35 | 31610.7 | 47416.05 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 207
SA-0495 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 6 | 120000 | 294858 | 414858 | 6 | Closed | 20.479 | 15.7895 | 20 | 18.9764 | LOW | 0.8 | 0.5 | 165943.2 | 33188.64 | 66377.28 | 99565.92 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 208
SA-0502 | Drilling | Stuck Pipe | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 8 | 163333 | 182981 | 346314 | 8 | Closed | 17.0954 | 21.0526 | 20 | 18.8635 | LOW | 0.65 | 0.5 | 112552.05 | 22510.41 | 45020.82 | 67531.23 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 209
SA-0114 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 118750 | 291172 | 409922 | 6 | In Progress | 20.2354 | 15.7895 | 20 | 18.8545 | LOW | 0.8 | 0.75 | 245953.2 | 49190.64 | 98381.28 | 147571.92 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 210
SA-0462 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 8 | 160000 | 185853 | 345853 | 8 | Closed | 17.0727 | 21.0526 | 20 | 18.8521 | LOW | 0.65 | 0.5 | 112402.225 | 22480.445 | 44960.89 | 67441.335 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 211
SA-0315 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 1 | 6 | 114999 | 126753 | 241752 | 3 | In Progress | 11.9338 | 15.7895 | 40 | 18.7038 | LOW | 0.8 | 0.75 | 145051.2 | 29010.24 | 58020.48 | 87030.72 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 212
SA-0116 | Weather | Strong Wind | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 118750 | 279850 | 398600 | 6 | In Progress | 19.6765 | 15.7895 | 20 | 18.5751 | LOW | 0.3 | 0.75 | 89685 | 17937 | 35874 | 53811 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 213
SA-0384 | Drilling | Bit Failure | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 6 | 120000 | 273652 | 393652 | 6 | Closed | 19.4322 | 15.7895 | 20 | 18.453 | LOW | 0.8 | 0.5 | 157460.8 | 31492.16 | 62984.32 | 94476.48 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 214
SA-0492 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 120000 | 270679 | 390679 | 6 | Closed | 19.2855 | 15.7895 | 20 | 18.3796 | LOW | 0.7 | 0.5 | 136737.65 | 27347.53 | 54695.06 | 82042.59 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 215
SA-0470 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 120000 | 270341 | 390341 | 6 | Closed | 19.2688 | 15.7895 | 20 | 18.3712 | LOW | 0.6 | 0.5 | 117102.3 | 23420.46 | 46840.92 | 70261.38 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 216
SA-0287 | Weather | High Waves | Strong Wind | Weather | Resume Operations | 1 | 1 | 1 | 6 | 122500 | 265620 | 388120 | 6 | Open | 19.1592 | 15.7895 | 20 | 18.3164 | LOW | 0.3 | 1 | 116436 | 23287.2 | 46574.4 | 69861.6 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 217
SA-0223 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 160000 | 163949 | 323949 | 8 | Closed | 15.9914 | 21.0526 | 20 | 18.3115 | LOW | 0.6 | 0.5 | 97184.7 | 19436.94 | 38873.88 | 58310.82 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 218
SA-0488 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 272813 | 387813 | 6 | Closed | 19.144 | 15.7895 | 20 | 18.3088 | LOW | 0.9 | 0.5 | 174515.85 | 34903.17 | 69806.34 | 104709.51 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 219
SA-0190 | Weather | Lightning | Strong Wind | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 264246 | 386746 | 6 | Closed | 19.0913 | 15.7895 | 20 | 18.2825 | LOW | 0.3 | 0.5 | 58011.9 | 11602.38 | 23204.76 | 34807.14 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 220
SA-0339 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 169026 | 322359 | 8 | In Progress | 15.9129 | 21.0526 | 20 | 18.2723 | LOW | 0.9 | 0.75 | 217592.325 | 43518.465 | 87036.93 | 130555.395 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 221
SA-0158 | Weather | Strong Wind | Storm | Weather | Resume Operations | 1 | 1 | 1 | 8 | 160000 | 158983 | 318983 | 8 | Open | 15.7463 | 21.0526 | 20 | 18.1889 | LOW | 0.3 | 1 | 95694.9 | 19138.98 | 38277.96 | 57416.94 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 222
SA-0319 | Weather | Strong Wind | Storm | Weather | Suspend Operations | 2 | 2 | 2 | 6 | 116666 | 102380 | 219046 | 3 | Open | 10.813 | 15.7895 | 40 | 18.1433 | LOW | 0.3 | 1 | 65713.8 | 13142.76 | 26285.52 | 39428.28 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 223
SA-0263 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 6 | 122500 | 257837 | 380337 | 6 | Closed | 18.775 | 15.7895 | 20 | 18.1243 | LOW | 0.6 | 0.5 | 114101.1 | 22820.22 | 45640.44 | 68460.66 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 224
SA-0353 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 163333 | 152781 | 316114 | 8 | Closed | 15.6046 | 21.0526 | 20 | 18.1181 | LOW | 0.9 | 0.5 | 142251.3 | 28450.26 | 56900.52 | 85350.78 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 225
SA-0144 | Logistics | Waiting on Boat | Port Congestion | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 255221 | 377721 | 6 | Closed | 18.6458 | 15.7895 | 20 | 18.0598 | LOW | 0.6 | 0.5 | 113316.3 | 22663.26 | 45326.52 | 67989.78 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 226
SA-0267 | Personnel | Medical Evacuation | Medical Emergency | HR | Crew Replacement | 1 | 1 | 1 | 6 | 122500 | 253590 | 376090 | 6 | Closed | 18.5653 | 15.7895 | 20 | 18.0195 | LOW | 0.6 | 0.5 | 112827 | 22565.4 | 45130.8 | 67696.2 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 227
SA-0151 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 253064 | 373064 | 6 | Closed | 18.4159 | 15.7895 | 20 | 17.9448 | LOW | 0.8 | 0.5 | 149225.6 | 29845.12 | 59690.24 | 89535.36 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 228
SA-0272 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 152401 | 305734 | 8 | Closed | 15.0923 | 21.0526 | 20 | 17.8619 | LOW | 0.9 | 0.5 | 137580.3 | 27516.06 | 55032.12 | 82548.18 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 229
SA-0118 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 152314 | 305647 | 8 | Open | 15.088 | 21.0526 | 20 | 17.8598 | LOW | 0.9 | 1 | 275082.3 | 55016.46 | 110032.92 | 165049.38 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 230
SA-0414 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 8 | 163333 | 141844 | 305177 | 8 | Closed | 15.0648 | 21.0526 | 20 | 17.8482 | LOW | 0.65 | 0.5 | 99182.525 | 19836.505 | 39673.01 | 59509.515 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 231
SA-0387 | Drilling | Well Control | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 6 | 115000 | 253781 | 368781 | 6 | Closed | 18.2045 | 15.7895 | 20 | 17.8391 | LOW | 0.65 | 0.5 | 119853.825 | 23970.765 | 47941.53 | 71912.295 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 232
SA-0408 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 122500 | 244320 | 366820 | 6 | Closed | 18.1077 | 15.7895 | 20 | 17.7907 | LOW | 0.9 | 0.5 | 165069 | 33013.8 | 66027.6 | 99041.4 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 233
SA-0185 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 6 | 120000 | 245352 | 365352 | 6 | Open | 18.0352 | 15.7895 | 20 | 17.7545 | LOW | 0.9 | 1 | 328816.8 | 65763.36 | 131526.72 | 197290.08 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 234
SA-0456 | Drilling | Stuck Pipe | Formation Instability | Operator | Condition Hole | 1 | 1 | 1 | 6 | 115000 | 247949 | 362949 | 6 | Closed | 17.9166 | 15.7895 | 20 | 17.6951 | LOW | 0.65 | 0.5 | 117958.425 | 23591.685 | 47183.37 | 70775.055 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 235
SA-0356 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 231858 | 354358 | 6 | Closed | 17.4925 | 15.7895 | 20 | 17.4831 | LOW | 0.6 | 0.5 | 106307.4 | 21261.48 | 42522.96 | 63784.44 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 236
SA-0014 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 122500 | 230529 | 353029 | 6 | In Progress | 17.4269 | 15.7895 | 20 | 17.4503 | LOW | 0.65 | 0.75 | 172101.6375 | 34420.3275 | 68840.655 | 103260.9825 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 237
SA-0449 | Weather | Poor Visibility | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 6 | 115000 | 236890 | 351890 | 6 | Open | 17.3707 | 15.7895 | 20 | 17.4222 | LOW | 0.3 | 1 | 105567 | 21113.4 | 42226.8 | 63340.2 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 238
SA-0076 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 115000 | 236864 | 351864 | 6 | Closed | 17.3694 | 15.7895 | 20 | 17.4215 | LOW | 0.9 | 0.5 | 158338.8 | 31667.76 | 63335.52 | 95003.28 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 239
SA-0143 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 122500 | 226126 | 348626 | 6 | Closed | 17.2096 | 15.7895 | 20 | 17.3416 | LOW | 0.9 | 0.5 | 156881.7 | 31376.34 | 62752.68 | 94129.02 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 240
SA-0333 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 115000 | 233024 | 348024 | 6 | Closed | 17.1799 | 15.7895 | 20 | 17.3268 | LOW | 0.6 | 0.5 | 104407.2 | 20881.44 | 41762.88 | 62644.32 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 241
SA-0324 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 130015 | 283348 | 8 | Closed | 13.9872 | 21.0526 | 20 | 17.3094 | LOW | 0.9 | 0.5 | 127506.6 | 25501.32 | 51002.64 | 76503.96 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 242
SA-0020 | Drilling | Bit Failure | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 118750 | 226214 | 344964 | 6 | Closed | 17.0288 | 15.7895 | 20 | 17.2512 | LOW | 0.8 | 0.5 | 137985.6 | 27597.12 | 55194.24 | 82791.36 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 243
SA-0154 | Weather | Heavy Rain | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 6 | 120000 | 223619 | 343619 | 6 | Closed | 16.9624 | 15.7895 | 20 | 17.218 | LOW | 0.3 | 0.5 | 51542.85 | 10308.57 | 20617.14 | 30925.71 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 244
SA-0236 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 223111 | 343111 | 6 | Closed | 16.9373 | 15.7895 | 20 | 17.2055 | LOW | 0.8 | 0.5 | 137244.4 | 27448.88 | 54897.76 | 82346.64 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 245
SA-0362 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 225265 | 340265 | 6 | Open | 16.7968 | 15.7895 | 20 | 17.1353 | LOW | 0.65 | 1 | 221172.25 | 44234.45 | 88468.9 | 132703.35 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 246
SA-0121 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 1 | 1 | 1 | 8 | 153333 | 121885 | 275218 | 8 | Closed | 13.5859 | 21.0526 | 20 | 17.1087 | LOW | 0.9 | 0.5 | 123848.1 | 24769.62 | 49539.24 | 74308.86 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 247
SA-0217 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 217687 | 337687 | 6 | Closed | 16.6696 | 15.7895 | 20 | 17.0716 | LOW | 0.8 | 0.5 | 135074.8 | 27014.96 | 54029.92 | 81044.88 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 248
SA-0057 | Weather | Heavy Rain | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 222173 | 337173 | 6 | In Progress | 16.6442 | 15.7895 | 20 | 17.0589 | LOW | 0.3 | 0.75 | 75863.925 | 15172.785 | 30345.57 | 45518.355 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 249
SA-0428 | Weather | Heavy Rain | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 220006 | 335006 | 6 | In Progress | 16.5372 | 15.7895 | 20 | 17.0055 | LOW | 0.3 | 0.75 | 75376.35 | 15075.27 | 30150.54 | 45225.81 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 250
SA-0348 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 2 | 1 | 4 | 81666 | 148998 | 230664 | 2 | Closed | 11.3865 | 10.5263 | 40 | 16.8511 | LOW | 0.6 | 0.5 | 69199.2 | 13839.84 | 27679.68 | 41519.52 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 251
SA-0165 | Drilling | Fishing Operation | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 8 | 160000 | 104193 | 264193 | 8 | Closed | 13.0416 | 21.0526 | 20 | 16.8366 | LOW | 0.8 | 0.5 | 105677.2 | 21135.44 | 42270.88 | 63406.32 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 252
SA-0243 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 115000 | 207678 | 322678 | 6 | Closed | 15.9287 | 15.7895 | 20 | 16.7012 | LOW | 0.9 | 0.5 | 145205.1 | 29041.02 | 58082.04 | 87123.06 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 253
SA-0472 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 160000 | 96020 | 256020 | 8 | In Progress | 12.6382 | 21.0526 | 20 | 16.6349 | LOW | 0.9 | 0.75 | 172813.5 | 34562.7 | 69125.4 | 103688.1 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 254
SA-0483 | Drilling | Well Control | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 196965 | 319465 | 6 | Closed | 15.7701 | 15.7895 | 20 | 16.6219 | LOW | 0.8 | 0.5 | 127786 | 25557.2 | 51114.4 | 76671.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 255
SA-0389 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Condition Hole | 1 | 1 | 1 | 6 | 115000 | 202496 | 317496 | 6 | Closed | 15.6729 | 15.7895 | 20 | 16.5733 | LOW | 0.8 | 0.5 | 126998.4 | 25399.68 | 50799.36 | 76199.04 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 256
SA-0145 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | 2 | 2 | 2 | 4 | 80833 | 138489 | 219322 | 2 | In Progress | 10.8266 | 10.5263 | 40 | 16.5712 | LOW | 0.6 | 0.75 | 98694.9 | 19738.98 | 39477.96 | 59216.94 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 257
SA-0068 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | 2 | 2 | 2 | 4 | 77916 | 138622 | 216538 | 2 | Closed | 10.6892 | 10.5263 | 40 | 16.5025 | LOW | 0.3 | 0.5 | 32480.7 | 6496.14 | 12992.28 | 19488.42 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 258
SA-0451 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 115000 | 199093 | 314093 | 6 | Closed | 15.5049 | 15.7895 | 20 | 16.4893 | LOW | 0.6 | 0.5 | 94227.9 | 18845.58 | 37691.16 | 56536.74 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 259
SA-0249 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 196670 | 311670 | 6 | Closed | 15.3853 | 15.7895 | 20 | 16.4295 | LOW | 0.9 | 0.5 | 140251.5 | 28050.3 | 56100.6 | 84150.9 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 260
SA-0298 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 186115 | 308615 | 6 | In Progress | 15.2345 | 15.7895 | 20 | 16.3541 | LOW | 0.6 | 0.75 | 138876.75 | 27775.35 | 55550.7 | 83326.05 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 261
SA-0026 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 118750 | 188958 | 307708 | 6 | Closed | 15.1897 | 15.7895 | 20 | 16.3317 | LOW | 0.65 | 0.5 | 100005.1 | 20001.02 | 40002.04 | 60003.06 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 262
SA-0084 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | 2 | 2 | 2 | 4 | 77916 | 130734 | 208650 | 2 | Closed | 10.2998 | 10.5263 | 40 | 16.3078 | LOW | 0.65 | 0.5 | 67811.25 | 13562.25 | 27124.5 | 40686.75 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 263
SA-0278 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 184818 | 299818 | 6 | Closed | 14.8002 | 15.7895 | 20 | 16.1369 | LOW | 0.8 | 0.5 | 119927.2 | 23985.44 | 47970.88 | 71956.32 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 264
SA-0497 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 174028 | 296528 | 6 | Closed | 14.6378 | 15.7895 | 20 | 16.0557 | LOW | 0.6 | 0.5 | 88958.4 | 17791.68 | 35583.36 | 53375.04 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 265
SA-0100 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 8 | 153333 | 77458 | 230791 | 8 | In Progress | 11.3928 | 21.0526 | 20 | 16.0122 | LOW | 0.65 | 0.75 | 112510.6125 | 22502.1225 | 45004.245 | 67506.3675 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 266
SA-0450 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 178383 | 293383 | 6 | Open | 14.4826 | 15.7895 | 20 | 15.9781 | LOW | 0.9 | 1 | 264044.7 | 52808.94 | 105617.88 | 158426.82 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 267
SA-0359 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 177855 | 292855 | 6 | Closed | 14.4565 | 15.7895 | 20 | 15.9651 | LOW | 0.9 | 0.5 | 131784.75 | 26356.95 | 52713.9 | 79070.85 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 268
SA-0241 | Drilling | Well Control | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 172490 | 287490 | 6 | Closed | 14.1917 | 15.7895 | 20 | 15.8327 | LOW | 0.65 | 0.5 | 93434.25 | 18686.85 | 37373.7 | 56060.55 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 269
SA-0094 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 6 | 118750 | 164765 | 283515 | 6 | Closed | 13.9954 | 15.7895 | 20 | 15.7346 | LOW | 0.9 | 0.5 | 127581.75 | 25516.35 | 51032.7 | 76549.05 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 270
SA-0443 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 159958 | 282458 | 6 | Open | 13.9433 | 15.7895 | 20 | 15.7085 | LOW | 0.9 | 1 | 254212.2 | 50842.44 | 101684.88 | 152527.32 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 271
SA-0043 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | 2 | 2 | 2 | 4 | 80416 | 102981 | 183397 | 2 | Closed | 9.0532 | 10.5263 | 40 | 15.6845 | LOW | 0.6 | 0.5 | 55019.1 | 11003.82 | 22007.64 | 33011.46 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 272
SA-0284 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 154285 | 276785 | 6 | In Progress | 13.6632 | 15.7895 | 20 | 15.5684 | LOW | 0.8 | 0.75 | 166071 | 33214.2 | 66428.4 | 99642.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 273
SA-0199 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 1 | 1 | 6 | 118750 | 154929 | 273679 | 6 | Closed | 13.5099 | 15.7895 | 20 | 15.4918 | LOW | 0.6 | 0.5 | 82103.7 | 16420.74 | 32841.48 | 49262.22 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 274
SA-0289 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | 2 | 2 | 1 | 4 | 81666 | 89838 | 171504 | 2 | Open | 8.4661 | 10.5263 | 40 | 15.391 | LOW | 0.3 | 1 | 51451.2 | 10290.24 | 20580.48 | 30870.72 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 275
SA-0328 | Weather | Poor Visibility | Heavy Rain | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 152059 | 267059 | 6 | In Progress | 13.1831 | 15.7895 | 20 | 15.3284 | LOW | 0.3 | 0.75 | 60088.275 | 12017.655 | 24035.31 | 36052.965 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 276
SA-0281 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 122500 | 144551 | 267051 | 6 | Closed | 13.1827 | 15.7895 | 20 | 15.3282 | LOW | 0.8 | 0.5 | 106820.4 | 21364.08 | 42728.16 | 64092.24 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 277
SA-0399 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 115000 | 150582 | 265582 | 6 | Closed | 13.1102 | 15.7895 | 20 | 15.2919 | LOW | 0.8 | 0.5 | 106232.8 | 21246.56 | 42493.12 | 63739.68 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 278
SA-0494 | Weather | Heavy Rain | Strong Wind | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 120000 | 143523 | 263523 | 6 | Open | 13.0085 | 15.7895 | 20 | 15.2411 | LOW | 0.3 | 1 | 79056.9 | 15811.38 | 31622.76 | 47434.14 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 279
SA-0078 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 145730 | 260730 | 6 | Closed | 12.8707 | 15.7895 | 20 | 15.1722 | LOW | 0.9 | 0.5 | 117328.5 | 23465.7 | 46931.4 | 70397.1 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 280
SA-0175 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 135468 | 257968 | 6 | Closed | 12.7343 | 15.7895 | 20 | 15.104 | LOW | 0.65 | 0.5 | 83839.6 | 16767.92 | 33535.84 | 50303.76 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 281
SA-0253 | Weather | Poor Visibility | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 6 | 118750 | 138221 | 256971 | 6 | In Progress | 12.6851 | 15.7895 | 20 | 15.0794 | LOW | 0.3 | 0.75 | 57818.475 | 11563.695 | 23127.39 | 34691.085 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 282
SA-0227 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | 2 | 2 | 2 | 4 | 80833 | 78042 | 158875 | 2 | Closed | 7.8427 | 10.5263 | 40 | 15.0792 | LOW | 0.6 | 0.5 | 47662.5 | 9532.5 | 19065 | 28597.5 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 283
SA-0196 | Weather | Strong Wind | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 6 | 118750 | 136446 | 255196 | 6 | Closed | 12.5975 | 15.7895 | 20 | 15.0356 | LOW | 0.3 | 0.5 | 38279.4 | 7655.88 | 15311.76 | 22967.64 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 284
SA-0415 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 137040 | 252040 | 6 | In Progress | 12.4417 | 15.7895 | 20 | 14.9577 | LOW | 0.9 | 0.75 | 170127 | 34025.4 | 68050.8 | 102076.2 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 285
SA-0195 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 6 | 118750 | 120704 | 239454 | 6 | In Progress | 11.8204 | 15.7895 | 20 | 14.647 | LOW | 0.9 | 0.75 | 161631.45 | 32326.29 | 64652.58 | 96978.87 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 286
SA-0500 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 116840 | 239340 | 6 | Closed | 11.8148 | 15.7895 | 20 | 14.6442 | LOW | 0.9 | 0.5 | 107703 | 21540.6 | 43081.2 | 64621.8 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 287
SA-0258 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 6 | 118750 | 120114 | 238864 | 6 | In Progress | 11.7913 | 15.7895 | 20 | 14.6325 | LOW | 0.6 | 0.75 | 107488.8 | 21497.76 | 42995.52 | 64493.28 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 288
SA-0395 | Weather | Strong Wind | Lightning | Marine Operations | Resume Operations | 1 | 1 | 1 | 6 | 115000 | 123339 | 238339 | 6 | Closed | 11.7654 | 15.7895 | 20 | 14.6195 | LOW | 0.3 | 0.5 | 35750.85 | 7150.17 | 14300.34 | 21450.51 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 289
SA-0110 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 118750 | 114628 | 233378 | 6 | In Progress | 11.5205 | 15.7895 | 20 | 14.4971 | LOW | 0.9 | 0.75 | 157530.15 | 31506.03 | 63012.06 | 94518.09 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 290
SA-0323 | Personnel | Crew Change | Medical Emergency | HR | Medical Clearance | 1 | 1 | 1 | 6 | 115000 | 117452 | 232452 | 6 | In Progress | 11.4748 | 15.7895 | 20 | 14.4742 | LOW | 0.6 | 0.75 | 104603.4 | 20920.68 | 41841.36 | 62762.04 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 291
SA-0140 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | 2 | 2 | 2 | 4 | 79166 | 50540 | 129706 | 2 | In Progress | 6.4028 | 10.5263 | 40 | 14.3593 | LOW | 0.8 | 0.75 | 77823.6 | 15564.72 | 31129.44 | 46694.16 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 292
SA-0305 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 115000 | 112412 | 227412 | 6 | In Progress | 11.226 | 15.7895 | 20 | 14.3498 | LOW | 0.6 | 0.75 | 102335.4 | 20467.08 | 40934.16 | 61401.24 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 293
SA-0394 | Drilling | Hole Cleaning | Differential Sticking | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 111365 | 226365 | 6 | Closed | 11.1743 | 15.7895 | 20 | 14.324 | LOW | 0.8 | 0.5 | 90546 | 18109.2 | 36218.4 | 54327.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 294
SA-0458 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 6 | 120000 | 106088 | 226088 | 6 | Closed | 11.1606 | 15.7895 | 20 | 14.3171 | LOW | 0.8 | 0.5 | 90435.2 | 18087.04 | 36174.08 | 54261.12 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 295
SA-0416 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 6 | 115000 | 109082 | 224082 | 6 | Closed | 11.0616 | 15.7895 | 20 | 14.2676 | LOW | 0.6 | 0.5 | 67224.6 | 13444.92 | 26889.84 | 40334.76 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 296
SA-0035 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Safety Briefing | 1 | 1 | 1 | 6 | 122500 | 101091 | 223591 | 6 | Closed | 11.0373 | 15.7895 | 20 | 14.2555 | LOW | 0.6 | 0.5 | 67077.3 | 13415.46 | 26830.92 | 40246.38 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 297
SA-0208 | Weather | Heavy Rain | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 81666 | 202290 | 283956 | 4 | Closed | 14.0172 | 10.5263 | 20 | 14.1665 | LOW | 0.3 | 0.5 | 42593.4 | 8518.68 | 17037.36 | 25556.04 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 298
SA-0025 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 118750 | 98071 | 216821 | 6 | Closed | 10.7032 | 15.7895 | 20 | 14.0884 | LOW | 0.6 | 0.5 | 65046.3 | 13009.26 | 26018.52 | 39027.78 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 299
SA-0038 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | Repair Component | 1 | 1 | 1 | 4 | 81666 | 198934 | 280600 | 4 | Closed | 13.8515 | 10.5263 | 20 | 14.0837 | LOW | 0.9 | 0.5 | 126270 | 25254 | 50508 | 75762 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 300
SA-0019 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 198718 | 280384 | 4 | Closed | 13.8409 | 10.5263 | 20 | 14.0783 | LOW | 0.6 | 0.5 | 84115.2 | 16823.04 | 33646.08 | 50469.12 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 301
SA-0202 | Weather | Poor Visibility | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 92594 | 215094 | 6 | Closed | 10.6179 | 15.7895 | 20 | 14.0458 | LOW | 0.3 | 0.5 | 32264.1 | 6452.82 | 12905.64 | 19358.46 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 302
SA-0134 | Personnel | Training | Crew Rotation | Medical Team | Safety Briefing | 1 | 1 | 1 | 6 | 122500 | 90710 | 213210 | 6 | In Progress | 10.5249 | 15.7895 | 20 | 13.9993 | LOW | 0.6 | 0.75 | 95944.5 | 19188.9 | 38377.8 | 57566.7 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 303
SA-0411 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 88110 | 210610 | 6 | In Progress | 10.3966 | 15.7895 | 20 | 13.9351 | LOW | 0.9 | 0.75 | 142161.75 | 28432.35 | 56864.7 | 85297.05 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 304
SA-0194 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 192615 | 274281 | 4 | Closed | 13.5396 | 10.5263 | 20 | 13.9277 | LOW | 0.3 | 0.5 | 41142.15 | 8228.43 | 16456.86 | 24685.29 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 305
SA-0379 | Weather | High Waves | Heavy Rain | Weather | Suspend Operations | 1 | 1 | 1 | 6 | 120000 | 88739 | 208739 | 6 | Closed | 10.3042 | 15.7895 | 20 | 13.8889 | LOW | 0.3 | 0.5 | 31310.85 | 6262.17 | 12524.34 | 18786.51 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 306
SA-0262 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 1 | 1 | 4 | 81666 | 189343 | 271009 | 4 | Closed | 13.3781 | 10.5263 | 20 | 13.8469 | LOW | 0.7 | 0.5 | 94853.15 | 18970.63 | 37941.26 | 56911.89 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 307
SA-0474 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 120000 | 86494 | 206494 | 6 | Closed | 10.1934 | 15.7895 | 20 | 13.8335 | LOW | 0.9 | 0.5 | 92922.3 | 18584.46 | 37168.92 | 55753.38 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 308
SA-0247 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 90497 | 205497 | 6 | In Progress | 10.1442 | 15.7895 | 20 | 13.8089 | LOW | 0.9 | 0.75 | 138710.475 | 27742.095 | 55484.19 | 83226.285 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 309
SA-0340 | Weather | High Waves | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 191641 | 268307 | 4 | In Progress | 13.2447 | 10.5263 | 20 | 13.7802 | LOW | 0.3 | 0.75 | 60369.075 | 12073.815 | 24147.63 | 36221.445 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 310
SA-0468 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 186247 | 267913 | 4 | Closed | 13.2253 | 10.5263 | 20 | 13.7705 | LOW | 0.9 | 0.5 | 120560.85 | 24112.17 | 48224.34 | 72336.51 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 311
SA-0016 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 185722 | 267388 | 4 | Closed | 13.1993 | 10.5263 | 20 | 13.7576 | LOW | 0.8 | 0.5 | 106955.2 | 21391.04 | 42782.08 | 64173.12 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 312
SA-0269 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 81666 | 185627 | 267293 | 4 | Closed | 13.1947 | 10.5263 | 20 | 13.7552 | LOW | 0.8 | 0.5 | 106917.2 | 21383.44 | 42766.88 | 64150.32 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 313
SA-0294 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 185274 | 266940 | 4 | Closed | 13.1772 | 10.5263 | 20 | 13.7465 | LOW | 0.9 | 0.5 | 120123 | 24024.6 | 48049.2 | 72073.8 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 314
SA-0351 | Weather | High Waves | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 184832 | 266498 | 4 | Closed | 13.1554 | 10.5263 | 20 | 13.7356 | LOW | 0.3 | 0.5 | 39974.7 | 7994.94 | 15989.88 | 23984.82 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 315
SA-0376 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 79166 | 187319 | 266485 | 4 | Closed | 13.1548 | 10.5263 | 20 | 13.7353 | LOW | 0.6 | 0.5 | 79945.5 | 15989.1 | 31978.2 | 47967.3 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 316
SA-0159 | Weather | Heavy Rain | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 80000 | 185590 | 265590 | 4 | Closed | 13.1106 | 10.5263 | 20 | 13.7132 | LOW | 0.3 | 0.5 | 39838.5 | 7967.7 | 15935.4 | 23903.1 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 317
SA-0189 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | Repair Component | 1 | 1 | 1 | 6 | 122500 | 78520 | 201020 | 6 | In Progress | 9.9232 | 15.7895 | 20 | 13.6984 | LOW | 0.9 | 0.75 | 135688.5 | 27137.7 | 54275.4 | 81413.1 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 318
SA-0197 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 118750 | 81777 | 200527 | 6 | Closed | 9.8988 | 15.7895 | 20 | 13.6862 | LOW | 0.65 | 0.5 | 65171.275 | 13034.255 | 26068.51 | 39102.765 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 319
SA-0491 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 183601 | 263601 | 4 | Closed | 13.0124 | 10.5263 | 20 | 13.6641 | LOW | 0.6 | 0.5 | 79080.3 | 15816.06 | 31632.12 | 47448.18 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 320
SA-0326 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 185391 | 262057 | 4 | Closed | 12.9362 | 10.5263 | 20 | 13.626 | LOW | 0.8 | 0.5 | 104822.8 | 20964.56 | 41929.12 | 62893.68 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 321
SA-0209 | Weather | Poor Visibility | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 74361 | 196861 | 6 | Closed | 9.7178 | 15.7895 | 20 | 13.5958 | LOW | 0.3 | 0.5 | 29529.15 | 5905.83 | 11811.66 | 17717.49 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 322
SA-0063 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 183892 | 260558 | 4 | Closed | 12.8622 | 10.5263 | 20 | 13.589 | LOW | 0.8 | 0.5 | 104223.2 | 20844.64 | 41689.28 | 62533.92 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 323
SA-0331 | Drilling | Well Control | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 6 | 115000 | 74266 | 189266 | 6 | Closed | 9.3429 | 15.7895 | 20 | 13.4083 | LOW | 0.65 | 0.5 | 61511.45 | 12302.29 | 24604.58 | 36906.87 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 324
SA-0021 | Drilling | Bit Failure | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 6 | 118750 | 68245 | 186995 | 6 | Open | 9.2308 | 15.7895 | 20 | 13.3523 | LOW | 0.8 | 1 | 149596 | 29919.2 | 59838.4 | 89757.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 325
SA-0245 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 173767 | 250433 | 4 | In Progress | 12.3624 | 10.5263 | 20 | 13.3391 | LOW | 0.9 | 0.75 | 169042.275 | 33808.455 | 67616.91 | 101425.365 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 326
SA-0141 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 122500 | 63732 | 186232 | 6 | Closed | 9.1932 | 15.7895 | 20 | 13.3334 | LOW | 0.9 | 0.5 | 83804.4 | 16760.88 | 33521.76 | 50282.64 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 327
SA-0486 | Weather | High Waves | High Waves | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 70319 | 185319 | 6 | Closed | 9.1481 | 15.7895 | 20 | 13.3109 | LOW | 0.3 | 0.5 | 27797.85 | 5559.57 | 11119.14 | 16678.71 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 328
SA-0177 | Drilling | Stuck Pipe | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 4 | 80000 | 168562 | 248562 | 4 | Open | 12.27 | 10.5263 | 20 | 13.2929 | LOW | 0.8 | 1 | 198849.6 | 39769.92 | 79539.84 | 119309.76 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 329
SA-0027 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 118750 | 64902 | 183652 | 6 | Closed | 9.0658 | 15.7895 | 20 | 13.2697 | LOW | 0.7 | 0.5 | 64278.2 | 12855.64 | 25711.28 | 38566.92 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 330
SA-0073 | Logistics | Delayed Helicopter | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 169001 | 245667 | 4 | Open | 12.1271 | 10.5263 | 20 | 13.2214 | LOW | 0.6 | 1 | 147400.2 | 29480.04 | 58960.08 | 88440.12 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 331
SA-0412 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 161966 | 243632 | 4 | In Progress | 12.0266 | 10.5263 | 20 | 13.1712 | LOW | 0.8 | 0.75 | 146179.2 | 29235.84 | 58471.68 | 87707.52 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 332
SA-0363 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 4 | 76666 | 165696 | 242362 | 4 | Open | 11.964 | 10.5263 | 20 | 13.1399 | LOW | 0.6 | 1 | 145417.2 | 29083.44 | 58166.88 | 87250.32 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 333
SA-0157 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Air Freight Materials | 1 | 1 | 1 | 4 | 80000 | 159783 | 239783 | 4 | Open | 11.8366 | 10.5263 | 20 | 13.0762 | LOW | 0.6 | 1 | 143869.8 | 28773.96 | 57547.92 | 86321.88 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 334
SA-0173 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 154123 | 235789 | 4 | Closed | 11.6395 | 10.5263 | 20 | 12.9776 | LOW | 0.9 | 0.5 | 106105.05 | 21221.01 | 42442.02 | 63663.03 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 335
SA-0081 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 157410 | 234076 | 4 | Closed | 11.5549 | 10.5263 | 20 | 12.9354 | LOW | 0.8 | 0.5 | 93630.4 | 18726.08 | 37452.16 | 56178.24 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 336
SA-0012 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 152013 | 233679 | 4 | Closed | 11.5353 | 10.5263 | 20 | 12.9256 | LOW | 0.6 | 0.5 | 70103.7 | 14020.74 | 28041.48 | 42062.22 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 337
SA-0386 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 153896 | 230562 | 4 | In Progress | 11.3815 | 10.5263 | 20 | 12.8486 | LOW | 0.65 | 0.75 | 112398.975 | 22479.795 | 44959.59 | 67439.385 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 338
SA-0388 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 152544 | 229210 | 4 | Closed | 11.3147 | 10.5263 | 20 | 12.8153 | LOW | 0.9 | 0.5 | 103144.5 | 20628.9 | 41257.8 | 61886.7 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 339
SA-0193 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 146635 | 228301 | 4 | Closed | 11.2698 | 10.5263 | 20 | 12.7928 | LOW | 0.3 | 0.5 | 34245.15 | 6849.03 | 13698.06 | 20547.09 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 340
SA-0187 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 147308 | 227308 | 4 | Closed | 11.2208 | 10.5263 | 20 | 12.7683 | LOW | 0.6 | 0.5 | 68192.4 | 13638.48 | 27276.96 | 40915.44 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 341
SA-0282 | Drilling | Well Control | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 144601 | 226267 | 4 | Closed | 11.1694 | 10.5263 | 20 | 12.7426 | LOW | 0.65 | 0.5 | 73536.775 | 14707.355 | 29414.71 | 44122.065 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 342
SA-0327 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 148435 | 225101 | 4 | Closed | 11.1119 | 10.5263 | 20 | 12.7138 | LOW | 0.65 | 0.5 | 73157.825 | 14631.565 | 29263.13 | 43894.695 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 343
SA-0123 | Drilling | Lost Circulation | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 146588 | 223254 | 4 | Closed | 11.0207 | 10.5263 | 20 | 12.6682 | LOW | 0.8 | 0.5 | 89301.6 | 17860.32 | 35720.64 | 53580.96 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 344
SA-0238 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 80000 | 143184 | 223184 | 4 | Closed | 11.0173 | 10.5263 | 20 | 12.6665 | LOW | 0.9 | 0.5 | 100432.8 | 20086.56 | 40173.12 | 60259.68 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 345
SA-0112 | Weather | Heavy Rain | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 79166 | 143929 | 223095 | 4 | Closed | 11.0129 | 10.5263 | 20 | 12.6643 | LOW | 0.3 | 0.5 | 33464.25 | 6692.85 | 13385.7 | 20078.55 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 346
SA-0413 | Weather | High Waves | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 141093 | 222759 | 4 | In Progress | 10.9963 | 10.5263 | 20 | 12.656 | LOW | 0.3 | 0.75 | 50120.775 | 10024.155 | 20048.31 | 30072.465 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 347
SA-0213 | Weather | Heavy Rain | Heavy Rain | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 138389 | 220055 | 4 | Closed | 10.8628 | 10.5263 | 20 | 12.5893 | LOW | 0.3 | 0.5 | 33008.25 | 6601.65 | 13203.3 | 19804.95 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 348
SA-0205 | Weather | Strong Wind | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 130214 | 211880 | 4 | Closed | 10.4592 | 10.5263 | 20 | 12.3875 | LOW | 0.3 | 0.5 | 31782 | 6356.4 | 12712.8 | 19069.2 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 349
SA-0279 | Drilling | Stuck Pipe | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 132348 | 209014 | 4 | Closed | 10.3178 | 10.5263 | 20 | 12.3168 | LOW | 0.8 | 0.5 | 83605.6 | 16721.12 | 33442.24 | 50163.36 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 350
SA-0283 | Weather | Heavy Rain | Storm | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 127004 | 208670 | 4 | Closed | 10.3008 | 10.5263 | 20 | 12.3083 | LOW | 0.3 | 0.5 | 31300.5 | 6260.1 | 12520.2 | 18780.3 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 351
SA-0344 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 76666 | 128931 | 205597 | 4 | Closed | 10.1491 | 10.5263 | 20 | 12.2324 | LOW | 0.6 | 0.5 | 61679.1 | 12335.82 | 24671.64 | 37007.46 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 352
SA-0489 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 121829 | 201829 | 4 | In Progress | 9.9631 | 10.5263 | 20 | 12.1394 | LOW | 0.6 | 0.75 | 90823.05 | 18164.61 | 36329.22 | 54493.83 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 353
SA-0369 | Weather | Poor Visibility | High Waves | Marine Operations | Suspend Operations | 1 | 1 | 1 | 4 | 76666 | 124855 | 201521 | 4 | Closed | 9.9479 | 10.5263 | 20 | 12.1318 | LOW | 0.3 | 0.5 | 30228.15 | 6045.63 | 12091.26 | 18136.89 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 354
SA-0049 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 120129 | 196795 | 4 | Closed | 9.7146 | 10.5263 | 20 | 12.0152 | LOW | 0.3 | 0.5 | 29519.25 | 5903.85 | 11807.7 | 17711.55 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 355
SA-0342 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 115177 | 191843 | 4 | Open | 9.4701 | 10.5263 | 20 | 11.893 | LOW | 0.8 | 1 | 153474.4 | 30694.88 | 61389.76 | 92084.64 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 356
SA-0499 | Weather | High Waves | Storm | Weather | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 110150 | 191816 | 4 | Closed | 9.4688 | 10.5263 | 20 | 11.8923 | LOW | 0.3 | 0.5 | 28772.4 | 5754.48 | 11508.96 | 17263.44 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 357
SA-0009 | Weather | Lightning | Storm | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 108862 | 190528 | 4 | In Progress | 9.4052 | 10.5263 | 20 | 11.8605 | LOW | 0.3 | 0.75 | 42868.8 | 8573.76 | 17147.52 | 25721.28 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 358
SA-0391 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 112293 | 188959 | 4 | Closed | 9.3278 | 10.5263 | 20 | 11.8218 | LOW | 0.65 | 0.5 | 61411.675 | 12282.335 | 24564.67 | 36847.005 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 359
SA-0097 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 111806 | 188472 | 4 | Closed | 9.3037 | 10.5263 | 20 | 11.8098 | LOW | 0.8 | 0.5 | 75388.8 | 15077.76 | 30155.52 | 45233.28 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 360
SA-0226 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 80000 | 107175 | 187175 | 4 | Closed | 9.2397 | 10.5263 | 20 | 11.7777 | LOW | 0.65 | 0.5 | 60831.875 | 12166.375 | 24332.75 | 36499.125 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 361
SA-0372 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 4 | 79166 | 107969 | 187135 | 4 | Closed | 9.2377 | 10.5263 | 20 | 11.7768 | LOW | 0.9 | 0.5 | 84210.75 | 16842.15 | 33684.3 | 50526.45 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 362
SA-0079 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 4 | 76666 | 107545 | 184211 | 4 | Closed | 9.0934 | 10.5263 | 20 | 11.7046 | LOW | 0.6 | 0.5 | 55263.3 | 11052.66 | 22105.32 | 33157.98 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 363
SA-0257 | Weather | Strong Wind | Heavy Rain | Marine Operations | Suspend Operations | 1 | 1 | 1 | 4 | 79166 | 104081 | 183247 | 4 | Closed | 9.0458 | 10.5263 | 20 | 11.6808 | LOW | 0.3 | 0.5 | 27487.05 | 5497.41 | 10994.82 | 16492.23 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 364
SA-0437 | Drilling | Well Control | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 102592 | 179258 | 4 | Closed | 8.8489 | 10.5263 | 20 | 11.5823 | LOW | 0.65 | 0.5 | 58258.85 | 11651.77 | 23303.54 | 34955.31 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 365
SA-0346 | Drilling | Stuck Pipe | Formation Instability | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 100999 | 177665 | 4 | Closed | 8.7703 | 10.5263 | 20 | 11.543 | LOW | 0.65 | 0.5 | 57741.125 | 11548.225 | 23096.45 | 34644.675 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 366
SA-0060 | Logistics | Waiting on Materials | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 100056 | 176722 | 4 | Closed | 8.7237 | 10.5263 | 20 | 11.5197 | LOW | 0.6 | 0.5 | 53016.6 | 10603.32 | 21206.64 | 31809.96 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 367
SA-0355 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 4 | 81666 | 94096 | 175762 | 4 | In Progress | 8.6763 | 10.5263 | 20 | 11.4961 | LOW | 0.6 | 0.75 | 79092.9 | 15818.58 | 31637.16 | 47455.74 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 368
SA-0228 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 4 | 80000 | 95170 | 175170 | 4 | Closed | 8.6471 | 10.5263 | 20 | 11.4814 | LOW | 0.9 | 0.5 | 78826.5 | 15765.3 | 31530.6 | 47295.9 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 369
SA-0128 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 4 | 76666 | 96663 | 173329 | 4 | Closed | 8.5562 | 10.5263 | 20 | 11.436 | LOW | 0.9 | 0.5 | 77998.05 | 15599.61 | 31199.22 | 46798.83 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 370
SA-0427 | Weather | High Waves | Lightning | Weather | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 95669 | 172335 | 4 | Closed | 8.5071 | 10.5263 | 20 | 11.4115 | LOW | 0.3 | 0.5 | 25850.25 | 5170.05 | 10340.1 | 15510.15 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 371
SA-0476 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 80000 | 91574 | 171574 | 4 | Closed | 8.4696 | 10.5263 | 20 | 11.3927 | LOW | 0.65 | 0.5 | 55761.55 | 11152.31 | 22304.62 | 33456.93 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 372
SA-0473 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 80000 | 89940 | 169940 | 4 | Open | 8.3889 | 10.5263 | 20 | 11.3524 | LOW | 0.9 | 1 | 152946 | 30589.2 | 61178.4 | 91767.6 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 373
SA-0286 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 86786 | 168452 | 4 | In Progress | 8.3155 | 10.5263 | 20 | 11.3156 | LOW | 0.9 | 0.75 | 113705.1 | 22741.02 | 45482.04 | 68223.06 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 374
SA-0054 | Weather | Lightning | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 91438 | 168104 | 4 | Closed | 8.2983 | 10.5263 | 20 | 11.307 | LOW | 0.3 | 0.5 | 25215.6 | 5043.12 | 10086.24 | 15129.36 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 375
SA-0211 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Condition Hole | 1 | 1 | 1 | 4 | 81666 | 86316 | 167982 | 4 | Closed | 8.2923 | 10.5263 | 20 | 11.304 | LOW | 0.65 | 0.5 | 54594.15 | 10918.83 | 21837.66 | 32756.49 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 376
SA-0102 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 90633 | 167299 | 4 | Open | 8.2585 | 10.5263 | 20 | 11.2872 | LOW | 0.9 | 1 | 150569.1 | 30113.82 | 60227.64 | 90341.46 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 377
SA-0303 | Weather | Lightning | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 85784 | 162450 | 4 | In Progress | 8.0192 | 10.5263 | 20 | 11.1675 | LOW | 0.3 | 0.75 | 36551.25 | 7310.25 | 14620.5 | 21930.75 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 378
SA-0477 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 81666 | 77971 | 159637 | 4 | In Progress | 7.8803 | 10.5263 | 20 | 11.0981 | LOW | 0.65 | 0.75 | 77823.0375 | 15564.6075 | 31129.215 | 46693.8225 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 379
SA-0174 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 77766 | 159432 | 4 | Closed | 7.8702 | 10.5263 | 20 | 11.093 | LOW | 0.9 | 0.5 | 71744.4 | 14348.88 | 28697.76 | 43046.64 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 380
SA-0312 | Personnel | Crew Change | Training Requirement | Rig Management | Crew Replacement | 1 | 1 | 1 | 4 | 76666 | 79447 | 156113 | 4 | Closed | 7.7064 | 10.5263 | 20 | 11.0111 | LOW | 0.6 | 0.5 | 46833.9 | 9366.78 | 18733.56 | 28100.34 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 381
SA-0373 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 79166 | 76620 | 155786 | 4 | Closed | 7.6902 | 10.5263 | 20 | 11.003 | LOW | 0.65 | 0.5 | 50630.45 | 10126.09 | 20252.18 | 30378.27 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 382
SA-0390 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 76666 | 78814 | 155480 | 4 | Closed | 7.6751 | 10.5263 | 20 | 10.9955 | LOW | 0.9 | 0.5 | 69966 | 13993.2 | 27986.4 | 41979.6 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 383
SA-0270 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 71396 | 153062 | 4 | Open | 7.5558 | 10.5263 | 20 | 10.9358 | LOW | 0.9 | 1 | 137755.8 | 27551.16 | 55102.32 | 82653.48 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 384
SA-0321 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 74370 | 151036 | 4 | Closed | 7.4557 | 10.5263 | 20 | 10.8858 | LOW | 0.9 | 0.5 | 67966.2 | 13593.24 | 27186.48 | 40779.72 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 385
SA-0101 | Weather | Poor Visibility | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 73637 | 150303 | 4 | Closed | 7.4196 | 10.5263 | 20 | 10.8677 | LOW | 0.3 | 0.5 | 22545.45 | 4509.09 | 9018.18 | 13527.27 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 386
SA-0444 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 72518 | 149184 | 4 | Open | 7.3643 | 10.5263 | 20 | 10.8401 | LOW | 0.6 | 1 | 89510.4 | 17902.08 | 35804.16 | 53706.24 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 387
SA-0113 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 79166 | 68905 | 148071 | 4 | Closed | 7.3094 | 10.5263 | 20 | 10.8126 | LOW | 0.9 | 0.5 | 66631.95 | 13326.39 | 26652.78 | 39979.17 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 388
SA-0276 | Drilling | Well Control | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 70081 | 146747 | 4 | Closed | 7.244 | 10.5263 | 20 | 10.7799 | LOW | 0.8 | 0.5 | 58698.8 | 11739.76 | 23479.52 | 35219.28 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 389
SA-0040 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 81666 | 64854 | 146520 | 4 | Closed | 7.2328 | 10.5263 | 20 | 10.7743 | LOW | 0.6 | 0.5 | 43956 | 8791.2 | 17582.4 | 26373.6 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 390
SA-0397 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 76666 | 67923 | 144589 | 4 | In Progress | 7.1375 | 10.5263 | 20 | 10.7266 | LOW | 0.7 | 0.75 | 75909.225 | 15181.845 | 30363.69 | 45545.535 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 391
SA-0067 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 67864 | 144530 | 4 | Closed | 7.1346 | 10.5263 | 20 | 10.7252 | LOW | 0.8 | 0.5 | 57812 | 11562.4 | 23124.8 | 34687.2 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 392
SA-0403 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 76666 | 67775 | 144441 | 4 | Open | 7.1302 | 10.5263 | 20 | 10.723 | LOW | 0.9 | 1 | 129996.9 | 25999.38 | 51998.76 | 77998.14 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 393
SA-0463 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 4 | 80000 | 63153 | 143153 | 4 | In Progress | 7.0666 | 10.5263 | 20 | 10.6912 | LOW | 0.6 | 0.75 | 64418.85 | 12883.77 | 25767.54 | 38651.31 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 394
SA-0271 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | Medical Clearance | 1 | 1 | 1 | 4 | 81666 | 60840 | 142506 | 4 | Closed | 7.0347 | 10.5263 | 20 | 10.6752 | LOW | 0.6 | 0.5 | 42751.8 | 8550.36 | 17100.72 | 25651.08 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 395
SA-0170 | Logistics | Waiting on Cement | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 60188 | 141854 | 4 | Closed | 7.0025 | 10.5263 | 20 | 10.6591 | LOW | 0.6 | 0.5 | 42556.2 | 8511.24 | 17022.48 | 25533.72 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 396
SA-0445 | Weather | Lightning | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 61263 | 137929 | 4 | Closed | 6.8087 | 10.5263 | 20 | 10.5623 | LOW | 0.3 | 0.5 | 20689.35 | 4137.87 | 8275.74 | 12413.61 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 397
SA-0410 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 55857 | 137523 | 4 | Open | 6.7887 | 10.5263 | 20 | 10.5522 | LOW | 0.9 | 1 | 123770.7 | 24754.14 | 49508.28 | 74262.42 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 398
SA-0265 | Drilling | Well Control | Bit Wear | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 4 | 81666 | 55231 | 136897 | 4 | In Progress | 6.7578 | 10.5263 | 20 | 10.5368 | LOW | 0.8 | 0.75 | 82138.2 | 16427.64 | 32855.28 | 49282.92 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 399
SA-0398 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 58910 | 135576 | 4 | Open | 6.6926 | 10.5263 | 20 | 10.5042 | LOW | 0.6 | 1 | 81345.6 | 16269.12 | 32538.24 | 48807.36 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 400
SA-0436 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 58805 | 135471 | 4 | Closed | 6.6874 | 10.5263 | 20 | 10.5016 | LOW | 0.9 | 0.5 | 60961.95 | 12192.39 | 24384.78 | 36577.17 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 401
SA-0370 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 55282 | 131948 | 4 | Open | 6.5135 | 10.5263 | 20 | 10.4146 | LOW | 0.9 | 1 | 118753.2 | 23750.64 | 47501.28 | 71251.92 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 402
SA-0332 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 52243 | 128909 | 4 | Open | 6.3635 | 10.5263 | 20 | 10.3396 | LOW | 0.65 | 1 | 83790.85 | 16758.17 | 33516.34 | 50274.51 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 403
SA-0377 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 79166 | 45728 | 124894 | 4 | Closed | 6.1653 | 10.5263 | 20 | 10.2405 | LOW | 0.9 | 0.5 | 56202.3 | 11240.46 | 22480.92 | 33721.38 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 404
SA-0107 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 79166 | 43669 | 122835 | 4 | Open | 6.0636 | 10.5263 | 20 | 10.1897 | LOW | 0.65 | 1 | 79842.75 | 15968.55 | 31937.1 | 47905.65 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 405
SA-0274 | Weather | Poor Visibility | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 44941 | 121607 | 4 | Closed | 6.003 | 10.5263 | 20 | 10.1594 | LOW | 0.3 | 0.5 | 18241.05 | 3648.21 | 7296.42 | 10944.63 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 406
SA-0343 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 44040 | 120706 | 4 | Closed | 5.9585 | 10.5263 | 20 | 10.1372 | LOW | 0.9 | 0.5 | 54317.7 | 10863.54 | 21727.08 | 32590.62 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 407
SA-0345 | Weather | Poor Visibility | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 76666 | 41049 | 117715 | 4 | Closed | 5.8109 | 10.5263 | 20 | 10.0633 | LOW | 0.3 | 0.5 | 17657.25 | 3531.45 | 7062.9 | 10594.35 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 408
SA-0452 | Drilling | Well Control | Unexpected Pressure | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 39001 | 115667 | 4 | Closed | 5.7098 | 10.5263 | 20 | 10.0128 | LOW | 0.65 | 0.5 | 37591.775 | 7518.355 | 15036.71 | 22555.065 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 409
SA-0308 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 4 | 76666 | 38651 | 115317 | 4 | Closed | 5.6925 | 10.5263 | 20 | 10.0041 | LOW | 0.9 | 0.5 | 51892.65 | 10378.53 | 20757.06 | 31135.59 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 410
SA-0168 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 2 | 40833 | 98245 | 139078 | 2 | Closed | 6.8654 | 5.2632 | 20 | 9.0117 | LOW | 0.6 | 0.5 | 41723.4 | 8344.68 | 16689.36 | 25034.04 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 411
SA-0207 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 96130 | 136963 | 2 | In Progress | 6.761 | 5.2632 | 20 | 8.9595 | LOW | 0.65 | 0.75 | 66769.4625 | 13353.8925 | 26707.785 | 40061.6775 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 412
SA-0037 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 40833 | 94991 | 135824 | 2 | Closed | 6.7048 | 5.2632 | 20 | 8.9314 | LOW | 0.9 | 0.5 | 61120.8 | 12224.16 | 24448.32 | 36672.48 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 413
SA-0008 | Drilling | Lost Circulation | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 94533 | 135366 | 2 | Closed | 6.6822 | 5.2632 | 20 | 8.9201 | LOW | 0.8 | 0.5 | 54146.4 | 10829.28 | 21658.56 | 32487.84 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 414
SA-0498 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 2 | 40833 | 91284 | 132117 | 2 | Closed | 6.5218 | 5.2632 | 20 | 8.8399 | LOW | 0.9 | 0.5 | 59452.65 | 11890.53 | 23781.06 | 35671.59 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 415
SA-0239 | Weather | Lightning | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 2 | 40000 | 91903 | 131903 | 2 | Closed | 6.5113 | 5.2632 | 20 | 8.8346 | LOW | 0.3 | 0.5 | 19785.45 | 3957.09 | 7914.18 | 11871.27 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 416
SA-0191 | Weather | Heavy Rain | Lightning | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 90548 | 131381 | 2 | Closed | 6.4855 | 5.2632 | 20 | 8.8217 | LOW | 0.3 | 0.5 | 19707.15 | 3941.43 | 7882.86 | 11824.29 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 417
SA-0072 | Weather | Poor Visibility | Lightning | Marine Operations | Suspend Operations | 1 | 1 | 1 | 2 | 38333 | 92556 | 130889 | 2 | Open | 6.4612 | 5.2632 | 20 | 8.8095 | LOW | 0.3 | 1 | 39266.7 | 7853.34 | 15706.68 | 23560.02 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 418
SA-0392 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 91400 | 129733 | 2 | Closed | 6.4041 | 5.2632 | 20 | 8.781 | LOW | 0.9 | 0.5 | 58379.85 | 11675.97 | 23351.94 | 35027.91 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 419
SA-0422 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 2 | 38333 | 90911 | 129244 | 2 | Closed | 6.38 | 5.2632 | 20 | 8.7689 | LOW | 0.6 | 0.5 | 38773.2 | 7754.64 | 15509.28 | 23263.92 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 420
SA-0124 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 89900 | 128233 | 2 | Closed | 6.3301 | 5.2632 | 20 | 8.744 | LOW | 0.6 | 0.5 | 38469.9 | 7693.98 | 15387.96 | 23081.94 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 421
SA-0459 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 88171 | 128171 | 2 | Closed | 6.327 | 5.2632 | 20 | 8.7425 | LOW | 0.6 | 0.5 | 38451.3 | 7690.26 | 15380.52 | 23070.78 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 422
SA-0053 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 89763 | 128096 | 2 | In Progress | 6.3233 | 5.2632 | 20 | 8.7406 | LOW | 0.9 | 0.75 | 86464.8 | 17292.96 | 34585.92 | 51878.88 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 423
SA-0268 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 86980 | 127813 | 2 | Closed | 6.3094 | 5.2632 | 20 | 8.7336 | LOW | 0.9 | 0.5 | 57515.85 | 11503.17 | 23006.34 | 34509.51 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 424
SA-0478 | Drilling | Bit Failure | Bit Wear | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 84650 | 125483 | 2 | In Progress | 6.1943 | 5.2632 | 20 | 8.6761 | LOW | 0.8 | 0.75 | 75289.8 | 15057.96 | 30115.92 | 45173.88 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 425
SA-0493 | Drilling | Well Control | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 85472 | 125472 | 2 | Closed | 6.1938 | 5.2632 | 20 | 8.6758 | LOW | 0.8 | 0.5 | 50188.8 | 10037.76 | 20075.52 | 30113.28 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 426
SA-0460 | Drilling | Bit Failure | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40000 | 85034 | 125034 | 2 | In Progress | 6.1722 | 5.2632 | 20 | 8.665 | LOW | 0.65 | 0.75 | 60954.075 | 12190.815 | 24381.63 | 36572.445 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 427
SA-0090 | Personnel | Training | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 2 | 39583 | 85410 | 124993 | 2 | Closed | 6.1702 | 5.2632 | 20 | 8.664 | LOW | 0.6 | 0.5 | 37497.9 | 7499.58 | 14999.16 | 22498.74 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 428
SA-0277 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 86067 | 124400 | 2 | In Progress | 6.1409 | 5.2632 | 20 | 8.6494 | LOW | 0.9 | 0.75 | 83970 | 16794 | 33588 | 50382 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 429
SA-0307 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 85268 | 123601 | 2 | In Progress | 6.1014 | 5.2632 | 20 | 8.6297 | LOW | 0.65 | 0.75 | 60255.4875 | 12051.0975 | 24102.195 | 36153.2925 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 430
SA-0318 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 83567 | 121900 | 2 | Closed | 6.0175 | 5.2632 | 20 | 8.5877 | LOW | 0.9 | 0.5 | 54855 | 10971 | 21942 | 32913 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 431
SA-0087 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 2 | 39583 | 82308 | 121891 | 2 | In Progress | 6.017 | 5.2632 | 20 | 8.5875 | LOW | 0.9 | 0.75 | 82276.425 | 16455.285 | 32910.57 | 49365.855 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 432
SA-0232 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40000 | 81266 | 121266 | 2 | Closed | 5.9862 | 5.2632 | 20 | 8.572 | LOW | 0.9 | 0.5 | 54569.7 | 10913.94 | 21827.88 | 32741.82 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 433
SA-0365 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 82613 | 120946 | 2 | Open | 5.9704 | 5.2632 | 20 | 8.5641 | LOW | 0.9 | 1 | 108851.4 | 21770.28 | 43540.56 | 65310.84 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 434
SA-0233 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 40000 | 79766 | 119766 | 2 | Closed | 5.9121 | 5.2632 | 20 | 8.535 | LOW | 0.9 | 0.5 | 53894.7 | 10778.94 | 21557.88 | 32336.82 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 435
SA-0371 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 81222 | 119555 | 2 | Closed | 5.9017 | 5.2632 | 20 | 8.5298 | LOW | 0.9 | 0.5 | 53799.75 | 10759.95 | 21519.9 | 32279.85 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 436
SA-0250 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 78798 | 117131 | 2 | Closed | 5.7821 | 5.2632 | 20 | 8.47 | LOW | 0.7 | 0.5 | 40995.85 | 8199.17 | 16398.34 | 24597.51 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 437
SA-0023 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 2 | 39583 | 76363 | 115946 | 2 | Closed | 5.7236 | 5.2632 | 20 | 8.4407 | LOW | 0.9 | 0.5 | 52175.7 | 10435.14 | 20870.28 | 31305.42 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 438
SA-0163 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 74203 | 114203 | 2 | Closed | 5.6375 | 5.2632 | 20 | 8.3977 | LOW | 0.65 | 0.5 | 37115.975 | 7423.195 | 14846.39 | 22269.585 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 439
SA-0479 | Weather | Strong Wind | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 73113 | 113946 | 2 | Closed | 5.6248 | 5.2632 | 20 | 8.3914 | LOW | 0.3 | 0.5 | 17091.9 | 3418.38 | 6836.76 | 10255.14 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 440
SA-0204 | Weather | Heavy Rain | Strong Wind | Weather | Resume Operations | 1 | 1 | 1 | 2 | 40833 | 71375 | 112208 | 2 | In Progress | 5.539 | 5.2632 | 20 | 8.3485 | LOW | 0.3 | 0.75 | 25246.8 | 5049.36 | 10098.72 | 15148.08 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 441
SA-0002 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 2 | 40833 | 70917 | 111750 | 2 | Open | 5.5164 | 5.2632 | 20 | 8.3372 | LOW | 0.9 | 1 | 100575 | 20115 | 40230 | 60345 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 442
SA-0360 | Weather | Heavy Rain | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 2 | 38333 | 72796 | 111129 | 2 | Closed | 5.4858 | 5.2632 | 20 | 8.3218 | LOW | 0.3 | 0.5 | 16669.35 | 3333.87 | 6667.74 | 10001.61 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 443
SA-0230 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 40000 | 71032 | 111032 | 2 | Closed | 5.481 | 5.2632 | 20 | 8.3194 | LOW | 0.6 | 0.5 | 33309.6 | 6661.92 | 13323.84 | 19985.76 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 444
SA-0430 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 38333 | 71989 | 110322 | 2 | Closed | 5.4459 | 5.2632 | 20 | 8.3019 | LOW | 0.7 | 0.5 | 38612.7 | 7722.54 | 15445.08 | 23167.62 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 445
SA-0439 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 38333 | 71728 | 110061 | 2 | Closed | 5.4331 | 5.2632 | 20 | 8.2955 | LOW | 0.8 | 0.5 | 44024.4 | 8804.88 | 17609.76 | 26414.64 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 446
SA-0380 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 40000 | 69853 | 109853 | 2 | Closed | 5.4228 | 5.2632 | 20 | 8.2903 | LOW | 0.65 | 0.5 | 35702.225 | 7140.445 | 14280.89 | 21421.335 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 447
SA-0022 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 39583 | 70254 | 109837 | 2 | Closed | 5.422 | 5.2632 | 20 | 8.2899 | LOW | 0.8 | 0.5 | 43934.8 | 8786.96 | 17573.92 | 26360.88 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 448
SA-0440 | Weather | Heavy Rain | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 2 | 38333 | 71077 | 109410 | 2 | Closed | 5.4009 | 5.2632 | 20 | 8.2794 | LOW | 0.3 | 0.5 | 16411.5 | 3282.3 | 6564.6 | 9846.9 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 449
SA-0142 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 67554 | 108387 | 2 | Closed | 5.3504 | 5.2632 | 20 | 8.2542 | LOW | 0.6 | 0.5 | 32516.1 | 6503.22 | 13006.44 | 19509.66 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 450
SA-0466 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 67011 | 107844 | 2 | Closed | 5.3236 | 5.2632 | 20 | 8.2408 | LOW | 0.6 | 0.5 | 32353.2 | 6470.64 | 12941.28 | 19411.92 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 451
SA-0341 | Drilling | Stuck Pipe | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 38333 | 69018 | 107351 | 2 | Closed | 5.2993 | 5.2632 | 20 | 8.2286 | LOW | 0.8 | 0.5 | 42940.4 | 8588.08 | 17176.16 | 25764.24 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 452
SA-0219 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 65954 | 105954 | 2 | Closed | 5.2303 | 5.2632 | 20 | 8.1941 | LOW | 0.8 | 0.5 | 42381.6 | 8476.32 | 16952.64 | 25428.96 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 453
SA-0396 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 1 | 1 | 2 | 38333 | 67158 | 105491 | 2 | Closed | 5.2075 | 5.2632 | 20 | 8.1827 | LOW | 0.6 | 0.5 | 31647.3 | 6329.46 | 12658.92 | 18988.38 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 454
SA-0098 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 38333 | 66496 | 104829 | 2 | In Progress | 5.1748 | 5.2632 | 20 | 8.1663 | LOW | 0.6 | 0.75 | 47173.05 | 9434.61 | 18869.22 | 28303.83 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 455
SA-0252 | Weather | High Waves | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 2 | 39583 | 63322 | 102905 | 2 | Closed | 5.0798 | 5.2632 | 20 | 8.1188 | LOW | 0.3 | 0.5 | 15435.75 | 3087.15 | 6174.3 | 9261.45 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 456
SA-0003 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 60855 | 101688 | 2 | In Progress | 5.0197 | 5.2632 | 20 | 8.0888 | LOW | 0.6 | 0.75 | 45759.6 | 9151.92 | 18303.84 | 27455.76 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 457
SA-0484 | Drilling | Lost Circulation | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 2 | 40833 | 59674 | 100507 | 2 | In Progress | 4.9614 | 5.2632 | 20 | 8.0597 | LOW | 0.65 | 0.75 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 458
SA-0148 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 2 | 40833 | 57857 | 98690 | 2 | Closed | 4.8717 | 5.2632 | 20 | 8.0148 | LOW | 0.6 | 0.5 | 29607 | 5921.4 | 11842.8 | 17764.2 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 459
SA-0383 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 58559 | 98559 | 2 | Closed | 4.8653 | 5.2632 | 20 | 8.0116 | LOW | 0.8 | 0.5 | 39423.6 | 7884.72 | 15769.44 | 23654.16 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 460
SA-0099 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 59428 | 97761 | 2 | In Progress | 4.8259 | 5.2632 | 20 | 7.9919 | LOW | 0.6 | 0.75 | 43992.45 | 8798.49 | 17596.98 | 26395.47 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 461
SA-0375 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 39583 | 57298 | 96881 | 2 | Closed | 4.7824 | 5.2632 | 20 | 7.9702 | LOW | 0.9 | 0.5 | 43596.45 | 8719.29 | 17438.58 | 26157.87 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 462
SA-0465 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 55477 | 96310 | 2 | Open | 4.7542 | 5.2632 | 20 | 7.9561 | LOW | 0.9 | 1 | 86679 | 17335.8 | 34671.6 | 52007.4 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 463
SA-0201 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 39583 | 55699 | 95282 | 2 | In Progress | 4.7035 | 5.2632 | 20 | 7.9307 | LOW | 0.65 | 0.75 | 46449.975 | 9289.995 | 18579.99 | 27869.985 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 464
SA-0069 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 55949 | 94282 | 2 | Open | 4.6541 | 5.2632 | 20 | 7.906 | LOW | 0.9 | 1 | 84853.8 | 16970.76 | 33941.52 | 50912.28 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 465
SA-0188 | Personnel | Safety Stand Down | Training Requirement | HR | Crew Replacement | 1 | 1 | 1 | 2 | 40000 | 53981 | 93981 | 2 | Closed | 4.6393 | 5.2632 | 20 | 7.8986 | LOW | 0.6 | 0.5 | 28194.3 | 5638.86 | 11277.72 | 16916.58 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 466
SA-0234 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 40000 | 52909 | 92909 | 2 | Closed | 4.5864 | 5.2632 | 20 | 7.8721 | LOW | 0.9 | 0.5 | 41809.05 | 8361.81 | 16723.62 | 25085.43 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 467
SA-0347 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 54487 | 92820 | 2 | In Progress | 4.582 | 5.2632 | 20 | 7.8699 | LOW | 0.9 | 0.75 | 62653.5 | 12530.7 | 25061.4 | 37592.1 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 468
SA-0320 | Drilling | Hole Cleaning | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 38333 | 53610 | 91943 | 2 | Open | 4.5387 | 5.2632 | 20 | 7.8483 | LOW | 0.8 | 1 | 73554.4 | 14710.88 | 29421.76 | 44132.64 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 469
SA-0461 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 51341 | 91341 | 2 | Closed | 4.509 | 5.2632 | 20 | 7.8334 | LOW | 0.6 | 0.5 | 27402.3 | 5480.46 | 10960.92 | 16441.38 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 470
SA-0418 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 38333 | 52302 | 90635 | 2 | Closed | 4.4741 | 5.2632 | 20 | 7.816 | LOW | 0.6 | 0.5 | 27190.5 | 5438.1 | 10876.2 | 16314.3 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 471
SA-0288 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 40833 | 48689 | 89522 | 2 | Closed | 4.4192 | 5.2632 | 20 | 7.7885 | LOW | 0.7 | 0.5 | 31332.7 | 6266.54 | 12533.08 | 18799.62 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 472
SA-0200 | Drilling | Well Control | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 39583 | 49805 | 89388 | 2 | Closed | 4.4125 | 5.2632 | 20 | 7.7852 | LOW | 0.8 | 0.5 | 35755.2 | 7151.04 | 14302.08 | 21453.12 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 473
SA-0167 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 2 | 40000 | 48341 | 88341 | 2 | Closed | 4.3609 | 5.2632 | 20 | 7.7594 | LOW | 0.9 | 0.5 | 39753.45 | 7950.69 | 15901.38 | 23852.07 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 474
SA-0446 | Drilling | Fishing Operation | Bit Wear | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 49722 | 88055 | 2 | In Progress | 4.3467 | 5.2632 | 20 | 7.7523 | LOW | 0.8 | 0.75 | 52833 | 10566.6 | 21133.2 | 31699.8 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 475
SA-0105 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 48369 | 86702 | 2 | Closed | 4.28 | 5.2632 | 20 | 7.7189 | LOW | 0.6 | 0.5 | 26010.6 | 5202.12 | 10404.24 | 15606.36 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 476
SA-0358 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40833 | 45052 | 85885 | 2 | Closed | 4.2396 | 5.2632 | 20 | 7.6988 | LOW | 0.65 | 0.5 | 27912.625 | 5582.525 | 11165.05 | 16747.575 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 477
SA-0285 | Weather | Strong Wind | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 2 | 40833 | 43926 | 84759 | 2 | Closed | 4.184 | 5.2632 | 20 | 7.671 | LOW | 0.3 | 0.5 | 12713.85 | 2542.77 | 5085.54 | 7628.31 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 478
SA-0198 | Drilling | Hole Cleaning | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 39583 | 44552 | 84135 | 2 | Closed | 4.1532 | 5.2632 | 20 | 7.6556 | LOW | 0.8 | 0.5 | 33654 | 6730.8 | 13461.6 | 20192.4 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 479
SA-0409 | Logistics | Waiting on Materials | Port Congestion | Procurement | Air Freight Materials | 1 | 1 | 1 | 2 | 40833 | 42029 | 82862 | 2 | Closed | 4.0904 | 5.2632 | 20 | 7.6241 | LOW | 0.6 | 0.5 | 24858.6 | 4971.72 | 9943.44 | 14915.16 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 480
SA-0405 | Weather | Poor Visibility | Lightning | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 41869 | 82702 | 2 | Closed | 4.0825 | 5.2632 | 20 | 7.6202 | LOW | 0.3 | 0.5 | 12405.3 | 2481.06 | 4962.12 | 7443.18 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 481
SA-0155 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 42480 | 82480 | 2 | In Progress | 4.0715 | 5.2632 | 20 | 7.6147 | LOW | 0.6 | 0.75 | 37116 | 7423.2 | 14846.4 | 22269.6 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 482
SA-0300 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 41456 | 82289 | 2 | Open | 4.0621 | 5.2632 | 20 | 7.61 | LOW | 0.6 | 1 | 49373.4 | 9874.68 | 19749.36 | 29624.04 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 483
SA-0335 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 43940 | 82273 | 2 | Open | 4.0613 | 5.2632 | 20 | 7.6096 | LOW | 0.9 | 1 | 74045.7 | 14809.14 | 29618.28 | 44427.42 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 484
SA-0485 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | Medical Clearance | 1 | 1 | 1 | 2 | 38333 | 43207 | 81540 | 2 | Closed | 4.0251 | 5.2632 | 20 | 7.5915 | LOW | 0.6 | 0.5 | 24462 | 4892.4 | 9784.8 | 14677.2 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 485
SA-0093 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 39583 | 39917 | 79500 | 2 | Closed | 3.9244 | 5.2632 | 20 | 7.5412 | LOW | 0.9 | 0.5 | 35775 | 7155 | 14310 | 21465 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 486
SA-0242 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Repair Component | 1 | 1 | 1 | 2 | 38333 | 40806 | 79139 | 2 | Closed | 3.9066 | 5.2632 | 20 | 7.5323 | LOW | 0.7 | 0.5 | 27698.65 | 5539.73 | 11079.46 | 16619.19 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 487
SA-0448 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 37321 | 75654 | 2 | Closed | 3.7346 | 5.2632 | 20 | 7.4462 | LOW | 0.9 | 0.5 | 34044.3 | 6808.86 | 13617.72 | 20426.58 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 488
SA-0235 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 2 | 40000 | 33971 | 73971 | 2 | Closed | 3.6515 | 5.2632 | 20 | 7.4047 | LOW | 0.9 | 0.5 | 33286.95 | 6657.39 | 13314.78 | 19972.17 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 489
SA-0261 | Weather | Strong Wind | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 39583 | 34235 | 73818 | 2 | Open | 3.644 | 5.2632 | 20 | 7.4009 | LOW | 0.3 | 1 | 22145.4 | 4429.08 | 8858.16 | 13287.24 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 490
SA-0297 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 2 | 40833 | 31395 | 72228 | 2 | Closed | 3.5655 | 5.2632 | 20 | 7.3617 | LOW | 0.9 | 0.5 | 32502.6 | 6500.52 | 13001.04 | 19501.56 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 491
SA-0438 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 2 | 38333 | 33873 | 72206 | 2 | Closed | 3.5644 | 5.2632 | 20 | 7.3611 | LOW | 0.6 | 0.5 | 21661.8 | 4332.36 | 8664.72 | 12997.08 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 492
SA-0381 | Drilling | Well Control | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 2 | 40000 | 30168 | 70168 | 2 | Closed | 3.4638 | 5.2632 | 20 | 7.3108 | LOW | 0.8 | 0.5 | 28067.2 | 5613.44 | 11226.88 | 16840.32 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 493
SA-0127 | Weather | Lightning | Heavy Rain | Weather | Wait on Weather | 1 | 1 | 1 | 2 | 38333 | 31793 | 70126 | 2 | In Progress | 3.4617 | 5.2632 | 20 | 7.3098 | LOW | 0.3 | 0.75 | 15778.35 | 3155.67 | 6311.34 | 9467.01 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 494
SA-0119 | Drilling | Bit Failure | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 2 | 38333 | 30581 | 68914 | 2 | Closed | 3.4019 | 5.2632 | 20 | 7.2799 | LOW | 0.65 | 0.5 | 22397.05 | 4479.41 | 8958.82 | 13438.23 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 495
SA-0447 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 29667 | 68000 | 2 | Closed | 3.3568 | 5.2632 | 20 | 7.2573 | LOW | 0.8 | 0.5 | 27200 | 5440 | 10880 | 16320 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 496
SA-0136 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 27130 | 67963 | 2 | Closed | 3.3549 | 5.2632 | 20 | 7.2564 | LOW | 0.9 | 0.5 | 30583.35 | 6116.67 | 12233.34 | 18350.01 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 497
SA-0162 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 26827 | 66827 | 2 | Closed | 3.2988 | 5.2632 | 20 | 7.2284 | LOW | 0.8 | 0.5 | 26730.8 | 5346.16 | 10692.32 | 16038.48 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 498
SA-0183 | Drilling | Fishing Operation | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 25923 | 65923 | 2 | Closed | 3.2542 | 5.2632 | 20 | 7.2061 | LOW | 0.8 | 0.5 | 26369.2 | 5273.84 | 10547.68 | 15821.52 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 499
SA-0152 | Personnel | Safety Stand Down | Medical Emergency | HR | Safety Briefing | 1 | 1 | 1 | 2 | 40000 | 25522 | 65522 | 2 | Closed | 3.2344 | 5.2632 | 20 | 7.1962 | LOW | 0.6 | 0.5 | 19656.6 | 3931.32 | 7862.64 | 11793.96 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 500
SA-0220 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 24142 | 64142 | 2 | In Progress | 3.1663 | 5.2632 | 20 | 7.1621 | LOW | 0.65 | 0.75 | 31269.225 | 6253.845 | 12507.69 | 18761.535 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 501
SA-0120 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Condition Hole | 1 | 1 | 1 | 2 | 38333 | 24138 | 62471 | 2 | Closed | 3.0838 | 5.2632 | 20 | 7.1209 | LOW | 0.65 | 0.5 | 20303.075 | 4060.615 | 8121.23 | 12181.845 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 502

## Action_Detail
Strategic_Action_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Corrective_Action | NPT_Events | Affected_Wells | Affected_Rigs | Baseline_NPT_Hours | Direct_NPT_Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Avg_Duration_hr | Action_Status | Impact_Score | NPT_Hours_Score | Frequency_Score | Priority_Score | Priority | Addressability_Factor | Actionability_Factor | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD | KPI | Target_NPT_Reduction_pct | Target_NPT_Hours | KPI_Baseline | KPI_Target | Implementation_Horizon | Monitoring_Frequency | Action_Rank
SA-0033 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 3 | 3 | 2 | 38 | 765833 | 1234524 | 2000357 | 12.6667 | Open | 98.7456 | 100 | 60 | 91.3728 | CRITICAL | 0.8 | 1 | 1600285.6 | 320057.12 | 640114.24 | 960171.36 | NPT Hours + ROP | 0.4 | 22.8 | 38 | 22.8 | 0-30 Days | Weekly | 1
SA-0108 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | 3 | 3 | 3 | 36 | 728750 | 1297018 | 2025768 | 12 | Closed | 100 | 94.7368 | 60 | 90.4211 | CRITICAL | 0.6 | 0.5 | 607730.4 | 121546.08 | 243092.16 | 364638.24 | Logistics NPT Hours | 0.4 | 21.6 | 36 | 21.6 | 0-30 Days | Weekly | 2
SA-0036 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | 2 | 2 | 2 | 32 | 643333 | 1352053 | 1995386 | 16 | In Progress | 98.5002 | 84.2105 | 40 | 82.5133 | CRITICAL | 0.9 | 0.75 | 1346885.55 | 269377.11 | 538754.22 | 808131.33 | Mechanical NPT Hours | 0.4 | 19.2 | 32 | 19.2 | 0-30 Days | Weekly | 3
SA-0135 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 32 | 643333 | 1343195 | 1986528 | 16 | Open | 98.063 | 84.2105 | 40 | 82.2946 | CRITICAL | 0.9 | 1 | 1787875.2 | 357575.04 | 715150.08 | 1072725.12 | Mechanical NPT Hours | 0.4 | 19.2 | 32 | 19.2 | 0-30 Days | Weekly | 4
SA-0426 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | 2 | 2 | 2 | 30 | 590000 | 1334964 | 1924964 | 15 | In Progress | 95.0239 | 78.9474 | 40 | 79.1962 | HIGH | 0.3 | 0.75 | 433116.9 | 86623.38 | 173246.76 | 259870.14 | Weather NPT Hours | 0.35 | 19.5 | 30 | 19.5 | 31-90 Days | Weekly | 5
SA-0275 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | 4 | 4 | 2 | 28 | 544166 | 889814 | 1433980 | 7 | In Progress | 70.787 | 73.6842 | 80 | 73.4988 | HIGH | 0.6 | 0.75 | 645291 | 129058.2 | 258116.4 | 387174.6 | Logistics NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 6
SA-0149 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 3 | 3 | 26 | 517916 | 1032154 | 1550070 | 8.6667 | In Progress | 76.5176 | 68.4211 | 60 | 70.7851 | HIGH | 0.65 | 0.75 | 755659.125 | 151131.825 | 302263.65 | 453395.475 | NPT Hours + ROP | 0.35 | 16.9 | 26 | 16.9 | 31-90 Days | Weekly | 7
SA-0092 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 2 | 2 | 26 | 519583 | 1168225 | 1687808 | 13 | Open | 83.3169 | 68.4211 | 40 | 70.1848 | HIGH | 0.9 | 1 | 1519027.2 | 303805.44 | 607610.88 | 911416.32 | Mechanical NPT Hours | 0.35 | 16.9 | 26 | 16.9 | 31-90 Days | Weekly | 8
SA-0164 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | 2 | 2 | 2 | 28 | 540000 | 1066675 | 1606675 | 14 | In Progress | 79.3119 | 73.6842 | 40 | 69.7612 | HIGH | 0.9 | 0.75 | 1084505.625 | 216901.125 | 433802.25 | 650703.375 | Mechanical NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 9
SA-0031 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | 3 | 3 | 3 | 28 | 561666 | 810093 | 1371759 | 9.3333 | In Progress | 67.7155 | 73.6842 | 60 | 67.963 | HIGH | 0.3 | 0.75 | 308645.775 | 61729.155 | 123458.31 | 185187.465 | Weather NPT Hours | 0.35 | 18.2 | 28 | 18.2 | 31-90 Days | Weekly | 10
SA-0048 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | 3 | 3 | 1 | 24 | 460000 | 872986 | 1332986 | 8 | Closed | 65.8015 | 63.1579 | 60 | 63.8481 | MEDIUM | 0.8 | 0.5 | 533194.4 | 106638.88 | 213277.76 | 319916.64 | NPT Hours + ROP | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 11
SA-0182 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 2 | 1 | 24 | 480000 | 995042 | 1475042 | 12 | Closed | 72.814 | 63.1579 | 40 | 63.3544 | MEDIUM | 0.6 | 0.5 | 442512.6 | 88502.52 | 177005.04 | 265507.56 | Logistics NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 12
SA-0423 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | 3 | 3 | 3 | 26 | 510833 | 735512 | 1246345 | 8.6667 | Open | 61.5246 | 68.4211 | 60 | 63.2886 | MEDIUM | 0.3 | 1 | 373903.5 | 74780.7 | 149561.4 | 224342.1 | Weather NPT Hours | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 13
SA-0160 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 2 | 1 | 22 | 440000 | 882159 | 1322159 | 7.3333 | In Progress | 65.267 | 57.8947 | 60 | 62.0019 | MEDIUM | 0.65 | 0.75 | 644552.5125 | 128910.5025 | 257821.005 | 386731.5075 | NPT Hours + ROP | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 14
SA-0088 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | 2 | 2 | 1 | 24 | 475000 | 941581 | 1416581 | 12 | Closed | 69.9281 | 63.1579 | 40 | 61.9114 | MEDIUM | 0.9 | 0.5 | 637461.45 | 127492.29 | 254984.58 | 382476.87 | Mechanical NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 15
SA-0122 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | 2 | 2 | 1 | 26 | 498333 | 839821 | 1338154 | 13 | In Progress | 66.0566 | 68.4211 | 40 | 61.5546 | MEDIUM | 0.3 | 0.75 | 301084.65 | 60216.93 | 120433.86 | 180650.79 | Weather NPT Hours | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 16
SA-0034 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | 4 | 4 | 2 | 22 | 446666 | 667061 | 1113727 | 5.5 | Open | 54.978 | 57.8947 | 80 | 60.8574 | MEDIUM | 0.9 | 1 | 1002354.3 | 200470.86 | 400941.72 | 601412.58 | Mechanical NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 17
SA-0222 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 1 | 22 | 440000 | 957755 | 1397755 | 11 | Closed | 68.9988 | 57.8947 | 40 | 59.8678 | MEDIUM | 0.8 | 0.5 | 559102 | 111820.4 | 223640.8 | 335461.2 | NPT Hours + ROP | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 18
SA-0109 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | 2 | 2 | 2 | 28 | 551666 | 594279 | 1145945 | 14 | Closed | 56.5684 | 73.6842 | 40 | 58.3895 | MEDIUM | 0.65 | 0.5 | 372432.125 | 74486.425 | 148972.85 | 223459.275 | NPT Hours + ROP | 0.25 | 21 | 28 | 21 | 91-180 Days | Weekly | 19
SA-0080 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | 2 | 2 | 2 | 26 | 508333 | 696290 | 1204623 | 13 | Closed | 59.465 | 68.4211 | 40 | 58.2588 | MEDIUM | 0.8 | 0.5 | 481849.2 | 96369.84 | 192739.68 | 289109.52 | NPT Hours + ROP | 0.25 | 19.5 | 26 | 19.5 | 91-180 Days | Weekly | 20
SA-0064 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | 4 | 4 | 2 | 22 | 426666 | 568889 | 995555 | 5.5 | In Progress | 49.1446 | 57.8947 | 80 | 57.9407 | MEDIUM | 0.3 | 0.75 | 223999.875 | 44799.975 | 89599.95 | 134399.925 | Weather NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 21
SA-0032 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 3 | 3 | 2 | 22 | 441666 | 645962 | 1087628 | 7.3333 | In Progress | 53.6897 | 57.8947 | 60 | 56.2133 | MEDIUM | 0.9 | 0.75 | 734148.9 | 146829.78 | 293659.56 | 440489.34 | Mechanical NPT Hours | 0.25 | 16.5 | 22 | 16.5 | 91-180 Days | Weekly | 22
SA-0042 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 2 | 2 | 2 | 20 | 385833 | 826420 | 1212253 | 10 | In Progress | 59.8417 | 52.6316 | 40 | 53.7103 | MEDIUM | 0.9 | 0.75 | 818270.775 | 163654.155 | 327308.31 | 490962.465 | Mechanical NPT Hours | 0.25 | 15 | 20 | 15 | 91-180 Days | Weekly | 23
SA-0056 | Weather | Lightning | Lightning | Weather | Suspend Operations | 5 | 5 | 3 | 16 | 317915 | 517569 | 835484 | 3.2 | In Progress | 41.2428 | 42.1053 | 100 | 53.253 | MEDIUM | 0.3 | 0.75 | 187983.9 | 37596.78 | 75193.56 | 112790.34 | Weather NPT Hours | 0.25 | 12 | 16 | 12 | 91-180 Days | Weekly | 24
SA-0404 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Expedite Shipment | 1 | 1 | 1 | 24 | 460000 | 763810 | 1223810 | 24 | In Progress | 60.4121 | 63.1579 | 20 | 53.1534 | MEDIUM | 0.6 | 0.75 | 550714.5 | 110142.9 | 220285.8 | 330428.7 | Logistics NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 25
SA-0214 | Weather | Lightning | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 24 | 480000 | 674701 | 1154701 | 24 | Closed | 57.0007 | 63.1579 | 20 | 51.4477 | MEDIUM | 0.3 | 0.5 | 173205.15 | 34641.03 | 69282.06 | 103923.09 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 26
SA-0018 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | 2 | 2 | 2 | 24 | 467500 | 492320 | 959820 | 12 | In Progress | 47.3805 | 63.1579 | 40 | 50.6376 | MEDIUM | 0.3 | 0.75 | 215959.5 | 43191.9 | 86383.8 | 129575.7 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 27
SA-0293 | Weather | Heavy Rain | Storm | Weather | Resume Operations | 1 | 1 | 1 | 24 | 490000 | 614657 | 1104657 | 24 | Closed | 54.5303 | 63.1579 | 20 | 50.2125 | MEDIUM | 0.3 | 0.5 | 165698.55 | 33139.71 | 66279.42 | 99419.13 | Weather NPT Hours | 0.25 | 18 | 24 | 18 | 91-180 Days | Weekly | 28
SA-0147 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | 2 | 2 | 2 | 20 | 405833 | 618606 | 1024439 | 10 | Closed | 50.5704 | 52.6316 | 40 | 49.0747 | LOW | 0.65 | 0.5 | 332942.675 | 66588.535 | 133177.07 | 199765.605 | NPT Hours + ROP | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 29
SA-0104 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | 4 | 4 | 3 | 16 | 311665 | 496610 | 808275 | 4 | Open | 39.8997 | 42.1053 | 80 | 48.5814 | LOW | 0.65 | 1 | 525378.75 | 105075.75 | 210151.5 | 315227.25 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 30
SA-0431 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | 2 | 2 | 2 | 18 | 360000 | 705290 | 1065290 | 9 | Open | 52.587 | 47.3684 | 40 | 48.504 | LOW | 0.6 | 1 | 639174 | 127834.8 | 255669.6 | 383504.4 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 31
SA-0464 | Weather | Poor Visibility | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 18 | 367500 | 851850 | 1219350 | 18 | Closed | 60.192 | 47.3684 | 20 | 48.3065 | LOW | 0.3 | 0.5 | 182902.5 | 36580.5 | 73161 | 109741.5 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 32
SA-0066 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 3 | 3 | 1 | 16 | 306665 | 637880 | 944545 | 5.3333 | Closed | 46.6265 | 42.1053 | 60 | 47.9448 | LOW | 0.6 | 0.5 | 283363.5 | 56672.7 | 113345.4 | 170018.1 | Logistics NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 33
SA-0393 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 2 | 2 | 1 | 20 | 383333 | 561038 | 944371 | 10 | Closed | 46.6179 | 52.6316 | 40 | 47.0984 | LOW | 0.9 | 0.5 | 424966.95 | 84993.39 | 169986.78 | 254980.17 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 34
SA-0086 | Drilling | Well Control | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 18 | 356250 | 798690 | 1154940 | 18 | Closed | 57.0125 | 47.3684 | 20 | 46.7168 | LOW | 0.8 | 0.5 | 461976 | 92395.2 | 184790.4 | 277185.6 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 35
SA-0210 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 3 | 2 | 2 | 18 | 354999 | 474535 | 829534 | 6 | In Progress | 40.9491 | 47.3684 | 60 | 46.6851 | LOW | 0.8 | 0.75 | 497720.4 | 99544.08 | 199088.16 | 298632.24 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 36
SA-0260 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 16 | 317500 | 736254 | 1053754 | 8 | Closed | 52.0175 | 42.1053 | 40 | 46.6403 | LOW | 0.3 | 0.5 | 158063.1 | 31612.62 | 63225.24 | 94837.86 | Weather NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 37
SA-0065 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 3 | 2 | 1 | 16 | 306666 | 582800 | 889466 | 5.3333 | Closed | 43.9076 | 42.1053 | 60 | 46.5854 | LOW | 0.9 | 0.5 | 400259.7 | 80051.94 | 160103.88 | 240155.82 | Mechanical NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 38
SA-0264 | Personnel | Crew Change | Medical Emergency | Medical Team | Medical Clearance | 1 | 1 | 1 | 18 | 367500 | 774135 | 1141635 | 18 | Closed | 56.3557 | 47.3684 | 20 | 46.3884 | LOW | 0.6 | 0.5 | 342490.5 | 68498.1 | 136996.2 | 205494.3 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 39
SA-0024 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 1 | 1 | 18 | 356250 | 753050 | 1109300 | 18 | Closed | 54.7595 | 47.3684 | 20 | 45.5903 | LOW | 0.9 | 0.5 | 499185 | 99837 | 199674 | 299511 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 40
SA-0138 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 2 | 2 | 2 | 20 | 385833 | 495197 | 881030 | 10 | Closed | 43.4912 | 52.6316 | 40 | 45.5351 | LOW | 0.9 | 0.5 | 396463.5 | 79292.7 | 158585.4 | 237878.1 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 41
SA-0374 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 2 | 2 | 2 | 22 | 437916 | 362099 | 800015 | 11 | Closed | 39.4919 | 57.8947 | 40 | 45.1144 | LOW | 0.9 | 0.5 | 360006.75 | 72001.35 | 144002.7 | 216004.05 | Mechanical NPT Hours | 0.15 | 18.7 | 22 | 18.7 | >180 Days | Weekly | 42
SA-0203 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 24 | 490000 | 397460 | 887460 | 24 | Open | 43.8086 | 63.1579 | 20 | 44.8517 | LOW | 0.6 | 1 | 532476 | 106495.2 | 212990.4 | 319485.6 | Logistics NPT Hours | 0.15 | 20.4 | 24 | 20.4 | >180 Days | Weekly | 43
SA-0225 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 18 | 360000 | 663187 | 1023187 | 18 | Closed | 50.5086 | 47.3684 | 20 | 43.4648 | LOW | 0.9 | 0.5 | 460434.15 | 92086.83 | 184173.66 | 276260.49 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 44
SA-0304 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | 3 | 3 | 2 | 14 | 269999 | 527973 | 797972 | 4.6667 | Open | 39.3911 | 36.8421 | 60 | 42.7482 | LOW | 0.8 | 1 | 638377.6 | 127675.52 | 255351.04 | 383026.56 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 45
SA-0130 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 3 | 3 | 2 | 18 | 349999 | 300526 | 650525 | 6 | Open | 32.1125 | 47.3684 | 60 | 42.2668 | LOW | 0.65 | 1 | 422841.25 | 84568.25 | 169136.5 | 253704.75 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 46
SA-0150 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 2 | 2 | 1 | 16 | 326666 | 538360 | 865026 | 8 | In Progress | 42.7011 | 42.1053 | 40 | 41.9821 | LOW | 0.6 | 0.75 | 389261.7 | 77852.34 | 155704.68 | 233557.02 | Logistics NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 47
SA-0218 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 2 | 2 | 16 | 316666 | 546892 | 863558 | 8 | Closed | 42.6287 | 42.1053 | 40 | 41.9459 | LOW | 0.65 | 0.5 | 280656.35 | 56131.27 | 112262.54 | 168393.81 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 48
SA-0047 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | 3 | 3 | 3 | 14 | 280833 | 462346 | 743179 | 4.6667 | Open | 36.6863 | 36.8421 | 60 | 41.3958 | LOW | 0.3 | 1 | 222953.7 | 44590.74 | 89181.48 | 133772.22 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 49
SA-0050 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 3 | 1 | 16 | 306666 | 372009 | 678675 | 5.3333 | Open | 33.5021 | 42.1053 | 60 | 41.3826 | LOW | 0.65 | 1 | 441138.75 | 88227.75 | 176455.5 | 264683.25 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 50
SA-0246 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 18 | 345000 | 573898 | 918898 | 18 | Closed | 45.3605 | 47.3684 | 20 | 40.8908 | LOW | 0.6 | 0.5 | 275669.4 | 55133.88 | 110267.76 | 165401.64 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 51
SA-0378 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | 2 | 2 | 2 | 20 | 398333 | 293688 | 692021 | 10 | Closed | 34.1609 | 52.6316 | 40 | 40.8699 | LOW | 0.8 | 0.5 | 276808.4 | 55361.68 | 110723.36 | 166085.04 | NPT Hours + ROP | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 52
SA-0301 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 18 | 345000 | 565252 | 910252 | 18 | In Progress | 44.9337 | 47.3684 | 20 | 40.6774 | LOW | 0.8 | 0.75 | 546151.2 | 109230.24 | 218460.48 | 327690.72 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 53
SA-0229 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 20 | 390000 | 291870 | 681870 | 10 | Open | 33.6598 | 52.6316 | 40 | 40.6194 | LOW | 0.9 | 1 | 613683 | 122736.6 | 245473.2 | 368209.8 | Mechanical NPT Hours | 0.15 | 17 | 20 | 17 | >180 Days | Weekly | 54
SA-0126 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | 3 | 3 | 2 | 12 | 236666 | 520254 | 756920 | 4 | Open | 37.3646 | 31.5789 | 60 | 40.156 | LOW | 0.8 | 1 | 605536 | 121107.2 | 242214.4 | 363321.6 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 55
SA-0432 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 18 | 345000 | 503296 | 848296 | 18 | Open | 41.8753 | 47.3684 | 20 | 39.1482 | LOW | 0.9 | 1 | 763466.4 | 152693.28 | 305386.56 | 458079.84 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 56
SA-0316 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | 2 | 2 | 2 | 18 | 355000 | 316484 | 671484 | 9 | Closed | 33.1471 | 47.3684 | 40 | 38.7841 | LOW | 0.3 | 0.5 | 100722.6 | 20144.52 | 40289.04 | 60433.56 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 57
SA-0179 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | 3 | 2 | 2 | 12 | 233333 | 454582 | 687915 | 4 | Closed | 33.9582 | 31.5789 | 60 | 38.4528 | LOW | 0.6 | 0.5 | 206374.5 | 41274.9 | 82549.8 | 123824.7 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 58
SA-0352 | Weather | Lightning | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 18 | 367500 | 445857 | 813357 | 18 | Closed | 40.1506 | 47.3684 | 20 | 38.2858 | LOW | 0.3 | 0.5 | 122003.55 | 24400.71 | 48801.42 | 73202.13 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 59
SA-0091 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | 2 | 2 | 2 | 16 | 321666 | 379930 | 701596 | 8 | Closed | 34.6336 | 42.1053 | 40 | 37.9484 | LOW | 0.8 | 0.5 | 280638.4 | 56127.68 | 112255.36 | 168383.04 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 60
SA-0161 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | 2 | 2 | 2 | 16 | 310000 | 389182 | 699182 | 8 | Closed | 34.5144 | 42.1053 | 40 | 37.8888 | LOW | 0.65 | 0.5 | 227234.15 | 45446.83 | 90893.66 | 136340.49 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 61
SA-0013 | Weather | High Waves | Lightning | Weather | Resume Operations | 2 | 2 | 2 | 14 | 282500 | 479621 | 762121 | 7 | Closed | 37.6213 | 36.8421 | 40 | 37.8633 | LOW | 0.3 | 0.5 | 114318.15 | 22863.63 | 45727.26 | 68590.89 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 62
SA-0095 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 18 | 356250 | 426483 | 782733 | 18 | Closed | 38.6388 | 47.3684 | 20 | 37.5299 | LOW | 0.6 | 0.5 | 234819.9 | 46963.98 | 93927.96 | 140891.94 | Logistics NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 63
SA-0453 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 18 | 345000 | 418285 | 763285 | 18 | Closed | 37.6788 | 47.3684 | 20 | 37.0499 | LOW | 0.7 | 0.5 | 267149.75 | 53429.95 | 106859.9 | 160289.85 | Mechanical NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 64
SA-0299 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | Crew Replacement | 1 | 1 | 1 | 18 | 367500 | 388821 | 756321 | 18 | In Progress | 37.335 | 47.3684 | 20 | 36.878 | LOW | 0.6 | 0.75 | 340344.45 | 68068.89 | 136137.78 | 204206.67 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 65
SA-0115 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | 3 | 3 | 3 | 12 | 238749 | 365010 | 603759 | 4 | Open | 29.804 | 31.5789 | 60 | 36.3757 | LOW | 0.3 | 1 | 181127.7 | 36225.54 | 72451.08 | 108676.62 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 66
SA-0442 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Condition Hole | 1 | 1 | 1 | 18 | 345000 | 390612 | 735612 | 18 | In Progress | 36.3127 | 47.3684 | 20 | 36.3669 | LOW | 0.8 | 0.75 | 441367.2 | 88273.44 | 176546.88 | 264820.32 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 67
SA-0317 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 18 | 345000 | 380594 | 725594 | 18 | Closed | 35.8182 | 47.3684 | 20 | 36.1196 | LOW | 0.8 | 0.5 | 290237.6 | 58047.52 | 116095.04 | 174142.56 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 68
SA-0364 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | 2 | 2 | 1 | 16 | 306666 | 304611 | 611277 | 8 | In Progress | 30.1751 | 42.1053 | 40 | 35.7191 | LOW | 0.9 | 0.75 | 412611.975 | 82522.395 | 165044.79 | 247567.185 | Mechanical NPT Hours | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 69
SA-0132 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | 3 | 3 | 2 | 12 | 237499 | 332937 | 570436 | 4 | Open | 28.159 | 31.5789 | 60 | 35.5532 | LOW | 0.8 | 1 | 456348.8 | 91269.76 | 182539.52 | 273809.28 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 70
SA-0273 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 1 | 16 | 306666 | 297182 | 603848 | 8 | In Progress | 29.8083 | 42.1053 | 40 | 35.5358 | LOW | 0.65 | 0.75 | 294375.9 | 58875.18 | 117750.36 | 176625.54 | NPT Hours + ROP | 0.15 | 13.6 | 16 | 13.6 | >180 Days | Weekly | 71
SA-0350 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | 2 | 2 | 2 | 14 | 275833 | 386541 | 662374 | 7 | Closed | 32.6974 | 36.8421 | 40 | 35.4013 | LOW | 0.3 | 0.5 | 99356.1 | 19871.22 | 39742.44 | 59613.66 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 72
SA-0361 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 2 | 12 | 239999 | 484268 | 724267 | 6 | Open | 35.7527 | 31.5789 | 40 | 35.35 | LOW | 0.65 | 1 | 470773.55 | 94154.71 | 188309.42 | 282464.13 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 73
SA-0017 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 3 | 3 | 2 | 12 | 242499 | 317760 | 560259 | 4 | In Progress | 27.6566 | 31.5789 | 60 | 35.302 | LOW | 0.9 | 0.75 | 378174.825 | 75634.965 | 151269.93 | 226904.895 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 74
SA-0028 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | 2 | 2 | 1 | 14 | 277083 | 376455 | 653538 | 7 | In Progress | 32.2612 | 36.8421 | 40 | 35.1833 | LOW | 0.8 | 0.75 | 392122.8 | 78424.56 | 156849.12 | 235273.68 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 75
SA-0490 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 18 | 360000 | 314096 | 674096 | 18 | Closed | 33.2761 | 47.3684 | 20 | 34.8486 | LOW | 0.8 | 0.5 | 269638.4 | 53927.68 | 107855.36 | 161783.04 | NPT Hours + ROP | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 76
SA-0010 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | 3 | 3 | 2 | 12 | 242499 | 292812 | 535311 | 4 | Open | 26.4251 | 31.5789 | 60 | 34.6862 | LOW | 0.3 | 1 | 160593.3 | 32118.66 | 64237.32 | 96355.98 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 77
SA-0006 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | 2 | 2 | 2 | 14 | 283333 | 349479 | 632812 | 7 | Closed | 31.2381 | 36.8421 | 40 | 34.6717 | LOW | 0.3 | 0.5 | 94921.8 | 18984.36 | 37968.72 | 56953.08 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 78
SA-0153 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | 2 | 2 | 2 | 14 | 278750 | 341823 | 620573 | 7 | Closed | 30.634 | 36.8421 | 40 | 34.3696 | LOW | 0.6 | 0.5 | 186171.9 | 37234.38 | 74468.76 | 111703.14 | Personnel NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 79
SA-0005 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | 3 | 3 | 1 | 12 | 244999 | 274737 | 519736 | 4 | Closed | 25.6562 | 31.5789 | 60 | 34.3018 | LOW | 0.7 | 0.5 | 181907.6 | 36381.52 | 72763.04 | 109144.56 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 80
SA-0292 | Weather | High Waves | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 12 | 245000 | 580843 | 825843 | 12 | In Progress | 40.7669 | 31.5789 | 20 | 33.8571 | LOW | 0.3 | 0.75 | 185814.675 | 37162.935 | 74325.87 | 111488.805 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 81
SA-0058 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | 2 | 2 | 1 | 12 | 230000 | 432865 | 662865 | 6 | Open | 32.7217 | 31.5789 | 40 | 33.8345 | LOW | 0.9 | 1 | 596578.5 | 119315.7 | 238631.4 | 357947.1 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 82
SA-0044 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | 2 | 2 | 2 | 14 | 275833 | 314795 | 590628 | 7 | Closed | 29.1558 | 36.8421 | 40 | 33.6305 | LOW | 0.9 | 0.5 | 265782.6 | 53156.52 | 106313.04 | 159469.56 | Mechanical NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 83
SA-0176 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 2 | 2 | 14 | 275000 | 315044 | 590044 | 7 | Open | 29.1269 | 36.8421 | 40 | 33.6161 | LOW | 0.65 | 1 | 383528.6 | 76705.72 | 153411.44 | 230117.16 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 84
SA-0051 | Weather | Lightning | Lightning | Weather | Wait on Weather | 2 | 2 | 1 | 14 | 268333 | 320404 | 588737 | 7 | In Progress | 29.0624 | 36.8421 | 40 | 33.5838 | LOW | 0.3 | 0.75 | 132465.825 | 26493.165 | 52986.33 | 79479.495 | Weather NPT Hours | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 85
SA-0400 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | 2 | 2 | 2 | 12 | 236666 | 406159 | 642825 | 6 | Open | 31.7324 | 31.5789 | 40 | 33.3399 | LOW | 0.65 | 1 | 417836.25 | 83567.25 | 167134.5 | 250701.75 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 86
SA-0180 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 3 | 3 | 3 | 10 | 200833 | 341199 | 542032 | 3.3333 | In Progress | 26.7569 | 26.3158 | 60 | 33.2732 | LOW | 0.65 | 0.75 | 264240.6 | 52848.12 | 105696.24 | 158544.36 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 87
SA-0139 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 554806 | 799806 | 12 | Closed | 39.4816 | 31.5789 | 20 | 33.2145 | LOW | 0.8 | 0.5 | 319922.4 | 63984.48 | 127968.96 | 191953.44 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 88
SA-0481 | Personnel | Crew Change | Crew Rotation | Rig Management | Medical Clearance | 1 | 1 | 1 | 18 | 367500 | 236304 | 603804 | 18 | Closed | 29.8062 | 47.3684 | 20 | 33.1136 | LOW | 0.6 | 0.5 | 181141.2 | 36228.24 | 72456.48 | 108684.72 | Personnel NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 89
SA-0338 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 2 | 2 | 10 | 201666 | 487332 | 688998 | 5 | In Progress | 34.0117 | 26.3158 | 40 | 32.9006 | LOW | 0.9 | 0.75 | 465073.65 | 93014.73 | 186029.46 | 279044.19 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 90
SA-0290 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 539466 | 784466 | 12 | Closed | 38.7244 | 31.5789 | 20 | 32.8359 | LOW | 0.8 | 0.5 | 313786.4 | 62757.28 | 125514.56 | 188271.84 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 91
SA-0074 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | 2 | 2 | 2 | 12 | 234999 | 378680 | 613679 | 6 | In Progress | 30.2936 | 31.5789 | 40 | 32.6205 | LOW | 0.3 | 0.75 | 138077.775 | 27615.555 | 55231.11 | 82846.665 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 92
SA-0011 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | 2 | 2 | 2 | 10 | 199166 | 463374 | 662540 | 5 | Open | 32.7056 | 26.3158 | 40 | 32.2475 | LOW | 0.3 | 1 | 198762 | 39752.4 | 79504.8 | 119257.2 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 93
SA-0045 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | 2 | 2 | 1 | 12 | 244999 | 347986 | 592985 | 6 | Closed | 29.2721 | 31.5789 | 40 | 32.1097 | LOW | 0.3 | 0.5 | 88947.75 | 17789.55 | 35579.1 | 53368.65 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 94
SA-0171 | Drilling | Stuck Pipe | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 12 | 245000 | 508399 | 753399 | 12 | Closed | 37.1908 | 31.5789 | 20 | 32.0691 | LOW | 0.8 | 0.5 | 301359.6 | 60271.92 | 120543.84 | 180815.76 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 95
SA-0325 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 10 | 196666 | 457574 | 654240 | 5 | Open | 32.2959 | 26.3158 | 40 | 32.0427 | LOW | 0.3 | 1 | 196272 | 39254.4 | 78508.8 | 117763.2 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 96
SA-0382 | Weather | High Waves | Strong Wind | Marine Operations | Resume Operations | 1 | 1 | 1 | 18 | 360000 | 200297 | 560297 | 18 | Open | 27.6585 | 47.3684 | 20 | 32.0398 | LOW | 0.3 | 1 | 168089.1 | 33617.82 | 67235.64 | 100853.46 | Weather NPT Hours | 0.15 | 15.3 | 18 | 15.3 | >180 Days | Weekly | 97
SA-0030 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 2 | 2 | 12 | 234999 | 331197 | 566196 | 6 | Open | 27.9497 | 31.5789 | 40 | 31.4485 | LOW | 0.9 | 1 | 509576.4 | 101915.28 | 203830.56 | 305745.84 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 98
SA-0237 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 10 | 203333 | 426701 | 630034 | 5 | Closed | 31.101 | 26.3158 | 40 | 31.4452 | LOW | 0.7 | 0.5 | 220511.9 | 44102.38 | 88204.76 | 132307.14 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 99
SA-0251 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | 2 | 2 | 1 | 14 | 277083 | 222114 | 499197 | 7 | Open | 24.6424 | 36.8421 | 40 | 31.3738 | LOW | 0.8 | 1 | 399357.6 | 79871.52 | 159743.04 | 239614.56 | NPT Hours + ROP | 0.15 | 11.9 | 14 | 11.9 | >180 Days | Weekly | 100
SA-0419 | Weather | Lightning | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 12 | 230000 | 493028 | 723028 | 12 | In Progress | 35.6916 | 31.5789 | 20 | 31.3195 | LOW | 0.3 | 0.75 | 162681.3 | 32536.26 | 65072.52 | 97608.78 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 101
SA-0125 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 199166 | 421566 | 620732 | 5 | In Progress | 30.6418 | 26.3158 | 40 | 31.2156 | LOW | 0.65 | 0.75 | 302606.85 | 60521.37 | 121042.74 | 181564.11 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 102
SA-0421 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | 2 | 2 | 1 | 12 | 229999 | 320012 | 550011 | 6 | Closed | 27.1507 | 31.5789 | 40 | 31.0491 | LOW | 0.8 | 0.5 | 220004.4 | 44000.88 | 88001.76 | 132002.64 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 103
SA-0402 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 1 | 12 | 229999 | 319959 | 549958 | 6 | Open | 27.1481 | 31.5789 | 40 | 31.0477 | LOW | 0.65 | 1 | 357472.7 | 71494.54 | 142989.08 | 214483.62 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 104
SA-0007 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | 2 | 2 | 1 | 12 | 244999 | 276910 | 521909 | 6 | Closed | 25.7635 | 31.5789 | 40 | 30.3554 | LOW | 0.8 | 0.5 | 208763.6 | 41752.72 | 83505.44 | 125258.16 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 105
SA-0266 | Weather | Lightning | Storm | Weather | Resume Operations | 1 | 1 | 1 | 12 | 245000 | 431874 | 676874 | 12 | Closed | 33.4132 | 31.5789 | 20 | 30.1803 | LOW | 0.3 | 0.5 | 101531.1 | 20306.22 | 40612.44 | 60918.66 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 106
SA-0302 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | 3 | 3 | 2 | 10 | 194166 | 218892 | 413058 | 3.3333 | Open | 20.3902 | 26.3158 | 60 | 30.0898 | LOW | 0.3 | 1 | 123917.4 | 24783.48 | 49566.96 | 74350.44 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 107
SA-0001 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | 2 | 2 | 2 | 10 | 199166 | 375778 | 574944 | 5 | Open | 28.3815 | 26.3158 | 40 | 30.0855 | LOW | 0.6 | 1 | 344966.4 | 68993.28 | 137986.56 | 206979.84 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 108
SA-0336 | Weather | High Waves | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 12 | 230000 | 429330 | 659330 | 12 | Closed | 32.5472 | 31.5789 | 20 | 29.7473 | LOW | 0.3 | 0.5 | 98899.5 | 19779.9 | 39559.8 | 59339.7 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 109
SA-0337 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 12 | 230000 | 418094 | 648094 | 12 | Closed | 31.9925 | 31.5789 | 20 | 29.4699 | LOW | 0.9 | 0.5 | 291642.3 | 58328.46 | 116656.92 | 174985.38 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 110
SA-0015 | Weather | High Waves | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 12 | 245000 | 394548 | 639548 | 12 | Closed | 31.5706 | 31.5789 | 20 | 29.259 | LOW | 0.3 | 0.5 | 95932.2 | 19186.44 | 38372.88 | 57559.32 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 111
SA-0368 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 12 | 230000 | 407608 | 637608 | 12 | Closed | 31.4749 | 31.5789 | 20 | 29.2111 | LOW | 0.6 | 0.5 | 191282.4 | 38256.48 | 76512.96 | 114769.44 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 112
SA-0455 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 12 | 230000 | 403320 | 633320 | 12 | Closed | 31.2632 | 31.5789 | 20 | 29.1053 | LOW | 0.6 | 0.5 | 189996 | 37999.2 | 75998.4 | 113997.6 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 113
SA-0425 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 196666 | 337978 | 534644 | 5 | Closed | 26.3922 | 26.3158 | 40 | 29.0908 | LOW | 0.65 | 0.5 | 173759.3 | 34751.86 | 69503.72 | 104255.58 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 114
SA-0366 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | 2 | 2 | 1 | 12 | 229999 | 237442 | 467441 | 6 | Closed | 23.0748 | 31.5789 | 40 | 29.0111 | LOW | 0.3 | 0.5 | 70116.15 | 14023.23 | 28046.46 | 42069.69 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 115
SA-0469 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 12 | 240000 | 374455 | 614455 | 12 | Closed | 30.332 | 31.5789 | 20 | 28.6397 | LOW | 0.6 | 0.5 | 184336.5 | 36867.3 | 73734.6 | 110601.9 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 116
SA-0501 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 12 | 245000 | 368627 | 613627 | 12 | Closed | 30.2911 | 31.5789 | 20 | 28.6192 | LOW | 0.8 | 0.5 | 245450.8 | 49090.16 | 98180.32 | 147270.48 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 117
SA-0224 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 12 | 240000 | 366765 | 606765 | 12 | Closed | 29.9523 | 31.5789 | 20 | 28.4499 | LOW | 0.6 | 0.5 | 182029.5 | 36405.9 | 72811.8 | 109217.7 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 118
SA-0004 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 10 | 201666 | 303664 | 505330 | 5 | Closed | 24.9451 | 26.3158 | 40 | 28.3673 | LOW | 0.6 | 0.5 | 151599 | 30319.8 | 60639.6 | 90959.4 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 119
SA-0129 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | 2 | 2 | 2 | 10 | 201666 | 288567 | 490233 | 5 | Closed | 24.1999 | 26.3158 | 40 | 27.9947 | LOW | 0.3 | 0.5 | 73534.95 | 14706.99 | 29413.98 | 44120.97 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 120
SA-0330 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | 2 | 2 | 1 | 12 | 229999 | 191770 | 421769 | 6 | In Progress | 20.8202 | 31.5789 | 40 | 27.8838 | LOW | 0.6 | 0.75 | 189796.05 | 37959.21 | 75918.42 | 113877.63 | Personnel NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 121
SA-0103 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 2 | 2 | 1 | 8 | 153333 | 372524 | 525857 | 4 | Open | 25.9584 | 21.0526 | 40 | 27.295 | LOW | 0.65 | 1 | 341807.05 | 68361.41 | 136722.82 | 205084.23 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 122
SA-0111 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 10 | 195416 | 263218 | 458634 | 5 | Open | 22.64 | 26.3158 | 40 | 27.2147 | LOW | 0.9 | 1 | 412770.6 | 82554.12 | 165108.24 | 247662.36 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 123
SA-0314 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 8 | 156666 | 354270 | 510936 | 4 | Open | 25.2218 | 21.0526 | 40 | 26.9267 | LOW | 0.6 | 1 | 306561.6 | 61312.32 | 122624.64 | 183936.96 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 124
SA-0106 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 154583 | 343057 | 497640 | 4 | Closed | 24.5655 | 21.0526 | 40 | 26.5985 | LOW | 0.3 | 0.5 | 74646 | 14929.2 | 29858.4 | 44787.6 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 125
SA-0385 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 12 | 240000 | 291067 | 531067 | 12 | Closed | 26.2156 | 31.5789 | 20 | 26.5815 | LOW | 0.8 | 0.5 | 212426.8 | 42485.36 | 84970.72 | 127456.08 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 126
SA-0441 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | 2 | 2 | 2 | 8 | 160833 | 335439 | 496272 | 4 | In Progress | 24.498 | 21.0526 | 40 | 26.5648 | LOW | 0.3 | 0.75 | 111661.2 | 22332.24 | 44664.48 | 66996.72 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 127
SA-0255 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | 2 | 2 | 2 | 10 | 192916 | 237182 | 430098 | 5 | In Progress | 21.2314 | 26.3158 | 40 | 26.5104 | LOW | 0.3 | 0.75 | 96772.05 | 19354.41 | 38708.82 | 58063.23 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 128
SA-0212 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Condition Hole | 1 | 1 | 1 | 12 | 245000 | 278344 | 523344 | 12 | Closed | 25.8344 | 31.5789 | 20 | 26.3909 | LOW | 0.65 | 0.5 | 170086.8 | 34017.36 | 68034.72 | 102052.08 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 129
SA-0184 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 2 | 2 | 8 | 154999 | 149294 | 304293 | 2.6667 | Open | 15.0211 | 21.0526 | 60 | 25.8263 | LOW | 0.65 | 1 | 197790.45 | 39558.09 | 79116.18 | 118674.27 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 130
SA-0291 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 2 | 1 | 10 | 204166 | 193759 | 397925 | 5 | In Progress | 19.6432 | 26.3158 | 40 | 25.7163 | LOW | 0.65 | 0.75 | 193988.4375 | 38797.6875 | 77595.375 | 116393.0625 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 131
SA-0240 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 12 | 230000 | 265392 | 495392 | 12 | Closed | 24.4545 | 31.5789 | 20 | 25.7009 | LOW | 0.9 | 0.5 | 222926.4 | 44585.28 | 89170.56 | 133755.84 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 132
SA-0306 | Weather | Lightning | High Waves | Weather | Suspend Operations | 1 | 1 | 1 | 12 | 230000 | 258903 | 488903 | 12 | Closed | 24.1342 | 31.5789 | 20 | 25.5408 | LOW | 0.3 | 0.5 | 73335.45 | 14667.09 | 29334.18 | 44001.27 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 133
SA-0137 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | 2 | 2 | 2 | 10 | 201666 | 188549 | 390215 | 5 | In Progress | 19.2626 | 26.3158 | 40 | 25.526 | LOW | 0.3 | 0.75 | 87798.375 | 17559.675 | 35119.35 | 52679.025 | Weather NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 134
SA-0206 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 2 | 2 | 2 | 8 | 158332 | 281116 | 439448 | 4 | In Progress | 21.6929 | 21.0526 | 40 | 25.1622 | LOW | 0.9 | 0.75 | 296627.4 | 59325.48 | 118650.96 | 177976.44 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 135
SA-0083 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 2 | 8 | 159166 | 271976 | 431142 | 4 | Closed | 21.2829 | 21.0526 | 40 | 24.9572 | LOW | 0.8 | 0.5 | 172456.8 | 34491.36 | 68982.72 | 103474.08 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 136
SA-0117 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 12 | 237500 | 223755 | 461255 | 12 | Closed | 22.7694 | 31.5789 | 20 | 24.8584 | LOW | 0.6 | 0.5 | 138376.5 | 27675.3 | 55350.6 | 83025.9 | Logistics NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 137
SA-0131 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | 2 | 2 | 2 | 8 | 158332 | 268310 | 426642 | 4 | Closed | 21.0608 | 21.0526 | 40 | 24.8462 | LOW | 0.3 | 0.5 | 63996.3 | 12799.26 | 25598.52 | 38397.78 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 138
SA-0077 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | 2 | 2 | 2 | 10 | 199166 | 161598 | 360764 | 5 | Closed | 17.8088 | 26.3158 | 40 | 24.7991 | LOW | 0.6 | 0.5 | 108229.2 | 21645.84 | 43291.68 | 64937.52 | Logistics NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 139
SA-0052 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 2 | 2 | 10 | 198333 | 161890 | 360223 | 5 | Open | 17.782 | 26.3158 | 40 | 24.7858 | LOW | 0.65 | 1 | 234144.95 | 46828.99 | 93657.98 | 140486.97 | NPT Hours + ROP | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 140
SA-0041 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | 2 | 2 | 2 | 8 | 160833 | 262056 | 422889 | 4 | Closed | 20.8755 | 21.0526 | 40 | 24.7535 | LOW | 0.9 | 0.5 | 190300.05 | 38060.01 | 76120.02 | 114180.03 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 141
SA-0186 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 2 | 2 | 8 | 158333 | 264510 | 422843 | 4 | Closed | 20.8732 | 21.0526 | 40 | 24.7524 | LOW | 0.8 | 0.5 | 169137.2 | 33827.44 | 67654.88 | 101482.32 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 142
SA-0169 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 2 | 2 | 2 | 8 | 160832 | 254020 | 414852 | 4 | Closed | 20.4788 | 21.0526 | 40 | 24.5552 | LOW | 0.9 | 0.5 | 186683.4 | 37336.68 | 74673.36 | 112010.04 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 143
SA-0248 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | 2 | 2 | 2 | 8 | 160833 | 252168 | 413001 | 4 | Closed | 20.3874 | 21.0526 | 40 | 24.5095 | LOW | 0.6 | 0.5 | 123900.3 | 24780.06 | 49560.12 | 74340.18 | Personnel NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 144
SA-0146 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | 2 | 2 | 1 | 10 | 204166 | 138905 | 343071 | 5 | Closed | 16.9354 | 26.3158 | 40 | 24.3624 | LOW | 0.9 | 0.5 | 154381.95 | 30876.39 | 61752.78 | 92629.17 | Mechanical NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 145
SA-0496 | Drilling | Lost Circulation | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 163333 | 405188 | 568521 | 8 | Open | 28.0645 | 21.0526 | 20 | 24.348 | LOW | 0.8 | 1 | 454816.8 | 90963.36 | 181926.72 | 272890.08 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 146
SA-0178 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 160000 | 393128 | 553128 | 8 | Closed | 27.3046 | 21.0526 | 20 | 23.9681 | LOW | 0.9 | 0.5 | 248907.6 | 49781.52 | 99563.04 | 149344.56 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 147
SA-0061 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | 2 | 2 | 1 | 10 | 191666 | 135250 | 326916 | 5 | Closed | 16.1379 | 26.3158 | 40 | 23.9637 | LOW | 0.6 | 0.5 | 98074.8 | 19614.96 | 39229.92 | 58844.88 | Personnel NPT Hours | 0.15 | 8.5 | 10 | 8.5 | >180 Days | Weekly | 148
SA-0070 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 157083 | 226281 | 383364 | 4 | In Progress | 18.9244 | 21.0526 | 40 | 23.778 | LOW | 0.3 | 0.75 | 86256.9 | 17251.38 | 34502.76 | 51754.14 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 149
SA-0424 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 8 | 155833 | 227263 | 383096 | 4 | Closed | 18.9111 | 21.0526 | 40 | 23.7714 | LOW | 0.3 | 0.5 | 57464.4 | 11492.88 | 22985.76 | 34478.64 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 150
SA-0029 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 2 | 2 | 8 | 160832 | 221794 | 382626 | 4 | Closed | 18.8879 | 21.0526 | 40 | 23.7598 | LOW | 0.6 | 0.5 | 114787.8 | 22957.56 | 45915.12 | 68872.68 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 151
SA-0046 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 2 | 2 | 8 | 158333 | 212501 | 370834 | 4 | Closed | 18.3058 | 21.0526 | 40 | 23.4687 | LOW | 0.8 | 0.5 | 148333.6 | 29666.72 | 59333.44 | 89000.16 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 152
SA-0231 | Weather | High Waves | Heavy Rain | Marine Operations | Suspend Operations | 1 | 1 | 1 | 8 | 160000 | 364772 | 524772 | 8 | Open | 25.9048 | 21.0526 | 20 | 23.2682 | LOW | 0.3 | 1 | 157431.6 | 31486.32 | 62972.64 | 94458.96 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 153
SA-0334 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 363755 | 517088 | 8 | Closed | 25.5255 | 21.0526 | 20 | 23.0786 | LOW | 0.9 | 0.5 | 232689.6 | 46537.92 | 93075.84 | 139613.76 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 154
SA-0096 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 158333 | 357164 | 515497 | 8 | Closed | 25.447 | 21.0526 | 20 | 23.0393 | LOW | 0.9 | 0.5 | 231973.65 | 46394.73 | 92789.46 | 139184.19 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 155
SA-0420 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | 2 | 2 | 1 | 8 | 153332 | 193661 | 346993 | 4 | In Progress | 17.129 | 21.0526 | 40 | 22.8803 | LOW | 0.3 | 0.75 | 78073.425 | 15614.685 | 31229.37 | 46844.055 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 156
SA-0313 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 12 | 230000 | 150405 | 380405 | 12 | Closed | 18.7783 | 31.5789 | 20 | 22.8628 | LOW | 0.65 | 0.5 | 123631.625 | 24726.325 | 49452.65 | 74178.975 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 157
SA-0467 | Weather | Heavy Rain | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 12 | 245000 | 133994 | 378994 | 12 | Closed | 18.7087 | 31.5789 | 20 | 22.828 | LOW | 0.3 | 0.5 | 56849.1 | 11369.82 | 22739.64 | 34109.46 | Weather NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 158
SA-0059 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | 2 | 2 | 1 | 8 | 153333 | 190713 | 344046 | 4 | In Progress | 16.9835 | 21.0526 | 40 | 22.8075 | LOW | 0.3 | 0.75 | 77410.35 | 15482.07 | 30964.14 | 46446.21 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 159
SA-0071 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 347820 | 501153 | 8 | Closed | 24.7389 | 21.0526 | 20 | 22.6852 | LOW | 0.9 | 0.5 | 225518.85 | 45103.77 | 90207.54 | 135311.31 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 160
SA-0367 | Weather | Strong Wind | High Waves | Weather | Wait on Weather | 1 | 1 | 1 | 8 | 153333 | 347209 | 500542 | 8 | Closed | 24.7088 | 21.0526 | 20 | 22.6702 | LOW | 0.3 | 0.5 | 75081.3 | 15016.26 | 30032.52 | 45048.78 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 161
SA-0039 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | 2 | 2 | 2 | 6 | 119999 | 282138 | 402137 | 3 | Closed | 19.8511 | 15.7895 | 40 | 22.6624 | LOW | 0.6 | 0.5 | 120641.1 | 24128.22 | 48256.44 | 72384.66 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 162
SA-0310 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 153333 | 342295 | 495628 | 8 | Open | 24.4662 | 21.0526 | 20 | 22.5489 | LOW | 0.65 | 1 | 322158.2 | 64431.64 | 128863.28 | 193294.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 163
SA-0221 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | 2 | 2 | 1 | 8 | 160000 | 170172 | 330172 | 4 | Closed | 16.2986 | 21.0526 | 40 | 22.4651 | LOW | 0.8 | 0.5 | 132068.8 | 26413.76 | 52827.52 | 79241.28 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 164
SA-0216 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 2 | 2 | 8 | 156666 | 173136 | 329802 | 4 | Closed | 16.2803 | 21.0526 | 40 | 22.456 | LOW | 0.65 | 0.5 | 107185.65 | 21437.13 | 42874.26 | 64311.39 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 165
SA-0215 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 12 | 240000 | 123301 | 363301 | 12 | Open | 17.934 | 31.5789 | 20 | 22.4407 | LOW | 0.9 | 1 | 326970.9 | 65394.18 | 130788.36 | 196182.54 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 166
SA-0401 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 12 | 230000 | 132340 | 362340 | 12 | Closed | 17.8865 | 31.5789 | 20 | 22.417 | LOW | 0.8 | 0.5 | 144936 | 28987.2 | 57974.4 | 86961.6 | NPT Hours + ROP | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 167
SA-0085 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | 2 | 2 | 2 | 8 | 155832 | 161232 | 317064 | 4 | In Progress | 15.6515 | 21.0526 | 40 | 22.1416 | LOW | 0.3 | 0.75 | 71339.4 | 14267.88 | 28535.76 | 42803.64 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 168
SA-0055 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 12 | 230000 | 121023 | 351023 | 12 | Closed | 17.3279 | 31.5789 | 20 | 22.1376 | LOW | 0.9 | 0.5 | 157960.35 | 31592.07 | 63184.14 | 94776.21 | Mechanical NPT Hours | 0.15 | 10.2 | 12 | 10.2 | >180 Days | Weekly | 169
SA-0433 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Air Freight Materials | 1 | 1 | 1 | 8 | 153333 | 317647 | 470980 | 8 | Closed | 23.2495 | 21.0526 | 20 | 21.9405 | LOW | 0.6 | 0.5 | 141294 | 28258.8 | 56517.6 | 84776.4 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 170
SA-0471 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 8 | 160000 | 306975 | 466975 | 8 | Closed | 23.0518 | 21.0526 | 20 | 21.8417 | LOW | 0.8 | 0.5 | 186790 | 37358 | 74716 | 112074 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 171
SA-0166 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | 2 | 2 | 1 | 8 | 160000 | 143591 | 303591 | 4 | Closed | 14.9865 | 21.0526 | 40 | 21.809 | LOW | 0.8 | 0.5 | 121436.4 | 24287.28 | 48574.56 | 72861.84 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 172
SA-0254 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 158333 | 298315 | 456648 | 8 | Open | 22.542 | 21.0526 | 20 | 21.5868 | LOW | 0.9 | 1 | 410983.2 | 82196.64 | 164393.28 | 246589.92 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 173
SA-0349 | Weather | Heavy Rain | Lightning | Marine Operations | Suspend Operations | 1 | 1 | 1 | 8 | 163333 | 288692 | 452025 | 8 | Closed | 22.3138 | 21.0526 | 20 | 21.4727 | LOW | 0.3 | 0.5 | 67803.75 | 13560.75 | 27121.5 | 40682.25 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 174
SA-0156 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 2 | 2 | 8 | 155000 | 133274 | 288274 | 4 | Closed | 14.2304 | 21.0526 | 40 | 21.431 | LOW | 0.6 | 0.5 | 86482.2 | 17296.44 | 34592.88 | 51889.32 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 175
SA-0487 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 8 | 153333 | 289177 | 442510 | 8 | Closed | 21.8441 | 21.0526 | 20 | 21.2378 | LOW | 0.8 | 0.5 | 177004 | 35400.8 | 70801.6 | 106202.4 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 176
SA-0082 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 286906 | 440239 | 8 | In Progress | 21.732 | 21.0526 | 20 | 21.1818 | LOW | 0.9 | 0.75 | 297161.325 | 59432.265 | 118864.53 | 178296.795 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 177
SA-0417 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | 2 | 2 | 2 | 6 | 119999 | 221517 | 341516 | 3 | Closed | 16.8586 | 15.7895 | 40 | 21.1661 | LOW | 0.3 | 0.5 | 51227.4 | 10245.48 | 20490.96 | 30736.44 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 178
SA-0322 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 279943 | 433276 | 8 | In Progress | 21.3882 | 21.0526 | 20 | 21.0099 | LOW | 0.9 | 0.75 | 292461.3 | 58492.26 | 116984.52 | 175476.78 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 179
SA-0357 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 163333 | 267513 | 430846 | 8 | Closed | 21.2683 | 21.0526 | 20 | 20.9499 | LOW | 0.9 | 0.5 | 193880.7 | 38776.14 | 77552.28 | 116328.42 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 180
SA-0311 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 153333 | 276056 | 429389 | 8 | In Progress | 21.1964 | 21.0526 | 20 | 20.914 | LOW | 0.9 | 0.75 | 289837.575 | 57967.515 | 115935.03 | 173902.545 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 181
SA-0407 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | 2 | 2 | 2 | 6 | 119999 | 211261 | 331260 | 3 | Closed | 16.3523 | 15.7895 | 40 | 20.913 | LOW | 0.8 | 0.5 | 132504 | 26500.8 | 53001.6 | 79502.4 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 182
SA-0429 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | 2 | 2 | 1 | 6 | 114999 | 212937 | 327936 | 3 | In Progress | 16.1882 | 15.7895 | 40 | 20.831 | LOW | 0.6 | 0.75 | 147571.2 | 29514.24 | 59028.48 | 88542.72 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 183
SA-0296 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 2 | 1 | 6 | 122499 | 195352 | 317851 | 3 | Closed | 15.6904 | 15.7895 | 40 | 20.582 | LOW | 0.9 | 0.5 | 143032.95 | 28606.59 | 57213.18 | 85819.77 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 184
SA-0280 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 260743 | 414076 | 8 | Closed | 20.4404 | 21.0526 | 20 | 20.536 | LOW | 0.7 | 0.5 | 144926.6 | 28985.32 | 57970.64 | 86955.96 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 185
SA-0295 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 163333 | 249120 | 412453 | 8 | Closed | 20.3603 | 21.0526 | 20 | 20.496 | LOW | 0.9 | 0.5 | 185603.85 | 37120.77 | 74241.54 | 111362.31 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 186
SA-0482 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 8 | 163333 | 248690 | 412023 | 8 | Closed | 20.3391 | 21.0526 | 20 | 20.4853 | LOW | 0.65 | 0.5 | 133907.475 | 26781.495 | 53562.99 | 80344.485 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 187
SA-0457 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 2 | 1 | 8 | 160000 | 85257 | 245257 | 4 | In Progress | 12.1069 | 21.0526 | 40 | 20.3692 | LOW | 0.6 | 0.75 | 110365.65 | 22073.13 | 44146.26 | 66219.39 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 188
SA-0062 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 252476 | 405809 | 8 | Closed | 20.0324 | 21.0526 | 20 | 20.332 | LOW | 0.9 | 0.5 | 182614.05 | 36522.81 | 73045.62 | 109568.43 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 189
SA-0256 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | 2 | 2 | 2 | 6 | 117499 | 189151 | 306650 | 3 | In Progress | 15.1375 | 15.7895 | 40 | 20.3056 | LOW | 0.3 | 0.75 | 68996.25 | 13799.25 | 27598.5 | 41397.75 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 190
SA-0309 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | 2 | 2 | 2 | 6 | 117499 | 186352 | 303851 | 3 | Closed | 14.9993 | 15.7895 | 40 | 20.2365 | LOW | 0.3 | 0.5 | 45577.65 | 9115.53 | 18231.06 | 27346.59 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 191
SA-0406 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 8 | 163333 | 237483 | 400816 | 8 | Closed | 19.7859 | 21.0526 | 20 | 20.2087 | LOW | 0.9 | 0.5 | 180367.2 | 36073.44 | 72146.88 | 108220.32 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 192
SA-0454 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 2 | 1 | 6 | 114999 | 187090 | 302089 | 3 | In Progress | 14.9123 | 15.7895 | 40 | 20.193 | LOW | 0.9 | 0.75 | 203910.075 | 40782.015 | 81564.03 | 122346.045 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 193
SA-0244 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 153333 | 239111 | 392444 | 8 | Closed | 19.3726 | 21.0526 | 20 | 20.0021 | LOW | 0.6 | 0.5 | 117733.2 | 23546.64 | 47093.28 | 70639.92 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 194
SA-0172 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | 2 | 2 | 2 | 6 | 120833 | 168955 | 289788 | 3 | Open | 14.3051 | 15.7895 | 40 | 19.8894 | LOW | 0.3 | 1 | 86936.4 | 17387.28 | 34774.56 | 52161.84 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 195
SA-0075 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 153333 | 232289 | 385622 | 8 | Closed | 19.0358 | 21.0526 | 20 | 19.8337 | LOW | 0.6 | 0.5 | 115686.6 | 23137.32 | 46274.64 | 69411.96 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 196
SA-0475 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 8 | 160000 | 218432 | 378432 | 8 | Open | 18.6809 | 21.0526 | 20 | 19.6562 | LOW | 0.9 | 1 | 340588.8 | 68117.76 | 136235.52 | 204353.28 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 197
SA-0480 | Drilling | Hole Cleaning | Differential Sticking | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 163333 | 205525 | 368858 | 8 | Closed | 18.2083 | 21.0526 | 20 | 19.4199 | LOW | 0.8 | 0.5 | 147543.2 | 29508.64 | 59017.28 | 88525.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 198
SA-0435 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 8 | 153333 | 214639 | 367972 | 8 | Closed | 18.1646 | 21.0526 | 20 | 19.3981 | LOW | 0.65 | 0.5 | 119590.9 | 23918.18 | 47836.36 | 71754.54 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 199
SA-0192 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 2 | 2 | 6 | 117499 | 151879 | 269378 | 3 | In Progress | 13.2976 | 15.7895 | 40 | 19.3856 | LOW | 0.65 | 0.75 | 131321.775 | 26264.355 | 52528.71 | 78793.065 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 200
SA-0434 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Condition Hole | 1 | 1 | 1 | 8 | 153333 | 210689 | 364022 | 8 | In Progress | 17.9696 | 21.0526 | 20 | 19.3006 | LOW | 0.8 | 0.75 | 218413.2 | 43682.64 | 87365.28 | 131047.92 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 201
SA-0354 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Air Freight Materials | 1 | 1 | 1 | 6 | 122500 | 301536 | 424036 | 6 | Closed | 20.9321 | 15.7895 | 20 | 19.2029 | LOW | 0.6 | 0.5 | 127210.8 | 25442.16 | 50884.32 | 76326.48 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 202
SA-0329 | Drilling | Lost Circulation | Differential Sticking | Operator | Run Fishing Tools | 1 | 1 | 1 | 8 | 153333 | 201314 | 354647 | 8 | Closed | 17.5068 | 21.0526 | 20 | 19.0692 | LOW | 0.8 | 0.5 | 141858.8 | 28371.76 | 56743.52 | 85115.28 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 203
SA-0133 | Weather | Lightning | Lightning | Weather | Resume Operations | 2 | 2 | 2 | 6 | 119999 | 136286 | 256285 | 3 | Closed | 12.6513 | 15.7895 | 40 | 19.0625 | LOW | 0.3 | 0.5 | 38442.75 | 7688.55 | 15377.1 | 23065.65 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 204
SA-0181 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 6 | 120000 | 295691 | 415691 | 6 | Closed | 20.5202 | 15.7895 | 20 | 18.9969 | LOW | 0.6 | 0.5 | 124707.3 | 24941.46 | 49882.92 | 74824.38 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 205
SA-0259 | Logistics | Waiting on Materials | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 8 | 158333 | 193285 | 351618 | 8 | Open | 17.3573 | 21.0526 | 20 | 18.9944 | LOW | 0.6 | 1 | 210970.8 | 42194.16 | 84388.32 | 126582.48 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 206
SA-0089 | Weather | Lightning | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 8 | 158333 | 192897 | 351230 | 8 | In Progress | 17.3381 | 21.0526 | 20 | 18.9848 | LOW | 0.3 | 0.75 | 79026.75 | 15805.35 | 31610.7 | 47416.05 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 207
SA-0495 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 6 | 120000 | 294858 | 414858 | 6 | Closed | 20.479 | 15.7895 | 20 | 18.9764 | LOW | 0.8 | 0.5 | 165943.2 | 33188.64 | 66377.28 | 99565.92 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 208
SA-0502 | Drilling | Stuck Pipe | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 8 | 163333 | 182981 | 346314 | 8 | Closed | 17.0954 | 21.0526 | 20 | 18.8635 | LOW | 0.65 | 0.5 | 112552.05 | 22510.41 | 45020.82 | 67531.23 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 209
SA-0114 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 118750 | 291172 | 409922 | 6 | In Progress | 20.2354 | 15.7895 | 20 | 18.8545 | LOW | 0.8 | 0.75 | 245953.2 | 49190.64 | 98381.28 | 147571.92 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 210
SA-0462 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 8 | 160000 | 185853 | 345853 | 8 | Closed | 17.0727 | 21.0526 | 20 | 18.8521 | LOW | 0.65 | 0.5 | 112402.225 | 22480.445 | 44960.89 | 67441.335 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 211
SA-0315 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 2 | 1 | 6 | 114999 | 126753 | 241752 | 3 | In Progress | 11.9338 | 15.7895 | 40 | 18.7038 | LOW | 0.8 | 0.75 | 145051.2 | 29010.24 | 58020.48 | 87030.72 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 212
SA-0116 | Weather | Strong Wind | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 118750 | 279850 | 398600 | 6 | In Progress | 19.6765 | 15.7895 | 20 | 18.5751 | LOW | 0.3 | 0.75 | 89685 | 17937 | 35874 | 53811 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 213
SA-0384 | Drilling | Bit Failure | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 6 | 120000 | 273652 | 393652 | 6 | Closed | 19.4322 | 15.7895 | 20 | 18.453 | LOW | 0.8 | 0.5 | 157460.8 | 31492.16 | 62984.32 | 94476.48 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 214
SA-0492 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 120000 | 270679 | 390679 | 6 | Closed | 19.2855 | 15.7895 | 20 | 18.3796 | LOW | 0.7 | 0.5 | 136737.65 | 27347.53 | 54695.06 | 82042.59 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 215
SA-0470 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 120000 | 270341 | 390341 | 6 | Closed | 19.2688 | 15.7895 | 20 | 18.3712 | LOW | 0.6 | 0.5 | 117102.3 | 23420.46 | 46840.92 | 70261.38 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 216
SA-0287 | Weather | High Waves | Strong Wind | Weather | Resume Operations | 1 | 1 | 1 | 6 | 122500 | 265620 | 388120 | 6 | Open | 19.1592 | 15.7895 | 20 | 18.3164 | LOW | 0.3 | 1 | 116436 | 23287.2 | 46574.4 | 69861.6 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 217
SA-0223 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 8 | 160000 | 163949 | 323949 | 8 | Closed | 15.9914 | 21.0526 | 20 | 18.3115 | LOW | 0.6 | 0.5 | 97184.7 | 19436.94 | 38873.88 | 58310.82 | Logistics NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 218
SA-0488 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 272813 | 387813 | 6 | Closed | 19.144 | 15.7895 | 20 | 18.3088 | LOW | 0.9 | 0.5 | 174515.85 | 34903.17 | 69806.34 | 104709.51 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 219
SA-0190 | Weather | Lightning | Strong Wind | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 264246 | 386746 | 6 | Closed | 19.0913 | 15.7895 | 20 | 18.2825 | LOW | 0.3 | 0.5 | 58011.9 | 11602.38 | 23204.76 | 34807.14 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 220
SA-0339 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 1 | 1 | 8 | 153333 | 169026 | 322359 | 8 | In Progress | 15.9129 | 21.0526 | 20 | 18.2723 | LOW | 0.9 | 0.75 | 217592.325 | 43518.465 | 87036.93 | 130555.395 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 221
SA-0158 | Weather | Strong Wind | Storm | Weather | Resume Operations | 1 | 1 | 1 | 8 | 160000 | 158983 | 318983 | 8 | Open | 15.7463 | 21.0526 | 20 | 18.1889 | LOW | 0.3 | 1 | 95694.9 | 19138.98 | 38277.96 | 57416.94 | Weather NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 222
SA-0319 | Weather | Strong Wind | Storm | Weather | Suspend Operations | 2 | 2 | 2 | 6 | 116666 | 102380 | 219046 | 3 | Open | 10.813 | 15.7895 | 40 | 18.1433 | LOW | 0.3 | 1 | 65713.8 | 13142.76 | 26285.52 | 39428.28 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 223
SA-0263 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 6 | 122500 | 257837 | 380337 | 6 | Closed | 18.775 | 15.7895 | 20 | 18.1243 | LOW | 0.6 | 0.5 | 114101.1 | 22820.22 | 45640.44 | 68460.66 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 224
SA-0353 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 8 | 163333 | 152781 | 316114 | 8 | Closed | 15.6046 | 21.0526 | 20 | 18.1181 | LOW | 0.9 | 0.5 | 142251.3 | 28450.26 | 56900.52 | 85350.78 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 225
SA-0144 | Logistics | Waiting on Boat | Port Congestion | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 255221 | 377721 | 6 | Closed | 18.6458 | 15.7895 | 20 | 18.0598 | LOW | 0.6 | 0.5 | 113316.3 | 22663.26 | 45326.52 | 67989.78 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 226
SA-0267 | Personnel | Medical Evacuation | Medical Emergency | HR | Crew Replacement | 1 | 1 | 1 | 6 | 122500 | 253590 | 376090 | 6 | Closed | 18.5653 | 15.7895 | 20 | 18.0195 | LOW | 0.6 | 0.5 | 112827 | 22565.4 | 45130.8 | 67696.2 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 227
SA-0151 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 253064 | 373064 | 6 | Closed | 18.4159 | 15.7895 | 20 | 17.9448 | LOW | 0.8 | 0.5 | 149225.6 | 29845.12 | 59690.24 | 89535.36 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 228
SA-0272 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 152401 | 305734 | 8 | Closed | 15.0923 | 21.0526 | 20 | 17.8619 | LOW | 0.9 | 0.5 | 137580.3 | 27516.06 | 55032.12 | 82548.18 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 229
SA-0118 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 152314 | 305647 | 8 | Open | 15.088 | 21.0526 | 20 | 17.8598 | LOW | 0.9 | 1 | 275082.3 | 55016.46 | 110032.92 | 165049.38 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 230
SA-0414 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 8 | 163333 | 141844 | 305177 | 8 | Closed | 15.0648 | 21.0526 | 20 | 17.8482 | LOW | 0.65 | 0.5 | 99182.525 | 19836.505 | 39673.01 | 59509.515 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 231
SA-0387 | Drilling | Well Control | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 6 | 115000 | 253781 | 368781 | 6 | Closed | 18.2045 | 15.7895 | 20 | 17.8391 | LOW | 0.65 | 0.5 | 119853.825 | 23970.765 | 47941.53 | 71912.295 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 232
SA-0408 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 122500 | 244320 | 366820 | 6 | Closed | 18.1077 | 15.7895 | 20 | 17.7907 | LOW | 0.9 | 0.5 | 165069 | 33013.8 | 66027.6 | 99041.4 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 233
SA-0185 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 6 | 120000 | 245352 | 365352 | 6 | Open | 18.0352 | 15.7895 | 20 | 17.7545 | LOW | 0.9 | 1 | 328816.8 | 65763.36 | 131526.72 | 197290.08 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 234
SA-0456 | Drilling | Stuck Pipe | Formation Instability | Operator | Condition Hole | 1 | 1 | 1 | 6 | 115000 | 247949 | 362949 | 6 | Closed | 17.9166 | 15.7895 | 20 | 17.6951 | LOW | 0.65 | 0.5 | 117958.425 | 23591.685 | 47183.37 | 70775.055 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 235
SA-0356 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 231858 | 354358 | 6 | Closed | 17.4925 | 15.7895 | 20 | 17.4831 | LOW | 0.6 | 0.5 | 106307.4 | 21261.48 | 42522.96 | 63784.44 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 236
SA-0014 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 122500 | 230529 | 353029 | 6 | In Progress | 17.4269 | 15.7895 | 20 | 17.4503 | LOW | 0.65 | 0.75 | 172101.6375 | 34420.3275 | 68840.655 | 103260.9825 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 237
SA-0449 | Weather | Poor Visibility | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 6 | 115000 | 236890 | 351890 | 6 | Open | 17.3707 | 15.7895 | 20 | 17.4222 | LOW | 0.3 | 1 | 105567 | 21113.4 | 42226.8 | 63340.2 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 238
SA-0076 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 115000 | 236864 | 351864 | 6 | Closed | 17.3694 | 15.7895 | 20 | 17.4215 | LOW | 0.9 | 0.5 | 158338.8 | 31667.76 | 63335.52 | 95003.28 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 239
SA-0143 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 122500 | 226126 | 348626 | 6 | Closed | 17.2096 | 15.7895 | 20 | 17.3416 | LOW | 0.9 | 0.5 | 156881.7 | 31376.34 | 62752.68 | 94129.02 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 240
SA-0333 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 115000 | 233024 | 348024 | 6 | Closed | 17.1799 | 15.7895 | 20 | 17.3268 | LOW | 0.6 | 0.5 | 104407.2 | 20881.44 | 41762.88 | 62644.32 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 241
SA-0324 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 153333 | 130015 | 283348 | 8 | Closed | 13.9872 | 21.0526 | 20 | 17.3094 | LOW | 0.9 | 0.5 | 127506.6 | 25501.32 | 51002.64 | 76503.96 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 242
SA-0020 | Drilling | Bit Failure | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 118750 | 226214 | 344964 | 6 | Closed | 17.0288 | 15.7895 | 20 | 17.2512 | LOW | 0.8 | 0.5 | 137985.6 | 27597.12 | 55194.24 | 82791.36 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 243
SA-0154 | Weather | Heavy Rain | Strong Wind | Marine Operations | Suspend Operations | 1 | 1 | 1 | 6 | 120000 | 223619 | 343619 | 6 | Closed | 16.9624 | 15.7895 | 20 | 17.218 | LOW | 0.3 | 0.5 | 51542.85 | 10308.57 | 20617.14 | 30925.71 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 244
SA-0236 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 223111 | 343111 | 6 | Closed | 16.9373 | 15.7895 | 20 | 17.2055 | LOW | 0.8 | 0.5 | 137244.4 | 27448.88 | 54897.76 | 82346.64 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 245
SA-0362 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 225265 | 340265 | 6 | Open | 16.7968 | 15.7895 | 20 | 17.1353 | LOW | 0.65 | 1 | 221172.25 | 44234.45 | 88468.9 | 132703.35 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 246
SA-0121 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 1 | 1 | 1 | 8 | 153333 | 121885 | 275218 | 8 | Closed | 13.5859 | 21.0526 | 20 | 17.1087 | LOW | 0.9 | 0.5 | 123848.1 | 24769.62 | 49539.24 | 74308.86 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 247
SA-0217 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 6 | 120000 | 217687 | 337687 | 6 | Closed | 16.6696 | 15.7895 | 20 | 17.0716 | LOW | 0.8 | 0.5 | 135074.8 | 27014.96 | 54029.92 | 81044.88 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 248
SA-0057 | Weather | Heavy Rain | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 222173 | 337173 | 6 | In Progress | 16.6442 | 15.7895 | 20 | 17.0589 | LOW | 0.3 | 0.75 | 75863.925 | 15172.785 | 30345.57 | 45518.355 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 249
SA-0428 | Weather | Heavy Rain | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 220006 | 335006 | 6 | In Progress | 16.5372 | 15.7895 | 20 | 17.0055 | LOW | 0.3 | 0.75 | 75376.35 | 15075.27 | 30150.54 | 45225.81 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 250
SA-0348 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 2 | 1 | 4 | 81666 | 148998 | 230664 | 2 | Closed | 11.3865 | 10.5263 | 40 | 16.8511 | LOW | 0.6 | 0.5 | 69199.2 | 13839.84 | 27679.68 | 41519.52 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 251
SA-0165 | Drilling | Fishing Operation | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 8 | 160000 | 104193 | 264193 | 8 | Closed | 13.0416 | 21.0526 | 20 | 16.8366 | LOW | 0.8 | 0.5 | 105677.2 | 21135.44 | 42270.88 | 63406.32 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 252
SA-0243 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 115000 | 207678 | 322678 | 6 | Closed | 15.9287 | 15.7895 | 20 | 16.7012 | LOW | 0.9 | 0.5 | 145205.1 | 29041.02 | 58082.04 | 87123.06 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 253
SA-0472 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 8 | 160000 | 96020 | 256020 | 8 | In Progress | 12.6382 | 21.0526 | 20 | 16.6349 | LOW | 0.9 | 0.75 | 172813.5 | 34562.7 | 69125.4 | 103688.1 | Mechanical NPT Hours | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 254
SA-0483 | Drilling | Well Control | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 196965 | 319465 | 6 | Closed | 15.7701 | 15.7895 | 20 | 16.6219 | LOW | 0.8 | 0.5 | 127786 | 25557.2 | 51114.4 | 76671.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 255
SA-0389 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Condition Hole | 1 | 1 | 1 | 6 | 115000 | 202496 | 317496 | 6 | Closed | 15.6729 | 15.7895 | 20 | 16.5733 | LOW | 0.8 | 0.5 | 126998.4 | 25399.68 | 50799.36 | 76199.04 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 256
SA-0145 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | 2 | 2 | 2 | 4 | 80833 | 138489 | 219322 | 2 | In Progress | 10.8266 | 10.5263 | 40 | 16.5712 | LOW | 0.6 | 0.75 | 98694.9 | 19738.98 | 39477.96 | 59216.94 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 257
SA-0068 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | 2 | 2 | 2 | 4 | 77916 | 138622 | 216538 | 2 | Closed | 10.6892 | 10.5263 | 40 | 16.5025 | LOW | 0.3 | 0.5 | 32480.7 | 6496.14 | 12992.28 | 19488.42 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 258
SA-0451 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 115000 | 199093 | 314093 | 6 | Closed | 15.5049 | 15.7895 | 20 | 16.4893 | LOW | 0.6 | 0.5 | 94227.9 | 18845.58 | 37691.16 | 56536.74 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 259
SA-0249 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 196670 | 311670 | 6 | Closed | 15.3853 | 15.7895 | 20 | 16.4295 | LOW | 0.9 | 0.5 | 140251.5 | 28050.3 | 56100.6 | 84150.9 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 260
SA-0298 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 186115 | 308615 | 6 | In Progress | 15.2345 | 15.7895 | 20 | 16.3541 | LOW | 0.6 | 0.75 | 138876.75 | 27775.35 | 55550.7 | 83326.05 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 261
SA-0026 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 118750 | 188958 | 307708 | 6 | Closed | 15.1897 | 15.7895 | 20 | 16.3317 | LOW | 0.65 | 0.5 | 100005.1 | 20001.02 | 40002.04 | 60003.06 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 262
SA-0084 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | 2 | 2 | 2 | 4 | 77916 | 130734 | 208650 | 2 | Closed | 10.2998 | 10.5263 | 40 | 16.3078 | LOW | 0.65 | 0.5 | 67811.25 | 13562.25 | 27124.5 | 40686.75 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 263
SA-0278 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 184818 | 299818 | 6 | Closed | 14.8002 | 15.7895 | 20 | 16.1369 | LOW | 0.8 | 0.5 | 119927.2 | 23985.44 | 47970.88 | 71956.32 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 264
SA-0497 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 122500 | 174028 | 296528 | 6 | Closed | 14.6378 | 15.7895 | 20 | 16.0557 | LOW | 0.6 | 0.5 | 88958.4 | 17791.68 | 35583.36 | 53375.04 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 265
SA-0100 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 8 | 153333 | 77458 | 230791 | 8 | In Progress | 11.3928 | 21.0526 | 20 | 16.0122 | LOW | 0.65 | 0.75 | 112510.6125 | 22502.1225 | 45004.245 | 67506.3675 | NPT Hours + ROP | 0.15 | 6.8 | 8 | 6.8 | >180 Days | Weekly | 266
SA-0450 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 178383 | 293383 | 6 | Open | 14.4826 | 15.7895 | 20 | 15.9781 | LOW | 0.9 | 1 | 264044.7 | 52808.94 | 105617.88 | 158426.82 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 267
SA-0359 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 177855 | 292855 | 6 | Closed | 14.4565 | 15.7895 | 20 | 15.9651 | LOW | 0.9 | 0.5 | 131784.75 | 26356.95 | 52713.9 | 79070.85 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 268
SA-0241 | Drilling | Well Control | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 172490 | 287490 | 6 | Closed | 14.1917 | 15.7895 | 20 | 15.8327 | LOW | 0.65 | 0.5 | 93434.25 | 18686.85 | 37373.7 | 56060.55 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 269
SA-0094 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 6 | 118750 | 164765 | 283515 | 6 | Closed | 13.9954 | 15.7895 | 20 | 15.7346 | LOW | 0.9 | 0.5 | 127581.75 | 25516.35 | 51032.7 | 76549.05 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 270
SA-0443 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 159958 | 282458 | 6 | Open | 13.9433 | 15.7895 | 20 | 15.7085 | LOW | 0.9 | 1 | 254212.2 | 50842.44 | 101684.88 | 152527.32 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 271
SA-0043 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | 2 | 2 | 2 | 4 | 80416 | 102981 | 183397 | 2 | Closed | 9.0532 | 10.5263 | 40 | 15.6845 | LOW | 0.6 | 0.5 | 55019.1 | 11003.82 | 22007.64 | 33011.46 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 272
SA-0284 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 154285 | 276785 | 6 | In Progress | 13.6632 | 15.7895 | 20 | 15.5684 | LOW | 0.8 | 0.75 | 166071 | 33214.2 | 66428.4 | 99642.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 273
SA-0199 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 1 | 1 | 6 | 118750 | 154929 | 273679 | 6 | Closed | 13.5099 | 15.7895 | 20 | 15.4918 | LOW | 0.6 | 0.5 | 82103.7 | 16420.74 | 32841.48 | 49262.22 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 274
SA-0289 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | 2 | 2 | 1 | 4 | 81666 | 89838 | 171504 | 2 | Open | 8.4661 | 10.5263 | 40 | 15.391 | LOW | 0.3 | 1 | 51451.2 | 10290.24 | 20580.48 | 30870.72 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 275
SA-0328 | Weather | Poor Visibility | Heavy Rain | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 152059 | 267059 | 6 | In Progress | 13.1831 | 15.7895 | 20 | 15.3284 | LOW | 0.3 | 0.75 | 60088.275 | 12017.655 | 24035.31 | 36052.965 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 276
SA-0281 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 122500 | 144551 | 267051 | 6 | Closed | 13.1827 | 15.7895 | 20 | 15.3282 | LOW | 0.8 | 0.5 | 106820.4 | 21364.08 | 42728.16 | 64092.24 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 277
SA-0399 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 6 | 115000 | 150582 | 265582 | 6 | Closed | 13.1102 | 15.7895 | 20 | 15.2919 | LOW | 0.8 | 0.5 | 106232.8 | 21246.56 | 42493.12 | 63739.68 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 278
SA-0494 | Weather | Heavy Rain | Strong Wind | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 120000 | 143523 | 263523 | 6 | Open | 13.0085 | 15.7895 | 20 | 15.2411 | LOW | 0.3 | 1 | 79056.9 | 15811.38 | 31622.76 | 47434.14 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 279
SA-0078 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 145730 | 260730 | 6 | Closed | 12.8707 | 15.7895 | 20 | 15.1722 | LOW | 0.9 | 0.5 | 117328.5 | 23465.7 | 46931.4 | 70397.1 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 280
SA-0175 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 122500 | 135468 | 257968 | 6 | Closed | 12.7343 | 15.7895 | 20 | 15.104 | LOW | 0.65 | 0.5 | 83839.6 | 16767.92 | 33535.84 | 50303.76 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 281
SA-0253 | Weather | Poor Visibility | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 6 | 118750 | 138221 | 256971 | 6 | In Progress | 12.6851 | 15.7895 | 20 | 15.0794 | LOW | 0.3 | 0.75 | 57818.475 | 11563.695 | 23127.39 | 34691.085 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 282
SA-0227 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | 2 | 2 | 2 | 4 | 80833 | 78042 | 158875 | 2 | Closed | 7.8427 | 10.5263 | 40 | 15.0792 | LOW | 0.6 | 0.5 | 47662.5 | 9532.5 | 19065 | 28597.5 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 283
SA-0196 | Weather | Strong Wind | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 6 | 118750 | 136446 | 255196 | 6 | Closed | 12.5975 | 15.7895 | 20 | 15.0356 | LOW | 0.3 | 0.5 | 38279.4 | 7655.88 | 15311.76 | 22967.64 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 284
SA-0415 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 6 | 115000 | 137040 | 252040 | 6 | In Progress | 12.4417 | 15.7895 | 20 | 14.9577 | LOW | 0.9 | 0.75 | 170127 | 34025.4 | 68050.8 | 102076.2 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 285
SA-0195 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 6 | 118750 | 120704 | 239454 | 6 | In Progress | 11.8204 | 15.7895 | 20 | 14.647 | LOW | 0.9 | 0.75 | 161631.45 | 32326.29 | 64652.58 | 96978.87 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 286
SA-0500 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 116840 | 239340 | 6 | Closed | 11.8148 | 15.7895 | 20 | 14.6442 | LOW | 0.9 | 0.5 | 107703 | 21540.6 | 43081.2 | 64621.8 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 287
SA-0258 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 6 | 118750 | 120114 | 238864 | 6 | In Progress | 11.7913 | 15.7895 | 20 | 14.6325 | LOW | 0.6 | 0.75 | 107488.8 | 21497.76 | 42995.52 | 64493.28 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 288
SA-0395 | Weather | Strong Wind | Lightning | Marine Operations | Resume Operations | 1 | 1 | 1 | 6 | 115000 | 123339 | 238339 | 6 | Closed | 11.7654 | 15.7895 | 20 | 14.6195 | LOW | 0.3 | 0.5 | 35750.85 | 7150.17 | 14300.34 | 21450.51 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 289
SA-0110 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 6 | 118750 | 114628 | 233378 | 6 | In Progress | 11.5205 | 15.7895 | 20 | 14.4971 | LOW | 0.9 | 0.75 | 157530.15 | 31506.03 | 63012.06 | 94518.09 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 290
SA-0323 | Personnel | Crew Change | Medical Emergency | HR | Medical Clearance | 1 | 1 | 1 | 6 | 115000 | 117452 | 232452 | 6 | In Progress | 11.4748 | 15.7895 | 20 | 14.4742 | LOW | 0.6 | 0.75 | 104603.4 | 20920.68 | 41841.36 | 62762.04 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 291
SA-0140 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | 2 | 2 | 2 | 4 | 79166 | 50540 | 129706 | 2 | In Progress | 6.4028 | 10.5263 | 40 | 14.3593 | LOW | 0.8 | 0.75 | 77823.6 | 15564.72 | 31129.44 | 46694.16 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 292
SA-0305 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 6 | 115000 | 112412 | 227412 | 6 | In Progress | 11.226 | 15.7895 | 20 | 14.3498 | LOW | 0.6 | 0.75 | 102335.4 | 20467.08 | 40934.16 | 61401.24 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 293
SA-0394 | Drilling | Hole Cleaning | Differential Sticking | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 6 | 115000 | 111365 | 226365 | 6 | Closed | 11.1743 | 15.7895 | 20 | 14.324 | LOW | 0.8 | 0.5 | 90546 | 18109.2 | 36218.4 | 54327.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 294
SA-0458 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 6 | 120000 | 106088 | 226088 | 6 | Closed | 11.1606 | 15.7895 | 20 | 14.3171 | LOW | 0.8 | 0.5 | 90435.2 | 18087.04 | 36174.08 | 54261.12 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 295
SA-0416 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 6 | 115000 | 109082 | 224082 | 6 | Closed | 11.0616 | 15.7895 | 20 | 14.2676 | LOW | 0.6 | 0.5 | 67224.6 | 13444.92 | 26889.84 | 40334.76 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 296
SA-0035 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Safety Briefing | 1 | 1 | 1 | 6 | 122500 | 101091 | 223591 | 6 | Closed | 11.0373 | 15.7895 | 20 | 14.2555 | LOW | 0.6 | 0.5 | 67077.3 | 13415.46 | 26830.92 | 40246.38 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 297
SA-0208 | Weather | Heavy Rain | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 81666 | 202290 | 283956 | 4 | Closed | 14.0172 | 10.5263 | 20 | 14.1665 | LOW | 0.3 | 0.5 | 42593.4 | 8518.68 | 17037.36 | 25556.04 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 298
SA-0025 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Expedite Shipment | 1 | 1 | 1 | 6 | 118750 | 98071 | 216821 | 6 | Closed | 10.7032 | 15.7895 | 20 | 14.0884 | LOW | 0.6 | 0.5 | 65046.3 | 13009.26 | 26018.52 | 39027.78 | Logistics NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 299
SA-0038 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | Repair Component | 1 | 1 | 1 | 4 | 81666 | 198934 | 280600 | 4 | Closed | 13.8515 | 10.5263 | 20 | 14.0837 | LOW | 0.9 | 0.5 | 126270 | 25254 | 50508 | 75762 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 300
SA-0019 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 198718 | 280384 | 4 | Closed | 13.8409 | 10.5263 | 20 | 14.0783 | LOW | 0.6 | 0.5 | 84115.2 | 16823.04 | 33646.08 | 50469.12 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 301
SA-0202 | Weather | Poor Visibility | Storm | Marine Operations | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 92594 | 215094 | 6 | Closed | 10.6179 | 15.7895 | 20 | 14.0458 | LOW | 0.3 | 0.5 | 32264.1 | 6452.82 | 12905.64 | 19358.46 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 302
SA-0134 | Personnel | Training | Crew Rotation | Medical Team | Safety Briefing | 1 | 1 | 1 | 6 | 122500 | 90710 | 213210 | 6 | In Progress | 10.5249 | 15.7895 | 20 | 13.9993 | LOW | 0.6 | 0.75 | 95944.5 | 19188.9 | 38377.8 | 57566.7 | Personnel NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 303
SA-0411 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 6 | 122500 | 88110 | 210610 | 6 | In Progress | 10.3966 | 15.7895 | 20 | 13.9351 | LOW | 0.9 | 0.75 | 142161.75 | 28432.35 | 56864.7 | 85297.05 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 304
SA-0194 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 192615 | 274281 | 4 | Closed | 13.5396 | 10.5263 | 20 | 13.9277 | LOW | 0.3 | 0.5 | 41142.15 | 8228.43 | 16456.86 | 24685.29 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 305
SA-0379 | Weather | High Waves | Heavy Rain | Weather | Suspend Operations | 1 | 1 | 1 | 6 | 120000 | 88739 | 208739 | 6 | Closed | 10.3042 | 15.7895 | 20 | 13.8889 | LOW | 0.3 | 0.5 | 31310.85 | 6262.17 | 12524.34 | 18786.51 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 306
SA-0262 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 1 | 1 | 4 | 81666 | 189343 | 271009 | 4 | Closed | 13.3781 | 10.5263 | 20 | 13.8469 | LOW | 0.7 | 0.5 | 94853.15 | 18970.63 | 37941.26 | 56911.89 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 307
SA-0474 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 6 | 120000 | 86494 | 206494 | 6 | Closed | 10.1934 | 15.7895 | 20 | 13.8335 | LOW | 0.9 | 0.5 | 92922.3 | 18584.46 | 37168.92 | 55753.38 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 308
SA-0247 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 6 | 115000 | 90497 | 205497 | 6 | In Progress | 10.1442 | 15.7895 | 20 | 13.8089 | LOW | 0.9 | 0.75 | 138710.475 | 27742.095 | 55484.19 | 83226.285 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 309
SA-0340 | Weather | High Waves | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 191641 | 268307 | 4 | In Progress | 13.2447 | 10.5263 | 20 | 13.7802 | LOW | 0.3 | 0.75 | 60369.075 | 12073.815 | 24147.63 | 36221.445 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 310
SA-0468 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 186247 | 267913 | 4 | Closed | 13.2253 | 10.5263 | 20 | 13.7705 | LOW | 0.9 | 0.5 | 120560.85 | 24112.17 | 48224.34 | 72336.51 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 311
SA-0016 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 185722 | 267388 | 4 | Closed | 13.1993 | 10.5263 | 20 | 13.7576 | LOW | 0.8 | 0.5 | 106955.2 | 21391.04 | 42782.08 | 64173.12 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 312
SA-0269 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 81666 | 185627 | 267293 | 4 | Closed | 13.1947 | 10.5263 | 20 | 13.7552 | LOW | 0.8 | 0.5 | 106917.2 | 21383.44 | 42766.88 | 64150.32 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 313
SA-0294 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 185274 | 266940 | 4 | Closed | 13.1772 | 10.5263 | 20 | 13.7465 | LOW | 0.9 | 0.5 | 120123 | 24024.6 | 48049.2 | 72073.8 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 314
SA-0351 | Weather | High Waves | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 184832 | 266498 | 4 | Closed | 13.1554 | 10.5263 | 20 | 13.7356 | LOW | 0.3 | 0.5 | 39974.7 | 7994.94 | 15989.88 | 23984.82 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 315
SA-0376 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 79166 | 187319 | 266485 | 4 | Closed | 13.1548 | 10.5263 | 20 | 13.7353 | LOW | 0.6 | 0.5 | 79945.5 | 15989.1 | 31978.2 | 47967.3 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 316
SA-0159 | Weather | Heavy Rain | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 80000 | 185590 | 265590 | 4 | Closed | 13.1106 | 10.5263 | 20 | 13.7132 | LOW | 0.3 | 0.5 | 39838.5 | 7967.7 | 15935.4 | 23903.1 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 317
SA-0189 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | Repair Component | 1 | 1 | 1 | 6 | 122500 | 78520 | 201020 | 6 | In Progress | 9.9232 | 15.7895 | 20 | 13.6984 | LOW | 0.9 | 0.75 | 135688.5 | 27137.7 | 54275.4 | 81413.1 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 318
SA-0197 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 6 | 118750 | 81777 | 200527 | 6 | Closed | 9.8988 | 15.7895 | 20 | 13.6862 | LOW | 0.65 | 0.5 | 65171.275 | 13034.255 | 26068.51 | 39102.765 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 319
SA-0491 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 183601 | 263601 | 4 | Closed | 13.0124 | 10.5263 | 20 | 13.6641 | LOW | 0.6 | 0.5 | 79080.3 | 15816.06 | 31632.12 | 47448.18 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 320
SA-0326 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 185391 | 262057 | 4 | Closed | 12.9362 | 10.5263 | 20 | 13.626 | LOW | 0.8 | 0.5 | 104822.8 | 20964.56 | 41929.12 | 62893.68 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 321
SA-0209 | Weather | Poor Visibility | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 122500 | 74361 | 196861 | 6 | Closed | 9.7178 | 15.7895 | 20 | 13.5958 | LOW | 0.3 | 0.5 | 29529.15 | 5905.83 | 11811.66 | 17717.49 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 322
SA-0063 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 183892 | 260558 | 4 | Closed | 12.8622 | 10.5263 | 20 | 13.589 | LOW | 0.8 | 0.5 | 104223.2 | 20844.64 | 41689.28 | 62533.92 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 323
SA-0331 | Drilling | Well Control | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 6 | 115000 | 74266 | 189266 | 6 | Closed | 9.3429 | 15.7895 | 20 | 13.4083 | LOW | 0.65 | 0.5 | 61511.45 | 12302.29 | 24604.58 | 36906.87 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 324
SA-0021 | Drilling | Bit Failure | Bit Wear | Operator | Run Fishing Tools | 1 | 1 | 1 | 6 | 118750 | 68245 | 186995 | 6 | Open | 9.2308 | 15.7895 | 20 | 13.3523 | LOW | 0.8 | 1 | 149596 | 29919.2 | 59838.4 | 89757.6 | NPT Hours + ROP | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 325
SA-0245 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 173767 | 250433 | 4 | In Progress | 12.3624 | 10.5263 | 20 | 13.3391 | LOW | 0.9 | 0.75 | 169042.275 | 33808.455 | 67616.91 | 101425.365 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 326
SA-0141 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 122500 | 63732 | 186232 | 6 | Closed | 9.1932 | 15.7895 | 20 | 13.3334 | LOW | 0.9 | 0.5 | 83804.4 | 16760.88 | 33521.76 | 50282.64 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 327
SA-0486 | Weather | High Waves | High Waves | Weather | Wait on Weather | 1 | 1 | 1 | 6 | 115000 | 70319 | 185319 | 6 | Closed | 9.1481 | 15.7895 | 20 | 13.3109 | LOW | 0.3 | 0.5 | 27797.85 | 5559.57 | 11119.14 | 16678.71 | Weather NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 328
SA-0177 | Drilling | Stuck Pipe | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 4 | 80000 | 168562 | 248562 | 4 | Open | 12.27 | 10.5263 | 20 | 13.2929 | LOW | 0.8 | 1 | 198849.6 | 39769.92 | 79539.84 | 119309.76 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 329
SA-0027 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 1 | 1 | 6 | 118750 | 64902 | 183652 | 6 | Closed | 9.0658 | 15.7895 | 20 | 13.2697 | LOW | 0.7 | 0.5 | 64278.2 | 12855.64 | 25711.28 | 38566.92 | Mechanical NPT Hours | 0.15 | 5.1 | 6 | 5.1 | >180 Days | Weekly | 330
SA-0073 | Logistics | Delayed Helicopter | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 169001 | 245667 | 4 | Open | 12.1271 | 10.5263 | 20 | 13.2214 | LOW | 0.6 | 1 | 147400.2 | 29480.04 | 58960.08 | 88440.12 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 331
SA-0412 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 161966 | 243632 | 4 | In Progress | 12.0266 | 10.5263 | 20 | 13.1712 | LOW | 0.8 | 0.75 | 146179.2 | 29235.84 | 58471.68 | 87707.52 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 332
SA-0363 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 4 | 76666 | 165696 | 242362 | 4 | Open | 11.964 | 10.5263 | 20 | 13.1399 | LOW | 0.6 | 1 | 145417.2 | 29083.44 | 58166.88 | 87250.32 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 333
SA-0157 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Air Freight Materials | 1 | 1 | 1 | 4 | 80000 | 159783 | 239783 | 4 | Open | 11.8366 | 10.5263 | 20 | 13.0762 | LOW | 0.6 | 1 | 143869.8 | 28773.96 | 57547.92 | 86321.88 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 334
SA-0173 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 154123 | 235789 | 4 | Closed | 11.6395 | 10.5263 | 20 | 12.9776 | LOW | 0.9 | 0.5 | 106105.05 | 21221.01 | 42442.02 | 63663.03 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 335
SA-0081 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 157410 | 234076 | 4 | Closed | 11.5549 | 10.5263 | 20 | 12.9354 | LOW | 0.8 | 0.5 | 93630.4 | 18726.08 | 37452.16 | 56178.24 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 336
SA-0012 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 152013 | 233679 | 4 | Closed | 11.5353 | 10.5263 | 20 | 12.9256 | LOW | 0.6 | 0.5 | 70103.7 | 14020.74 | 28041.48 | 42062.22 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 337
SA-0386 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 153896 | 230562 | 4 | In Progress | 11.3815 | 10.5263 | 20 | 12.8486 | LOW | 0.65 | 0.75 | 112398.975 | 22479.795 | 44959.59 | 67439.385 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 338
SA-0388 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 152544 | 229210 | 4 | Closed | 11.3147 | 10.5263 | 20 | 12.8153 | LOW | 0.9 | 0.5 | 103144.5 | 20628.9 | 41257.8 | 61886.7 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 339
SA-0193 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 146635 | 228301 | 4 | Closed | 11.2698 | 10.5263 | 20 | 12.7928 | LOW | 0.3 | 0.5 | 34245.15 | 6849.03 | 13698.06 | 20547.09 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 340
SA-0187 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 147308 | 227308 | 4 | Closed | 11.2208 | 10.5263 | 20 | 12.7683 | LOW | 0.6 | 0.5 | 68192.4 | 13638.48 | 27276.96 | 40915.44 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 341
SA-0282 | Drilling | Well Control | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 81666 | 144601 | 226267 | 4 | Closed | 11.1694 | 10.5263 | 20 | 12.7426 | LOW | 0.65 | 0.5 | 73536.775 | 14707.355 | 29414.71 | 44122.065 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 342
SA-0327 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 148435 | 225101 | 4 | Closed | 11.1119 | 10.5263 | 20 | 12.7138 | LOW | 0.65 | 0.5 | 73157.825 | 14631.565 | 29263.13 | 43894.695 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 343
SA-0123 | Drilling | Lost Circulation | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 146588 | 223254 | 4 | Closed | 11.0207 | 10.5263 | 20 | 12.6682 | LOW | 0.8 | 0.5 | 89301.6 | 17860.32 | 35720.64 | 53580.96 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 344
SA-0238 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 80000 | 143184 | 223184 | 4 | Closed | 11.0173 | 10.5263 | 20 | 12.6665 | LOW | 0.9 | 0.5 | 100432.8 | 20086.56 | 40173.12 | 60259.68 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 345
SA-0112 | Weather | Heavy Rain | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 79166 | 143929 | 223095 | 4 | Closed | 11.0129 | 10.5263 | 20 | 12.6643 | LOW | 0.3 | 0.5 | 33464.25 | 6692.85 | 13385.7 | 20078.55 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 346
SA-0413 | Weather | High Waves | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 141093 | 222759 | 4 | In Progress | 10.9963 | 10.5263 | 20 | 12.656 | LOW | 0.3 | 0.75 | 50120.775 | 10024.155 | 20048.31 | 30072.465 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 347
SA-0213 | Weather | Heavy Rain | Heavy Rain | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 138389 | 220055 | 4 | Closed | 10.8628 | 10.5263 | 20 | 12.5893 | LOW | 0.3 | 0.5 | 33008.25 | 6601.65 | 13203.3 | 19804.95 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 348
SA-0205 | Weather | Strong Wind | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 130214 | 211880 | 4 | Closed | 10.4592 | 10.5263 | 20 | 12.3875 | LOW | 0.3 | 0.5 | 31782 | 6356.4 | 12712.8 | 19069.2 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 349
SA-0279 | Drilling | Stuck Pipe | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 132348 | 209014 | 4 | Closed | 10.3178 | 10.5263 | 20 | 12.3168 | LOW | 0.8 | 0.5 | 83605.6 | 16721.12 | 33442.24 | 50163.36 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 350
SA-0283 | Weather | Heavy Rain | Storm | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 127004 | 208670 | 4 | Closed | 10.3008 | 10.5263 | 20 | 12.3083 | LOW | 0.3 | 0.5 | 31300.5 | 6260.1 | 12520.2 | 18780.3 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 351
SA-0344 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 76666 | 128931 | 205597 | 4 | Closed | 10.1491 | 10.5263 | 20 | 12.2324 | LOW | 0.6 | 0.5 | 61679.1 | 12335.82 | 24671.64 | 37007.46 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 352
SA-0489 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 80000 | 121829 | 201829 | 4 | In Progress | 9.9631 | 10.5263 | 20 | 12.1394 | LOW | 0.6 | 0.75 | 90823.05 | 18164.61 | 36329.22 | 54493.83 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 353
SA-0369 | Weather | Poor Visibility | High Waves | Marine Operations | Suspend Operations | 1 | 1 | 1 | 4 | 76666 | 124855 | 201521 | 4 | Closed | 9.9479 | 10.5263 | 20 | 12.1318 | LOW | 0.3 | 0.5 | 30228.15 | 6045.63 | 12091.26 | 18136.89 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 354
SA-0049 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 120129 | 196795 | 4 | Closed | 9.7146 | 10.5263 | 20 | 12.0152 | LOW | 0.3 | 0.5 | 29519.25 | 5903.85 | 11807.7 | 17711.55 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 355
SA-0342 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 115177 | 191843 | 4 | Open | 9.4701 | 10.5263 | 20 | 11.893 | LOW | 0.8 | 1 | 153474.4 | 30694.88 | 61389.76 | 92084.64 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 356
SA-0499 | Weather | High Waves | Storm | Weather | Resume Operations | 1 | 1 | 1 | 4 | 81666 | 110150 | 191816 | 4 | Closed | 9.4688 | 10.5263 | 20 | 11.8923 | LOW | 0.3 | 0.5 | 28772.4 | 5754.48 | 11508.96 | 17263.44 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 357
SA-0009 | Weather | Lightning | Storm | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 81666 | 108862 | 190528 | 4 | In Progress | 9.4052 | 10.5263 | 20 | 11.8605 | LOW | 0.3 | 0.75 | 42868.8 | 8573.76 | 17147.52 | 25721.28 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 358
SA-0391 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 112293 | 188959 | 4 | Closed | 9.3278 | 10.5263 | 20 | 11.8218 | LOW | 0.65 | 0.5 | 61411.675 | 12282.335 | 24564.67 | 36847.005 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 359
SA-0097 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 4 | 76666 | 111806 | 188472 | 4 | Closed | 9.3037 | 10.5263 | 20 | 11.8098 | LOW | 0.8 | 0.5 | 75388.8 | 15077.76 | 30155.52 | 45233.28 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 360
SA-0226 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 80000 | 107175 | 187175 | 4 | Closed | 9.2397 | 10.5263 | 20 | 11.7777 | LOW | 0.65 | 0.5 | 60831.875 | 12166.375 | 24332.75 | 36499.125 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 361
SA-0372 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 4 | 79166 | 107969 | 187135 | 4 | Closed | 9.2377 | 10.5263 | 20 | 11.7768 | LOW | 0.9 | 0.5 | 84210.75 | 16842.15 | 33684.3 | 50526.45 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 362
SA-0079 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 4 | 76666 | 107545 | 184211 | 4 | Closed | 9.0934 | 10.5263 | 20 | 11.7046 | LOW | 0.6 | 0.5 | 55263.3 | 11052.66 | 22105.32 | 33157.98 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 363
SA-0257 | Weather | Strong Wind | Heavy Rain | Marine Operations | Suspend Operations | 1 | 1 | 1 | 4 | 79166 | 104081 | 183247 | 4 | Closed | 9.0458 | 10.5263 | 20 | 11.6808 | LOW | 0.3 | 0.5 | 27487.05 | 5497.41 | 10994.82 | 16492.23 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 364
SA-0437 | Drilling | Well Control | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 4 | 76666 | 102592 | 179258 | 4 | Closed | 8.8489 | 10.5263 | 20 | 11.5823 | LOW | 0.65 | 0.5 | 58258.85 | 11651.77 | 23303.54 | 34955.31 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 365
SA-0346 | Drilling | Stuck Pipe | Formation Instability | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 100999 | 177665 | 4 | Closed | 8.7703 | 10.5263 | 20 | 11.543 | LOW | 0.65 | 0.5 | 57741.125 | 11548.225 | 23096.45 | 34644.675 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 366
SA-0060 | Logistics | Waiting on Materials | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 100056 | 176722 | 4 | Closed | 8.7237 | 10.5263 | 20 | 11.5197 | LOW | 0.6 | 0.5 | 53016.6 | 10603.32 | 21206.64 | 31809.96 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 367
SA-0355 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 4 | 81666 | 94096 | 175762 | 4 | In Progress | 8.6763 | 10.5263 | 20 | 11.4961 | LOW | 0.6 | 0.75 | 79092.9 | 15818.58 | 31637.16 | 47455.74 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 368
SA-0228 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 4 | 80000 | 95170 | 175170 | 4 | Closed | 8.6471 | 10.5263 | 20 | 11.4814 | LOW | 0.9 | 0.5 | 78826.5 | 15765.3 | 31530.6 | 47295.9 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 369
SA-0128 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 1 | 1 | 4 | 76666 | 96663 | 173329 | 4 | Closed | 8.5562 | 10.5263 | 20 | 11.436 | LOW | 0.9 | 0.5 | 77998.05 | 15599.61 | 31199.22 | 46798.83 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 370
SA-0427 | Weather | High Waves | Lightning | Weather | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 95669 | 172335 | 4 | Closed | 8.5071 | 10.5263 | 20 | 11.4115 | LOW | 0.3 | 0.5 | 25850.25 | 5170.05 | 10340.1 | 15510.15 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 371
SA-0476 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 80000 | 91574 | 171574 | 4 | Closed | 8.4696 | 10.5263 | 20 | 11.3927 | LOW | 0.65 | 0.5 | 55761.55 | 11152.31 | 22304.62 | 33456.93 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 372
SA-0473 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 80000 | 89940 | 169940 | 4 | Open | 8.3889 | 10.5263 | 20 | 11.3524 | LOW | 0.9 | 1 | 152946 | 30589.2 | 61178.4 | 91767.6 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 373
SA-0286 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 86786 | 168452 | 4 | In Progress | 8.3155 | 10.5263 | 20 | 11.3156 | LOW | 0.9 | 0.75 | 113705.1 | 22741.02 | 45482.04 | 68223.06 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 374
SA-0054 | Weather | Lightning | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 91438 | 168104 | 4 | Closed | 8.2983 | 10.5263 | 20 | 11.307 | LOW | 0.3 | 0.5 | 25215.6 | 5043.12 | 10086.24 | 15129.36 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 375
SA-0211 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Condition Hole | 1 | 1 | 1 | 4 | 81666 | 86316 | 167982 | 4 | Closed | 8.2923 | 10.5263 | 20 | 11.304 | LOW | 0.65 | 0.5 | 54594.15 | 10918.83 | 21837.66 | 32756.49 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 376
SA-0102 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 90633 | 167299 | 4 | Open | 8.2585 | 10.5263 | 20 | 11.2872 | LOW | 0.9 | 1 | 150569.1 | 30113.82 | 60227.64 | 90341.46 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 377
SA-0303 | Weather | Lightning | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 85784 | 162450 | 4 | In Progress | 8.0192 | 10.5263 | 20 | 11.1675 | LOW | 0.3 | 0.75 | 36551.25 | 7310.25 | 14620.5 | 21930.75 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 378
SA-0477 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 81666 | 77971 | 159637 | 4 | In Progress | 7.8803 | 10.5263 | 20 | 11.0981 | LOW | 0.65 | 0.75 | 77823.0375 | 15564.6075 | 31129.215 | 46693.8225 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 379
SA-0174 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 81666 | 77766 | 159432 | 4 | Closed | 7.8702 | 10.5263 | 20 | 11.093 | LOW | 0.9 | 0.5 | 71744.4 | 14348.88 | 28697.76 | 43046.64 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 380
SA-0312 | Personnel | Crew Change | Training Requirement | Rig Management | Crew Replacement | 1 | 1 | 1 | 4 | 76666 | 79447 | 156113 | 4 | Closed | 7.7064 | 10.5263 | 20 | 11.0111 | LOW | 0.6 | 0.5 | 46833.9 | 9366.78 | 18733.56 | 28100.34 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 381
SA-0373 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 79166 | 76620 | 155786 | 4 | Closed | 7.6902 | 10.5263 | 20 | 11.003 | LOW | 0.65 | 0.5 | 50630.45 | 10126.09 | 20252.18 | 30378.27 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 382
SA-0390 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 76666 | 78814 | 155480 | 4 | Closed | 7.6751 | 10.5263 | 20 | 10.9955 | LOW | 0.9 | 0.5 | 69966 | 13993.2 | 27986.4 | 41979.6 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 383
SA-0270 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 71396 | 153062 | 4 | Open | 7.5558 | 10.5263 | 20 | 10.9358 | LOW | 0.9 | 1 | 137755.8 | 27551.16 | 55102.32 | 82653.48 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 384
SA-0321 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 74370 | 151036 | 4 | Closed | 7.4557 | 10.5263 | 20 | 10.8858 | LOW | 0.9 | 0.5 | 67966.2 | 13593.24 | 27186.48 | 40779.72 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 385
SA-0101 | Weather | Poor Visibility | High Waves | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 73637 | 150303 | 4 | Closed | 7.4196 | 10.5263 | 20 | 10.8677 | LOW | 0.3 | 0.5 | 22545.45 | 4509.09 | 9018.18 | 13527.27 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 386
SA-0444 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 72518 | 149184 | 4 | Open | 7.3643 | 10.5263 | 20 | 10.8401 | LOW | 0.6 | 1 | 89510.4 | 17902.08 | 35804.16 | 53706.24 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 387
SA-0113 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 79166 | 68905 | 148071 | 4 | Closed | 7.3094 | 10.5263 | 20 | 10.8126 | LOW | 0.9 | 0.5 | 66631.95 | 13326.39 | 26652.78 | 39979.17 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 388
SA-0276 | Drilling | Well Control | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 70081 | 146747 | 4 | Closed | 7.244 | 10.5263 | 20 | 10.7799 | LOW | 0.8 | 0.5 | 58698.8 | 11739.76 | 23479.52 | 35219.28 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 389
SA-0040 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | Air Freight Materials | 1 | 1 | 1 | 4 | 81666 | 64854 | 146520 | 4 | Closed | 7.2328 | 10.5263 | 20 | 10.7743 | LOW | 0.6 | 0.5 | 43956 | 8791.2 | 17582.4 | 26373.6 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 390
SA-0397 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 76666 | 67923 | 144589 | 4 | In Progress | 7.1375 | 10.5263 | 20 | 10.7266 | LOW | 0.7 | 0.75 | 75909.225 | 15181.845 | 30363.69 | 45545.535 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 391
SA-0067 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 67864 | 144530 | 4 | Closed | 7.1346 | 10.5263 | 20 | 10.7252 | LOW | 0.8 | 0.5 | 57812 | 11562.4 | 23124.8 | 34687.2 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 392
SA-0403 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 4 | 76666 | 67775 | 144441 | 4 | Open | 7.1302 | 10.5263 | 20 | 10.723 | LOW | 0.9 | 1 | 129996.9 | 25999.38 | 51998.76 | 77998.14 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 393
SA-0463 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 4 | 80000 | 63153 | 143153 | 4 | In Progress | 7.0666 | 10.5263 | 20 | 10.6912 | LOW | 0.6 | 0.75 | 64418.85 | 12883.77 | 25767.54 | 38651.31 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 394
SA-0271 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | Medical Clearance | 1 | 1 | 1 | 4 | 81666 | 60840 | 142506 | 4 | Closed | 7.0347 | 10.5263 | 20 | 10.6752 | LOW | 0.6 | 0.5 | 42751.8 | 8550.36 | 17100.72 | 25651.08 | Personnel NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 395
SA-0170 | Logistics | Waiting on Cement | Port Congestion | Procurement | Expedite Shipment | 1 | 1 | 1 | 4 | 81666 | 60188 | 141854 | 4 | Closed | 7.0025 | 10.5263 | 20 | 10.6591 | LOW | 0.6 | 0.5 | 42556.2 | 8511.24 | 17022.48 | 25533.72 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 396
SA-0445 | Weather | Lightning | Heavy Rain | Marine Operations | Resume Operations | 1 | 1 | 1 | 4 | 76666 | 61263 | 137929 | 4 | Closed | 6.8087 | 10.5263 | 20 | 10.5623 | LOW | 0.3 | 0.5 | 20689.35 | 4137.87 | 8275.74 | 12413.61 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 397
SA-0410 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 4 | 81666 | 55857 | 137523 | 4 | Open | 6.7887 | 10.5263 | 20 | 10.5522 | LOW | 0.9 | 1 | 123770.7 | 24754.14 | 49508.28 | 74262.42 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 398
SA-0265 | Drilling | Well Control | Bit Wear | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 4 | 81666 | 55231 | 136897 | 4 | In Progress | 6.7578 | 10.5263 | 20 | 10.5368 | LOW | 0.8 | 0.75 | 82138.2 | 16427.64 | 32855.28 | 49282.92 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 399
SA-0398 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 1 | 1 | 4 | 76666 | 58910 | 135576 | 4 | Open | 6.6926 | 10.5263 | 20 | 10.5042 | LOW | 0.6 | 1 | 81345.6 | 16269.12 | 32538.24 | 48807.36 | Logistics NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 400
SA-0436 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 58805 | 135471 | 4 | Closed | 6.6874 | 10.5263 | 20 | 10.5016 | LOW | 0.9 | 0.5 | 60961.95 | 12192.39 | 24384.78 | 36577.17 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 401
SA-0370 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 55282 | 131948 | 4 | Open | 6.5135 | 10.5263 | 20 | 10.4146 | LOW | 0.9 | 1 | 118753.2 | 23750.64 | 47501.28 | 71251.92 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 402
SA-0332 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 4 | 76666 | 52243 | 128909 | 4 | Open | 6.3635 | 10.5263 | 20 | 10.3396 | LOW | 0.65 | 1 | 83790.85 | 16758.17 | 33516.34 | 50274.51 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 403
SA-0377 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 4 | 79166 | 45728 | 124894 | 4 | Closed | 6.1653 | 10.5263 | 20 | 10.2405 | LOW | 0.9 | 0.5 | 56202.3 | 11240.46 | 22480.92 | 33721.38 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 404
SA-0107 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 1 | 1 | 4 | 79166 | 43669 | 122835 | 4 | Open | 6.0636 | 10.5263 | 20 | 10.1897 | LOW | 0.65 | 1 | 79842.75 | 15968.55 | 31937.1 | 47905.65 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 405
SA-0274 | Weather | Poor Visibility | High Waves | Marine Operations | Wait on Weather | 1 | 1 | 1 | 4 | 76666 | 44941 | 121607 | 4 | Closed | 6.003 | 10.5263 | 20 | 10.1594 | LOW | 0.3 | 0.5 | 18241.05 | 3648.21 | 7296.42 | 10944.63 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 406
SA-0343 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 4 | 76666 | 44040 | 120706 | 4 | Closed | 5.9585 | 10.5263 | 20 | 10.1372 | LOW | 0.9 | 0.5 | 54317.7 | 10863.54 | 21727.08 | 32590.62 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 407
SA-0345 | Weather | Poor Visibility | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 4 | 76666 | 41049 | 117715 | 4 | Closed | 5.8109 | 10.5263 | 20 | 10.0633 | LOW | 0.3 | 0.5 | 17657.25 | 3531.45 | 7062.9 | 10594.35 | Weather NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 408
SA-0452 | Drilling | Well Control | Unexpected Pressure | Operator | Condition Hole | 1 | 1 | 1 | 4 | 76666 | 39001 | 115667 | 4 | Closed | 5.7098 | 10.5263 | 20 | 10.0128 | LOW | 0.65 | 0.5 | 37591.775 | 7518.355 | 15036.71 | 22555.065 | NPT Hours + ROP | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 409
SA-0308 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 4 | 76666 | 38651 | 115317 | 4 | Closed | 5.6925 | 10.5263 | 20 | 10.0041 | LOW | 0.9 | 0.5 | 51892.65 | 10378.53 | 20757.06 | 31135.59 | Mechanical NPT Hours | 0.15 | 3.4 | 4 | 3.4 | >180 Days | Weekly | 410
SA-0168 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 2 | 40833 | 98245 | 139078 | 2 | Closed | 6.8654 | 5.2632 | 20 | 9.0117 | LOW | 0.6 | 0.5 | 41723.4 | 8344.68 | 16689.36 | 25034.04 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 411
SA-0207 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 96130 | 136963 | 2 | In Progress | 6.761 | 5.2632 | 20 | 8.9595 | LOW | 0.65 | 0.75 | 66769.4625 | 13353.8925 | 26707.785 | 40061.6775 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 412
SA-0037 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 40833 | 94991 | 135824 | 2 | Closed | 6.7048 | 5.2632 | 20 | 8.9314 | LOW | 0.9 | 0.5 | 61120.8 | 12224.16 | 24448.32 | 36672.48 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 413
SA-0008 | Drilling | Lost Circulation | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 94533 | 135366 | 2 | Closed | 6.6822 | 5.2632 | 20 | 8.9201 | LOW | 0.8 | 0.5 | 54146.4 | 10829.28 | 21658.56 | 32487.84 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 414
SA-0498 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 2 | 40833 | 91284 | 132117 | 2 | Closed | 6.5218 | 5.2632 | 20 | 8.8399 | LOW | 0.9 | 0.5 | 59452.65 | 11890.53 | 23781.06 | 35671.59 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 415
SA-0239 | Weather | Lightning | Heavy Rain | Weather | Resume Operations | 1 | 1 | 1 | 2 | 40000 | 91903 | 131903 | 2 | Closed | 6.5113 | 5.2632 | 20 | 8.8346 | LOW | 0.3 | 0.5 | 19785.45 | 3957.09 | 7914.18 | 11871.27 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 416
SA-0191 | Weather | Heavy Rain | Lightning | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 90548 | 131381 | 2 | Closed | 6.4855 | 5.2632 | 20 | 8.8217 | LOW | 0.3 | 0.5 | 19707.15 | 3941.43 | 7882.86 | 11824.29 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 417
SA-0072 | Weather | Poor Visibility | Lightning | Marine Operations | Suspend Operations | 1 | 1 | 1 | 2 | 38333 | 92556 | 130889 | 2 | Open | 6.4612 | 5.2632 | 20 | 8.8095 | LOW | 0.3 | 1 | 39266.7 | 7853.34 | 15706.68 | 23560.02 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 418
SA-0392 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 91400 | 129733 | 2 | Closed | 6.4041 | 5.2632 | 20 | 8.781 | LOW | 0.9 | 0.5 | 58379.85 | 11675.97 | 23351.94 | 35027.91 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 419
SA-0422 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 1 | 1 | 2 | 38333 | 90911 | 129244 | 2 | Closed | 6.38 | 5.2632 | 20 | 8.7689 | LOW | 0.6 | 0.5 | 38773.2 | 7754.64 | 15509.28 | 23263.92 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 420
SA-0124 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 89900 | 128233 | 2 | Closed | 6.3301 | 5.2632 | 20 | 8.744 | LOW | 0.6 | 0.5 | 38469.9 | 7693.98 | 15387.96 | 23081.94 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 421
SA-0459 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 88171 | 128171 | 2 | Closed | 6.327 | 5.2632 | 20 | 8.7425 | LOW | 0.6 | 0.5 | 38451.3 | 7690.26 | 15380.52 | 23070.78 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 422
SA-0053 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 89763 | 128096 | 2 | In Progress | 6.3233 | 5.2632 | 20 | 8.7406 | LOW | 0.9 | 0.75 | 86464.8 | 17292.96 | 34585.92 | 51878.88 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 423
SA-0268 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 86980 | 127813 | 2 | Closed | 6.3094 | 5.2632 | 20 | 8.7336 | LOW | 0.9 | 0.5 | 57515.85 | 11503.17 | 23006.34 | 34509.51 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 424
SA-0478 | Drilling | Bit Failure | Bit Wear | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40833 | 84650 | 125483 | 2 | In Progress | 6.1943 | 5.2632 | 20 | 8.6761 | LOW | 0.8 | 0.75 | 75289.8 | 15057.96 | 30115.92 | 45173.88 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 425
SA-0493 | Drilling | Well Control | Bit Wear | Operator | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 85472 | 125472 | 2 | Closed | 6.1938 | 5.2632 | 20 | 8.6758 | LOW | 0.8 | 0.5 | 50188.8 | 10037.76 | 20075.52 | 30113.28 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 426
SA-0460 | Drilling | Bit Failure | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 40000 | 85034 | 125034 | 2 | In Progress | 6.1722 | 5.2632 | 20 | 8.665 | LOW | 0.65 | 0.75 | 60954.075 | 12190.815 | 24381.63 | 36572.445 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 427
SA-0090 | Personnel | Training | Training Requirement | Medical Team | Medical Clearance | 1 | 1 | 1 | 2 | 39583 | 85410 | 124993 | 2 | Closed | 6.1702 | 5.2632 | 20 | 8.664 | LOW | 0.6 | 0.5 | 37497.9 | 7499.58 | 14999.16 | 22498.74 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 428
SA-0277 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 86067 | 124400 | 2 | In Progress | 6.1409 | 5.2632 | 20 | 8.6494 | LOW | 0.9 | 0.75 | 83970 | 16794 | 33588 | 50382 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 429
SA-0307 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 85268 | 123601 | 2 | In Progress | 6.1014 | 5.2632 | 20 | 8.6297 | LOW | 0.65 | 0.75 | 60255.4875 | 12051.0975 | 24102.195 | 36153.2925 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 430
SA-0318 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 83567 | 121900 | 2 | Closed | 6.0175 | 5.2632 | 20 | 8.5877 | LOW | 0.9 | 0.5 | 54855 | 10971 | 21942 | 32913 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 431
SA-0087 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 2 | 39583 | 82308 | 121891 | 2 | In Progress | 6.017 | 5.2632 | 20 | 8.5875 | LOW | 0.9 | 0.75 | 82276.425 | 16455.285 | 32910.57 | 49365.855 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 432
SA-0232 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40000 | 81266 | 121266 | 2 | Closed | 5.9862 | 5.2632 | 20 | 8.572 | LOW | 0.9 | 0.5 | 54569.7 | 10913.94 | 21827.88 | 32741.82 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 433
SA-0365 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 82613 | 120946 | 2 | Open | 5.9704 | 5.2632 | 20 | 8.5641 | LOW | 0.9 | 1 | 108851.4 | 21770.28 | 43540.56 | 65310.84 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 434
SA-0233 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 40000 | 79766 | 119766 | 2 | Closed | 5.9121 | 5.2632 | 20 | 8.535 | LOW | 0.9 | 0.5 | 53894.7 | 10778.94 | 21557.88 | 32336.82 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 435
SA-0371 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 81222 | 119555 | 2 | Closed | 5.9017 | 5.2632 | 20 | 8.5298 | LOW | 0.9 | 0.5 | 53799.75 | 10759.95 | 21519.9 | 32279.85 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 436
SA-0250 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 78798 | 117131 | 2 | Closed | 5.7821 | 5.2632 | 20 | 8.47 | LOW | 0.7 | 0.5 | 40995.85 | 8199.17 | 16398.34 | 24597.51 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 437
SA-0023 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 1 | 1 | 2 | 39583 | 76363 | 115946 | 2 | Closed | 5.7236 | 5.2632 | 20 | 8.4407 | LOW | 0.9 | 0.5 | 52175.7 | 10435.14 | 20870.28 | 31305.42 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 438
SA-0163 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 74203 | 114203 | 2 | Closed | 5.6375 | 5.2632 | 20 | 8.3977 | LOW | 0.65 | 0.5 | 37115.975 | 7423.195 | 14846.39 | 22269.585 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 439
SA-0479 | Weather | Strong Wind | Storm | Weather | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 73113 | 113946 | 2 | Closed | 5.6248 | 5.2632 | 20 | 8.3914 | LOW | 0.3 | 0.5 | 17091.9 | 3418.38 | 6836.76 | 10255.14 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 440
SA-0204 | Weather | Heavy Rain | Strong Wind | Weather | Resume Operations | 1 | 1 | 1 | 2 | 40833 | 71375 | 112208 | 2 | In Progress | 5.539 | 5.2632 | 20 | 8.3485 | LOW | 0.3 | 0.75 | 25246.8 | 5049.36 | 10098.72 | 15148.08 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 441
SA-0002 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Repair Component | 1 | 1 | 1 | 2 | 40833 | 70917 | 111750 | 2 | Open | 5.5164 | 5.2632 | 20 | 8.3372 | LOW | 0.9 | 1 | 100575 | 20115 | 40230 | 60345 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 442
SA-0360 | Weather | Heavy Rain | Storm | Marine Operations | Resume Operations | 1 | 1 | 1 | 2 | 38333 | 72796 | 111129 | 2 | Closed | 5.4858 | 5.2632 | 20 | 8.3218 | LOW | 0.3 | 0.5 | 16669.35 | 3333.87 | 6667.74 | 10001.61 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 443
SA-0230 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 40000 | 71032 | 111032 | 2 | Closed | 5.481 | 5.2632 | 20 | 8.3194 | LOW | 0.6 | 0.5 | 33309.6 | 6661.92 | 13323.84 | 19985.76 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 444
SA-0430 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 38333 | 71989 | 110322 | 2 | Closed | 5.4459 | 5.2632 | 20 | 8.3019 | LOW | 0.7 | 0.5 | 38612.7 | 7722.54 | 15445.08 | 23167.62 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 445
SA-0439 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 38333 | 71728 | 110061 | 2 | Closed | 5.4331 | 5.2632 | 20 | 8.2955 | LOW | 0.8 | 0.5 | 44024.4 | 8804.88 | 17609.76 | 26414.64 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 446
SA-0380 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 40000 | 69853 | 109853 | 2 | Closed | 5.4228 | 5.2632 | 20 | 8.2903 | LOW | 0.65 | 0.5 | 35702.225 | 7140.445 | 14280.89 | 21421.335 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 447
SA-0022 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 39583 | 70254 | 109837 | 2 | Closed | 5.422 | 5.2632 | 20 | 8.2899 | LOW | 0.8 | 0.5 | 43934.8 | 8786.96 | 17573.92 | 26360.88 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 448
SA-0440 | Weather | Heavy Rain | High Waves | Weather | Resume Operations | 1 | 1 | 1 | 2 | 38333 | 71077 | 109410 | 2 | Closed | 5.4009 | 5.2632 | 20 | 8.2794 | LOW | 0.3 | 0.5 | 16411.5 | 3282.3 | 6564.6 | 9846.9 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 449
SA-0142 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 67554 | 108387 | 2 | Closed | 5.3504 | 5.2632 | 20 | 8.2542 | LOW | 0.6 | 0.5 | 32516.1 | 6503.22 | 13006.44 | 19509.66 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 450
SA-0466 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 67011 | 107844 | 2 | Closed | 5.3236 | 5.2632 | 20 | 8.2408 | LOW | 0.6 | 0.5 | 32353.2 | 6470.64 | 12941.28 | 19411.92 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 451
SA-0341 | Drilling | Stuck Pipe | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 38333 | 69018 | 107351 | 2 | Closed | 5.2993 | 5.2632 | 20 | 8.2286 | LOW | 0.8 | 0.5 | 42940.4 | 8588.08 | 17176.16 | 25764.24 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 452
SA-0219 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 65954 | 105954 | 2 | Closed | 5.2303 | 5.2632 | 20 | 8.1941 | LOW | 0.8 | 0.5 | 42381.6 | 8476.32 | 16952.64 | 25428.96 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 453
SA-0396 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 1 | 1 | 2 | 38333 | 67158 | 105491 | 2 | Closed | 5.2075 | 5.2632 | 20 | 8.1827 | LOW | 0.6 | 0.5 | 31647.3 | 6329.46 | 12658.92 | 18988.38 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 454
SA-0098 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 38333 | 66496 | 104829 | 2 | In Progress | 5.1748 | 5.2632 | 20 | 8.1663 | LOW | 0.6 | 0.75 | 47173.05 | 9434.61 | 18869.22 | 28303.83 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 455
SA-0252 | Weather | High Waves | Strong Wind | Weather | Suspend Operations | 1 | 1 | 1 | 2 | 39583 | 63322 | 102905 | 2 | Closed | 5.0798 | 5.2632 | 20 | 8.1188 | LOW | 0.3 | 0.5 | 15435.75 | 3087.15 | 6174.3 | 9261.45 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 456
SA-0003 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 60855 | 101688 | 2 | In Progress | 5.0197 | 5.2632 | 20 | 8.0888 | LOW | 0.6 | 0.75 | 45759.6 | 9151.92 | 18303.84 | 27455.76 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 457
SA-0484 | Drilling | Lost Circulation | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 2 | 40833 | 59674 | 100507 | 2 | In Progress | 4.9614 | 5.2632 | 20 | 8.0597 | LOW | 0.65 | 0.75 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 458
SA-0148 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 2 | 40833 | 57857 | 98690 | 2 | Closed | 4.8717 | 5.2632 | 20 | 8.0148 | LOW | 0.6 | 0.5 | 29607 | 5921.4 | 11842.8 | 17764.2 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 459
SA-0383 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 58559 | 98559 | 2 | Closed | 4.8653 | 5.2632 | 20 | 8.0116 | LOW | 0.8 | 0.5 | 39423.6 | 7884.72 | 15769.44 | 23654.16 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 460
SA-0099 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 59428 | 97761 | 2 | In Progress | 4.8259 | 5.2632 | 20 | 7.9919 | LOW | 0.6 | 0.75 | 43992.45 | 8798.49 | 17596.98 | 26395.47 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 461
SA-0375 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 39583 | 57298 | 96881 | 2 | Closed | 4.7824 | 5.2632 | 20 | 7.9702 | LOW | 0.9 | 0.5 | 43596.45 | 8719.29 | 17438.58 | 26157.87 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 462
SA-0465 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 55477 | 96310 | 2 | Open | 4.7542 | 5.2632 | 20 | 7.9561 | LOW | 0.9 | 1 | 86679 | 17335.8 | 34671.6 | 52007.4 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 463
SA-0201 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 39583 | 55699 | 95282 | 2 | In Progress | 4.7035 | 5.2632 | 20 | 7.9307 | LOW | 0.65 | 0.75 | 46449.975 | 9289.995 | 18579.99 | 27869.985 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 464
SA-0069 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 38333 | 55949 | 94282 | 2 | Open | 4.6541 | 5.2632 | 20 | 7.906 | LOW | 0.9 | 1 | 84853.8 | 16970.76 | 33941.52 | 50912.28 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 465
SA-0188 | Personnel | Safety Stand Down | Training Requirement | HR | Crew Replacement | 1 | 1 | 1 | 2 | 40000 | 53981 | 93981 | 2 | Closed | 4.6393 | 5.2632 | 20 | 7.8986 | LOW | 0.6 | 0.5 | 28194.3 | 5638.86 | 11277.72 | 16916.58 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 466
SA-0234 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | Preventive Maintenance | 1 | 1 | 1 | 2 | 40000 | 52909 | 92909 | 2 | Closed | 4.5864 | 5.2632 | 20 | 7.8721 | LOW | 0.9 | 0.5 | 41809.05 | 8361.81 | 16723.62 | 25085.43 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 467
SA-0347 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 38333 | 54487 | 92820 | 2 | In Progress | 4.582 | 5.2632 | 20 | 7.8699 | LOW | 0.9 | 0.75 | 62653.5 | 12530.7 | 25061.4 | 37592.1 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 468
SA-0320 | Drilling | Hole Cleaning | Differential Sticking | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 38333 | 53610 | 91943 | 2 | Open | 4.5387 | 5.2632 | 20 | 7.8483 | LOW | 0.8 | 1 | 73554.4 | 14710.88 | 29421.76 | 44132.64 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 469
SA-0461 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 51341 | 91341 | 2 | Closed | 4.509 | 5.2632 | 20 | 7.8334 | LOW | 0.6 | 0.5 | 27402.3 | 5480.46 | 10960.92 | 16441.38 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 470
SA-0418 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Safety Briefing | 1 | 1 | 1 | 2 | 38333 | 52302 | 90635 | 2 | Closed | 4.4741 | 5.2632 | 20 | 7.816 | LOW | 0.6 | 0.5 | 27190.5 | 5438.1 | 10876.2 | 16314.3 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 471
SA-0288 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 1 | 1 | 2 | 40833 | 48689 | 89522 | 2 | Closed | 4.4192 | 5.2632 | 20 | 7.7885 | LOW | 0.7 | 0.5 | 31332.7 | 6266.54 | 12533.08 | 18799.62 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 472
SA-0200 | Drilling | Well Control | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 1 | 1 | 2 | 39583 | 49805 | 89388 | 2 | Closed | 4.4125 | 5.2632 | 20 | 7.7852 | LOW | 0.8 | 0.5 | 35755.2 | 7151.04 | 14302.08 | 21453.12 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 473
SA-0167 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 1 | 1 | 2 | 40000 | 48341 | 88341 | 2 | Closed | 4.3609 | 5.2632 | 20 | 7.7594 | LOW | 0.9 | 0.5 | 39753.45 | 7950.69 | 15901.38 | 23852.07 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 474
SA-0446 | Drilling | Fishing Operation | Bit Wear | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 49722 | 88055 | 2 | In Progress | 4.3467 | 5.2632 | 20 | 7.7523 | LOW | 0.8 | 0.75 | 52833 | 10566.6 | 21133.2 | 31699.8 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 475
SA-0105 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 38333 | 48369 | 86702 | 2 | Closed | 4.28 | 5.2632 | 20 | 7.7189 | LOW | 0.6 | 0.5 | 26010.6 | 5202.12 | 10404.24 | 15606.36 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 476
SA-0358 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40833 | 45052 | 85885 | 2 | Closed | 4.2396 | 5.2632 | 20 | 7.6988 | LOW | 0.65 | 0.5 | 27912.625 | 5582.525 | 11165.05 | 16747.575 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 477
SA-0285 | Weather | Strong Wind | Lightning | Weather | Suspend Operations | 1 | 1 | 1 | 2 | 40833 | 43926 | 84759 | 2 | Closed | 4.184 | 5.2632 | 20 | 7.671 | LOW | 0.3 | 0.5 | 12713.85 | 2542.77 | 5085.54 | 7628.31 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 478
SA-0198 | Drilling | Hole Cleaning | Formation Instability | Operator | Increase Mud Weight | 1 | 1 | 1 | 2 | 39583 | 44552 | 84135 | 2 | Closed | 4.1532 | 5.2632 | 20 | 7.6556 | LOW | 0.8 | 0.5 | 33654 | 6730.8 | 13461.6 | 20192.4 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 479
SA-0409 | Logistics | Waiting on Materials | Port Congestion | Procurement | Air Freight Materials | 1 | 1 | 1 | 2 | 40833 | 42029 | 82862 | 2 | Closed | 4.0904 | 5.2632 | 20 | 7.6241 | LOW | 0.6 | 0.5 | 24858.6 | 4971.72 | 9943.44 | 14915.16 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 480
SA-0405 | Weather | Poor Visibility | Lightning | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 40833 | 41869 | 82702 | 2 | Closed | 4.0825 | 5.2632 | 20 | 7.6202 | LOW | 0.3 | 0.5 | 12405.3 | 2481.06 | 4962.12 | 7443.18 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 481
SA-0155 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 1 | 1 | 2 | 40000 | 42480 | 82480 | 2 | In Progress | 4.0715 | 5.2632 | 20 | 7.6147 | LOW | 0.6 | 0.75 | 37116 | 7423.2 | 14846.4 | 22269.6 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 482
SA-0300 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Expedite Shipment | 1 | 1 | 1 | 2 | 40833 | 41456 | 82289 | 2 | Open | 4.0621 | 5.2632 | 20 | 7.61 | LOW | 0.6 | 1 | 49373.4 | 9874.68 | 19749.36 | 29624.04 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 483
SA-0335 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 43940 | 82273 | 2 | Open | 4.0613 | 5.2632 | 20 | 7.6096 | LOW | 0.9 | 1 | 74045.7 | 14809.14 | 29618.28 | 44427.42 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 484
SA-0485 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | Medical Clearance | 1 | 1 | 1 | 2 | 38333 | 43207 | 81540 | 2 | Closed | 4.0251 | 5.2632 | 20 | 7.5915 | LOW | 0.6 | 0.5 | 24462 | 4892.4 | 9784.8 | 14677.2 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 485
SA-0093 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 1 | 1 | 2 | 39583 | 39917 | 79500 | 2 | Closed | 3.9244 | 5.2632 | 20 | 7.5412 | LOW | 0.9 | 0.5 | 35775 | 7155 | 14310 | 21465 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 486
SA-0242 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Repair Component | 1 | 1 | 1 | 2 | 38333 | 40806 | 79139 | 2 | Closed | 3.9066 | 5.2632 | 20 | 7.5323 | LOW | 0.7 | 0.5 | 27698.65 | 5539.73 | 11079.46 | 16619.19 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 487
SA-0448 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 1 | 1 | 2 | 38333 | 37321 | 75654 | 2 | Closed | 3.7346 | 5.2632 | 20 | 7.4462 | LOW | 0.9 | 0.5 | 34044.3 | 6808.86 | 13617.72 | 20426.58 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 488
SA-0235 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 1 | 1 | 2 | 40000 | 33971 | 73971 | 2 | Closed | 3.6515 | 5.2632 | 20 | 7.4047 | LOW | 0.9 | 0.5 | 33286.95 | 6657.39 | 13314.78 | 19972.17 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 489
SA-0261 | Weather | Strong Wind | Heavy Rain | Marine Operations | Wait on Weather | 1 | 1 | 1 | 2 | 39583 | 34235 | 73818 | 2 | Open | 3.644 | 5.2632 | 20 | 7.4009 | LOW | 0.3 | 1 | 22145.4 | 4429.08 | 8858.16 | 13287.24 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 490
SA-0297 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 1 | 1 | 2 | 40833 | 31395 | 72228 | 2 | Closed | 3.5655 | 5.2632 | 20 | 7.3617 | LOW | 0.9 | 0.5 | 32502.6 | 6500.52 | 13001.04 | 19501.56 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 491
SA-0438 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 1 | 1 | 2 | 38333 | 33873 | 72206 | 2 | Closed | 3.5644 | 5.2632 | 20 | 7.3611 | LOW | 0.6 | 0.5 | 21661.8 | 4332.36 | 8664.72 | 12997.08 | Logistics NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 492
SA-0381 | Drilling | Well Control | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 1 | 1 | 2 | 40000 | 30168 | 70168 | 2 | Closed | 3.4638 | 5.2632 | 20 | 7.3108 | LOW | 0.8 | 0.5 | 28067.2 | 5613.44 | 11226.88 | 16840.32 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 493
SA-0127 | Weather | Lightning | Heavy Rain | Weather | Wait on Weather | 1 | 1 | 1 | 2 | 38333 | 31793 | 70126 | 2 | In Progress | 3.4617 | 5.2632 | 20 | 7.3098 | LOW | 0.3 | 0.75 | 15778.35 | 3155.67 | 6311.34 | 9467.01 | Weather NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 494
SA-0119 | Drilling | Bit Failure | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 1 | 1 | 2 | 38333 | 30581 | 68914 | 2 | Closed | 3.4019 | 5.2632 | 20 | 7.2799 | LOW | 0.65 | 0.5 | 22397.05 | 4479.41 | 8958.82 | 13438.23 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 495
SA-0447 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 38333 | 29667 | 68000 | 2 | Closed | 3.3568 | 5.2632 | 20 | 7.2573 | LOW | 0.8 | 0.5 | 27200 | 5440 | 10880 | 16320 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 496
SA-0136 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Replace Equipment | 1 | 1 | 1 | 2 | 40833 | 27130 | 67963 | 2 | Closed | 3.3549 | 5.2632 | 20 | 7.2564 | LOW | 0.9 | 0.5 | 30583.35 | 6116.67 | 12233.34 | 18350.01 | Mechanical NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 497
SA-0162 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 1 | 1 | 2 | 40000 | 26827 | 66827 | 2 | Closed | 3.2988 | 5.2632 | 20 | 7.2284 | LOW | 0.8 | 0.5 | 26730.8 | 5346.16 | 10692.32 | 16038.48 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 498
SA-0183 | Drilling | Fishing Operation | Differential Sticking | Operator | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 25923 | 65923 | 2 | Closed | 3.2542 | 5.2632 | 20 | 7.2061 | LOW | 0.8 | 0.5 | 26369.2 | 5273.84 | 10547.68 | 15821.52 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 499
SA-0152 | Personnel | Safety Stand Down | Medical Emergency | HR | Safety Briefing | 1 | 1 | 1 | 2 | 40000 | 25522 | 65522 | 2 | Closed | 3.2344 | 5.2632 | 20 | 7.1962 | LOW | 0.6 | 0.5 | 19656.6 | 3931.32 | 7862.64 | 11793.96 | Personnel NPT Hours | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 500
SA-0220 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Condition Hole | 1 | 1 | 1 | 2 | 40000 | 24142 | 64142 | 2 | In Progress | 3.1663 | 5.2632 | 20 | 7.1621 | LOW | 0.65 | 0.75 | 31269.225 | 6253.845 | 12507.69 | 18761.535 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 501
SA-0120 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Condition Hole | 1 | 1 | 1 | 2 | 38333 | 24138 | 62471 | 2 | Closed | 3.0838 | 5.2632 | 20 | 7.1209 | LOW | 0.65 | 0.5 | 20303.075 | 4060.615 | 8121.23 | 12181.845 | NPT Hours + ROP | 0.15 | 1.7 | 2 | 1.7 | >180 Days | Weekly | 502

## Rig_Action_Plan
Rig_ID | Strategic_Actions | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD
R002 | 245 | 282 | 1610 | 76560445 | 23800565.85
R004 | 181 | 199 | 1186 | 61470399 | 17361888.19
R003 | 108 | 116 | 694 | 34396458 | 9149982.855
R001 | 77 | 80 | 518 | 25722876 | 7084163.72

## Well_Action_Plan
Well_ID | Rig_ID | Strategic_Actions | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD
W011 | R004 | 16 | 16 | 104 | 5187621 | 2783920.55
W040 | R002 | 20 | 21 | 130 | 6620110 | 2365541.36
W003 | R004 | 13 | 13 | 88 | 5225678 | 2314764.37
W048 | R002 | 13 | 14 | 86 | 4208923 | 1905243.44
W013 | R003 | 19 | 20 | 96 | 4883822 | 1827858.67
W010 | R002 | 16 | 16 | 106 | 4734861 | 1772480
W028 | R002 | 15 | 15 | 90 | 4143050 | 1746871.46
W007 | R001 | 16 | 16 | 128 | 6815911 | 1711007.11
W023 | R004 | 14 | 14 | 84 | 4828213 | 1556882.4
W020 | R003 | 20 | 20 | 90 | 4565483 | 1483124.07
W009 | R001 | 15 | 15 | 100 | 4669372 | 1477515.05
W046 | R003 | 16 | 16 | 102 | 5032158 | 1383271.5
W015 | R003 | 14 | 14 | 76 | 4385282 | 1377312.11
W018 | R004 | 14 | 14 | 88 | 3855804 | 1336172.385
W036 | R002 | 19 | 19 | 108 | 5411508 | 1297140.81
W002 | R001 | 13 | 13 | 88 | 4546361 | 1268595.35
W019 | R003 | 13 | 13 | 114 | 5561717 | 1261677.515
W043 | R002 | 18 | 18 | 94 | 4350399 | 1225148.07
W033 | R002 | 16 | 16 | 90 | 4243450 | 1200778.17
W039 | R002 | 12 | 13 | 70 | 3123391 | 1154960.61
W030 | R002 | 15 | 15 | 90 | 4137386 | 1132577.93
W001 | R004 | 19 | 19 | 88 | 4605541 | 1129009.565
W045 | R004 | 10 | 10 | 80 | 4553567 | 1106010.8
W021 | R002 | 15 | 16 | 94 | 4506303 | 1044759.11
W006 | R002 | 15 | 15 | 84 | 4231281 | 972890.02
W041 | R002 | 14 | 14 | 76 | 3512146 | 971254.4
W031 | R002 | 11 | 11 | 60 | 3032755 | 969404.73
W004 | R002 | 11 | 11 | 52 | 2334494 | 955826.42
W005 | R002 | 13 | 13 | 64 | 3143733 | 949472.44
W029 | R002 | 14 | 14 | 70 | 3349062 | 943232.58
W024 | R002 | 12 | 12 | 68 | 3242338 | 910756.44
W034 | R001 | 12 | 12 | 74 | 3657546 | 901986.74
W012 | R004 | 11 | 11 | 64 | 3233740 | 889955.78
W050 | R004 | 11 | 11 | 74 | 3894520 | 878053.2
W037 | R002 | 9 | 9 | 72 | 3194393 | 868663.04
W017 | R001 | 11 | 11 | 54 | 2591314 | 862809.4
W022 | R001 | 13 | 13 | 74 | 3442372 | 862250.07
W047 | R004 | 13 | 13 | 78 | 3918083 | 819772.97
W026 | R004 | 11 | 11 | 90 | 4452824 | 814883.145
W027 | R002 | 10 | 10 | 66 | 3222709 | 800220.915
W038 | R004 | 15 | 15 | 68 | 3555637 | 788012.6
W042 | R004 | 8 | 8 | 52 | 2398167 | 737788
W044 | R003 | 12 | 12 | 64 | 3417944 | 700086.16
W016 | R004 | 10 | 10 | 50 | 2543830 | 696281.67
W032 | R004 | 15 | 15 | 86 | 4251690 | 657544.59
W008 | R002 | 10 | 10 | 40 | 1818153 | 613343.905
W049 | R003 | 9 | 9 | 60 | 2954155 | 559868.08
W035 | R003 | 12 | 12 | 92 | 3595897 | 556784.75
W025 | R004 | 11 | 11 | 54 | 2858646 | 484456.945
W014 | R004 | 8 | 8 | 38 | 2106838 | 368379.22

## Root_Cause_Action_Plan
NPT_Category | NPT_Subcategory | Root_Cause | Strategic_Actions | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD | Stretch_Savings_USD
Mechanical | Top Drive Failure | Poor Preventive Maintenance | 6 | 9 | 78 | 4520732 | 1255083.39 | 1882625.085
Mechanical | Top Drive Failure | Equipment Wear | 5 | 11 | 78 | 4444086 | 1179991.08 | 1769986.62
Drilling | Hole Cleaning | Differential Sticking | 8 | 11 | 104 | 4901437 | 1177846.88 | 1766770.32
Drilling | Lost Circulation | Formation Instability | 8 | 14 | 100 | 4882950 | 922262.055 | 1383393.0825
Mechanical | Draw Works Failure | Hydraulic Failure | 7 | 8 | 62 | 3096667 | 845545.77 | 1268318.655
Drilling | Stuck Pipe | Differential Sticking | 7 | 12 | 80 | 3977501 | 757507.36 | 1136261.04
Drilling | Fishing Operation | Formation Instability | 5 | 11 | 66 | 3534755 | 718485.495 | 1077728.2425
Mechanical | BOP Repair | Equipment Wear | 4 | 6 | 56 | 2779241 | 699879.06 | 1049818.59
Mechanical | Mud Pump Failure | Equipment Wear | 3 | 4 | 32 | 2028719 | 668974.86 | 1003462.29
Drilling | Stuck Pipe | Unexpected Pressure | 8 | 13 | 86 | 3913518 | 638304.225 | 957456.3375
Drilling | Bit Failure | Differential Sticking | 7 | 11 | 62 | 3099059 | 623524.96 | 935287.44
Drilling | Lost Circulation | Bit Wear | 7 | 10 | 48 | 2623049 | 601920.96 | 902881.44
Drilling | Hole Cleaning | Unexpected Pressure | 8 | 13 | 60 | 2884582 | 566726.56 | 850089.84
Mechanical | Power System Failure | Electrical Failure | 5 | 7 | 48 | 2465029 | 563020.92 | 844531.38
Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 5 | 8 | 46 | 1855063 | 562087.71 | 843131.565
Drilling | Stuck Pipe | Bit Wear | 8 | 9 | 66 | 2978603 | 548865.68 | 823298.52
Logistics | Delayed Helicopter | Customs Clearance | 5 | 7 | 60 | 3437722 | 547267.56 | 820901.34
Logistics | Fuel Supply Delay | Customs Clearance | 6 | 10 | 70 | 3927139 | 545198.76 | 817798.14
Drilling | Fishing Operation | Differential Sticking | 7 | 8 | 58 | 2703486 | 534499.68 | 801749.52
Mechanical | Generator Failure | Equipment Wear | 7 | 8 | 44 | 2539624 | 531403.47 | 797105.205
Drilling | Well Control | Bit Wear | 6 | 7 | 54 | 3223917 | 526778.48 | 790167.72
Drilling | Bit Failure | Unexpected Pressure | 6 | 9 | 54 | 2726099 | 494248.82 | 741373.23
Drilling | Hole Cleaning | Bit Wear | 5 | 8 | 48 | 2187474 | 482150.4 | 723225.6
Drilling | Bit Failure | Bit Wear | 5 | 6 | 52 | 2661871 | 465857.2 | 698785.8
Drilling | Lost Circulation | Unexpected Pressure | 5 | 8 | 50 | 1917720 | 432111.94 | 648167.91
Mechanical | Generator Failure | Poor Preventive Maintenance | 5 | 5 | 34 | 1423482 | 426255.84 | 639383.76
Mechanical | BOP Repair | Electrical Failure | 4 | 5 | 40 | 2092385 | 396744.3 | 595116.45
Logistics | Waiting on Cement | Port Congestion | 3 | 4 | 40 | 2126042 | 382959.84 | 574439.76
Weather | Poor Visibility | Heavy Rain | 5 | 9 | 78 | 4182298 | 369557.79 | 554336.685
Drilling | Fishing Operation | Unexpected Pressure | 6 | 8 | 38 | 1612033 | 367095.105 | 550642.6575
Mechanical | Power System Failure | Poor Preventive Maintenance | 5 | 6 | 34 | 1536199 | 363279.78 | 544919.67
Mechanical | Power System Failure | Equipment Wear | 5 | 6 | 42 | 1828126 | 358074.99 | 537112.485
Drilling | Well Control | Formation Instability | 6 | 9 | 40 | 1996829 | 339493.44 | 509240.16
Drilling | Lost Circulation | Differential Sticking | 6 | 6 | 32 | 1709092 | 336943.36 | 505415.04
Mechanical | Rotary Table Failure | Electrical Failure | 6 | 7 | 36 | 1623404 | 334987.02 | 502480.53
Drilling | Well Control | Unexpected Pressure | 8 | 11 | 40 | 1962300 | 330787.535 | 496181.3025
Mechanical | Draw Works Failure | Equipment Wear | 5 | 6 | 26 | 1264479 | 329521.5 | 494282.25
Mechanical | BOP Repair | Hydraulic Failure | 4 | 4 | 26 | 1356626 | 325116.72 | 487675.08
Mechanical | Mud Pump Failure | Hydraulic Failure | 5 | 5 | 30 | 1329879 | 324098.46 | 486147.69
Logistics | Waiting on Materials | Material Shortage | 3 | 6 | 38 | 1849566 | 322318.56 | 483477.84
Weather | Lightning | Lightning | 6 | 16 | 66 | 3303321 | 311905.71 | 467858.565
Mechanical | Top Drive Failure | Electrical Failure | 5 | 6 | 26 | 1095591 | 309380.94 | 464071.41
Mechanical | Generator Failure | Hydraulic Failure | 2 | 4 | 24 | 1167128 | 307969.56 | 461954.34
Logistics | Waiting on Cement | Late Supply Vessel | 6 | 9 | 48 | 2374908 | 290854.62 | 436281.93
Mechanical | Top Drive Failure | Hydraulic Failure | 4 | 4 | 24 | 918695 | 281601.72 | 422402.58
Drilling | Stuck Pipe | Formation Instability | 8 | 9 | 42 | 2009379 | 275446.665 | 413169.9975
Mechanical | BOP Repair | Poor Preventive Maintenance | 5 | 5 | 20 | 1251063 | 267280.11 | 400920.165
Logistics | Waiting on Materials | Port Congestion | 6 | 6 | 40 | 1849672 | 264154.8 | 396232.2
Logistics | Fuel Supply Delay | Material Shortage | 6 | 7 | 36 | 1886060 | 263999.82 | 395999.73
Mechanical | Draw Works Failure | Poor Preventive Maintenance | 3 | 3 | 18 | 988867 | 260192.7 | 390289.05
Logistics | Waiting on Cement | Customs Clearance | 5 | 6 | 34 | 1721673 | 248534.04 | 372801.06
Mechanical | Draw Works Failure | Electrical Failure | 4 | 6 | 26 | 1201879 | 243889.38 | 365834.07
Personnel | Crew Change | Medical Emergency | 3 | 4 | 30 | 1702023 | 237866.04 | 356799.06
Weather | High Waves | Strong Wind | 5 | 6 | 52 | 2509977 | 232278.93 | 348418.395
Logistics | Fuel Supply Delay | Late Supply Vessel | 6 | 7 | 42 | 1792582 | 229825.26 | 344737.89
Mechanical | Power System Failure | Hydraulic Failure | 3 | 3 | 18 | 1021659 | 222543.63 | 333815.445
Weather | Heavy Rain | Strong Wind | 5 | 7 | 54 | 2719878 | 222514.92 | 333772.38
Logistics | Waiting on Boat | Late Supply Vessel | 3 | 4 | 24 | 1260343 | 221659.62 | 332489.43
Drilling | Fishing Operation | Bit Wear | 5 | 5 | 22 | 1335740 | 220762.8 | 331144.2
Mechanical | Rotary Table Failure | Hydraulic Failure | 2 | 3 | 26 | 1091640 | 215450.1 | 323175.15
Weather | Heavy Rain | Heavy Rain | 5 | 7 | 50 | 2316470 | 213768.9 | 320653.35
Logistics | Fuel Supply Delay | Port Congestion | 1 | 1 | 24 | 887460 | 212990.4 | 319485.6
Weather | Poor Visibility | Strong Wind | 5 | 8 | 58 | 3311150 | 211571.94 | 317357.91
Weather | Lightning | High Waves | 5 | 7 | 56 | 2577917 | 195774.06 | 293661.09
Logistics | Delayed Helicopter | Port Congestion | 6 | 7 | 30 | 1405411 | 184918.44 | 277377.66
Mechanical | Mud Pump Failure | Electrical Failure | 4 | 4 | 16 | 926039 | 183657.78 | 275486.67
Mechanical | Top Drive Failure | OEM Defect | 4 | 6 | 26 | 1206431 | 177160.1 | 265740.15
Weather | Lightning | Heavy Rain | 5 | 6 | 44 | 2022806 | 173957.58 | 260936.37
Mechanical | Mud Pump Failure | OEM Defect | 4 | 4 | 28 | 1186992 | 171368.2 | 257052.3
Mechanical | Draw Works Failure | OEM Defect | 5 | 5 | 20 | 882262 | 170689.77 | 256034.655
Logistics | Delayed Helicopter | Material Shortage | 3 | 3 | 20 | 1163659 | 169119.12 | 253678.68
Weather | Heavy Rain | High Waves | 5 | 7 | 28 | 1662334 | 166929.9 | 250394.85
Personnel | Safety Stand Down | Training Requirement | 5 | 6 | 26 | 1019932 | 164533.44 | 246800.16
Drilling | Hole Cleaning | Formation Instability | 5 | 6 | 20 | 1012102 | 161936.32 | 242904.48
Personnel | Safety Stand Down | Medical Emergency | 3 | 3 | 24 | 964349 | 161101.14 | 241651.71
Weather | High Waves | Lightning | 5 | 8 | 42 | 2312273 | 157146.75 | 235720.125
Logistics | Delayed Helicopter | Late Supply Vessel | 3 | 6 | 22 | 1303380 | 156405.6 | 234608.4
Drilling | Bit Failure | Formation Instability | 7 | 7 | 24 | 991445 | 152983.61 | 229475.415
Weather | Strong Wind | Strong Wind | 3 | 8 | 40 | 1895190 | 152777.55 | 229166.325
Weather | High Waves | Heavy Rain | 4 | 6 | 28 | 1414876 | 149211.57 | 223817.355
Mechanical | BOP Repair | OEM Defect | 2 | 3 | 14 | 797333 | 148432.4 | 222648.6
Weather | Heavy Rain | Lightning | 5 | 7 | 30 | 1802257 | 147389.82 | 221084.73
Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 2 | 22 | 800015 | 144002.7 | 216004.05
Weather | Heavy Rain | Storm | 5 | 5 | 40 | 2045585 | 132850.29 | 199275.435
Logistics | Waiting on Boat | Port Congestion | 3 | 3 | 16 | 1021659 | 122599.08 | 183898.62
Weather | Strong Wind | High Waves | 5 | 6 | 32 | 1683282 | 122466.84 | 183700.26
Weather | Poor Visibility | Lightning | 5 | 7 | 30 | 1379915 | 122171.43 | 183257.145
Personnel | Medical Evacuation | Training Requirement | 4 | 6 | 22 | 990027 | 118803.24 | 178204.86
Logistics | Waiting on Materials | Late Supply Vessel | 4 | 4 | 16 | 855809 | 116341.8 | 174512.7
Weather | Lightning | Storm | 4 | 5 | 32 | 1645274 | 114969.18 | 172453.77
Weather | High Waves | High Waves | 3 | 5 | 30 | 1379960 | 114916.26 | 172374.39
Weather | Strong Wind | Storm | 4 | 6 | 24 | 996021 | 102364.38 | 153546.57
Personnel | Safety Stand Down | Crew Rotation | 3 | 4 | 18 | 792748 | 95129.76 | 142694.64
Weather | Lightning | Strong Wind | 3 | 4 | 32 | 1583199 | 94991.94 | 142487.91
Logistics | Waiting on Materials | Customs Clearance | 4 | 4 | 12 | 545457 | 93231.6 | 139847.4
Weather | High Waves | Storm | 4 | 5 | 24 | 1225627 | 90510.63 | 135765.945
Logistics | Waiting on Cement | Material Shortage | 3 | 4 | 16 | 686490 | 88480.08 | 132720.12
Logistics | Waiting on Boat | Customs Clearance | 2 | 3 | 10 | 603966 | 84585.66 | 126878.49
Mechanical | Generator Failure | Electrical Failure | 2 | 2 | 8 | 375128 | 82332.18 | 123498.27
Mechanical | Power System Failure | OEM Defect | 2 | 2 | 10 | 531207 | 74368.98 | 111553.47
Personnel | Crew Change | Crew Rotation | 1 | 1 | 18 | 603804 | 72456.48 | 108684.72
Mechanical | Rotary Table Failure | Equipment Wear | 3 | 3 | 10 | 377235 | 67902.3 | 101853.45
Weather | Strong Wind | Heavy Rain | 3 | 4 | 24 | 928549 | 60142.02 | 90213.03
Weather | Poor Visibility | Storm | 4 | 6 | 22 | 932344 | 55940.64 | 83910.96
Weather | Poor Visibility | High Waves | 4 | 4 | 18 | 730402 | 51533.25 | 77299.875
Personnel | Medical Evacuation | Medical Emergency | 1 | 1 | 6 | 376090 | 45130.8 | 67696.2
Mechanical | Generator Failure | OEM Defect | 1 | 1 | 4 | 229210 | 41257.8 | 61886.7
Logistics | Waiting on Boat | Material Shortage | 2 | 3 | 8 | 329917 | 39590.04 | 59385.06
Personnel | Training | Crew Rotation | 1 | 1 | 6 | 213210 | 38377.8 | 57566.7
Drilling | Well Control | Differential Sticking | 2 | 2 | 6 | 216915 | 34706.4 | 52059.6
Weather | Strong Wind | Lightning | 2 | 2 | 8 | 323098 | 19385.88 | 29078.82
Personnel | Crew Change | Training Requirement | 1 | 1 | 4 | 156113 | 18733.56 | 28100.34
Personnel | Training | Training Requirement | 1 | 1 | 2 | 124993 | 14999.16 | 22498.74

## Responsible_Party
Responsible_Party | Strategic_Actions | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD
OEM Vendor | 49 | 59 | 376 | 18331322 | 4744851.33
Directional Drilling | 52 | 71 | 428 | 21180149 | 4334605.89
Drilling Contractor | 49 | 65 | 368 | 19000514 | 4253575.37
Mud Engineering | 50 | 70 | 438 | 21226556 | 3815891.51
Operator | 51 | 72 | 386 | 18655151 | 3560748.53
Maintenance Team | 39 | 47 | 308 | 14900279 | 3535118.52
Marine Operations | 57 | 88 | 490 | 25000021 | 2086396.53
Supply Chain | 26 | 32 | 236 | 12321042 | 1862162.4
Weather | 52 | 73 | 452 | 21883982 | 1700631.63
Procurement | 27 | 36 | 180 | 9196062 | 1474928.46
Marine Logistics | 27 | 36 | 190 | 9511811 | 1247943.84
Rig Management | 7 | 9 | 66 | 2571074 | 398890.44
Medical Team | 10 | 11 | 56 | 2864253 | 373338.42
HR | 6 | 8 | 34 | 1507962 | 194902.56

## KPI_Framework
KPI | Definition | Baseline | Target | Target_Reduction_pct | Frequency | Owner
Total NPT Hours | Total non-productive drilling hours | 4008 | 2605.2 | 0.35 | Weekly | Drilling Operations
Economic Impact | Total NPT economic impact | 198150178 | 128797615.7 | 0.35 | Monthly | Operations Management
Target Savings | Validated expected savings | 0 | 33583985.43 |  | Monthly | Operations Management
Strategic Action Closure Rate | Closed strategic actions / total actions | 0.62948 | 0.9 |  | Weekly | Action Owners
Critical Action Closure | Closed critical actions / critical actions | 0.25 | 0.9 |  | Weekly | Operations Management

## Implementation_Roadmap
Implementation_Horizon | Strategic_Actions | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD
0-30 Days | 4 | 10 | 138 | 8008039 | 2137110.7
31-90 Days | 6 | 16 | 166 | 9575256 | 1898498.25
91-180 Days | 18 | 44 | 420 | 21567225 | 3367371.155
>180 Days | 474 | 607 | 3284 | 158999658 | 26181005.325

## Savings_By_Action
Action_Rank | Strategic_Action_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Corrective_Action | Priority | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Addressable_Impact_USD | Conservative_Savings_USD | Target_Savings_USD | Stretch_Savings_USD
1 | SA-0033 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | CRITICAL | 3 | 38 | 2000357 | 1600285.6 | 320057.12 | 640114.24 | 960171.36
2 | SA-0108 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | CRITICAL | 3 | 36 | 2025768 | 607730.4 | 121546.08 | 243092.16 | 364638.24
3 | SA-0036 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | CRITICAL | 2 | 32 | 1995386 | 1346885.55 | 269377.11 | 538754.22 | 808131.33
4 | SA-0135 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | CRITICAL | 2 | 32 | 1986528 | 1787875.2 | 357575.04 | 715150.08 | 1072725.12
5 | SA-0426 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | HIGH | 2 | 30 | 1924964 | 433116.9 | 86623.38 | 173246.76 | 259870.14
6 | SA-0275 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | HIGH | 4 | 28 | 1433980 | 645291 | 129058.2 | 258116.4 | 387174.6
7 | SA-0149 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | HIGH | 3 | 26 | 1550070 | 755659.125 | 151131.825 | 302263.65 | 453395.475
8 | SA-0092 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | HIGH | 2 | 26 | 1687808 | 1519027.2 | 303805.44 | 607610.88 | 911416.32
9 | SA-0164 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | HIGH | 2 | 28 | 1606675 | 1084505.625 | 216901.125 | 433802.25 | 650703.375
10 | SA-0031 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | HIGH | 3 | 28 | 1371759 | 308645.775 | 61729.155 | 123458.31 | 185187.465
11 | SA-0048 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | MEDIUM | 3 | 24 | 1332986 | 533194.4 | 106638.88 | 213277.76 | 319916.64
12 | SA-0182 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | MEDIUM | 2 | 24 | 1475042 | 442512.6 | 88502.52 | 177005.04 | 265507.56
13 | SA-0423 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | MEDIUM | 3 | 26 | 1246345 | 373903.5 | 74780.7 | 149561.4 | 224342.1
14 | SA-0160 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | MEDIUM | 3 | 22 | 1322159 | 644552.5125 | 128910.5025 | 257821.005 | 386731.5075
15 | SA-0088 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | MEDIUM | 2 | 24 | 1416581 | 637461.45 | 127492.29 | 254984.58 | 382476.87
16 | SA-0122 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | MEDIUM | 2 | 26 | 1338154 | 301084.65 | 60216.93 | 120433.86 | 180650.79
17 | SA-0034 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | MEDIUM | 4 | 22 | 1113727 | 1002354.3 | 200470.86 | 400941.72 | 601412.58
18 | SA-0222 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | MEDIUM | 2 | 22 | 1397755 | 559102 | 111820.4 | 223640.8 | 335461.2
19 | SA-0109 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | MEDIUM | 2 | 28 | 1145945 | 372432.125 | 74486.425 | 148972.85 | 223459.275
20 | SA-0080 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | MEDIUM | 2 | 26 | 1204623 | 481849.2 | 96369.84 | 192739.68 | 289109.52
21 | SA-0064 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | MEDIUM | 4 | 22 | 995555 | 223999.875 | 44799.975 | 89599.95 | 134399.925
22 | SA-0032 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | MEDIUM | 3 | 22 | 1087628 | 734148.9 | 146829.78 | 293659.56 | 440489.34
23 | SA-0042 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | MEDIUM | 2 | 20 | 1212253 | 818270.775 | 163654.155 | 327308.31 | 490962.465
24 | SA-0056 | Weather | Lightning | Lightning | Weather | Suspend Operations | MEDIUM | 5 | 16 | 835484 | 187983.9 | 37596.78 | 75193.56 | 112790.34
25 | SA-0404 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Expedite Shipment | MEDIUM | 1 | 24 | 1223810 | 550714.5 | 110142.9 | 220285.8 | 330428.7
26 | SA-0214 | Weather | Lightning | High Waves | Weather | Resume Operations | MEDIUM | 1 | 24 | 1154701 | 173205.15 | 34641.03 | 69282.06 | 103923.09
27 | SA-0018 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | MEDIUM | 2 | 24 | 959820 | 215959.5 | 43191.9 | 86383.8 | 129575.7
28 | SA-0293 | Weather | Heavy Rain | Storm | Weather | Resume Operations | MEDIUM | 1 | 24 | 1104657 | 165698.55 | 33139.71 | 66279.42 | 99419.13
29 | SA-0147 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | LOW | 2 | 20 | 1024439 | 332942.675 | 66588.535 | 133177.07 | 199765.605
30 | SA-0104 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | LOW | 4 | 16 | 808275 | 525378.75 | 105075.75 | 210151.5 | 315227.25
31 | SA-0431 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | LOW | 2 | 18 | 1065290 | 639174 | 127834.8 | 255669.6 | 383504.4
32 | SA-0464 | Weather | Poor Visibility | Strong Wind | Marine Operations | Suspend Operations | LOW | 1 | 18 | 1219350 | 182902.5 | 36580.5 | 73161 | 109741.5
33 | SA-0066 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | LOW | 3 | 16 | 944545 | 283363.5 | 56672.7 | 113345.4 | 170018.1
34 | SA-0393 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | LOW | 2 | 20 | 944371 | 424966.95 | 84993.39 | 169986.78 | 254980.17
35 | SA-0086 | Drilling | Well Control | Bit Wear | Directional Drilling | Condition Hole | LOW | 1 | 18 | 1154940 | 461976 | 92395.2 | 184790.4 | 277185.6
36 | SA-0210 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | LOW | 3 | 18 | 829534 | 497720.4 | 99544.08 | 199088.16 | 298632.24
37 | SA-0260 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | LOW | 2 | 16 | 1053754 | 158063.1 | 31612.62 | 63225.24 | 94837.86
38 | SA-0065 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | LOW | 3 | 16 | 889466 | 400259.7 | 80051.94 | 160103.88 | 240155.82
39 | SA-0264 | Personnel | Crew Change | Medical Emergency | Medical Team | Medical Clearance | LOW | 1 | 18 | 1141635 | 342490.5 | 68498.1 | 136996.2 | 205494.3
40 | SA-0024 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Repair Component | LOW | 1 | 18 | 1109300 | 499185 | 99837 | 199674 | 299511
41 | SA-0138 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | LOW | 2 | 20 | 881030 | 396463.5 | 79292.7 | 158585.4 | 237878.1
42 | SA-0374 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | LOW | 2 | 22 | 800015 | 360006.75 | 72001.35 | 144002.7 | 216004.05
43 | SA-0203 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Air Freight Materials | LOW | 1 | 24 | 887460 | 532476 | 106495.2 | 212990.4 | 319485.6
44 | SA-0225 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 1 | 18 | 1023187 | 460434.15 | 92086.83 | 184173.66 | 276260.49
45 | SA-0304 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | LOW | 3 | 14 | 797972 | 638377.6 | 127675.52 | 255351.04 | 383026.56
46 | SA-0130 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | LOW | 3 | 18 | 650525 | 422841.25 | 84568.25 | 169136.5 | 253704.75
47 | SA-0150 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | LOW | 2 | 16 | 865026 | 389261.7 | 77852.34 | 155704.68 | 233557.02
48 | SA-0218 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | LOW | 2 | 16 | 863558 | 280656.35 | 56131.27 | 112262.54 | 168393.81
49 | SA-0047 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | LOW | 3 | 14 | 743179 | 222953.7 | 44590.74 | 89181.48 | 133772.22
50 | SA-0050 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | LOW | 3 | 16 | 678675 | 441138.75 | 88227.75 | 176455.5 | 264683.25
51 | SA-0246 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 18 | 918898 | 275669.4 | 55133.88 | 110267.76 | 165401.64
52 | SA-0378 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | LOW | 2 | 20 | 692021 | 276808.4 | 55361.68 | 110723.36 | 166085.04
53 | SA-0301 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 18 | 910252 | 546151.2 | 109230.24 | 218460.48 | 327690.72
54 | SA-0229 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | LOW | 2 | 20 | 681870 | 613683 | 122736.6 | 245473.2 | 368209.8
55 | SA-0126 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | LOW | 3 | 12 | 756920 | 605536 | 121107.2 | 242214.4 | 363321.6
56 | SA-0432 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | LOW | 1 | 18 | 848296 | 763466.4 | 152693.28 | 305386.56 | 458079.84
57 | SA-0316 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | LOW | 2 | 18 | 671484 | 100722.6 | 20144.52 | 40289.04 | 60433.56
58 | SA-0179 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | LOW | 3 | 12 | 687915 | 206374.5 | 41274.9 | 82549.8 | 123824.7
59 | SA-0352 | Weather | Lightning | Strong Wind | Weather | Suspend Operations | LOW | 1 | 18 | 813357 | 122003.55 | 24400.71 | 48801.42 | 73202.13
60 | SA-0091 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | LOW | 2 | 16 | 701596 | 280638.4 | 56127.68 | 112255.36 | 168383.04
61 | SA-0161 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | LOW | 2 | 16 | 699182 | 227234.15 | 45446.83 | 90893.66 | 136340.49
62 | SA-0013 | Weather | High Waves | Lightning | Weather | Resume Operations | LOW | 2 | 14 | 762121 | 114318.15 | 22863.63 | 45727.26 | 68590.89
63 | SA-0095 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | Air Freight Materials | LOW | 1 | 18 | 782733 | 234819.9 | 46963.98 | 93927.96 | 140891.94
64 | SA-0453 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Replace Equipment | LOW | 1 | 18 | 763285 | 267149.75 | 53429.95 | 106859.9 | 160289.85
65 | SA-0299 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | Crew Replacement | LOW | 1 | 18 | 756321 | 340344.45 | 68068.89 | 136137.78 | 204206.67
66 | SA-0115 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | LOW | 3 | 12 | 603759 | 181127.7 | 36225.54 | 72451.08 | 108676.62
67 | SA-0442 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Condition Hole | LOW | 1 | 18 | 735612 | 441367.2 | 88273.44 | 176546.88 | 264820.32
68 | SA-0317 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 18 | 725594 | 290237.6 | 58047.52 | 116095.04 | 174142.56
69 | SA-0364 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | LOW | 2 | 16 | 611277 | 412611.975 | 82522.395 | 165044.79 | 247567.185
70 | SA-0132 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | LOW | 3 | 12 | 570436 | 456348.8 | 91269.76 | 182539.52 | 273809.28
71 | SA-0273 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | LOW | 2 | 16 | 603848 | 294375.9 | 58875.18 | 117750.36 | 176625.54
72 | SA-0350 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | LOW | 2 | 14 | 662374 | 99356.1 | 19871.22 | 39742.44 | 59613.66
73 | SA-0361 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | LOW | 2 | 12 | 724267 | 470773.55 | 94154.71 | 188309.42 | 282464.13
74 | SA-0017 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | LOW | 3 | 12 | 560259 | 378174.825 | 75634.965 | 151269.93 | 226904.895
75 | SA-0028 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | LOW | 2 | 14 | 653538 | 392122.8 | 78424.56 | 156849.12 | 235273.68
76 | SA-0490 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Run Fishing Tools | LOW | 1 | 18 | 674096 | 269638.4 | 53927.68 | 107855.36 | 161783.04
77 | SA-0010 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | LOW | 3 | 12 | 535311 | 160593.3 | 32118.66 | 64237.32 | 96355.98
78 | SA-0006 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | LOW | 2 | 14 | 632812 | 94921.8 | 18984.36 | 37968.72 | 56953.08
79 | SA-0153 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | LOW | 2 | 14 | 620573 | 186171.9 | 37234.38 | 74468.76 | 111703.14
80 | SA-0005 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | LOW | 3 | 12 | 519736 | 181907.6 | 36381.52 | 72763.04 | 109144.56
81 | SA-0292 | Weather | High Waves | Strong Wind | Marine Operations | Suspend Operations | LOW | 1 | 12 | 825843 | 185814.675 | 37162.935 | 74325.87 | 111488.805
82 | SA-0058 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | LOW | 2 | 12 | 662865 | 596578.5 | 119315.7 | 238631.4 | 357947.1
83 | SA-0044 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | LOW | 2 | 14 | 590628 | 265782.6 | 53156.52 | 106313.04 | 159469.56
84 | SA-0176 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | LOW | 2 | 14 | 590044 | 383528.6 | 76705.72 | 153411.44 | 230117.16
85 | SA-0051 | Weather | Lightning | Lightning | Weather | Wait on Weather | LOW | 2 | 14 | 588737 | 132465.825 | 26493.165 | 52986.33 | 79479.495
86 | SA-0400 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | LOW | 2 | 12 | 642825 | 417836.25 | 83567.25 | 167134.5 | 250701.75
87 | SA-0180 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | LOW | 3 | 10 | 542032 | 264240.6 | 52848.12 | 105696.24 | 158544.36
88 | SA-0139 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Condition Hole | LOW | 1 | 12 | 799806 | 319922.4 | 63984.48 | 127968.96 | 191953.44
89 | SA-0481 | Personnel | Crew Change | Crew Rotation | Rig Management | Medical Clearance | LOW | 1 | 18 | 603804 | 181141.2 | 36228.24 | 72456.48 | 108684.72
90 | SA-0338 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | LOW | 2 | 10 | 688998 | 465073.65 | 93014.73 | 186029.46 | 279044.19
91 | SA-0290 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Condition Hole | LOW | 1 | 12 | 784466 | 313786.4 | 62757.28 | 125514.56 | 188271.84
92 | SA-0074 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | LOW | 2 | 12 | 613679 | 138077.775 | 27615.555 | 55231.11 | 82846.665
93 | SA-0011 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | LOW | 2 | 10 | 662540 | 198762 | 39752.4 | 79504.8 | 119257.2
94 | SA-0045 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | LOW | 2 | 12 | 592985 | 88947.75 | 17789.55 | 35579.1 | 53368.65
95 | SA-0171 | Drilling | Stuck Pipe | Bit Wear | Operator | Run Fishing Tools | LOW | 1 | 12 | 753399 | 301359.6 | 60271.92 | 120543.84 | 180815.76
96 | SA-0325 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | LOW | 2 | 10 | 654240 | 196272 | 39254.4 | 78508.8 | 117763.2
97 | SA-0382 | Weather | High Waves | Strong Wind | Marine Operations | Resume Operations | LOW | 1 | 18 | 560297 | 168089.1 | 33617.82 | 67235.64 | 100853.46
98 | SA-0030 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | LOW | 2 | 12 | 566196 | 509576.4 | 101915.28 | 203830.56 | 305745.84
99 | SA-0237 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | LOW | 2 | 10 | 630034 | 220511.9 | 44102.38 | 88204.76 | 132307.14
100 | SA-0251 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | LOW | 2 | 14 | 499197 | 399357.6 | 79871.52 | 159743.04 | 239614.56
101 | SA-0419 | Weather | Lightning | Heavy Rain | Marine Operations | Wait on Weather | LOW | 1 | 12 | 723028 | 162681.3 | 32536.26 | 65072.52 | 97608.78
102 | SA-0125 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | LOW | 2 | 10 | 620732 | 302606.85 | 60521.37 | 121042.74 | 181564.11
103 | SA-0421 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | LOW | 2 | 12 | 550011 | 220004.4 | 44000.88 | 88001.76 | 132002.64
104 | SA-0402 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | LOW | 2 | 12 | 549958 | 357472.7 | 71494.54 | 142989.08 | 214483.62
105 | SA-0007 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | LOW | 2 | 12 | 521909 | 208763.6 | 41752.72 | 83505.44 | 125258.16
106 | SA-0266 | Weather | Lightning | Storm | Weather | Resume Operations | LOW | 1 | 12 | 676874 | 101531.1 | 20306.22 | 40612.44 | 60918.66
107 | SA-0302 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | LOW | 3 | 10 | 413058 | 123917.4 | 24783.48 | 49566.96 | 74350.44
108 | SA-0001 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | LOW | 2 | 10 | 574944 | 344966.4 | 68993.28 | 137986.56 | 206979.84
109 | SA-0336 | Weather | High Waves | High Waves | Marine Operations | Resume Operations | LOW | 1 | 12 | 659330 | 98899.5 | 19779.9 | 39559.8 | 59339.7
110 | SA-0337 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | LOW | 1 | 12 | 648094 | 291642.3 | 58328.46 | 116656.92 | 174985.38
111 | SA-0015 | Weather | High Waves | Storm | Marine Operations | Wait on Weather | LOW | 1 | 12 | 639548 | 95932.2 | 19186.44 | 38372.88 | 57559.32
112 | SA-0368 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 12 | 637608 | 191282.4 | 38256.48 | 76512.96 | 114769.44
113 | SA-0455 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Expedite Shipment | LOW | 1 | 12 | 633320 | 189996 | 37999.2 | 75998.4 | 113997.6
114 | SA-0425 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | LOW | 2 | 10 | 534644 | 173759.3 | 34751.86 | 69503.72 | 104255.58
115 | SA-0366 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | LOW | 2 | 12 | 467441 | 70116.15 | 14023.23 | 28046.46 | 42069.69
116 | SA-0469 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Expedite Shipment | LOW | 1 | 12 | 614455 | 184336.5 | 36867.3 | 73734.6 | 110601.9
117 | SA-0501 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 12 | 613627 | 245450.8 | 49090.16 | 98180.32 | 147270.48
118 | SA-0224 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 12 | 606765 | 182029.5 | 36405.9 | 72811.8 | 109217.7
119 | SA-0004 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | LOW | 2 | 10 | 505330 | 151599 | 30319.8 | 60639.6 | 90959.4
120 | SA-0129 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | LOW | 2 | 10 | 490233 | 73534.95 | 14706.99 | 29413.98 | 44120.97
121 | SA-0330 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | LOW | 2 | 12 | 421769 | 189796.05 | 37959.21 | 75918.42 | 113877.63
122 | SA-0103 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | LOW | 2 | 8 | 525857 | 341807.05 | 68361.41 | 136722.82 | 205084.23
123 | SA-0111 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 2 | 10 | 458634 | 412770.6 | 82554.12 | 165108.24 | 247662.36
124 | SA-0314 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | LOW | 2 | 8 | 510936 | 306561.6 | 61312.32 | 122624.64 | 183936.96
125 | SA-0106 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | LOW | 2 | 8 | 497640 | 74646 | 14929.2 | 29858.4 | 44787.6
126 | SA-0385 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 12 | 531067 | 212426.8 | 42485.36 | 84970.72 | 127456.08
127 | SA-0441 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | LOW | 2 | 8 | 496272 | 111661.2 | 22332.24 | 44664.48 | 66996.72
128 | SA-0255 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | LOW | 2 | 10 | 430098 | 96772.05 | 19354.41 | 38708.82 | 58063.23
129 | SA-0212 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Condition Hole | LOW | 1 | 12 | 523344 | 170086.8 | 34017.36 | 68034.72 | 102052.08
130 | SA-0184 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | LOW | 3 | 8 | 304293 | 197790.45 | 39558.09 | 79116.18 | 118674.27
131 | SA-0291 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | LOW | 2 | 10 | 397925 | 193988.4375 | 38797.6875 | 77595.375 | 116393.0625
132 | SA-0240 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Repair Component | LOW | 1 | 12 | 495392 | 222926.4 | 44585.28 | 89170.56 | 133755.84
133 | SA-0306 | Weather | Lightning | High Waves | Weather | Suspend Operations | LOW | 1 | 12 | 488903 | 73335.45 | 14667.09 | 29334.18 | 44001.27
134 | SA-0137 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | LOW | 2 | 10 | 390215 | 87798.375 | 17559.675 | 35119.35 | 52679.025
135 | SA-0206 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | LOW | 2 | 8 | 439448 | 296627.4 | 59325.48 | 118650.96 | 177976.44
136 | SA-0083 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | LOW | 2 | 8 | 431142 | 172456.8 | 34491.36 | 68982.72 | 103474.08
137 | SA-0117 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Air Freight Materials | LOW | 1 | 12 | 461255 | 138376.5 | 27675.3 | 55350.6 | 83025.9
138 | SA-0131 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | LOW | 2 | 8 | 426642 | 63996.3 | 12799.26 | 25598.52 | 38397.78
139 | SA-0077 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | LOW | 2 | 10 | 360764 | 108229.2 | 21645.84 | 43291.68 | 64937.52
140 | SA-0052 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | LOW | 2 | 10 | 360223 | 234144.95 | 46828.99 | 93657.98 | 140486.97
141 | SA-0041 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | LOW | 2 | 8 | 422889 | 190300.05 | 38060.01 | 76120.02 | 114180.03
142 | SA-0186 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | LOW | 2 | 8 | 422843 | 169137.2 | 33827.44 | 67654.88 | 101482.32
143 | SA-0169 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | LOW | 2 | 8 | 414852 | 186683.4 | 37336.68 | 74673.36 | 112010.04
144 | SA-0248 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | LOW | 2 | 8 | 413001 | 123900.3 | 24780.06 | 49560.12 | 74340.18
145 | SA-0146 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | LOW | 2 | 10 | 343071 | 154381.95 | 30876.39 | 61752.78 | 92629.17
146 | SA-0496 | Drilling | Lost Circulation | Bit Wear | Operator | Run Fishing Tools | LOW | 1 | 8 | 568521 | 454816.8 | 90963.36 | 181926.72 | 272890.08
147 | SA-0178 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Repair Component | LOW | 1 | 8 | 553128 | 248907.6 | 49781.52 | 99563.04 | 149344.56
148 | SA-0061 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | LOW | 2 | 10 | 326916 | 98074.8 | 19614.96 | 39229.92 | 58844.88
149 | SA-0070 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | LOW | 2 | 8 | 383364 | 86256.9 | 17251.38 | 34502.76 | 51754.14
150 | SA-0424 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | LOW | 2 | 8 | 383096 | 57464.4 | 11492.88 | 22985.76 | 34478.64
151 | SA-0029 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | LOW | 2 | 8 | 382626 | 114787.8 | 22957.56 | 45915.12 | 68872.68
152 | SA-0046 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | LOW | 2 | 8 | 370834 | 148333.6 | 29666.72 | 59333.44 | 89000.16
153 | SA-0231 | Weather | High Waves | Heavy Rain | Marine Operations | Suspend Operations | LOW | 1 | 8 | 524772 | 157431.6 | 31486.32 | 62972.64 | 94458.96
154 | SA-0334 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | Replace Equipment | LOW | 1 | 8 | 517088 | 232689.6 | 46537.92 | 93075.84 | 139613.76
155 | SA-0096 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | LOW | 1 | 8 | 515497 | 231973.65 | 46394.73 | 92789.46 | 139184.19
156 | SA-0420 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | LOW | 2 | 8 | 346993 | 78073.425 | 15614.685 | 31229.37 | 46844.055
157 | SA-0313 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Increase Mud Weight | LOW | 1 | 12 | 380405 | 123631.625 | 24726.325 | 49452.65 | 74178.975
158 | SA-0467 | Weather | Heavy Rain | Heavy Rain | Weather | Resume Operations | LOW | 1 | 12 | 378994 | 56849.1 | 11369.82 | 22739.64 | 34109.46
159 | SA-0059 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | LOW | 2 | 8 | 344046 | 77410.35 | 15482.07 | 30964.14 | 46446.21
160 | SA-0071 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | LOW | 1 | 8 | 501153 | 225518.85 | 45103.77 | 90207.54 | 135311.31
161 | SA-0367 | Weather | Strong Wind | High Waves | Weather | Wait on Weather | LOW | 1 | 8 | 500542 | 75081.3 | 15016.26 | 30032.52 | 45048.78
162 | SA-0039 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | LOW | 2 | 6 | 402137 | 120641.1 | 24128.22 | 48256.44 | 72384.66
163 | SA-0310 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Run Fishing Tools | LOW | 1 | 8 | 495628 | 322158.2 | 64431.64 | 128863.28 | 193294.92
164 | SA-0221 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | LOW | 2 | 8 | 330172 | 132068.8 | 26413.76 | 52827.52 | 79241.28
165 | SA-0216 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | LOW | 2 | 8 | 329802 | 107185.65 | 21437.13 | 42874.26 | 64311.39
166 | SA-0215 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | Preventive Maintenance | LOW | 1 | 12 | 363301 | 326970.9 | 65394.18 | 130788.36 | 196182.54
167 | SA-0401 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Condition Hole | LOW | 1 | 12 | 362340 | 144936 | 28987.2 | 57974.4 | 86961.6
168 | SA-0085 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | LOW | 2 | 8 | 317064 | 71339.4 | 14267.88 | 28535.76 | 42803.64
169 | SA-0055 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | LOW | 1 | 12 | 351023 | 157960.35 | 31592.07 | 63184.14 | 94776.21
170 | SA-0433 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Air Freight Materials | LOW | 1 | 8 | 470980 | 141294 | 28258.8 | 56517.6 | 84776.4
171 | SA-0471 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 8 | 466975 | 186790 | 37358 | 74716 | 112074
172 | SA-0166 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | LOW | 2 | 8 | 303591 | 121436.4 | 24287.28 | 48574.56 | 72861.84
173 | SA-0254 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | LOW | 1 | 8 | 456648 | 410983.2 | 82196.64 | 164393.28 | 246589.92
174 | SA-0349 | Weather | Heavy Rain | Lightning | Marine Operations | Suspend Operations | LOW | 1 | 8 | 452025 | 67803.75 | 13560.75 | 27121.5 | 40682.25
175 | SA-0156 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | LOW | 2 | 8 | 288274 | 86482.2 | 17296.44 | 34592.88 | 51889.32
176 | SA-0487 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Condition Hole | LOW | 1 | 8 | 442510 | 177004 | 35400.8 | 70801.6 | 106202.4
177 | SA-0082 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | LOW | 1 | 8 | 440239 | 297161.325 | 59432.265 | 118864.53 | 178296.795
178 | SA-0417 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | LOW | 2 | 6 | 341516 | 51227.4 | 10245.48 | 20490.96 | 30736.44
179 | SA-0322 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | LOW | 1 | 8 | 433276 | 292461.3 | 58492.26 | 116984.52 | 175476.78
180 | SA-0357 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | Repair Component | LOW | 1 | 8 | 430846 | 193880.7 | 38776.14 | 77552.28 | 116328.42
181 | SA-0311 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | LOW | 1 | 8 | 429389 | 289837.575 | 57967.515 | 115935.03 | 173902.545
182 | SA-0407 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | LOW | 2 | 6 | 331260 | 132504 | 26500.8 | 53001.6 | 79502.4
183 | SA-0429 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | LOW | 2 | 6 | 327936 | 147571.2 | 29514.24 | 59028.48 | 88542.72
184 | SA-0296 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 2 | 6 | 317851 | 143032.95 | 28606.59 | 57213.18 | 85819.77
185 | SA-0280 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | Replace Equipment | LOW | 1 | 8 | 414076 | 144926.6 | 28985.32 | 57970.64 | 86955.96
186 | SA-0295 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | LOW | 1 | 8 | 412453 | 185603.85 | 37120.77 | 74241.54 | 111362.31
187 | SA-0482 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 8 | 412023 | 133907.475 | 26781.495 | 53562.99 | 80344.485
188 | SA-0457 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | LOW | 2 | 8 | 245257 | 110365.65 | 22073.13 | 44146.26 | 66219.39
189 | SA-0062 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | Repair Component | LOW | 1 | 8 | 405809 | 182614.05 | 36522.81 | 73045.62 | 109568.43
190 | SA-0256 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | LOW | 2 | 6 | 306650 | 68996.25 | 13799.25 | 27598.5 | 41397.75
191 | SA-0309 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | LOW | 2 | 6 | 303851 | 45577.65 | 9115.53 | 18231.06 | 27346.59
192 | SA-0406 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 1 | 8 | 400816 | 180367.2 | 36073.44 | 72146.88 | 108220.32
193 | SA-0454 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | LOW | 2 | 6 | 302089 | 203910.075 | 40782.015 | 81564.03 | 122346.045
194 | SA-0244 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Mobilize Supply Vessel | LOW | 1 | 8 | 392444 | 117733.2 | 23546.64 | 47093.28 | 70639.92
195 | SA-0172 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | LOW | 2 | 6 | 289788 | 86936.4 | 17387.28 | 34774.56 | 52161.84
196 | SA-0075 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Mobilize Supply Vessel | LOW | 1 | 8 | 385622 | 115686.6 | 23137.32 | 46274.64 | 69411.96
197 | SA-0475 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 8 | 378432 | 340588.8 | 68117.76 | 136235.52 | 204353.28
198 | SA-0480 | Drilling | Hole Cleaning | Differential Sticking | Operator | Run Fishing Tools | LOW | 1 | 8 | 368858 | 147543.2 | 29508.64 | 59017.28 | 88525.92
199 | SA-0435 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Increase Mud Weight | LOW | 1 | 8 | 367972 | 119590.9 | 23918.18 | 47836.36 | 71754.54
200 | SA-0192 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | LOW | 2 | 6 | 269378 | 131321.775 | 26264.355 | 52528.71 | 78793.065
201 | SA-0434 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Condition Hole | LOW | 1 | 8 | 364022 | 218413.2 | 43682.64 | 87365.28 | 131047.92
202 | SA-0354 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Air Freight Materials | LOW | 1 | 6 | 424036 | 127210.8 | 25442.16 | 50884.32 | 76326.48
203 | SA-0329 | Drilling | Lost Circulation | Differential Sticking | Operator | Run Fishing Tools | LOW | 1 | 8 | 354647 | 141858.8 | 28371.76 | 56743.52 | 85115.28
204 | SA-0133 | Weather | Lightning | Lightning | Weather | Resume Operations | LOW | 2 | 6 | 256285 | 38442.75 | 7688.55 | 15377.1 | 23065.65
205 | SA-0181 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | Air Freight Materials | LOW | 1 | 6 | 415691 | 124707.3 | 24941.46 | 49882.92 | 74824.38
206 | SA-0259 | Logistics | Waiting on Materials | Port Congestion | Procurement | Expedite Shipment | LOW | 1 | 8 | 351618 | 210970.8 | 42194.16 | 84388.32 | 126582.48
207 | SA-0089 | Weather | Lightning | Storm | Marine Operations | Resume Operations | LOW | 1 | 8 | 351230 | 79026.75 | 15805.35 | 31610.7 | 47416.05
208 | SA-0495 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Condition Hole | LOW | 1 | 6 | 414858 | 165943.2 | 33188.64 | 66377.28 | 99565.92
209 | SA-0502 | Drilling | Stuck Pipe | Formation Instability | Operator | Increase Mud Weight | LOW | 1 | 8 | 346314 | 112552.05 | 22510.41 | 45020.82 | 67531.23
210 | SA-0114 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 6 | 409922 | 245953.2 | 49190.64 | 98381.28 | 147571.92
211 | SA-0462 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Increase Mud Weight | LOW | 1 | 8 | 345853 | 112402.225 | 22480.445 | 44960.89 | 67441.335
212 | SA-0315 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | LOW | 2 | 6 | 241752 | 145051.2 | 29010.24 | 58020.48 | 87030.72
213 | SA-0116 | Weather | Strong Wind | High Waves | Marine Operations | Wait on Weather | LOW | 1 | 6 | 398600 | 89685 | 17937 | 35874 | 53811
214 | SA-0384 | Drilling | Bit Failure | Differential Sticking | Operator | Condition Hole | LOW | 1 | 6 | 393652 | 157460.8 | 31492.16 | 62984.32 | 94476.48
215 | SA-0492 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | OEM Inspection | LOW | 1 | 6 | 390679 | 136737.65 | 27347.53 | 54695.06 | 82042.59
216 | SA-0470 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Mobilize Supply Vessel | LOW | 1 | 6 | 390341 | 117102.3 | 23420.46 | 46840.92 | 70261.38
217 | SA-0287 | Weather | High Waves | Strong Wind | Weather | Resume Operations | LOW | 1 | 6 | 388120 | 116436 | 23287.2 | 46574.4 | 69861.6
218 | SA-0223 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 8 | 323949 | 97184.7 | 19436.94 | 38873.88 | 58310.82
219 | SA-0488 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 1 | 6 | 387813 | 174515.85 | 34903.17 | 69806.34 | 104709.51
220 | SA-0190 | Weather | Lightning | Strong Wind | Weather | Wait on Weather | LOW | 1 | 6 | 386746 | 58011.9 | 11602.38 | 23204.76 | 34807.14
221 | SA-0339 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Repair Component | LOW | 1 | 8 | 322359 | 217592.325 | 43518.465 | 87036.93 | 130555.395
222 | SA-0158 | Weather | Strong Wind | Storm | Weather | Resume Operations | LOW | 1 | 8 | 318983 | 95694.9 | 19138.98 | 38277.96 | 57416.94
223 | SA-0319 | Weather | Strong Wind | Storm | Weather | Suspend Operations | LOW | 2 | 6 | 219046 | 65713.8 | 13142.76 | 26285.52 | 39428.28
224 | SA-0263 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | Expedite Shipment | LOW | 1 | 6 | 380337 | 114101.1 | 22820.22 | 45640.44 | 68460.66
225 | SA-0353 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | OEM Inspection | LOW | 1 | 8 | 316114 | 142251.3 | 28450.26 | 56900.52 | 85350.78
226 | SA-0144 | Logistics | Waiting on Boat | Port Congestion | Procurement | Mobilize Supply Vessel | LOW | 1 | 6 | 377721 | 113316.3 | 22663.26 | 45326.52 | 67989.78
227 | SA-0267 | Personnel | Medical Evacuation | Medical Emergency | HR | Crew Replacement | LOW | 1 | 6 | 376090 | 112827 | 22565.4 | 45130.8 | 67696.2
228 | SA-0151 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Increase Mud Weight | LOW | 1 | 6 | 373064 | 149225.6 | 29845.12 | 59690.24 | 89535.36
229 | SA-0272 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 8 | 305734 | 137580.3 | 27516.06 | 55032.12 | 82548.18
230 | SA-0118 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | LOW | 1 | 8 | 305647 | 275082.3 | 55016.46 | 110032.92 | 165049.38
231 | SA-0414 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Increase Mud Weight | LOW | 1 | 8 | 305177 | 99182.525 | 19836.505 | 39673.01 | 59509.515
232 | SA-0387 | Drilling | Well Control | Formation Instability | Directional Drilling | Run Fishing Tools | LOW | 1 | 6 | 368781 | 119853.825 | 23970.765 | 47941.53 | 71912.295
233 | SA-0408 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | OEM Inspection | LOW | 1 | 6 | 366820 | 165069 | 33013.8 | 66027.6 | 99041.4
234 | SA-0185 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Repair Component | LOW | 1 | 6 | 365352 | 328816.8 | 65763.36 | 131526.72 | 197290.08
235 | SA-0456 | Drilling | Stuck Pipe | Formation Instability | Operator | Condition Hole | LOW | 1 | 6 | 362949 | 117958.425 | 23591.685 | 47183.37 | 70775.055
236 | SA-0356 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 6 | 354358 | 106307.4 | 21261.48 | 42522.96 | 63784.44
237 | SA-0014 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Run Fishing Tools | LOW | 1 | 6 | 353029 | 172101.6375 | 34420.3275 | 68840.655 | 103260.9825
238 | SA-0449 | Weather | Poor Visibility | Lightning | Weather | Suspend Operations | LOW | 1 | 6 | 351890 | 105567 | 21113.4 | 42226.8 | 63340.2
239 | SA-0076 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 6 | 351864 | 158338.8 | 31667.76 | 63335.52 | 95003.28
240 | SA-0143 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | OEM Inspection | LOW | 1 | 6 | 348626 | 156881.7 | 31376.34 | 62752.68 | 94129.02
241 | SA-0333 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Expedite Shipment | LOW | 1 | 6 | 348024 | 104407.2 | 20881.44 | 41762.88 | 62644.32
242 | SA-0324 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | LOW | 1 | 8 | 283348 | 127506.6 | 25501.32 | 51002.64 | 76503.96
243 | SA-0020 | Drilling | Bit Failure | Bit Wear | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 344964 | 137985.6 | 27597.12 | 55194.24 | 82791.36
244 | SA-0154 | Weather | Heavy Rain | Strong Wind | Marine Operations | Suspend Operations | LOW | 1 | 6 | 343619 | 51542.85 | 10308.57 | 20617.14 | 30925.71
245 | SA-0236 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 343111 | 137244.4 | 27448.88 | 54897.76 | 82346.64
246 | SA-0362 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 6 | 340265 | 221172.25 | 44234.45 | 88468.9 | 132703.35
247 | SA-0121 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | LOW | 1 | 8 | 275218 | 123848.1 | 24769.62 | 49539.24 | 74308.86
248 | SA-0217 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Increase Mud Weight | LOW | 1 | 6 | 337687 | 135074.8 | 27014.96 | 54029.92 | 81044.88
249 | SA-0057 | Weather | Heavy Rain | Storm | Weather | Wait on Weather | LOW | 1 | 6 | 337173 | 75863.925 | 15172.785 | 30345.57 | 45518.355
250 | SA-0428 | Weather | Heavy Rain | High Waves | Marine Operations | Wait on Weather | LOW | 1 | 6 | 335006 | 75376.35 | 15075.27 | 30150.54 | 45225.81
251 | SA-0348 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | LOW | 2 | 4 | 230664 | 69199.2 | 13839.84 | 27679.68 | 41519.52
252 | SA-0165 | Drilling | Fishing Operation | Differential Sticking | Operator | Increase Mud Weight | LOW | 1 | 8 | 264193 | 105677.2 | 21135.44 | 42270.88 | 63406.32
253 | SA-0243 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Repair Component | LOW | 1 | 6 | 322678 | 145205.1 | 29041.02 | 58082.04 | 87123.06
254 | SA-0472 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | LOW | 1 | 8 | 256020 | 172813.5 | 34562.7 | 69125.4 | 103688.1
255 | SA-0483 | Drilling | Well Control | Bit Wear | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 319465 | 127786 | 25557.2 | 51114.4 | 76671.6
256 | SA-0389 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Condition Hole | LOW | 1 | 6 | 317496 | 126998.4 | 25399.68 | 50799.36 | 76199.04
257 | SA-0145 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | LOW | 2 | 4 | 219322 | 98694.9 | 19738.98 | 39477.96 | 59216.94
258 | SA-0068 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | LOW | 2 | 4 | 216538 | 32480.7 | 6496.14 | 12992.28 | 19488.42
259 | SA-0451 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Expedite Shipment | LOW | 1 | 6 | 314093 | 94227.9 | 18845.58 | 37691.16 | 56536.74
260 | SA-0249 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | LOW | 1 | 6 | 311670 | 140251.5 | 28050.3 | 56100.6 | 84150.9
261 | SA-0298 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 6 | 308615 | 138876.75 | 27775.35 | 55550.7 | 83326.05
262 | SA-0026 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 6 | 307708 | 100005.1 | 20001.02 | 40002.04 | 60003.06
263 | SA-0084 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | LOW | 2 | 4 | 208650 | 67811.25 | 13562.25 | 27124.5 | 40686.75
264 | SA-0278 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 6 | 299818 | 119927.2 | 23985.44 | 47970.88 | 71956.32
265 | SA-0497 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 6 | 296528 | 88958.4 | 17791.68 | 35583.36 | 53375.04
266 | SA-0100 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | LOW | 1 | 8 | 230791 | 112510.6125 | 22502.1225 | 45004.245 | 67506.3675
267 | SA-0450 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | LOW | 1 | 6 | 293383 | 264044.7 | 52808.94 | 105617.88 | 158426.82
268 | SA-0359 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | OEM Inspection | LOW | 1 | 6 | 292855 | 131784.75 | 26356.95 | 52713.9 | 79070.85
269 | SA-0241 | Drilling | Well Control | Formation Instability | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 6 | 287490 | 93434.25 | 18686.85 | 37373.7 | 56060.55
270 | SA-0094 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | LOW | 1 | 6 | 283515 | 127581.75 | 25516.35 | 51032.7 | 76549.05
271 | SA-0443 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 6 | 282458 | 254212.2 | 50842.44 | 101684.88 | 152527.32
272 | SA-0043 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | LOW | 2 | 4 | 183397 | 55019.1 | 11003.82 | 22007.64 | 33011.46
273 | SA-0284 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 276785 | 166071 | 33214.2 | 66428.4 | 99642.6
274 | SA-0199 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Air Freight Materials | LOW | 1 | 6 | 273679 | 82103.7 | 16420.74 | 32841.48 | 49262.22
275 | SA-0289 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | LOW | 2 | 4 | 171504 | 51451.2 | 10290.24 | 20580.48 | 30870.72
276 | SA-0328 | Weather | Poor Visibility | Heavy Rain | Weather | Wait on Weather | LOW | 1 | 6 | 267059 | 60088.275 | 12017.655 | 24035.31 | 36052.965
277 | SA-0281 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Run Fishing Tools | LOW | 1 | 6 | 267051 | 106820.4 | 21364.08 | 42728.16 | 64092.24
278 | SA-0399 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Run Fishing Tools | LOW | 1 | 6 | 265582 | 106232.8 | 21246.56 | 42493.12 | 63739.68
279 | SA-0494 | Weather | Heavy Rain | Strong Wind | Weather | Wait on Weather | LOW | 1 | 6 | 263523 | 79056.9 | 15811.38 | 31622.76 | 47434.14
280 | SA-0078 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | LOW | 1 | 6 | 260730 | 117328.5 | 23465.7 | 46931.4 | 70397.1
281 | SA-0175 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 257968 | 83839.6 | 16767.92 | 33535.84 | 50303.76
282 | SA-0253 | Weather | Poor Visibility | High Waves | Weather | Resume Operations | LOW | 1 | 6 | 256971 | 57818.475 | 11563.695 | 23127.39 | 34691.085
283 | SA-0227 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | LOW | 2 | 4 | 158875 | 47662.5 | 9532.5 | 19065 | 28597.5
284 | SA-0196 | Weather | Strong Wind | High Waves | Weather | Resume Operations | LOW | 1 | 6 | 255196 | 38279.4 | 7655.88 | 15311.76 | 22967.64
285 | SA-0415 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | OEM Inspection | LOW | 1 | 6 | 252040 | 170127 | 34025.4 | 68050.8 | 102076.2
286 | SA-0195 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Preventive Maintenance | LOW | 1 | 6 | 239454 | 161631.45 | 32326.29 | 64652.58 | 96978.87
287 | SA-0500 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Replace Equipment | LOW | 1 | 6 | 239340 | 107703 | 21540.6 | 43081.2 | 64621.8
288 | SA-0258 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | Expedite Shipment | LOW | 1 | 6 | 238864 | 107488.8 | 21497.76 | 42995.52 | 64493.28
289 | SA-0395 | Weather | Strong Wind | Lightning | Marine Operations | Resume Operations | LOW | 1 | 6 | 238339 | 35750.85 | 7150.17 | 14300.34 | 21450.51
290 | SA-0110 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | OEM Inspection | LOW | 1 | 6 | 233378 | 157530.15 | 31506.03 | 63012.06 | 94518.09
291 | SA-0323 | Personnel | Crew Change | Medical Emergency | HR | Medical Clearance | LOW | 1 | 6 | 232452 | 104603.4 | 20920.68 | 41841.36 | 62762.04
292 | SA-0140 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | LOW | 2 | 4 | 129706 | 77823.6 | 15564.72 | 31129.44 | 46694.16
293 | SA-0305 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | LOW | 1 | 6 | 227412 | 102335.4 | 20467.08 | 40934.16 | 61401.24
294 | SA-0394 | Drilling | Hole Cleaning | Differential Sticking | Operator | Adjust Drilling Parameters | LOW | 1 | 6 | 226365 | 90546 | 18109.2 | 36218.4 | 54327.6
295 | SA-0458 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | Run Fishing Tools | LOW | 1 | 6 | 226088 | 90435.2 | 18087.04 | 36174.08 | 54261.12
296 | SA-0416 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Air Freight Materials | LOW | 1 | 6 | 224082 | 67224.6 | 13444.92 | 26889.84 | 40334.76
297 | SA-0035 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Safety Briefing | LOW | 1 | 6 | 223591 | 67077.3 | 13415.46 | 26830.92 | 40246.38
298 | SA-0208 | Weather | Heavy Rain | Storm | Marine Operations | Wait on Weather | LOW | 1 | 4 | 283956 | 42593.4 | 8518.68 | 17037.36 | 25556.04
299 | SA-0025 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Expedite Shipment | LOW | 1 | 6 | 216821 | 65046.3 | 13009.26 | 26018.52 | 39027.78
300 | SA-0038 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | Repair Component | LOW | 1 | 4 | 280600 | 126270 | 25254 | 50508 | 75762
301 | SA-0019 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | Expedite Shipment | LOW | 1 | 4 | 280384 | 84115.2 | 16823.04 | 33646.08 | 50469.12
302 | SA-0202 | Weather | Poor Visibility | Storm | Marine Operations | Wait on Weather | LOW | 1 | 6 | 215094 | 32264.1 | 6452.82 | 12905.64 | 19358.46
303 | SA-0134 | Personnel | Training | Crew Rotation | Medical Team | Safety Briefing | LOW | 1 | 6 | 213210 | 95944.5 | 19188.9 | 38377.8 | 57566.7
304 | SA-0411 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | LOW | 1 | 6 | 210610 | 142161.75 | 28432.35 | 56864.7 | 85297.05
305 | SA-0194 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Resume Operations | LOW | 1 | 4 | 274281 | 41142.15 | 8228.43 | 16456.86 | 24685.29
306 | SA-0379 | Weather | High Waves | Heavy Rain | Weather | Suspend Operations | LOW | 1 | 6 | 208739 | 31310.85 | 6262.17 | 12524.34 | 18786.51
307 | SA-0262 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Repair Component | LOW | 1 | 4 | 271009 | 94853.15 | 18970.63 | 37941.26 | 56911.89
308 | SA-0474 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | LOW | 1 | 6 | 206494 | 92922.3 | 18584.46 | 37168.92 | 55753.38
309 | SA-0247 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | LOW | 1 | 6 | 205497 | 138710.475 | 27742.095 | 55484.19 | 83226.285
310 | SA-0340 | Weather | High Waves | Heavy Rain | Weather | Resume Operations | LOW | 1 | 4 | 268307 | 60369.075 | 12073.815 | 24147.63 | 36221.445
311 | SA-0468 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 267913 | 120560.85 | 24112.17 | 48224.34 | 72336.51
312 | SA-0016 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Increase Mud Weight | LOW | 1 | 4 | 267388 | 106955.2 | 21391.04 | 42782.08 | 64173.12
313 | SA-0269 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 4 | 267293 | 106917.2 | 21383.44 | 42766.88 | 64150.32
314 | SA-0294 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | OEM Inspection | LOW | 1 | 4 | 266940 | 120123 | 24024.6 | 48049.2 | 72073.8
315 | SA-0351 | Weather | High Waves | Lightning | Weather | Suspend Operations | LOW | 1 | 4 | 266498 | 39974.7 | 7994.94 | 15989.88 | 23984.82
316 | SA-0376 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Air Freight Materials | LOW | 1 | 4 | 266485 | 79945.5 | 15989.1 | 31978.2 | 47967.3
317 | SA-0159 | Weather | Heavy Rain | High Waves | Marine Operations | Resume Operations | LOW | 1 | 4 | 265590 | 39838.5 | 7967.7 | 15935.4 | 23903.1
318 | SA-0189 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | Repair Component | LOW | 1 | 6 | 201020 | 135688.5 | 27137.7 | 54275.4 | 81413.1
319 | SA-0197 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Increase Mud Weight | LOW | 1 | 6 | 200527 | 65171.275 | 13034.255 | 26068.51 | 39102.765
320 | SA-0491 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | Mobilize Supply Vessel | LOW | 1 | 4 | 263601 | 79080.3 | 15816.06 | 31632.12 | 47448.18
321 | SA-0326 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Run Fishing Tools | LOW | 1 | 4 | 262057 | 104822.8 | 20964.56 | 41929.12 | 62893.68
322 | SA-0209 | Weather | Poor Visibility | Storm | Weather | Wait on Weather | LOW | 1 | 6 | 196861 | 29529.15 | 5905.83 | 11811.66 | 17717.49
323 | SA-0063 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 4 | 260558 | 104223.2 | 20844.64 | 41689.28 | 62533.92
324 | SA-0331 | Drilling | Well Control | Formation Instability | Operator | Increase Mud Weight | LOW | 1 | 6 | 189266 | 61511.45 | 12302.29 | 24604.58 | 36906.87
325 | SA-0021 | Drilling | Bit Failure | Bit Wear | Operator | Run Fishing Tools | LOW | 1 | 6 | 186995 | 149596 | 29919.2 | 59838.4 | 89757.6
326 | SA-0245 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | LOW | 1 | 4 | 250433 | 169042.275 | 33808.455 | 67616.91 | 101425.365
327 | SA-0141 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Repair Component | LOW | 1 | 6 | 186232 | 83804.4 | 16760.88 | 33521.76 | 50282.64
328 | SA-0486 | Weather | High Waves | High Waves | Weather | Wait on Weather | LOW | 1 | 6 | 185319 | 27797.85 | 5559.57 | 11119.14 | 16678.71
329 | SA-0177 | Drilling | Stuck Pipe | Bit Wear | Operator | Condition Hole | LOW | 1 | 4 | 248562 | 198849.6 | 39769.92 | 79539.84 | 119309.76
330 | SA-0027 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | Repair Component | LOW | 1 | 6 | 183652 | 64278.2 | 12855.64 | 25711.28 | 38566.92
331 | SA-0073 | Logistics | Delayed Helicopter | Material Shortage | Procurement | Mobilize Supply Vessel | LOW | 1 | 4 | 245667 | 147400.2 | 29480.04 | 58960.08 | 88440.12
332 | SA-0412 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Increase Mud Weight | LOW | 1 | 4 | 243632 | 146179.2 | 29235.84 | 58471.68 | 87707.52
333 | SA-0363 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | Expedite Shipment | LOW | 1 | 4 | 242362 | 145417.2 | 29083.44 | 58166.88 | 87250.32
334 | SA-0157 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Air Freight Materials | LOW | 1 | 4 | 239783 | 143869.8 | 28773.96 | 57547.92 | 86321.88
335 | SA-0173 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 235789 | 106105.05 | 21221.01 | 42442.02 | 63663.03
336 | SA-0081 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 4 | 234076 | 93630.4 | 18726.08 | 37452.16 | 56178.24
337 | SA-0012 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | Expedite Shipment | LOW | 1 | 4 | 233679 | 70103.7 | 14020.74 | 28041.48 | 42062.22
338 | SA-0386 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Increase Mud Weight | LOW | 1 | 4 | 230562 | 112398.975 | 22479.795 | 44959.59 | 67439.385
339 | SA-0388 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | LOW | 1 | 4 | 229210 | 103144.5 | 20628.9 | 41257.8 | 61886.7
340 | SA-0193 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Resume Operations | LOW | 1 | 4 | 228301 | 34245.15 | 6849.03 | 13698.06 | 20547.09
341 | SA-0187 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Mobilize Supply Vessel | LOW | 1 | 4 | 227308 | 68192.4 | 13638.48 | 27276.96 | 40915.44
342 | SA-0282 | Drilling | Well Control | Formation Instability | Mud Engineering | Increase Mud Weight | LOW | 1 | 4 | 226267 | 73536.775 | 14707.355 | 29414.71 | 44122.065
343 | SA-0327 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Increase Mud Weight | LOW | 1 | 4 | 225101 | 73157.825 | 14631.565 | 29263.13 | 43894.695
344 | SA-0123 | Drilling | Lost Circulation | Bit Wear | Operator | Condition Hole | LOW | 1 | 4 | 223254 | 89301.6 | 17860.32 | 35720.64 | 53580.96
345 | SA-0238 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 223184 | 100432.8 | 20086.56 | 40173.12 | 60259.68
346 | SA-0112 | Weather | Heavy Rain | Lightning | Weather | Suspend Operations | LOW | 1 | 4 | 223095 | 33464.25 | 6692.85 | 13385.7 | 20078.55
347 | SA-0413 | Weather | High Waves | Storm | Marine Operations | Resume Operations | LOW | 1 | 4 | 222759 | 50120.775 | 10024.155 | 20048.31 | 30072.465
348 | SA-0213 | Weather | Heavy Rain | Heavy Rain | Weather | Suspend Operations | LOW | 1 | 4 | 220055 | 33008.25 | 6601.65 | 13203.3 | 19804.95
349 | SA-0205 | Weather | Strong Wind | High Waves | Marine Operations | Resume Operations | LOW | 1 | 4 | 211880 | 31782 | 6356.4 | 12712.8 | 19069.2
350 | SA-0279 | Drilling | Stuck Pipe | Differential Sticking | Operator | Condition Hole | LOW | 1 | 4 | 209014 | 83605.6 | 16721.12 | 33442.24 | 50163.36
351 | SA-0283 | Weather | Heavy Rain | Storm | Weather | Suspend Operations | LOW | 1 | 4 | 208670 | 31300.5 | 6260.1 | 12520.2 | 18780.3
352 | SA-0344 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | Air Freight Materials | LOW | 1 | 4 | 205597 | 61679.1 | 12335.82 | 24671.64 | 37007.46
353 | SA-0489 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | Mobilize Supply Vessel | LOW | 1 | 4 | 201829 | 90823.05 | 18164.61 | 36329.22 | 54493.83
354 | SA-0369 | Weather | Poor Visibility | High Waves | Marine Operations | Suspend Operations | LOW | 1 | 4 | 201521 | 30228.15 | 6045.63 | 12091.26 | 18136.89
355 | SA-0049 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Wait on Weather | LOW | 1 | 4 | 196795 | 29519.25 | 5903.85 | 11807.7 | 17711.55
356 | SA-0342 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Run Fishing Tools | LOW | 1 | 4 | 191843 | 153474.4 | 30694.88 | 61389.76 | 92084.64
357 | SA-0499 | Weather | High Waves | Storm | Weather | Resume Operations | LOW | 1 | 4 | 191816 | 28772.4 | 5754.48 | 11508.96 | 17263.44
358 | SA-0009 | Weather | Lightning | Storm | Weather | Suspend Operations | LOW | 1 | 4 | 190528 | 42868.8 | 8573.76 | 17147.52 | 25721.28
359 | SA-0391 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Run Fishing Tools | LOW | 1 | 4 | 188959 | 61411.675 | 12282.335 | 24564.67 | 36847.005
360 | SA-0097 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Run Fishing Tools | LOW | 1 | 4 | 188472 | 75388.8 | 15077.76 | 30155.52 | 45233.28
361 | SA-0226 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Condition Hole | LOW | 1 | 4 | 187175 | 60831.875 | 12166.375 | 24332.75 | 36499.125
362 | SA-0372 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Repair Component | LOW | 1 | 4 | 187135 | 84210.75 | 16842.15 | 33684.3 | 50526.45
363 | SA-0079 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Air Freight Materials | LOW | 1 | 4 | 184211 | 55263.3 | 11052.66 | 22105.32 | 33157.98
364 | SA-0257 | Weather | Strong Wind | Heavy Rain | Marine Operations | Suspend Operations | LOW | 1 | 4 | 183247 | 27487.05 | 5497.41 | 10994.82 | 16492.23
365 | SA-0437 | Drilling | Well Control | Unexpected Pressure | Operator | Increase Mud Weight | LOW | 1 | 4 | 179258 | 58258.85 | 11651.77 | 23303.54 | 34955.31
366 | SA-0346 | Drilling | Stuck Pipe | Formation Instability | Operator | Adjust Drilling Parameters | LOW | 1 | 4 | 177665 | 57741.125 | 11548.225 | 23096.45 | 34644.675
367 | SA-0060 | Logistics | Waiting on Materials | Material Shortage | Procurement | Mobilize Supply Vessel | LOW | 1 | 4 | 176722 | 53016.6 | 10603.32 | 21206.64 | 31809.96
368 | SA-0355 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Medical Clearance | LOW | 1 | 4 | 175762 | 79092.9 | 15818.58 | 31637.16 | 47455.74
369 | SA-0228 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | LOW | 1 | 4 | 175170 | 78826.5 | 15765.3 | 31530.6 | 47295.9
370 | SA-0128 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Repair Component | LOW | 1 | 4 | 173329 | 77998.05 | 15599.61 | 31199.22 | 46798.83
371 | SA-0427 | Weather | High Waves | Lightning | Weather | Wait on Weather | LOW | 1 | 4 | 172335 | 25850.25 | 5170.05 | 10340.1 | 15510.15
372 | SA-0476 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 4 | 171574 | 55761.55 | 11152.31 | 22304.62 | 33456.93
373 | SA-0473 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | LOW | 1 | 4 | 169940 | 152946 | 30589.2 | 61178.4 | 91767.6
374 | SA-0286 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | OEM Inspection | LOW | 1 | 4 | 168452 | 113705.1 | 22741.02 | 45482.04 | 68223.06
375 | SA-0054 | Weather | Lightning | High Waves | Marine Operations | Resume Operations | LOW | 1 | 4 | 168104 | 25215.6 | 5043.12 | 10086.24 | 15129.36
376 | SA-0211 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Condition Hole | LOW | 1 | 4 | 167982 | 54594.15 | 10918.83 | 21837.66 | 32756.49
377 | SA-0102 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | Preventive Maintenance | LOW | 1 | 4 | 167299 | 150569.1 | 30113.82 | 60227.64 | 90341.46
378 | SA-0303 | Weather | Lightning | High Waves | Marine Operations | Wait on Weather | LOW | 1 | 4 | 162450 | 36551.25 | 7310.25 | 14620.5 | 21930.75
379 | SA-0477 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Condition Hole | LOW | 1 | 4 | 159637 | 77823.0375 | 15564.6075 | 31129.215 | 46693.8225
380 | SA-0174 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 159432 | 71744.4 | 14348.88 | 28697.76 | 43046.64
381 | SA-0312 | Personnel | Crew Change | Training Requirement | Rig Management | Crew Replacement | LOW | 1 | 4 | 156113 | 46833.9 | 9366.78 | 18733.56 | 28100.34
382 | SA-0373 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 4 | 155786 | 50630.45 | 10126.09 | 20252.18 | 30378.27
383 | SA-0390 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | OEM Inspection | LOW | 1 | 4 | 155480 | 69966 | 13993.2 | 27986.4 | 41979.6
384 | SA-0270 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | OEM Inspection | LOW | 1 | 4 | 153062 | 137755.8 | 27551.16 | 55102.32 | 82653.48
385 | SA-0321 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | LOW | 1 | 4 | 151036 | 67966.2 | 13593.24 | 27186.48 | 40779.72
386 | SA-0101 | Weather | Poor Visibility | High Waves | Marine Operations | Resume Operations | LOW | 1 | 4 | 150303 | 22545.45 | 4509.09 | 9018.18 | 13527.27
387 | SA-0444 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Mobilize Supply Vessel | LOW | 1 | 4 | 149184 | 89510.4 | 17902.08 | 35804.16 | 53706.24
388 | SA-0113 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | Preventive Maintenance | LOW | 1 | 4 | 148071 | 66631.95 | 13326.39 | 26652.78 | 39979.17
389 | SA-0276 | Drilling | Well Control | Differential Sticking | Operator | Condition Hole | LOW | 1 | 4 | 146747 | 58698.8 | 11739.76 | 23479.52 | 35219.28
390 | SA-0040 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | Air Freight Materials | LOW | 1 | 4 | 146520 | 43956 | 8791.2 | 17582.4 | 26373.6
391 | SA-0397 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 144589 | 75909.225 | 15181.845 | 30363.69 | 45545.535
392 | SA-0067 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Condition Hole | LOW | 1 | 4 | 144530 | 57812 | 11562.4 | 23124.8 | 34687.2
393 | SA-0403 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | LOW | 1 | 4 | 144441 | 129996.9 | 25999.38 | 51998.76 | 77998.14
394 | SA-0463 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Air Freight Materials | LOW | 1 | 4 | 143153 | 64418.85 | 12883.77 | 25767.54 | 38651.31
395 | SA-0271 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | Medical Clearance | LOW | 1 | 4 | 142506 | 42751.8 | 8550.36 | 17100.72 | 25651.08
396 | SA-0170 | Logistics | Waiting on Cement | Port Congestion | Procurement | Expedite Shipment | LOW | 1 | 4 | 141854 | 42556.2 | 8511.24 | 17022.48 | 25533.72
397 | SA-0445 | Weather | Lightning | Heavy Rain | Marine Operations | Resume Operations | LOW | 1 | 4 | 137929 | 20689.35 | 4137.87 | 8275.74 | 12413.61
398 | SA-0410 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | LOW | 1 | 4 | 137523 | 123770.7 | 24754.14 | 49508.28 | 74262.42
399 | SA-0265 | Drilling | Well Control | Bit Wear | Mud Engineering | Run Fishing Tools | LOW | 1 | 4 | 136897 | 82138.2 | 16427.64 | 32855.28 | 49282.92
400 | SA-0398 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Mobilize Supply Vessel | LOW | 1 | 4 | 135576 | 81345.6 | 16269.12 | 32538.24 | 48807.36
401 | SA-0436 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | LOW | 1 | 4 | 135471 | 60961.95 | 12192.39 | 24384.78 | 36577.17
402 | SA-0370 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | LOW | 1 | 4 | 131948 | 118753.2 | 23750.64 | 47501.28 | 71251.92
403 | SA-0332 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 4 | 128909 | 83790.85 | 16758.17 | 33516.34 | 50274.51
404 | SA-0377 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | OEM Inspection | LOW | 1 | 4 | 124894 | 56202.3 | 11240.46 | 22480.92 | 33721.38
405 | SA-0107 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Increase Mud Weight | LOW | 1 | 4 | 122835 | 79842.75 | 15968.55 | 31937.1 | 47905.65
406 | SA-0274 | Weather | Poor Visibility | High Waves | Marine Operations | Wait on Weather | LOW | 1 | 4 | 121607 | 18241.05 | 3648.21 | 7296.42 | 10944.63
407 | SA-0343 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | LOW | 1 | 4 | 120706 | 54317.7 | 10863.54 | 21727.08 | 32590.62
408 | SA-0345 | Weather | Poor Visibility | Strong Wind | Weather | Suspend Operations | LOW | 1 | 4 | 117715 | 17657.25 | 3531.45 | 7062.9 | 10594.35
409 | SA-0452 | Drilling | Well Control | Unexpected Pressure | Operator | Condition Hole | LOW | 1 | 4 | 115667 | 37591.775 | 7518.355 | 15036.71 | 22555.065
410 | SA-0308 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | LOW | 1 | 4 | 115317 | 51892.65 | 10378.53 | 20757.06 | 31135.59
411 | SA-0168 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Medical Clearance | LOW | 1 | 2 | 139078 | 41723.4 | 8344.68 | 16689.36 | 25034.04
412 | SA-0207 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Increase Mud Weight | LOW | 1 | 2 | 136963 | 66769.4625 | 13353.8925 | 26707.785 | 40061.6775
413 | SA-0037 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | OEM Inspection | LOW | 1 | 2 | 135824 | 61120.8 | 12224.16 | 24448.32 | 36672.48
414 | SA-0008 | Drilling | Lost Circulation | Differential Sticking | Operator | Increase Mud Weight | LOW | 1 | 2 | 135366 | 54146.4 | 10829.28 | 21658.56 | 32487.84
415 | SA-0498 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | LOW | 1 | 2 | 132117 | 59452.65 | 11890.53 | 23781.06 | 35671.59
416 | SA-0239 | Weather | Lightning | Heavy Rain | Weather | Resume Operations | LOW | 1 | 2 | 131903 | 19785.45 | 3957.09 | 7914.18 | 11871.27
417 | SA-0191 | Weather | Heavy Rain | Lightning | Marine Operations | Wait on Weather | LOW | 1 | 2 | 131381 | 19707.15 | 3941.43 | 7882.86 | 11824.29
418 | SA-0072 | Weather | Poor Visibility | Lightning | Marine Operations | Suspend Operations | LOW | 1 | 2 | 130889 | 39266.7 | 7853.34 | 15706.68 | 23560.02
419 | SA-0392 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Preventive Maintenance | LOW | 1 | 2 | 129733 | 58379.85 | 11675.97 | 23351.94 | 35027.91
420 | SA-0422 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Mobilize Supply Vessel | LOW | 1 | 2 | 129244 | 38773.2 | 7754.64 | 15509.28 | 23263.92
421 | SA-0124 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Expedite Shipment | LOW | 1 | 2 | 128233 | 38469.9 | 7693.98 | 15387.96 | 23081.94
422 | SA-0459 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | Expedite Shipment | LOW | 1 | 2 | 128171 | 38451.3 | 7690.26 | 15380.52 | 23070.78
423 | SA-0053 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 128096 | 86464.8 | 17292.96 | 34585.92 | 51878.88
424 | SA-0268 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | LOW | 1 | 2 | 127813 | 57515.85 | 11503.17 | 23006.34 | 34509.51
425 | SA-0478 | Drilling | Bit Failure | Bit Wear | Operator | Increase Mud Weight | LOW | 1 | 2 | 125483 | 75289.8 | 15057.96 | 30115.92 | 45173.88
426 | SA-0493 | Drilling | Well Control | Bit Wear | Operator | Condition Hole | LOW | 1 | 2 | 125472 | 50188.8 | 10037.76 | 20075.52 | 30113.28
427 | SA-0460 | Drilling | Bit Failure | Formation Instability | Operator | Increase Mud Weight | LOW | 1 | 2 | 125034 | 60954.075 | 12190.815 | 24381.63 | 36572.445
428 | SA-0090 | Personnel | Training | Training Requirement | Medical Team | Medical Clearance | LOW | 1 | 2 | 124993 | 37497.9 | 7499.58 | 14999.16 | 22498.74
429 | SA-0277 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | LOW | 1 | 2 | 124400 | 83970 | 16794 | 33588 | 50382
430 | SA-0307 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 2 | 123601 | 60255.4875 | 12051.0975 | 24102.195 | 36153.2925
431 | SA-0318 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 121900 | 54855 | 10971 | 21942 | 32913
432 | SA-0087 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Preventive Maintenance | LOW | 1 | 2 | 121891 | 82276.425 | 16455.285 | 32910.57 | 49365.855
433 | SA-0232 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 121266 | 54569.7 | 10913.94 | 21827.88 | 32741.82
434 | SA-0365 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | Preventive Maintenance | LOW | 1 | 2 | 120946 | 108851.4 | 21770.28 | 43540.56 | 65310.84
435 | SA-0233 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | LOW | 1 | 2 | 119766 | 53894.7 | 10778.94 | 21557.88 | 32336.82
436 | SA-0371 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | Replace Equipment | LOW | 1 | 2 | 119555 | 53799.75 | 10759.95 | 21519.9 | 32279.85
437 | SA-0250 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | OEM Inspection | LOW | 1 | 2 | 117131 | 40995.85 | 8199.17 | 16398.34 | 24597.51
438 | SA-0023 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Replace Equipment | LOW | 1 | 2 | 115946 | 52175.7 | 10435.14 | 20870.28 | 31305.42
439 | SA-0163 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 2 | 114203 | 37115.975 | 7423.195 | 14846.39 | 22269.585
440 | SA-0479 | Weather | Strong Wind | Storm | Weather | Wait on Weather | LOW | 1 | 2 | 113946 | 17091.9 | 3418.38 | 6836.76 | 10255.14
441 | SA-0204 | Weather | Heavy Rain | Strong Wind | Weather | Resume Operations | LOW | 1 | 2 | 112208 | 25246.8 | 5049.36 | 10098.72 | 15148.08
442 | SA-0002 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Repair Component | LOW | 1 | 2 | 111750 | 100575 | 20115 | 40230 | 60345
443 | SA-0360 | Weather | Heavy Rain | Storm | Marine Operations | Resume Operations | LOW | 1 | 2 | 111129 | 16669.35 | 3333.87 | 6667.74 | 10001.61
444 | SA-0230 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Safety Briefing | LOW | 1 | 2 | 111032 | 33309.6 | 6661.92 | 13323.84 | 19985.76
445 | SA-0430 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Repair Component | LOW | 1 | 2 | 110322 | 38612.7 | 7722.54 | 15445.08 | 23167.62
446 | SA-0439 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Condition Hole | LOW | 1 | 2 | 110061 | 44024.4 | 8804.88 | 17609.76 | 26414.64
447 | SA-0380 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Run Fishing Tools | LOW | 1 | 2 | 109853 | 35702.225 | 7140.445 | 14280.89 | 21421.335
448 | SA-0022 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Increase Mud Weight | LOW | 1 | 2 | 109837 | 43934.8 | 8786.96 | 17573.92 | 26360.88
449 | SA-0440 | Weather | Heavy Rain | High Waves | Weather | Resume Operations | LOW | 1 | 2 | 109410 | 16411.5 | 3282.3 | 6564.6 | 9846.9
450 | SA-0142 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | Expedite Shipment | LOW | 1 | 2 | 108387 | 32516.1 | 6503.22 | 13006.44 | 19509.66
451 | SA-0466 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Expedite Shipment | LOW | 1 | 2 | 107844 | 32353.2 | 6470.64 | 12941.28 | 19411.92
452 | SA-0341 | Drilling | Stuck Pipe | Differential Sticking | Operator | Increase Mud Weight | LOW | 1 | 2 | 107351 | 42940.4 | 8588.08 | 17176.16 | 25764.24
453 | SA-0219 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | LOW | 1 | 2 | 105954 | 42381.6 | 8476.32 | 16952.64 | 25428.96
454 | SA-0396 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Air Freight Materials | LOW | 1 | 2 | 105491 | 31647.3 | 6329.46 | 12658.92 | 18988.38
455 | SA-0098 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Safety Briefing | LOW | 1 | 2 | 104829 | 47173.05 | 9434.61 | 18869.22 | 28303.83
456 | SA-0252 | Weather | High Waves | Strong Wind | Weather | Suspend Operations | LOW | 1 | 2 | 102905 | 15435.75 | 3087.15 | 6174.3 | 9261.45
457 | SA-0003 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | Expedite Shipment | LOW | 1 | 2 | 101688 | 45759.6 | 9151.92 | 18303.84 | 27455.76
458 | SA-0484 | Drilling | Lost Circulation | Unexpected Pressure | Operator | Run Fishing Tools | LOW | 1 | 2 | 100507 | 48997.1625 | 9799.4325 | 19598.865 | 29398.2975
459 | SA-0148 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Air Freight Materials | LOW | 1 | 2 | 98690 | 29607 | 5921.4 | 11842.8 | 17764.2
460 | SA-0383 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Condition Hole | LOW | 1 | 2 | 98559 | 39423.6 | 7884.72 | 15769.44 | 23654.16
461 | SA-0099 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | Expedite Shipment | LOW | 1 | 2 | 97761 | 43992.45 | 8798.49 | 17596.98 | 26395.47
462 | SA-0375 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Repair Component | LOW | 1 | 2 | 96881 | 43596.45 | 8719.29 | 17438.58 | 26157.87
463 | SA-0465 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 96310 | 86679 | 17335.8 | 34671.6 | 52007.4
464 | SA-0201 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Run Fishing Tools | LOW | 1 | 2 | 95282 | 46449.975 | 9289.995 | 18579.99 | 27869.985
465 | SA-0069 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | LOW | 1 | 2 | 94282 | 84853.8 | 16970.76 | 33941.52 | 50912.28
466 | SA-0188 | Personnel | Safety Stand Down | Training Requirement | HR | Crew Replacement | LOW | 1 | 2 | 93981 | 28194.3 | 5638.86 | 11277.72 | 16916.58
467 | SA-0234 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | Preventive Maintenance | LOW | 1 | 2 | 92909 | 41809.05 | 8361.81 | 16723.62 | 25085.43
468 | SA-0347 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 92820 | 62653.5 | 12530.7 | 25061.4 | 37592.1
469 | SA-0320 | Drilling | Hole Cleaning | Differential Sticking | Operator | Increase Mud Weight | LOW | 1 | 2 | 91943 | 73554.4 | 14710.88 | 29421.76 | 44132.64
470 | SA-0461 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Expedite Shipment | LOW | 1 | 2 | 91341 | 27402.3 | 5480.46 | 10960.92 | 16441.38
471 | SA-0418 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Safety Briefing | LOW | 1 | 2 | 90635 | 27190.5 | 5438.1 | 10876.2 | 16314.3
472 | SA-0288 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | Repair Component | LOW | 1 | 2 | 89522 | 31332.7 | 6266.54 | 12533.08 | 18799.62
473 | SA-0200 | Drilling | Well Control | Bit Wear | Directional Drilling | Run Fishing Tools | LOW | 1 | 2 | 89388 | 35755.2 | 7151.04 | 14302.08 | 21453.12
474 | SA-0167 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | LOW | 1 | 2 | 88341 | 39753.45 | 7950.69 | 15901.38 | 23852.07
475 | SA-0446 | Drilling | Fishing Operation | Bit Wear | Operator | Adjust Drilling Parameters | LOW | 1 | 2 | 88055 | 52833 | 10566.6 | 21133.2 | 31699.8
476 | SA-0105 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Expedite Shipment | LOW | 1 | 2 | 86702 | 26010.6 | 5202.12 | 10404.24 | 15606.36
477 | SA-0358 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Condition Hole | LOW | 1 | 2 | 85885 | 27912.625 | 5582.525 | 11165.05 | 16747.575
478 | SA-0285 | Weather | Strong Wind | Lightning | Weather | Suspend Operations | LOW | 1 | 2 | 84759 | 12713.85 | 2542.77 | 5085.54 | 7628.31
479 | SA-0198 | Drilling | Hole Cleaning | Formation Instability | Operator | Increase Mud Weight | LOW | 1 | 2 | 84135 | 33654 | 6730.8 | 13461.6 | 20192.4
480 | SA-0409 | Logistics | Waiting on Materials | Port Congestion | Procurement | Air Freight Materials | LOW | 1 | 2 | 82862 | 24858.6 | 4971.72 | 9943.44 | 14915.16
481 | SA-0405 | Weather | Poor Visibility | Lightning | Marine Operations | Wait on Weather | LOW | 1 | 2 | 82702 | 12405.3 | 2481.06 | 4962.12 | 7443.18
482 | SA-0155 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | Expedite Shipment | LOW | 1 | 2 | 82480 | 37116 | 7423.2 | 14846.4 | 22269.6
483 | SA-0300 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Expedite Shipment | LOW | 1 | 2 | 82289 | 49373.4 | 9874.68 | 19749.36 | 29624.04
484 | SA-0335 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | OEM Inspection | LOW | 1 | 2 | 82273 | 74045.7 | 14809.14 | 29618.28 | 44427.42
485 | SA-0485 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | Medical Clearance | LOW | 1 | 2 | 81540 | 24462 | 4892.4 | 9784.8 | 14677.2
486 | SA-0093 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | LOW | 1 | 2 | 79500 | 35775 | 7155 | 14310 | 21465
487 | SA-0242 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Repair Component | LOW | 1 | 2 | 79139 | 27698.65 | 5539.73 | 11079.46 | 16619.19
488 | SA-0448 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | OEM Inspection | LOW | 1 | 2 | 75654 | 34044.3 | 6808.86 | 13617.72 | 20426.58
489 | SA-0235 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | OEM Inspection | LOW | 1 | 2 | 73971 | 33286.95 | 6657.39 | 13314.78 | 19972.17
490 | SA-0261 | Weather | Strong Wind | Heavy Rain | Marine Operations | Wait on Weather | LOW | 1 | 2 | 73818 | 22145.4 | 4429.08 | 8858.16 | 13287.24
491 | SA-0297 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Repair Component | LOW | 1 | 2 | 72228 | 32502.6 | 6500.52 | 13001.04 | 19501.56
492 | SA-0438 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Air Freight Materials | LOW | 1 | 2 | 72206 | 21661.8 | 4332.36 | 8664.72 | 12997.08
493 | SA-0381 | Drilling | Well Control | Differential Sticking | Mud Engineering | Run Fishing Tools | LOW | 1 | 2 | 70168 | 28067.2 | 5613.44 | 11226.88 | 16840.32
494 | SA-0127 | Weather | Lightning | Heavy Rain | Weather | Wait on Weather | LOW | 1 | 2 | 70126 | 15778.35 | 3155.67 | 6311.34 | 9467.01
495 | SA-0119 | Drilling | Bit Failure | Unexpected Pressure | Operator | Run Fishing Tools | LOW | 1 | 2 | 68914 | 22397.05 | 4479.41 | 8958.82 | 13438.23
496 | SA-0447 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Adjust Drilling Parameters | LOW | 1 | 2 | 68000 | 27200 | 5440 | 10880 | 16320
497 | SA-0136 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Replace Equipment | LOW | 1 | 2 | 67963 | 30583.35 | 6116.67 | 12233.34 | 18350.01
498 | SA-0162 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | LOW | 1 | 2 | 66827 | 26730.8 | 5346.16 | 10692.32 | 16038.48
499 | SA-0183 | Drilling | Fishing Operation | Differential Sticking | Operator | Condition Hole | LOW | 1 | 2 | 65923 | 26369.2 | 5273.84 | 10547.68 | 15821.52
500 | SA-0152 | Personnel | Safety Stand Down | Medical Emergency | HR | Safety Briefing | LOW | 1 | 2 | 65522 | 19656.6 | 3931.32 | 7862.64 | 11793.96
501 | SA-0220 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Condition Hole | LOW | 1 | 2 | 64142 | 31269.225 | 6253.845 | 12507.69 | 18761.535
502 | SA-0120 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Condition Hole | LOW | 1 | 2 | 62471 | 20303.075 | 4060.615 | 8121.23 | 12181.845

## Event_Audit
NPT_ID | Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Corrective_Action | Action_Status | Duration_hr | Cost_USD | Deferred_Cost_USD | Total_Impact_USD | Strategic_Action_ID
NPT00001 | W001 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | Open | 2 | 40833 | 101446 | 142279 | SA-0001
NPT00002 | W001 | R004 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Repair Component | Open | 2 | 40833 | 70917 | 111750 | SA-0002
NPT00003 | W001 | R004 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | Expedite Shipment | In Progress | 2 | 40833 | 60855 | 101688 | SA-0003
NPT00004 | W001 | R004 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | Closed | 6 | 122500 | 251157 | 373657 | SA-0004
NPT00005 | W001 | R004 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | Closed | 6 | 122500 | 128869 | 251369 | SA-0005
NPT00006 | W001 | R004 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | Closed | 8 | 163333 | 105854 | 269187 | SA-0006
NPT00007 | W001 | R004 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | Closed | 4 | 81666 | 85703 | 167369 | SA-0007
NPT00008 | W001 | R004 | Drilling | Lost Circulation | Differential Sticking | Operator | Increase Mud Weight | Closed | 2 | 40833 | 94533 | 135366 | SA-0008
NPT00009 | W001 | R004 | Weather | Lightning | Storm | Weather | Suspend Operations | In Progress | 4 | 81666 | 108862 | 190528 | SA-0009
NPT00010 | W001 | R004 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | Open | 4 | 81666 | 124254 | 205920 | SA-0010
NPT00011 | W001 | R004 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | Closed | 2 | 40833 | 78584 | 119417 | SA-0011
NPT00012 | W001 | R004 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 4 | 81666 | 152013 | 233679 | SA-0012
NPT00013 | W001 | R004 | Weather | High Waves | Lightning | Weather | Resume Operations | Closed | 6 | 122500 | 139841 | 262341 | SA-0013
NPT00014 | W001 | R004 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Run Fishing Tools | In Progress | 6 | 122500 | 230529 | 353029 | SA-0014
NPT00015 | W001 | R004 | Weather | High Waves | Storm | Marine Operations | Wait on Weather | Closed | 12 | 245000 | 394548 | 639548 | SA-0015
NPT00016 | W001 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Increase Mud Weight | Closed | 4 | 81666 | 185722 | 267388 | SA-0016
NPT00017 | W001 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | In Progress | 4 | 81666 | 90708 | 172374 | SA-0017
NPT00018 | W001 | R004 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | In Progress | 6 | 122500 | 205768 | 328268 | SA-0018
NPT00019 | W001 | R004 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | Expedite Shipment | Closed | 4 | 81666 | 198718 | 280384 | SA-0019
NPT00020 | W002 | R001 | Drilling | Bit Failure | Bit Wear | Directional Drilling | Increase Mud Weight | Closed | 6 | 118750 | 226214 | 344964 | SA-0020
NPT00021 | W002 | R001 | Drilling | Bit Failure | Bit Wear | Operator | Run Fishing Tools | Open | 6 | 118750 | 68245 | 186995 | SA-0021
NPT00022 | W002 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Increase Mud Weight | Closed | 2 | 39583 | 70254 | 109837 | SA-0022
NPT00023 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 2 | 39583 | 76363 | 115946 | SA-0023
NPT00024 | W002 | R001 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Repair Component | Closed | 18 | 356250 | 753050 | 1109300 | SA-0024
NPT00025 | W002 | R001 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Expedite Shipment | Closed | 6 | 118750 | 98071 | 216821 | SA-0025
NPT00026 | W002 | R001 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | Closed | 6 | 118750 | 188958 | 307708 | SA-0026
NPT00027 | W002 | R001 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | Repair Component | Closed | 6 | 118750 | 64902 | 183652 | SA-0027
NPT00028 | W002 | R001 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | In Progress | 8 | 158333 | 316860 | 475193 | SA-0028
NPT00029 | W002 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | Closed | 4 | 79166 | 173712 | 252878 | SA-0029
NPT00030 | W002 | R001 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | Open | 8 | 158333 | 235732 | 394065 | SA-0030
NPT00031 | W002 | R001 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | Closed | 4 | 79166 | 137466 | 216632 | SA-0031
NPT00032 | W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | In Progress | 12 | 237500 | 394870 | 632370 | SA-0032
NPT00033 | W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Open | 18 | 367500 | 863362 | 1230862 | SA-0033
NPT00034 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | In Progress | 6 | 122500 | 294100 | 416600 | SA-0034
NPT00035 | W003 | R004 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Safety Briefing | Closed | 6 | 122500 | 101091 | 223591 | SA-0035
NPT00036 | W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | Closed | 24 | 490000 | 1057580 | 1547580 | SA-0036
NPT00037 | W003 | R004 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | OEM Inspection | Closed | 2 | 40833 | 94991 | 135824 | SA-0037
NPT00038 | W003 | R004 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | Repair Component | Closed | 4 | 81666 | 198934 | 280600 | SA-0038
NPT00039 | W003 | R004 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | Closed | 4 | 81666 | 188346 | 270012 | SA-0039
NPT00040 | W003 | R004 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | Air Freight Materials | Closed | 4 | 81666 | 64854 | 146520 | SA-0040
NPT00041 | W003 | R004 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | Closed | 6 | 122500 | 177370 | 299870 | SA-0041
NPT00042 | W003 | R004 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | In Progress | 2 | 40833 | 50164 | 90997 | SA-0042
NPT00043 | W003 | R004 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | Closed | 2 | 40833 | 27318 | 68151 | SA-0043
NPT00044 | W003 | R004 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | Closed | 6 | 122500 | 191741 | 314241 | SA-0044
NPT00045 | W003 | R004 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | Closed | 4 | 81666 | 119164 | 200830 | SA-0045
NPT00046 | W004 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Closed | 2 | 38333 | 23125 | 61458 | SA-0017
NPT00047 | W004 | R002 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 2 | 38333 | 82098 | 120431 | SA-0046
NPT00048 | W004 | R002 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | Open | 2 | 38333 | 95062 | 133395 | SA-0047
NPT00049 | W004 | R002 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 12 | 230000 | 495852 | 725852 | SA-0048
NPT00050 | W004 | R002 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Wait on Weather | Closed | 4 | 76666 | 120129 | 196795 | SA-0049
NPT00051 | W004 | R002 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | Closed | 4 | 76666 | 57881 | 134547 | SA-0050
NPT00052 | W004 | R002 | Weather | Lightning | Lightning | Weather | Wait on Weather | In Progress | 6 | 115000 | 137010 | 252010 | SA-0051
NPT00053 | W004 | R002 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | Closed | 2 | 38333 | 24450 | 62783 | SA-0052
NPT00054 | W004 | R002 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Replace Equipment | In Progress | 2 | 38333 | 89763 | 128096 | SA-0053
NPT00055 | W004 | R002 | Weather | Lightning | High Waves | Marine Operations | Resume Operations | Closed | 4 | 76666 | 91438 | 168104 | SA-0054
NPT00056 | W004 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | Closed | 12 | 230000 | 121023 | 351023 | SA-0055
NPT00057 | W005 | R002 | Weather | Lightning | Lightning | Weather | Suspend Operations | Closed | 4 | 76666 | 160965 | 237631 | SA-0056
NPT00058 | W005 | R002 | Weather | Heavy Rain | Storm | Weather | Wait on Weather | In Progress | 6 | 115000 | 222173 | 337173 | SA-0057
NPT00059 | W005 | R002 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | Closed | 6 | 115000 | 185545 | 300545 | SA-0058
NPT00060 | W005 | R002 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | Closed | 2 | 38333 | 51475 | 89808 | SA-0059
NPT00061 | W005 | R002 | Logistics | Waiting on Materials | Material Shortage | Procurement | Mobilize Supply Vessel | Closed | 4 | 76666 | 100056 | 176722 | SA-0060
NPT00062 | W005 | R002 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | Closed | 8 | 153333 | 97266 | 250599 | SA-0061
NPT00063 | W005 | R002 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | Repair Component | Closed | 8 | 153333 | 252476 | 405809 | SA-0062
NPT00064 | W005 | R002 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 76666 | 183892 | 260558 | SA-0063
NPT00065 | W005 | R002 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | Closed | 6 | 115000 | 134376 | 249376 | SA-0064
NPT00066 | W005 | R002 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 6 | 115000 | 241365 | 356365 | SA-0065
NPT00067 | W005 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 4 | 76666 | 150606 | 227272 | SA-0066
NPT00068 | W005 | R002 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Condition Hole | Closed | 4 | 76666 | 67864 | 144530 | SA-0067
NPT00069 | W005 | R002 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | Closed | 2 | 38333 | 69012 | 107345 | SA-0068
NPT00070 | W006 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | Open | 2 | 38333 | 55949 | 94282 | SA-0069
NPT00071 | W006 | R002 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | Closed | 2 | 38333 | 74025 | 112358 | SA-0070
NPT00072 | W006 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | Closed | 8 | 153333 | 347820 | 501153 | SA-0071
NPT00073 | W006 | R002 | Weather | Poor Visibility | Lightning | Marine Operations | Suspend Operations | Open | 2 | 38333 | 92556 | 130889 | SA-0072
NPT00074 | W006 | R002 | Logistics | Delayed Helicopter | Material Shortage | Procurement | Mobilize Supply Vessel | Open | 4 | 76666 | 169001 | 245667 | SA-0073
NPT00075 | W006 | R002 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | Closed | 4 | 76666 | 45813 | 122479 | SA-0074
NPT00076 | W006 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 4 | 76666 | 142294 | 218960 | SA-0066
NPT00077 | W006 | R002 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Mobilize Supply Vessel | Closed | 8 | 153333 | 232289 | 385622 | SA-0075
NPT00078 | W006 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Replace Equipment | Closed | 6 | 115000 | 236864 | 351864 | SA-0076
NPT00079 | W006 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | Closed | 4 | 76666 | 64974 | 141640 | SA-0077
NPT00080 | W006 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | Closed | 6 | 115000 | 145730 | 260730 | SA-0078
NPT00081 | W006 | R002 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Air Freight Materials | Closed | 4 | 76666 | 107545 | 184211 | SA-0079
NPT00082 | W006 | R002 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 18 | 345000 | 462111 | 807111 | SA-0080
NPT00083 | W006 | R002 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 76666 | 157410 | 234076 | SA-0081
NPT00084 | W006 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | In Progress | 8 | 153333 | 286906 | 440239 | SA-0082
NPT00085 | W007 | R001 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 79166 | 115572 | 194738 | SA-0083
NPT00086 | W007 | R001 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | Closed | 2 | 39583 | 64096 | 103679 | SA-0084
NPT00087 | W007 | R001 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | Closed | 4 | 79166 | 60596 | 139762 | SA-0085
NPT00088 | W007 | R001 | Drilling | Well Control | Bit Wear | Directional Drilling | Condition Hole | Closed | 18 | 356250 | 798690 | 1154940 | SA-0086
NPT00089 | W007 | R001 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | Closed | 4 | 79166 | 52507 | 131673 | SA-0004
NPT00090 | W007 | R001 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Preventive Maintenance | In Progress | 2 | 39583 | 82308 | 121891 | SA-0087
NPT00091 | W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | Closed | 18 | 356250 | 702062 | 1058312 | SA-0088
NPT00092 | W007 | R001 | Weather | Lightning | Storm | Marine Operations | Resume Operations | In Progress | 8 | 158333 | 192897 | 351230 | SA-0089
NPT00093 | W007 | R001 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | In Progress | 6 | 118750 | 152256 | 271006 | SA-0070
NPT00094 | W007 | R001 | Personnel | Training | Training Requirement | Medical Team | Medical Clearance | Closed | 2 | 39583 | 85410 | 124993 | SA-0090
NPT00095 | W007 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | Closed | 8 | 158333 | 144349 | 302682 | SA-0091
NPT00096 | W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | Closed | 18 | 356250 | 843510 | 1199760 | SA-0092
NPT00097 | W007 | R001 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | Closed | 2 | 39583 | 39917 | 79500 | SA-0093
NPT00098 | W007 | R001 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | Closed | 6 | 118750 | 164765 | 283515 | SA-0094
NPT00099 | W007 | R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | Air Freight Materials | Closed | 18 | 356250 | 426483 | 782733 | SA-0095
NPT00100 | W007 | R001 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | Closed | 8 | 158333 | 357164 | 515497 | SA-0096
NPT00101 | W008 | R002 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Run Fishing Tools | Closed | 4 | 76666 | 111806 | 188472 | SA-0097
NPT00102 | W008 | R002 | Weather | Lightning | Lightning | Weather | Suspend Operations | Closed | 2 | 38333 | 76426 | 114759 | SA-0056
NPT00103 | W008 | R002 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Safety Briefing | In Progress | 2 | 38333 | 66496 | 104829 | SA-0098
NPT00104 | W008 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | Expedite Shipment | In Progress | 2 | 38333 | 59428 | 97761 | SA-0099
NPT00105 | W008 | R002 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | In Progress | 8 | 153333 | 77458 | 230791 | SA-0100
NPT00106 | W008 | R002 | Weather | Poor Visibility | High Waves | Marine Operations | Resume Operations | Closed | 4 | 76666 | 73637 | 150303 | SA-0101
NPT00107 | W008 | R002 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | Preventive Maintenance | Open | 4 | 76666 | 90633 | 167299 | SA-0102
NPT00108 | W008 | R002 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Closed | 6 | 115000 | 286152 | 401152 | SA-0103
NPT00109 | W008 | R002 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | Open | 6 | 115000 | 161085 | 276085 | SA-0104
NPT00110 | W008 | R002 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 2 | 38333 | 48369 | 86702 | SA-0105
NPT00111 | W009 | R001 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | Closed | 2 | 39583 | 93632 | 133215 | SA-0106
NPT00112 | W009 | R001 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Increase Mud Weight | Open | 4 | 79166 | 43669 | 122835 | SA-0107
NPT00113 | W009 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 6 | 118750 | 110684 | 229434 | SA-0108
NPT00114 | W009 | R001 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | Closed | 24 | 475000 | 464721 | 939721 | SA-0109
NPT00115 | W009 | R001 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | OEM Inspection | In Progress | 6 | 118750 | 114628 | 233378 | SA-0110
NPT00116 | W009 | R001 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | Closed | 2 | 39583 | 69610 | 109193 | SA-0068
NPT00117 | W009 | R001 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | In Progress | 6 | 118750 | 89584 | 208334 | SA-0111
NPT00118 | W009 | R001 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | Open | 4 | 79166 | 182360 | 261526 | SA-0034
NPT00119 | W009 | R001 | Weather | Heavy Rain | Lightning | Weather | Suspend Operations | Closed | 4 | 79166 | 143929 | 223095 | SA-0112
NPT00120 | W009 | R001 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | Preventive Maintenance | Closed | 4 | 79166 | 68905 | 148071 | SA-0113
NPT00121 | W009 | R001 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | In Progress | 6 | 118750 | 291172 | 409922 | SA-0114
NPT00122 | W009 | R001 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | Closed | 6 | 118750 | 128920 | 247670 | SA-0115
NPT00123 | W009 | R001 | Weather | Strong Wind | High Waves | Marine Operations | Wait on Weather | In Progress | 6 | 118750 | 279850 | 398600 | SA-0116
NPT00124 | W009 | R001 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Air Freight Materials | Closed | 12 | 237500 | 223755 | 461255 | SA-0117
NPT00125 | W009 | R001 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | Open | 8 | 158333 | 384790 | 543123 | SA-0011
NPT00126 | W010 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | Open | 8 | 153333 | 152314 | 305647 | SA-0118
NPT00127 | W010 | R002 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | In Progress | 6 | 115000 | 139238 | 254238 | SA-0059
NPT00128 | W010 | R002 | Drilling | Bit Failure | Unexpected Pressure | Operator | Run Fishing Tools | Closed | 2 | 38333 | 30581 | 68914 | SA-0119
NPT00129 | W010 | R002 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Condition Hole | Closed | 2 | 38333 | 24138 | 62471 | SA-0120
NPT00130 | W010 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | Closed | 8 | 153333 | 121885 | 275218 | SA-0121
NPT00131 | W010 | R002 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | Closed | 24 | 460000 | 815283 | 1275283 | SA-0122
NPT00132 | W010 | R002 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | Closed | 18 | 345000 | 286552 | 631552 | SA-0018
NPT00133 | W010 | R002 | Drilling | Lost Circulation | Bit Wear | Operator | Condition Hole | Closed | 4 | 76666 | 146588 | 223254 | SA-0123
NPT00134 | W010 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Expedite Shipment | Closed | 2 | 38333 | 89900 | 128233 | SA-0124
NPT00135 | W010 | R002 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | Closed | 4 | 76666 | 104095 | 180761 | SA-0064
NPT00136 | W010 | R002 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | In Progress | 4 | 76666 | 150640 | 227306 | SA-0125
NPT00137 | W010 | R002 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Closed | 8 | 153333 | 121122 | 274455 | SA-0033
NPT00138 | W010 | R002 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | Closed | 6 | 115000 | 223747 | 338747 | SA-0050
NPT00139 | W010 | R002 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | Closed | 4 | 76666 | 168661 | 245327 | SA-0126
NPT00140 | W010 | R002 | Weather | Lightning | Heavy Rain | Weather | Wait on Weather | In Progress | 2 | 38333 | 31793 | 70126 | SA-0127
NPT00141 | W010 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Repair Component | Closed | 4 | 76666 | 96663 | 173329 | SA-0128
NPT00142 | W011 | R004 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | Closed | 4 | 81666 | 60048 | 141714 | SA-0129
NPT00143 | W011 | R004 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Closed | 4 | 81666 | 126974 | 208640 | SA-0130
NPT00144 | W011 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | Closed | 8 | 163333 | 235581 | 398914 | SA-0091
NPT00145 | W011 | R004 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | Closed | 4 | 81666 | 98387 | 180053 | SA-0131
NPT00146 | W011 | R004 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | Open | 2 | 40833 | 26711 | 67544 | SA-0132
NPT00147 | W011 | R004 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Closed | 12 | 245000 | 250040 | 495040 | SA-0033
NPT00148 | W011 | R004 | Weather | Lightning | Lightning | Weather | Resume Operations | Closed | 4 | 81666 | 47696 | 129362 | SA-0133
NPT00149 | W011 | R004 | Personnel | Training | Crew Rotation | Medical Team | Safety Briefing | In Progress | 6 | 122500 | 90710 | 213210 | SA-0134
NPT00150 | W011 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | Closed | 6 | 122500 | 73044 | 195544 | SA-0034
NPT00151 | W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Open | 24 | 490000 | 1059746 | 1549746 | SA-0135
NPT00152 | W011 | R004 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Replace Equipment | Closed | 2 | 40833 | 27130 | 67963 | SA-0136
NPT00153 | W011 | R004 | Weather | Lightning | Lightning | Weather | Suspend Operations | In Progress | 6 | 122500 | 186779 | 309279 | SA-0056
NPT00154 | W011 | R004 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | In Progress | 4 | 81666 | 107304 | 188970 | SA-0137
NPT00155 | W011 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | Closed | 2 | 40833 | 71255 | 112088 | SA-0138
NPT00156 | W011 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | Closed | 4 | 81666 | 48082 | 129748 | SA-0029
NPT00157 | W011 | R004 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Condition Hole | Closed | 12 | 245000 | 554806 | 799806 | SA-0139
NPT00158 | W012 | R004 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | Closed | 2 | 40833 | 30300 | 71133 | SA-0140
NPT00159 | W012 | R004 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Repair Component | Closed | 6 | 122500 | 63732 | 186232 | SA-0141
NPT00160 | W012 | R004 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | Expedite Shipment | Closed | 2 | 40833 | 67554 | 108387 | SA-0142
NPT00161 | W012 | R004 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | OEM Inspection | Closed | 6 | 122500 | 226126 | 348626 | SA-0143
NPT00162 | W012 | R004 | Logistics | Waiting on Boat | Port Congestion | Procurement | Mobilize Supply Vessel | Closed | 6 | 122500 | 255221 | 377721 | SA-0144
NPT00163 | W012 | R004 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | In Progress | 2 | 40833 | 100241 | 141074 | SA-0145
NPT00164 | W012 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | Closed | 4 | 81666 | 62073 | 143739 | SA-0146
NPT00165 | W012 | R004 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | Closed | 18 | 367500 | 574959 | 942459 | SA-0147
NPT00166 | W012 | R004 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Air Freight Materials | Closed | 2 | 40833 | 57857 | 98690 | SA-0148
NPT00167 | W012 | R004 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | In Progress | 4 | 81666 | 116402 | 198068 | SA-0149
NPT00168 | W012 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | Closed | 12 | 245000 | 372611 | 617611 | SA-0150
NPT00169 | W013 | R003 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 6 | 120000 | 253064 | 373064 | SA-0151
NPT00170 | W013 | R003 | Personnel | Safety Stand Down | Medical Emergency | HR | Safety Briefing | Closed | 2 | 40000 | 25522 | 65522 | SA-0152
NPT00171 | W013 | R003 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | Closed | 8 | 160000 | 104847 | 264847 | SA-0153
NPT00172 | W013 | R003 | Weather | Heavy Rain | Strong Wind | Marine Operations | Suspend Operations | Closed | 6 | 120000 | 223619 | 343619 | SA-0154
NPT00173 | W013 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | Expedite Shipment | In Progress | 2 | 40000 | 42480 | 82480 | SA-0155
NPT00174 | W013 | R003 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | Closed | 2 | 40000 | 64200 | 104200 | SA-0156
NPT00175 | W013 | R003 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Air Freight Materials | Open | 4 | 80000 | 159783 | 239783 | SA-0157
NPT00176 | W013 | R003 | Weather | Strong Wind | Storm | Weather | Resume Operations | Open | 8 | 160000 | 158983 | 318983 | SA-0158
NPT00177 | W013 | R003 | Weather | Heavy Rain | High Waves | Marine Operations | Resume Operations | Closed | 4 | 80000 | 185590 | 265590 | SA-0159
NPT00178 | W013 | R003 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | In Progress | 6 | 120000 | 231131 | 351131 | SA-0160
NPT00179 | W013 | R003 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | Closed | 4 | 80000 | 113231 | 193231 | SA-0161
NPT00180 | W013 | R003 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 12 | 240000 | 542475 | 782475 | SA-0160
NPT00181 | W013 | R003 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 40000 | 26827 | 66827 | SA-0162
NPT00182 | W013 | R003 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | In Progress | 6 | 120000 | 278656 | 398656 | SA-0126
NPT00183 | W013 | R003 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 40000 | 74203 | 114203 | SA-0163
NPT00184 | W013 | R003 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | Closed | 4 | 80000 | 122873 | 202873 | SA-0164
NPT00185 | W013 | R003 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | Closed | 6 | 120000 | 129874 | 249874 | SA-0047
NPT00186 | W013 | R003 | Drilling | Fishing Operation | Differential Sticking | Operator | Increase Mud Weight | Closed | 8 | 160000 | 104193 | 264193 | SA-0165
NPT00187 | W013 | R003 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | Closed | 2 | 40000 | 73930 | 113930 | SA-0166
NPT00188 | W013 | R003 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | Closed | 2 | 40000 | 48341 | 88341 | SA-0167
NPT00189 | W014 | R004 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Medical Clearance | Closed | 2 | 40833 | 98245 | 139078 | SA-0168
NPT00190 | W014 | R004 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | Closed | 4 | 81666 | 198783 | 280449 | SA-0169
NPT00191 | W014 | R004 | Logistics | Waiting on Cement | Port Congestion | Procurement | Expedite Shipment | Closed | 4 | 81666 | 60188 | 141854 | SA-0170
NPT00192 | W014 | R004 | Drilling | Stuck Pipe | Bit Wear | Operator | Run Fishing Tools | Closed | 12 | 245000 | 508399 | 753399 | SA-0171
NPT00193 | W014 | R004 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | In Progress | 2 | 40833 | 98036 | 138869 | SA-0172
NPT00194 | W014 | R004 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Replace Equipment | Closed | 4 | 81666 | 154123 | 235789 | SA-0173
NPT00195 | W014 | R004 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 4 | 81666 | 77766 | 159432 | SA-0174
NPT00196 | W014 | R004 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Closed | 6 | 122500 | 135468 | 257968 | SA-0175
NPT00197 | W015 | R003 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Open | 8 | 160000 | 164904 | 324904 | SA-0176
NPT00198 | W015 | R003 | Drilling | Stuck Pipe | Bit Wear | Operator | Condition Hole | Open | 4 | 80000 | 168562 | 248562 | SA-0177
NPT00199 | W015 | R003 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Repair Component | Closed | 8 | 160000 | 393128 | 553128 | SA-0178
NPT00200 | W015 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 4 | 80000 | 127428 | 207428 | SA-0179
NPT00201 | W015 | R003 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 40000 | 30537 | 70537 | SA-0180
NPT00202 | W015 | R003 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 4 | 80000 | 93447 | 173447 | SA-0149
NPT00203 | W015 | R003 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 6 | 120000 | 295691 | 415691 | SA-0181
NPT00204 | W015 | R003 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | Closed | 18 | 360000 | 883515 | 1243515 | SA-0182
NPT00205 | W015 | R003 | Drilling | Fishing Operation | Differential Sticking | Operator | Condition Hole | Closed | 2 | 40000 | 25923 | 65923 | SA-0183
NPT00206 | W015 | R003 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | Closed | 2 | 40000 | 27367 | 67367 | SA-0184
NPT00207 | W015 | R003 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Repair Component | Open | 6 | 120000 | 245352 | 365352 | SA-0185
NPT00208 | W015 | R003 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | Closed | 6 | 120000 | 208139 | 328139 | SA-0186
NPT00209 | W015 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Mobilize Supply Vessel | Closed | 4 | 80000 | 147308 | 227308 | SA-0187
NPT00210 | W015 | R003 | Personnel | Safety Stand Down | Training Requirement | HR | Crew Replacement | Closed | 2 | 40000 | 53981 | 93981 | SA-0188
NPT00211 | W016 | R004 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | Closed | 6 | 122500 | 96624 | 219124 | SA-0077
NPT00212 | W016 | R004 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | Repair Component | In Progress | 6 | 122500 | 78520 | 201020 | SA-0189
NPT00213 | W016 | R004 | Weather | Lightning | Strong Wind | Weather | Wait on Weather | Closed | 6 | 122500 | 264246 | 386746 | SA-0190
NPT00214 | W016 | R004 | Weather | Heavy Rain | Lightning | Marine Operations | Wait on Weather | Closed | 2 | 40833 | 90548 | 131381 | SA-0191
NPT00215 | W016 | R004 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | Closed | 8 | 163333 | 216971 | 380304 | SA-0032
NPT00216 | W016 | R004 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | In Progress | 2 | 40833 | 42270 | 83103 | SA-0192
NPT00217 | W016 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | In Progress | 4 | 81666 | 165749 | 247415 | SA-0150
NPT00218 | W016 | R004 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Resume Operations | Closed | 4 | 81666 | 146635 | 228301 | SA-0193
NPT00219 | W016 | R004 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | Closed | 8 | 163333 | 228822 | 392155 | SA-0045
NPT00220 | W016 | R004 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Resume Operations | Closed | 4 | 81666 | 192615 | 274281 | SA-0194
NPT00221 | W017 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | Closed | 6 | 118750 | 239519 | 358269 | SA-0088
NPT00222 | W017 | R001 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Preventive Maintenance | In Progress | 6 | 118750 | 120704 | 239454 | SA-0195
NPT00223 | W017 | R001 | Weather | Strong Wind | High Waves | Weather | Resume Operations | Closed | 6 | 118750 | 136446 | 255196 | SA-0196
NPT00224 | W017 | R001 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | In Progress | 4 | 79166 | 127827 | 206993 | SA-0104
NPT00225 | W017 | R001 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Increase Mud Weight | Closed | 6 | 118750 | 81777 | 200527 | SA-0197
NPT00226 | W017 | R001 | Drilling | Hole Cleaning | Formation Instability | Operator | Increase Mud Weight | Closed | 2 | 39583 | 44552 | 84135 | SA-0198
NPT00227 | W017 | R001 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Air Freight Materials | Closed | 6 | 118750 | 154929 | 273679 | SA-0199
NPT00228 | W017 | R001 | Drilling | Well Control | Bit Wear | Directional Drilling | Run Fishing Tools | Closed | 2 | 39583 | 49805 | 89388 | SA-0200
NPT00229 | W017 | R001 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | Closed | 6 | 118750 | 236976 | 355726 | SA-0153
NPT00230 | W017 | R001 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Run Fishing Tools | In Progress | 2 | 39583 | 55699 | 95282 | SA-0201
NPT00231 | W017 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | Closed | 8 | 158333 | 274332 | 432665 | SA-0001
NPT00232 | W018 | R004 | Weather | Poor Visibility | Storm | Marine Operations | Wait on Weather | Closed | 6 | 122500 | 92594 | 215094 | SA-0202
NPT00233 | W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Air Freight Materials | Open | 24 | 490000 | 397460 | 887460 | SA-0203
NPT00234 | W018 | R004 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | In Progress | 2 | 40833 | 48398 | 89231 | SA-0104
NPT00235 | W018 | R004 | Weather | Heavy Rain | Strong Wind | Weather | Resume Operations | In Progress | 2 | 40833 | 71375 | 112208 | SA-0204
NPT00236 | W018 | R004 | Weather | Strong Wind | High Waves | Marine Operations | Resume Operations | Closed | 4 | 81666 | 130214 | 211880 | SA-0205
NPT00237 | W018 | R004 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | Closed | 4 | 81666 | 121285 | 202951 | SA-0206
NPT00238 | W018 | R004 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | Closed | 6 | 122500 | 117557 | 240057 | SA-0034
NPT00239 | W018 | R004 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Increase Mud Weight | In Progress | 2 | 40833 | 96130 | 136963 | SA-0207
NPT00240 | W018 | R004 | Weather | Heavy Rain | Storm | Marine Operations | Wait on Weather | Closed | 4 | 81666 | 202290 | 283956 | SA-0208
NPT00241 | W018 | R004 | Weather | Poor Visibility | Storm | Weather | Wait on Weather | Closed | 6 | 122500 | 74361 | 196861 | SA-0209
NPT00242 | W018 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 8 | 163333 | 204429 | 367762 | SA-0210
NPT00243 | W018 | R004 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Condition Hole | Closed | 4 | 81666 | 86316 | 167982 | SA-0211
NPT00244 | W018 | R004 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Condition Hole | Closed | 12 | 245000 | 278344 | 523344 | SA-0212
NPT00245 | W018 | R004 | Weather | Heavy Rain | Heavy Rain | Weather | Suspend Operations | Closed | 4 | 81666 | 138389 | 220055 | SA-0213
NPT00246 | W019 | R003 | Weather | Lightning | High Waves | Weather | Resume Operations | Closed | 24 | 480000 | 674701 | 1154701 | SA-0214
NPT00247 | W019 | R003 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | Preventive Maintenance | Open | 12 | 240000 | 123301 | 363301 | SA-0215
NPT00248 | W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | Closed | 4 | 80000 | 66304 | 146304 | SA-0216
NPT00249 | W019 | R003 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 6 | 120000 | 217687 | 337687 | SA-0217
NPT00250 | W019 | R003 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | Closed | 6 | 120000 | 111527 | 231527 | SA-0182
NPT00251 | W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 12 | 240000 | 479117 | 719117 | SA-0218
NPT00252 | W019 | R003 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 2 | 40000 | 65954 | 105954 | SA-0219
NPT00253 | W019 | R003 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Condition Hole | In Progress | 2 | 40000 | 24142 | 64142 | SA-0220
NPT00254 | W019 | R003 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | Closed | 4 | 80000 | 52250 | 132250 | SA-0221
NPT00255 | W019 | R003 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 18 | 360000 | 827467 | 1187467 | SA-0222
NPT00256 | W019 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 8 | 160000 | 163949 | 323949 | SA-0223
NPT00257 | W019 | R003 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 4 | 80000 | 108553 | 188553 | SA-0160
NPT00258 | W019 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 12 | 240000 | 366765 | 606765 | SA-0224
NPT00259 | W020 | R003 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 18 | 360000 | 663187 | 1023187 | SA-0225
NPT00260 | W020 | R003 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Condition Hole | Closed | 4 | 80000 | 107175 | 187175 | SA-0226
NPT00261 | W020 | R003 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | Open | 2 | 40000 | 72937 | 112937 | SA-0126
NPT00262 | W020 | R003 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | Closed | 2 | 40000 | 24049 | 64049 | SA-0227
NPT00263 | W020 | R003 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | Closed | 6 | 120000 | 69661 | 189661 | SA-0166
NPT00264 | W020 | R003 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | Open | 4 | 80000 | 70919 | 150919 | SA-0172
NPT00265 | W020 | R003 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 80000 | 156404 | 236404 | SA-0083
NPT00266 | W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | Closed | 4 | 80000 | 95170 | 175170 | SA-0228
NPT00267 | W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Closed | 8 | 160000 | 130021 | 290021 | SA-0229
NPT00268 | W020 | R003 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Safety Briefing | Closed | 2 | 40000 | 71032 | 111032 | SA-0230
NPT00269 | W020 | R003 | Weather | High Waves | Heavy Rain | Marine Operations | Suspend Operations | Open | 8 | 160000 | 364772 | 524772 | SA-0231
NPT00270 | W020 | R003 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Replace Equipment | Closed | 2 | 40000 | 81266 | 121266 | SA-0232
NPT00271 | W020 | R003 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | Closed | 2 | 40000 | 79766 | 119766 | SA-0233
NPT00272 | W020 | R003 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | Preventive Maintenance | Closed | 2 | 40000 | 52909 | 92909 | SA-0234
NPT00273 | W020 | R003 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | OEM Inspection | Closed | 2 | 40000 | 33971 | 73971 | SA-0235
NPT00274 | W020 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 6 | 120000 | 141830 | 261830 | SA-0108
NPT00275 | W020 | R003 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Increase Mud Weight | Closed | 6 | 120000 | 223111 | 343111 | SA-0236
NPT00276 | W020 | R003 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | Closed | 2 | 40000 | 92216 | 132216 | SA-0237
NPT00277 | W020 | R003 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | Closed | 4 | 80000 | 143184 | 223184 | SA-0238
NPT00278 | W020 | R003 | Weather | Lightning | Heavy Rain | Weather | Resume Operations | Closed | 2 | 40000 | 91903 | 131903 | SA-0239
NPT00279 | W021 | R002 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Repair Component | Closed | 12 | 230000 | 265392 | 495392 | SA-0240
NPT00280 | W021 | R002 | Drilling | Well Control | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 6 | 115000 | 172490 | 287490 | SA-0241
NPT00281 | W021 | R002 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Repair Component | Closed | 2 | 38333 | 40806 | 79139 | SA-0242
NPT00282 | W021 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Repair Component | Closed | 6 | 115000 | 207678 | 322678 | SA-0243
NPT00283 | W021 | R002 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Mobilize Supply Vessel | Closed | 8 | 153333 | 239111 | 392444 | SA-0244
NPT00284 | W021 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | In Progress | 4 | 76666 | 173767 | 250433 | SA-0245
NPT00285 | W021 | R002 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | Mobilize Supply Vessel | Closed | 18 | 345000 | 573898 | 918898 | SA-0246
NPT00286 | W021 | R002 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | Closed | 6 | 115000 | 80176 | 195176 | SA-0064
NPT00287 | W021 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | In Progress | 6 | 115000 | 90497 | 205497 | SA-0247
NPT00288 | W021 | R002 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | Closed | 2 | 38333 | 79231 | 117564 | SA-0248
NPT00289 | W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 6 | 115000 | 286496 | 401496 | SA-0179
NPT00290 | W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 2 | 38333 | 40658 | 78991 | SA-0179
NPT00291 | W021 | R002 | Weather | Lightning | Lightning | Weather | Resume Operations | Closed | 2 | 38333 | 88590 | 126923 | SA-0133
NPT00292 | W021 | R002 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | Closed | 6 | 115000 | 196670 | 311670 | SA-0249
NPT00293 | W021 | R002 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | Open | 6 | 115000 | 90381 | 205381 | SA-0050
NPT00294 | W021 | R002 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | OEM Inspection | Closed | 2 | 38333 | 78798 | 117131 | SA-0250
NPT00295 | W022 | R001 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | Closed | 12 | 237500 | 199439 | 436939 | SA-0251
NPT00296 | W022 | R001 | Weather | High Waves | Strong Wind | Weather | Suspend Operations | Closed | 2 | 39583 | 63322 | 102905 | SA-0252
NPT00297 | W022 | R001 | Weather | Poor Visibility | High Waves | Weather | Resume Operations | In Progress | 6 | 118750 | 138221 | 256971 | SA-0253
NPT00298 | W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | Open | 8 | 158333 | 298315 | 456648 | SA-0254
NPT00299 | W022 | R001 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | In Progress | 2 | 39583 | 32358 | 71941 | SA-0255
NPT00300 | W022 | R001 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | In Progress | 4 | 79166 | 120835 | 200001 | SA-0256
NPT00301 | W022 | R001 | Weather | Lightning | Lightning | Weather | Suspend Operations | Closed | 2 | 39583 | 52686 | 92269 | SA-0056
NPT00302 | W022 | R001 | Weather | Strong Wind | Heavy Rain | Marine Operations | Suspend Operations | Closed | 4 | 79166 | 104081 | 183247 | SA-0257
NPT00303 | W022 | R001 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | Expedite Shipment | In Progress | 6 | 118750 | 120114 | 238864 | SA-0258
NPT00304 | W022 | R001 | Logistics | Waiting on Materials | Port Congestion | Procurement | Expedite Shipment | Open | 8 | 158333 | 193285 | 351618 | SA-0259
NPT00305 | W022 | R001 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | In Progress | 6 | 118750 | 59595 | 178345 | SA-0028
NPT00306 | W022 | R001 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | Closed | 12 | 237500 | 561306 | 798806 | SA-0260
NPT00307 | W022 | R001 | Weather | Strong Wind | Heavy Rain | Marine Operations | Wait on Weather | Open | 2 | 39583 | 34235 | 73818 | SA-0261
NPT00308 | W023 | R004 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Repair Component | Closed | 4 | 81666 | 189343 | 271009 | SA-0262
NPT00309 | W023 | R004 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Closed | 6 | 122500 | 274722 | 397222 | SA-0180
NPT00310 | W023 | R004 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | Expedite Shipment | Closed | 6 | 122500 | 257837 | 380337 | SA-0263
NPT00311 | W023 | R004 | Personnel | Crew Change | Medical Emergency | Medical Team | Medical Clearance | Closed | 18 | 367500 | 774135 | 1141635 | SA-0264
NPT00312 | W023 | R004 | Drilling | Well Control | Bit Wear | Mud Engineering | Run Fishing Tools | In Progress | 4 | 81666 | 55231 | 136897 | SA-0265
NPT00313 | W023 | R004 | Weather | Lightning | Storm | Weather | Resume Operations | Closed | 12 | 245000 | 431874 | 676874 | SA-0266
NPT00314 | W023 | R004 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | Closed | 4 | 81666 | 112807 | 194473 | SA-0005
NPT00315 | W023 | R004 | Personnel | Medical Evacuation | Medical Emergency | HR | Crew Replacement | Closed | 6 | 122500 | 253590 | 376090 | SA-0267
NPT00316 | W023 | R004 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | Closed | 2 | 40833 | 34121 | 74954 | SA-0032
NPT00317 | W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | Open | 8 | 163333 | 324715 | 488048 | SA-0092
NPT00318 | W023 | R004 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | Closed | 2 | 40833 | 86980 | 127813 | SA-0268
NPT00319 | W023 | R004 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 81666 | 185627 | 267293 | SA-0269
NPT00320 | W023 | R004 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | OEM Inspection | Open | 4 | 81666 | 71396 | 153062 | SA-0270
NPT00321 | W023 | R004 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | Medical Clearance | Closed | 4 | 81666 | 60840 | 142506 | SA-0271
NPT00322 | W024 | R002 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Replace Equipment | Closed | 8 | 153333 | 152401 | 305734 | SA-0272
NPT00323 | W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | In Progress | 12 | 230000 | 245724 | 475724 | SA-0273
NPT00324 | W024 | R002 | Weather | Poor Visibility | High Waves | Marine Operations | Wait on Weather | Closed | 4 | 76666 | 44941 | 121607 | SA-0274
NPT00325 | W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 4 | 76666 | 67775 | 144441 | SA-0218
NPT00326 | W024 | R002 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | Closed | 12 | 230000 | 541101 | 771101 | SA-0275
NPT00327 | W024 | R002 | Drilling | Well Control | Differential Sticking | Operator | Condition Hole | Closed | 4 | 76666 | 70081 | 146747 | SA-0276
NPT00328 | W024 | R002 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Open | 2 | 38333 | 86372 | 124705 | SA-0103
NPT00329 | W024 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | In Progress | 2 | 38333 | 86067 | 124400 | SA-0277
NPT00330 | W024 | R002 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Closed | 6 | 115000 | 184818 | 299818 | SA-0278
NPT00331 | W024 | R002 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | Closed | 2 | 38333 | 66638 | 104971 | SA-0084
NPT00332 | W024 | R002 | Drilling | Stuck Pipe | Differential Sticking | Operator | Condition Hole | Closed | 4 | 76666 | 132348 | 209014 | SA-0279
NPT00333 | W024 | R002 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | Replace Equipment | Closed | 8 | 153333 | 260743 | 414076 | SA-0280
NPT00334 | W025 | R004 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Run Fishing Tools | Closed | 6 | 122500 | 144551 | 267051 | SA-0281
NPT00335 | W025 | R004 | Drilling | Well Control | Formation Instability | Mud Engineering | Increase Mud Weight | Closed | 4 | 81666 | 144601 | 226267 | SA-0282
NPT00336 | W025 | R004 | Weather | Heavy Rain | Storm | Weather | Suspend Operations | Closed | 4 | 81666 | 127004 | 208670 | SA-0283
NPT00337 | W025 | R004 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Increase Mud Weight | In Progress | 6 | 122500 | 154285 | 276785 | SA-0284
NPT00338 | W025 | R004 | Weather | Strong Wind | Lightning | Weather | Suspend Operations | Closed | 2 | 40833 | 43926 | 84759 | SA-0285
NPT00339 | W025 | R004 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | OEM Inspection | In Progress | 4 | 81666 | 86786 | 168452 | SA-0286
NPT00340 | W025 | R004 | Weather | High Waves | Strong Wind | Weather | Resume Operations | Open | 6 | 122500 | 265620 | 388120 | SA-0287
NPT00341 | W025 | R004 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | Repair Component | Closed | 2 | 40833 | 48689 | 89522 | SA-0288
NPT00342 | W025 | R004 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | In Progress | 2 | 40833 | 62499 | 103332 | SA-0289
NPT00343 | W025 | R004 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Condition Hole | Closed | 12 | 245000 | 539466 | 784466 | SA-0290
NPT00344 | W025 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | In Progress | 6 | 122500 | 138722 | 261222 | SA-0291
NPT00345 | W026 | R004 | Weather | High Waves | Strong Wind | Marine Operations | Suspend Operations | In Progress | 12 | 245000 | 580843 | 825843 | SA-0292
NPT00346 | W026 | R004 | Weather | Heavy Rain | Storm | Weather | Resume Operations | Closed | 24 | 490000 | 614657 | 1104657 | SA-0293
NPT00347 | W026 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | OEM Inspection | Closed | 4 | 81666 | 185274 | 266940 | SA-0294
NPT00348 | W026 | R004 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 8 | 163333 | 234179 | 397512 | SA-0080
NPT00349 | W026 | R004 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | Closed | 8 | 163333 | 249120 | 412453 | SA-0295
NPT00350 | W026 | R004 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 2 | 40833 | 48430 | 89263 | SA-0296
NPT00351 | W026 | R004 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Repair Component | Closed | 2 | 40833 | 31395 | 72228 | SA-0297
NPT00352 | W026 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | In Progress | 6 | 122500 | 186115 | 308615 | SA-0298
NPT00353 | W026 | R004 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | Crew Replacement | In Progress | 18 | 367500 | 388821 | 756321 | SA-0299
NPT00354 | W026 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | Closed | 4 | 81666 | 55037 | 136703 | SA-0291
NPT00355 | W026 | R004 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Expedite Shipment | Open | 2 | 40833 | 41456 | 82289 | SA-0300
NPT00356 | W027 | R002 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | In Progress | 18 | 345000 | 565252 | 910252 | SA-0301
NPT00357 | W027 | R002 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | Closed | 2 | 38333 | 72075 | 110408 | SA-0302
NPT00358 | W027 | R002 | Weather | Lightning | High Waves | Marine Operations | Wait on Weather | In Progress | 4 | 76666 | 85784 | 162450 | SA-0303
NPT00359 | W027 | R002 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | Open | 8 | 153333 | 335435 | 488768 | SA-0304
NPT00360 | W027 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | In Progress | 6 | 115000 | 112412 | 227412 | SA-0305
NPT00361 | W027 | R002 | Weather | Lightning | High Waves | Weather | Suspend Operations | Closed | 12 | 230000 | 258903 | 488903 | SA-0306
NPT00362 | W027 | R002 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Adjust Drilling Parameters | In Progress | 2 | 38333 | 85268 | 123601 | SA-0307
NPT00363 | W027 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | Closed | 4 | 76666 | 38651 | 115317 | SA-0308
NPT00364 | W027 | R002 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | Closed | 2 | 38333 | 61637 | 99970 | SA-0309
NPT00365 | W027 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Run Fishing Tools | Open | 8 | 153333 | 342295 | 495628 | SA-0310
NPT00366 | W028 | R002 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Closed | 6 | 115000 | 87189 | 202189 | SA-0130
NPT00367 | W028 | R002 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | Closed | 4 | 76666 | 169923 | 246589 | SA-0131
NPT00368 | W028 | R002 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | In Progress | 8 | 153333 | 276056 | 429389 | SA-0311
NPT00369 | W028 | R002 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | Closed | 2 | 38333 | 68316 | 106649 | SA-0256
NPT00370 | W028 | R002 | Personnel | Crew Change | Training Requirement | Rig Management | Crew Replacement | Closed | 4 | 76666 | 79447 | 156113 | SA-0312
NPT00371 | W028 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Increase Mud Weight | Closed | 12 | 230000 | 150405 | 380405 | SA-0313
NPT00372 | W028 | R002 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | Open | 4 | 76666 | 154351 | 231017 | SA-0314
NPT00373 | W028 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 38333 | 40944 | 79277 | SA-0315
NPT00374 | W028 | R002 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | Closed | 6 | 115000 | 249425 | 364425 | SA-0106
NPT00375 | W028 | R002 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | In Progress | 4 | 76666 | 159300 | 235966 | SA-0104
NPT00376 | W028 | R002 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | Closed | 6 | 115000 | 194047 | 309047 | SA-0316
NPT00377 | W028 | R002 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 18 | 345000 | 380594 | 725594 | SA-0317
NPT00378 | W028 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | Replace Equipment | Closed | 2 | 38333 | 83567 | 121900 | SA-0318
NPT00379 | W028 | R002 | Weather | Strong Wind | Storm | Weather | Suspend Operations | Open | 4 | 76666 | 41042 | 117708 | SA-0319
NPT00380 | W028 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Closed | 8 | 153333 | 283449 | 436782 | SA-0135
NPT00381 | W029 | R002 | Drilling | Hole Cleaning | Differential Sticking | Operator | Increase Mud Weight | Open | 2 | 38333 | 53610 | 91943 | SA-0320
NPT00382 | W029 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | Closed | 4 | 76666 | 74370 | 151036 | SA-0321
NPT00383 | W029 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | In Progress | 8 | 153333 | 279943 | 433276 | SA-0322
NPT00384 | W029 | R002 | Personnel | Crew Change | Medical Emergency | HR | Medical Clearance | In Progress | 6 | 115000 | 117452 | 232452 | SA-0323
NPT00385 | W029 | R002 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | In Progress | 2 | 38333 | 24538 | 62871 | SA-0122
NPT00386 | W029 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | Closed | 8 | 153333 | 130015 | 283348 | SA-0324
NPT00387 | W029 | R002 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | Closed | 6 | 115000 | 262434 | 377434 | SA-0325
NPT00388 | W029 | R002 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Run Fishing Tools | Closed | 4 | 76666 | 185391 | 262057 | SA-0326
NPT00389 | W029 | R002 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Closed | 4 | 76666 | 148435 | 225101 | SA-0327
NPT00390 | W029 | R002 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | In Progress | 4 | 76666 | 100636 | 177302 | SA-0085
NPT00391 | W029 | R002 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | Closed | 2 | 38333 | 37984 | 76317 | SA-0061
NPT00392 | W029 | R002 | Weather | Poor Visibility | Heavy Rain | Weather | Wait on Weather | In Progress | 6 | 115000 | 152059 | 267059 | SA-0328
NPT00393 | W029 | R002 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | In Progress | 6 | 115000 | 239219 | 354219 | SA-0275
NPT00394 | W029 | R002 | Drilling | Lost Circulation | Differential Sticking | Operator | Run Fishing Tools | Closed | 8 | 153333 | 201314 | 354647 | SA-0329
NPT00395 | W030 | R002 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | Closed | 8 | 153333 | 91956 | 245289 | SA-0330
NPT00396 | W030 | R002 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | In Progress | 2 | 38333 | 20240 | 58573 | SA-0140
NPT00397 | W030 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | Closed | 2 | 38333 | 56371 | 94704 | SA-0186
NPT00398 | W030 | R002 | Drilling | Well Control | Formation Instability | Operator | Increase Mud Weight | Closed | 6 | 115000 | 74266 | 189266 | SA-0331
NPT00399 | W030 | R002 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Open | 4 | 76666 | 52243 | 128909 | SA-0332
NPT00400 | W030 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Expedite Shipment | Closed | 6 | 115000 | 233024 | 348024 | SA-0333
NPT00401 | W030 | R002 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | Replace Equipment | Closed | 8 | 153333 | 363755 | 517088 | SA-0334
NPT00402 | W030 | R002 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | OEM Inspection | Open | 2 | 38333 | 43940 | 82273 | SA-0335
NPT00403 | W030 | R002 | Weather | High Waves | High Waves | Marine Operations | Resume Operations | Closed | 12 | 230000 | 429330 | 659330 | SA-0336
NPT00404 | W030 | R002 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | Closed | 12 | 230000 | 418094 | 648094 | SA-0337
NPT00405 | W030 | R002 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | Closed | 8 | 153333 | 123054 | 276387 | SA-0044
NPT00406 | W030 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | Closed | 2 | 38333 | 94383 | 132716 | SA-0338
NPT00407 | W030 | R002 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | Closed | 6 | 115000 | 69074 | 184074 | SA-0156
NPT00408 | W030 | R002 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Repair Component | In Progress | 8 | 153333 | 169026 | 322359 | SA-0339
NPT00409 | W030 | R002 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Open | 4 | 76666 | 173634 | 250300 | SA-0111
NPT00410 | W031 | R002 | Weather | High Waves | Heavy Rain | Weather | Resume Operations | In Progress | 4 | 76666 | 191641 | 268307 | SA-0340
NPT00411 | W031 | R002 | Drilling | Stuck Pipe | Differential Sticking | Operator | Increase Mud Weight | Closed | 2 | 38333 | 69018 | 107351 | SA-0341
NPT00412 | W031 | R002 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | In Progress | 4 | 76666 | 99814 | 176480 | SA-0330
NPT00413 | W031 | R002 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Run Fishing Tools | Open | 4 | 76666 | 115177 | 191843 | SA-0342
NPT00414 | W031 | R002 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | Closed | 4 | 76666 | 44040 | 120706 | SA-0343
NPT00415 | W031 | R002 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 4 | 76666 | 128931 | 205597 | SA-0344
NPT00416 | W031 | R002 | Weather | Poor Visibility | Strong Wind | Weather | Suspend Operations | Closed | 4 | 76666 | 41049 | 117715 | SA-0345
NPT00417 | W031 | R002 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | Closed | 4 | 76666 | 93803 | 170469 | SA-0304
NPT00418 | W031 | R002 | Drilling | Stuck Pipe | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 4 | 76666 | 100999 | 177665 | SA-0346
NPT00419 | W031 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | In Progress | 2 | 38333 | 54487 | 92820 | SA-0347
NPT00420 | W031 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | In Progress | 24 | 460000 | 943802 | 1403802 | SA-0164
NPT00421 | W032 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | Closed | 2 | 40833 | 99458 | 140291 | SA-0348
NPT00422 | W032 | R004 | Weather | Heavy Rain | Lightning | Marine Operations | Suspend Operations | Closed | 8 | 163333 | 288692 | 452025 | SA-0349
NPT00423 | W032 | R004 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | Closed | 6 | 122500 | 75891 | 198391 | SA-0350
NPT00424 | W032 | R004 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | Closed | 4 | 81666 | 171063 | 252729 | SA-0115
NPT00425 | W032 | R004 | Weather | High Waves | Lightning | Weather | Suspend Operations | Closed | 4 | 81666 | 184832 | 266498 | SA-0351
NPT00426 | W032 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | Closed | 6 | 122500 | 76832 | 199332 | SA-0146
NPT00427 | W032 | R004 | Weather | Lightning | Strong Wind | Weather | Suspend Operations | Closed | 18 | 367500 | 445857 | 813357 | SA-0352
NPT00428 | W032 | R004 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | OEM Inspection | Closed | 8 | 163333 | 152781 | 316114 | SA-0353
NPT00429 | W032 | R004 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | Open | 2 | 40833 | 27339 | 68172 | SA-0289
NPT00430 | W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Air Freight Materials | Closed | 6 | 122500 | 301536 | 424036 | SA-0354
NPT00431 | W032 | R004 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Medical Clearance | In Progress | 4 | 81666 | 94096 | 175762 | SA-0355
NPT00432 | W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Mobilize Supply Vessel | Closed | 6 | 122500 | 231858 | 354358 | SA-0356
NPT00433 | W032 | R004 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | Closed | 2 | 40833 | 33061 | 73894 | SA-0005
NPT00434 | W032 | R004 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | Repair Component | Closed | 8 | 163333 | 267513 | 430846 | SA-0357
NPT00435 | W032 | R004 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Condition Hole | Closed | 2 | 40833 | 45052 | 85885 | SA-0358
NPT00436 | W033 | R002 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 6 | 115000 | 177855 | 292855 | SA-0359
NPT00437 | W033 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Open | 12 | 230000 | 161849 | 391849 | SA-0229
NPT00438 | W033 | R002 | Weather | Heavy Rain | Storm | Marine Operations | Resume Operations | Closed | 2 | 38333 | 72796 | 111129 | SA-0360
NPT00439 | W033 | R002 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Open | 4 | 76666 | 107302 | 183968 | SA-0361
NPT00440 | W033 | R002 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Open | 6 | 115000 | 225265 | 340265 | SA-0362
NPT00441 | W033 | R002 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | Expedite Shipment | Open | 4 | 76666 | 165696 | 242362 | SA-0363
NPT00442 | W033 | R002 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | Closed | 2 | 38333 | 41966 | 80299 | SA-0010
NPT00443 | W033 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | In Progress | 12 | 230000 | 219568 | 449568 | SA-0364
NPT00444 | W033 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | Preventive Maintenance | Open | 2 | 38333 | 82613 | 120946 | SA-0365
NPT00445 | W033 | R002 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | Closed | 8 | 153333 | 182342 | 335675 | SA-0366
NPT00446 | W033 | R002 | Weather | Strong Wind | High Waves | Weather | Wait on Weather | Closed | 8 | 153333 | 347209 | 500542 | SA-0367
NPT00447 | W033 | R002 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | Open | 2 | 38333 | 65027 | 103360 | SA-0115
NPT00448 | W033 | R002 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | Mobilize Supply Vessel | Closed | 12 | 230000 | 407608 | 637608 | SA-0368
NPT00449 | W033 | R002 | Weather | Poor Visibility | High Waves | Marine Operations | Suspend Operations | Closed | 4 | 76666 | 124855 | 201521 | SA-0369
NPT00450 | W033 | R002 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | Open | 4 | 76666 | 55282 | 131948 | SA-0370
NPT00451 | W033 | R002 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | Replace Equipment | Closed | 2 | 38333 | 81222 | 119555 | SA-0371
NPT00452 | W034 | R001 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 18 | 356250 | 822305 | 1178555 | SA-0149
NPT00453 | W034 | R001 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Repair Component | Closed | 4 | 79166 | 107969 | 187135 | SA-0372
NPT00454 | W034 | R001 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 79166 | 76620 | 155786 | SA-0373
NPT00455 | W034 | R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | Closed | 18 | 356250 | 284572 | 640822 | SA-0374
NPT00456 | W034 | R001 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | In Progress | 8 | 158333 | 332867 | 491200 | SA-0074
NPT00457 | W034 | R001 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | Closed | 4 | 79166 | 55237 | 134403 | SA-0169
NPT00458 | W034 | R001 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | Closed | 4 | 79166 | 124715 | 203881 | SA-0309
NPT00459 | W034 | R001 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Repair Component | Closed | 2 | 39583 | 57298 | 96881 | SA-0375
NPT00460 | W034 | R001 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Air Freight Materials | Closed | 4 | 79166 | 187319 | 266485 | SA-0376
NPT00461 | W034 | R001 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | OEM Inspection | Closed | 4 | 79166 | 45728 | 124894 | SA-0377
NPT00462 | W034 | R001 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | Closed | 2 | 39583 | 75663 | 115246 | SA-0043
NPT00463 | W034 | R001 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | Open | 2 | 39583 | 22675 | 62258 | SA-0251
NPT00464 | W035 | R003 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | Closed | 18 | 360000 | 208849 | 568849 | SA-0378
NPT00465 | W035 | R003 | Weather | High Waves | Heavy Rain | Weather | Suspend Operations | Closed | 6 | 120000 | 88739 | 208739 | SA-0379
NPT00466 | W035 | R003 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Closed | 2 | 40000 | 69853 | 109853 | SA-0380
NPT00467 | W035 | R003 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | Closed | 6 | 120000 | 243625 | 363625 | SA-0006
NPT00468 | W035 | R003 | Drilling | Well Control | Differential Sticking | Mud Engineering | Run Fishing Tools | Closed | 2 | 40000 | 30168 | 70168 | SA-0381
NPT00469 | W035 | R003 | Weather | High Waves | Strong Wind | Marine Operations | Resume Operations | Open | 18 | 360000 | 200297 | 560297 | SA-0382
NPT00470 | W035 | R003 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Condition Hole | Closed | 2 | 40000 | 58559 | 98559 | SA-0383
NPT00471 | W035 | R003 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | Closed | 12 | 240000 | 122437 | 362437 | SA-0316
NPT00472 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | Operator | Condition Hole | Closed | 6 | 120000 | 273652 | 393652 | SA-0384
NPT00473 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Closed | 12 | 240000 | 291067 | 531067 | SA-0385
NPT00474 | W035 | R003 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | Closed | 2 | 40000 | 38248 | 78248 | SA-0145
NPT00475 | W035 | R003 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 6 | 120000 | 130403 | 250403 | SA-0046
NPT00476 | W036 | R002 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | Closed | 2 | 38333 | 93792 | 132125 | SA-0039
NPT00477 | W036 | R002 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Increase Mud Weight | In Progress | 4 | 76666 | 153896 | 230562 | SA-0386
NPT00478 | W036 | R002 | Drilling | Well Control | Formation Instability | Directional Drilling | Run Fishing Tools | Closed | 6 | 115000 | 253781 | 368781 | SA-0387
NPT00479 | W036 | R002 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | Closed | 4 | 76666 | 152544 | 229210 | SA-0388
NPT00480 | W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | Closed | 18 | 345000 | 776256 | 1121256 | SA-0042
NPT00481 | W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | Closed | 2 | 38333 | 84839 | 123172 | SA-0378
NPT00482 | W036 | R002 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Condition Hole | Closed | 6 | 115000 | 202496 | 317496 | SA-0389
NPT00483 | W036 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | OEM Inspection | Closed | 4 | 76666 | 78814 | 155480 | SA-0390
NPT00484 | W036 | R002 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Closed | 4 | 76666 | 112293 | 188959 | SA-0391
NPT00485 | W036 | R002 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Preventive Maintenance | Closed | 2 | 38333 | 91400 | 129733 | SA-0392
NPT00486 | W036 | R002 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | Closed | 18 | 345000 | 526177 | 871177 | SA-0393
NPT00487 | W036 | R002 | Drilling | Hole Cleaning | Differential Sticking | Operator | Adjust Drilling Parameters | Closed | 6 | 115000 | 111365 | 226365 | SA-0394
NPT00488 | W036 | R002 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 6 | 115000 | 150140 | 265140 | SA-0176
NPT00489 | W036 | R002 | Weather | Strong Wind | Lightning | Marine Operations | Resume Operations | Closed | 6 | 115000 | 123339 | 238339 | SA-0395
NPT00490 | W036 | R002 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Air Freight Materials | Closed | 2 | 38333 | 67158 | 105491 | SA-0396
NPT00491 | W036 | R002 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Replace Equipment | In Progress | 4 | 76666 | 67923 | 144589 | SA-0397
NPT00492 | W036 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | In Progress | 4 | 76666 | 85809 | 162475 | SA-0315
NPT00493 | W036 | R002 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Mobilize Supply Vessel | Open | 4 | 76666 | 58910 | 135576 | SA-0398
NPT00494 | W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Run Fishing Tools | Closed | 6 | 115000 | 150582 | 265582 | SA-0399
NPT00495 | W037 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | Closed | 4 | 76666 | 106832 | 183498 | SA-0216
NPT00496 | W037 | R002 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | Closed | 4 | 76666 | 55100 | 131766 | SA-0366
NPT00497 | W037 | R002 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | In Progress | 4 | 76666 | 159831 | 236497 | SA-0206
NPT00498 | W037 | R002 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | Closed | 8 | 153333 | 204824 | 358157 | SA-0255
NPT00499 | W037 | R002 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | In Progress | 4 | 76666 | 126288 | 202954 | SA-0400
NPT00500 | W037 | R002 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Condition Hole | Closed | 12 | 230000 | 132340 | 362340 | SA-0401
NPT00501 | W037 | R002 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | Closed | 8 | 153333 | 197597 | 350930 | SA-0402
NPT00502 | W037 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | Open | 4 | 76666 | 67775 | 144441 | SA-0403
NPT00503 | W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Expedite Shipment | In Progress | 24 | 460000 | 763810 | 1223810 | SA-0404
NPT00504 | W038 | R004 | Weather | Poor Visibility | Lightning | Marine Operations | Wait on Weather | Closed | 2 | 40833 | 41869 | 82702 | SA-0405
NPT00505 | W038 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 8 | 163333 | 237483 | 400816 | SA-0406
NPT00506 | W038 | R004 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | Closed | 4 | 81666 | 183089 | 264755 | SA-0407
NPT00507 | W038 | R004 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | OEM Inspection | Closed | 6 | 122500 | 244320 | 366820 | SA-0408
NPT00508 | W038 | R004 | Logistics | Waiting on Materials | Port Congestion | Procurement | Air Freight Materials | Closed | 2 | 40833 | 42029 | 82862 | SA-0409
NPT00509 | W038 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | Open | 4 | 81666 | 55857 | 137523 | SA-0410
NPT00510 | W038 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | In Progress | 6 | 122500 | 88110 | 210610 | SA-0411
NPT00511 | W038 | R004 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | Open | 2 | 40833 | 72180 | 113013 | SA-0302
NPT00512 | W038 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Increase Mud Weight | In Progress | 4 | 81666 | 161966 | 243632 | SA-0412
NPT00513 | W038 | R004 | Weather | High Waves | Storm | Marine Operations | Resume Operations | In Progress | 4 | 81666 | 141093 | 222759 | SA-0413
NPT00514 | W038 | R004 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | In Progress | 6 | 122500 | 237410 | 359910 | SA-0047
NPT00515 | W038 | R004 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | Open | 4 | 81666 | 195140 | 276806 | SA-0325
NPT00516 | W038 | R004 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | In Progress | 6 | 122500 | 270926 | 393426 | SA-0125
NPT00517 | W038 | R004 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Increase Mud Weight | Closed | 8 | 163333 | 141844 | 305177 | SA-0414
NPT00518 | W038 | R004 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | Closed | 2 | 40833 | 53993 | 94826 | SA-0227
NPT00519 | W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 4 | 76666 | 145357 | 222023 | SA-0210
NPT00520 | W039 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | OEM Inspection | In Progress | 6 | 115000 | 137040 | 252040 | SA-0415
NPT00521 | W039 | R002 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Air Freight Materials | Closed | 6 | 115000 | 109082 | 224082 | SA-0416
NPT00522 | W039 | R002 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | Closed | 2 | 38333 | 30704 | 69037 | SA-0417
NPT00523 | W039 | R002 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Safety Briefing | Closed | 2 | 38333 | 52302 | 90635 | SA-0418
NPT00524 | W039 | R002 | Weather | Lightning | Heavy Rain | Marine Operations | Wait on Weather | In Progress | 12 | 230000 | 493028 | 723028 | SA-0419
NPT00525 | W039 | R002 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | Closed | 4 | 76666 | 63467 | 140133 | SA-0420
NPT00526 | W039 | R002 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 4 | 76666 | 47093 | 123759 | SA-0421
NPT00527 | W039 | R002 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Mobilize Supply Vessel | Closed | 2 | 38333 | 90911 | 129244 | SA-0422
NPT00528 | W039 | R002 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | Open | 12 | 230000 | 239440 | 469440 | SA-0423
NPT00529 | W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | In Progress | 6 | 115000 | 124749 | 239749 | SA-0210
NPT00530 | W039 | R002 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | Closed | 6 | 115000 | 203939 | 318939 | SA-0424
NPT00531 | W039 | R002 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | In Progress | 4 | 76666 | 44616 | 121282 | SA-0275
NPT00532 | W040 | R002 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | Closed | 2 | 38333 | 80604 | 118937 | SA-0184
NPT00533 | W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | Closed | 6 | 115000 | 215251 | 330251 | SA-0425
NPT00534 | W040 | R002 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | In Progress | 4 | 76666 | 95465 | 172131 | SA-0030
NPT00535 | W040 | R002 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | Closed | 8 | 153333 | 310650 | 463983 | SA-0350
NPT00536 | W040 | R002 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | Closed | 4 | 76666 | 129558 | 206224 | SA-0109
NPT00537 | W040 | R002 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | Closed | 12 | 230000 | 561616 | 791616 | SA-0426
NPT00538 | W040 | R002 | Weather | High Waves | Lightning | Weather | Wait on Weather | Closed | 4 | 76666 | 95669 | 172335 | SA-0427
NPT00539 | W040 | R002 | Weather | Heavy Rain | High Waves | Marine Operations | Wait on Weather | In Progress | 6 | 115000 | 220006 | 335006 | SA-0428
NPT00540 | W040 | R002 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | Open | 4 | 76666 | 41323 | 117989 | SA-0184
NPT00541 | W040 | R002 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | In Progress | 4 | 76666 | 150344 | 227010 | SA-0429
NPT00542 | W040 | R002 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | Closed | 2 | 38333 | 34861 | 73194 | SA-0393
NPT00543 | W040 | R002 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Repair Component | Closed | 2 | 38333 | 71989 | 110322 | SA-0430
NPT00544 | W040 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 8 | 153333 | 344980 | 498313 | SA-0066
NPT00545 | W040 | R002 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | Closed | 12 | 230000 | 275951 | 505951 | SA-0161
NPT00546 | W040 | R002 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | Open | 4 | 76666 | 122362 | 199028 | SA-0402
NPT00547 | W040 | R002 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | Closed | 6 | 115000 | 282556 | 397556 | SA-0031
NPT00548 | W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Closed | 4 | 76666 | 51458 | 128124 | SA-0273
NPT00549 | W040 | R002 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | Open | 6 | 115000 | 192955 | 307955 | SA-0431
NPT00550 | W040 | R002 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | Open | 6 | 115000 | 74637 | 189637 | SA-0302
NPT00551 | W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Open | 18 | 345000 | 503296 | 848296 | SA-0432
NPT00552 | W040 | R002 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 8 | 153333 | 272919 | 426252 | SA-0421
NPT00553 | W041 | R002 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | Open | 6 | 115000 | 247320 | 362320 | SA-0058
NPT00554 | W041 | R002 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Air Freight Materials | Closed | 8 | 153333 | 317647 | 470980 | SA-0433
NPT00555 | W041 | R002 | Weather | Lightning | Lightning | Weather | Wait on Weather | Closed | 8 | 153333 | 183394 | 336727 | SA-0051
NPT00556 | W041 | R002 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Condition Hole | In Progress | 8 | 153333 | 210689 | 364022 | SA-0434
NPT00557 | W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Increase Mud Weight | Closed | 8 | 153333 | 214639 | 367972 | SA-0435
NPT00558 | W041 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Closed | 4 | 76666 | 58805 | 135471 | SA-0436
NPT00559 | W041 | R002 | Drilling | Well Control | Unexpected Pressure | Operator | Increase Mud Weight | Closed | 4 | 76666 | 102592 | 179258 | SA-0437
NPT00560 | W041 | R002 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Air Freight Materials | Closed | 2 | 38333 | 33873 | 72206 | SA-0438
NPT00561 | W041 | R002 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | Closed | 2 | 38333 | 28172 | 66505 | SA-0407
NPT00562 | W041 | R002 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Condition Hole | Closed | 2 | 38333 | 71728 | 110061 | SA-0439
NPT00563 | W041 | R002 | Weather | Heavy Rain | High Waves | Weather | Resume Operations | Closed | 2 | 38333 | 71077 | 109410 | SA-0440
NPT00564 | W041 | R002 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | In Progress | 2 | 38333 | 81289 | 119622 | SA-0441
NPT00565 | W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Condition Hole | In Progress | 18 | 345000 | 390612 | 735612 | SA-0442
NPT00566 | W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | Closed | 2 | 38333 | 43647 | 81980 | SA-0147
NPT00567 | W042 | R004 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | Closed | 6 | 122500 | 254150 | 376650 | SA-0441
NPT00568 | W042 | R004 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | Closed | 8 | 163333 | 191207 | 354540 | SA-0007
NPT00569 | W042 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | Closed | 2 | 40833 | 49540 | 90373 | SA-0348
NPT00570 | W042 | R004 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | In Progress | 18 | 367500 | 390071 | 757571 | SA-0031
NPT00571 | W042 | R004 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | Open | 6 | 122500 | 159958 | 282458 | SA-0443
NPT00572 | W042 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Closed | 6 | 122500 | 203927 | 326427 | SA-0017
NPT00573 | W042 | R004 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | Closed | 2 | 40833 | 23324 | 64157 | SA-0424
NPT00574 | W042 | R004 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 4 | 81666 | 64325 | 145991 | SA-0132
NPT00575 | W043 | R002 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Mobilize Supply Vessel | Open | 4 | 76666 | 72518 | 149184 | SA-0444
NPT00576 | W043 | R002 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 6 | 115000 | 248026 | 363026 | SA-0048
NPT00577 | W043 | R002 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Open | 8 | 153333 | 86363 | 239696 | SA-0130
NPT00578 | W043 | R002 | Weather | Lightning | Heavy Rain | Marine Operations | Resume Operations | Closed | 4 | 76666 | 61263 | 137929 | SA-0445
NPT00579 | W043 | R002 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | Closed | 2 | 38333 | 84686 | 123019 | SA-0041
NPT00580 | W043 | R002 | Drilling | Fishing Operation | Bit Wear | Operator | Adjust Drilling Parameters | In Progress | 2 | 38333 | 49722 | 88055 | SA-0446
NPT00581 | W043 | R002 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | Closed | 2 | 38333 | 62593 | 100926 | SA-0429
NPT00582 | W043 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Adjust Drilling Parameters | Closed | 2 | 38333 | 29667 | 68000 | SA-0447
NPT00583 | W043 | R002 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | In Progress | 2 | 38333 | 35940 | 74273 | SA-0180
NPT00584 | W043 | R002 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | OEM Inspection | Closed | 2 | 38333 | 37321 | 75654 | SA-0448
NPT00585 | W043 | R002 | Weather | Poor Visibility | Lightning | Weather | Suspend Operations | Open | 6 | 115000 | 236890 | 351890 | SA-0449
NPT00586 | W043 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | Open | 6 | 115000 | 178383 | 293383 | SA-0450
NPT00587 | W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Expedite Shipment | Closed | 6 | 115000 | 199093 | 314093 | SA-0451
NPT00588 | W043 | R002 | Drilling | Well Control | Unexpected Pressure | Operator | Condition Hole | Closed | 4 | 76666 | 39001 | 115667 | SA-0452
NPT00589 | W043 | R002 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Replace Equipment | Closed | 18 | 345000 | 418285 | 763285 | SA-0453
NPT00590 | W043 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | Closed | 2 | 38333 | 57717 | 96050 | SA-0454
NPT00591 | W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Expedite Shipment | Closed | 12 | 230000 | 403320 | 633320 | SA-0455
NPT00592 | W043 | R002 | Drilling | Stuck Pipe | Formation Instability | Operator | Condition Hole | Closed | 6 | 115000 | 247949 | 362949 | SA-0456
NPT00593 | W044 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | Closed | 2 | 40000 | 25031 | 65031 | SA-0457
NPT00594 | W044 | R003 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | In Progress | 18 | 360000 | 773348 | 1133348 | SA-0426
NPT00595 | W044 | R003 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | Run Fishing Tools | Closed | 6 | 120000 | 106088 | 226088 | SA-0458
NPT00596 | W044 | R003 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | Expedite Shipment | Closed | 2 | 40000 | 88171 | 128171 | SA-0459
NPT00597 | W044 | R003 | Drilling | Bit Failure | Formation Instability | Operator | Increase Mud Weight | In Progress | 2 | 40000 | 85034 | 125034 | SA-0460
NPT00598 | W044 | R003 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 80000 | 130288 | 210288 | SA-0222
NPT00599 | W044 | R003 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Expedite Shipment | Closed | 2 | 40000 | 51341 | 91341 | SA-0461
NPT00600 | W044 | R003 | Weather | Strong Wind | Storm | Weather | Suspend Operations | Closed | 2 | 40000 | 61338 | 101338 | SA-0319
NPT00601 | W044 | R003 | Weather | High Waves | Lightning | Weather | Resume Operations | Closed | 8 | 160000 | 339780 | 499780 | SA-0013
NPT00602 | W044 | R003 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Increase Mud Weight | Closed | 8 | 160000 | 185853 | 345853 | SA-0462
NPT00603 | W044 | R003 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | Closed | 6 | 120000 | 228519 | 348519 | SA-0129
NPT00604 | W044 | R003 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Air Freight Materials | In Progress | 4 | 80000 | 63153 | 143153 | SA-0463
NPT00605 | W045 | R004 | Weather | Poor Visibility | Strong Wind | Marine Operations | Suspend Operations | Closed | 18 | 367500 | 851850 | 1219350 | SA-0464
NPT00606 | W045 | R004 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | Open | 2 | 40833 | 55477 | 96310 | SA-0465
NPT00607 | W045 | R004 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Closed | 8 | 163333 | 376966 | 540299 | SA-0361
NPT00608 | W045 | R004 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 2 | 40833 | 67011 | 107844 | SA-0466
NPT00609 | W045 | R004 | Weather | Heavy Rain | Heavy Rain | Weather | Resume Operations | Closed | 12 | 245000 | 133994 | 378994 | SA-0467
NPT00610 | W045 | R004 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | Closed | 4 | 81666 | 186247 | 267913 | SA-0468
NPT00611 | W045 | R004 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | Closed | 6 | 122500 | 64878 | 187378 | SA-0275
NPT00612 | W045 | R004 | Weather | Lightning | Lightning | Weather | Suspend Operations | Closed | 2 | 40833 | 40713 | 81546 | SA-0056
NPT00613 | W045 | R004 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | Closed | 2 | 40833 | 98596 | 139429 | SA-0423
NPT00614 | W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 24 | 490000 | 1044504 | 1534504 | SA-0108
NPT00615 | W046 | R003 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | Open | 8 | 160000 | 137440 | 297440 | SA-0052
NPT00616 | W046 | R003 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Expedite Shipment | Closed | 12 | 240000 | 374455 | 614455 | SA-0469
NPT00617 | W046 | R003 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | Closed | 4 | 80000 | 174948 | 254948 | SA-0260
NPT00618 | W046 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Mobilize Supply Vessel | Closed | 6 | 120000 | 270341 | 390341 | SA-0470
NPT00619 | W046 | R003 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | Closed | 8 | 160000 | 306975 | 466975 | SA-0471
NPT00620 | W046 | R003 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | In Progress | 8 | 160000 | 96020 | 256020 | SA-0472
NPT00621 | W046 | R003 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | Closed | 12 | 240000 | 397476 | 637476 | SA-0423
NPT00622 | W046 | R003 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | Open | 4 | 80000 | 89940 | 169940 | SA-0473
NPT00623 | W046 | R003 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | Closed | 6 | 120000 | 86494 | 206494 | SA-0474
NPT00624 | W046 | R003 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | Closed | 2 | 40000 | 98735 | 138735 | SA-0304
NPT00625 | W046 | R003 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | Closed | 4 | 80000 | 199919 | 279919 | SA-0314
NPT00626 | W046 | R003 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | In Progress | 6 | 120000 | 250242 | 370242 | SA-0064
NPT00627 | W046 | R003 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | Closed | 4 | 80000 | 117922 | 197922 | SA-0221
NPT00628 | W046 | R003 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | Open | 8 | 160000 | 218432 | 378432 | SA-0475
NPT00629 | W046 | R003 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | Closed | 6 | 120000 | 81245 | 201245 | SA-0137
NPT00630 | W046 | R003 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 4 | 80000 | 91574 | 171574 | SA-0476
NPT00631 | W047 | R004 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Condition Hole | In Progress | 4 | 81666 | 77971 | 159637 | SA-0477
NPT00632 | W047 | R004 | Drilling | Bit Failure | Bit Wear | Operator | Increase Mud Weight | In Progress | 2 | 40833 | 84650 | 125483 | SA-0478
NPT00633 | W047 | R004 | Weather | Strong Wind | Storm | Weather | Wait on Weather | Closed | 2 | 40833 | 73113 | 113946 | SA-0479
NPT00634 | W047 | R004 | Drilling | Hole Cleaning | Differential Sticking | Operator | Run Fishing Tools | Closed | 8 | 163333 | 205525 | 368858 | SA-0480
NPT00635 | W047 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | In Progress | 8 | 163333 | 392949 | 556282 | SA-0338
NPT00636 | W047 | R004 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | Closed | 4 | 81666 | 77527 | 159193 | SA-0374
NPT00637 | W047 | R004 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | Closed | 8 | 163333 | 334485 | 497818 | SA-0237
NPT00638 | W047 | R004 | Personnel | Crew Change | Crew Rotation | Rig Management | Medical Clearance | Closed | 18 | 367500 | 236304 | 603804 | SA-0481
NPT00639 | W047 | R004 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | Closed | 4 | 81666 | 190813 | 272479 | SA-0417
NPT00640 | W047 | R004 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 8 | 163333 | 248690 | 412023 | SA-0482
NPT00641 | W047 | R004 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 4 | 81666 | 146922 | 228588 | SA-0296
NPT00642 | W047 | R004 | Drilling | Well Control | Bit Wear | Directional Drilling | Increase Mud Weight | Closed | 6 | 122500 | 196965 | 319465 | SA-0483
NPT00643 | W047 | R004 | Drilling | Lost Circulation | Unexpected Pressure | Operator | Run Fishing Tools | In Progress | 2 | 40833 | 59674 | 100507 | SA-0484
NPT00644 | W048 | R002 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | Medical Clearance | Closed | 2 | 38333 | 43207 | 81540 | SA-0485
NPT00645 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 2 | 38333 | 46414 | 84747 | SA-0065
NPT00646 | W048 | R002 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | Closed | 4 | 76666 | 109609 | 186275 | SA-0192
NPT00647 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 8 | 153333 | 295021 | 448354 | SA-0065
NPT00648 | W048 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | In Progress | 4 | 76666 | 129373 | 206039 | SA-0454
NPT00649 | W048 | R002 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | Closed | 18 | 345000 | 423942 | 768942 | SA-0138
NPT00650 | W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | In Progress | 8 | 153333 | 294473 | 447806 | SA-0036
NPT00651 | W048 | R002 | Weather | High Waves | High Waves | Weather | Wait on Weather | Closed | 6 | 115000 | 70319 | 185319 | SA-0486
NPT00652 | W048 | R002 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Condition Hole | Closed | 8 | 153333 | 289177 | 442510 | SA-0487
NPT00653 | W048 | R002 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | In Progress | 4 | 76666 | 130194 | 206860 | SA-0420
NPT00654 | W048 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 6 | 115000 | 272813 | 387813 | SA-0488
NPT00655 | W048 | R002 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 6 | 115000 | 241901 | 356901 | SA-0132
NPT00656 | W048 | R002 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | Closed | 4 | 76666 | 85043 | 161709 | SA-0364
NPT00657 | W048 | R002 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 6 | 115000 | 129108 | 244108 | SA-0048
NPT00658 | W049 | R003 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | Mobilize Supply Vessel | In Progress | 4 | 80000 | 121829 | 201829 | SA-0489
NPT00659 | W049 | R003 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Run Fishing Tools | Closed | 18 | 360000 | 314096 | 674096 | SA-0490
NPT00660 | W049 | R003 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | Mobilize Supply Vessel | Closed | 4 | 80000 | 183601 | 263601 | SA-0491
NPT00661 | W049 | R003 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | Open | 8 | 160000 | 279871 | 439871 | SA-0400
NPT00662 | W049 | R003 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | OEM Inspection | Closed | 6 | 120000 | 270679 | 390679 | SA-0492
NPT00663 | W049 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | In Progress | 6 | 120000 | 60226 | 180226 | SA-0457
NPT00664 | W049 | R003 | Drilling | Well Control | Bit Wear | Operator | Condition Hole | Closed | 2 | 40000 | 85472 | 125472 | SA-0493
NPT00665 | W049 | R003 | Weather | Heavy Rain | Strong Wind | Weather | Wait on Weather | Open | 6 | 120000 | 143523 | 263523 | SA-0494
NPT00666 | W049 | R003 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Condition Hole | Closed | 6 | 120000 | 294858 | 414858 | SA-0495
NPT00667 | W050 | R004 | Drilling | Lost Circulation | Bit Wear | Operator | Run Fishing Tools | Open | 8 | 163333 | 405188 | 568521 | SA-0496
NPT00668 | W050 | R004 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Mobilize Supply Vessel | Closed | 6 | 122500 | 174028 | 296528 | SA-0497
NPT00669 | W050 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | Closed | 2 | 40833 | 91284 | 132117 | SA-0498
NPT00670 | W050 | R004 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | Open | 12 | 245000 | 512335 | 757335 | SA-0431
NPT00671 | W050 | R004 | Weather | High Waves | Storm | Weather | Resume Operations | Closed | 4 | 81666 | 110150 | 191816 | SA-0499
NPT00672 | W050 | R004 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 6 | 122500 | 116840 | 239340 | SA-0500
NPT00673 | W050 | R004 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 12 | 245000 | 368627 | 613627 | SA-0501
NPT00674 | W050 | R004 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | Closed | 6 | 122500 | 126592 | 249092 | SA-0010
NPT00675 | W050 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | Closed | 4 | 81666 | 122727 | 204393 | SA-0425
NPT00676 | W050 | R004 | Drilling | Stuck Pipe | Formation Instability | Operator | Increase Mud Weight | Closed | 8 | 163333 | 182981 | 346314 | SA-0502
NPT00677 | W050 | R004 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | Closed | 6 | 122500 | 172937 | 295437 | SA-0248

## Data_Quality
Check | Value | Status
NPT rows | 677 | PASS
Strategic Action IDs | 502 | PASS
Duplicate NPT IDs | 0 | PASS
Missing Responsible Party | 0 | PASS
Missing Corrective Action | 0 | PASS
Economic Reconciliation | 0 | PASS
Target Savings Non-Negative | 0 | PASS
Target NPT Non-Negative | 0 | PASS