## Executive_Summary
Metric | Value
NPT Events | 677
NPT Hours | 4008
Direct NPT Cost USD | 79204408
Deferred Cost USD | 118945770
Total Economic Impact USD | 198150178
Validated Target Savings USD | 30825850
Validated Conservative Savings USD | 15412920
Validated Stretch Savings USD | 46238770
Target Savings % | 15.5568
Unique Wells | 50
Unique Rigs | 4
Drilling Days | 666
Total Footage ft | 952078.8
Average ROP ft/hr | 33.6733
Cost per Foot USD | 687.6662
NPT Hours per Drilling Day | 6.018
Data Quality Status | PASS

## KPI_Executive
KPI_ID | KPI_Name | Value | Unit
KPI001 | NPT Events | 677 | events
KPI002 | NPT Hours | 4008 | hours
KPI003 | Direct NPT Cost | 79204408 | USD
KPI004 | Deferred Cost | 118945770 | USD
KPI005 | Total Economic Impact | 198150178 | USD
KPI006 | Validated Target Savings | 30825850 | USD
KPI007 | Validated Conservative Savings | 15412920 | USD
KPI008 | Validated Stretch Savings | 46238770 | USD
KPI009 | Target Savings % of Impact | 15.5568 | %
KPI010 | Unique Wells | 50 | wells
KPI011 | Unique Rigs | 4 | rigs
KPI012 | Drilling Days | 666 | days
KPI013 | Total Footage | 952078.8 | ft
KPI014 | Average ROP | 33.6733 | ft/hr
KPI015 | Total Drilling Cost | 654712456.04 | USD
KPI016 | Cost per Foot | 687.6662 | USD/ft
KPI017 | NPT Hours per Drilling Day | 6.018 | hr/day
KPI018 | NPT Cost per NPT Hour | 19761.5788 | USD/hr

## KPI_Framework
KPI_ID | KPI_Name | Definition | Direction | Frequency | Owner
KPI001 | NPT Events | COUNT(NPT_ID) | Lower is better | Daily | Drilling Manager
KPI002 | NPT Hours | SUM(Duration_hr) | Lower is better | Daily | Drilling Manager
KPI003 | Direct NPT Cost | SUM(Cost_USD) | Lower is better | Daily | Operations Manager
KPI004 | Deferred Cost | SUM(Deferred_Cost_USD) | Lower is better | Weekly | Operations Manager
KPI005 | Total Economic Impact | SUM(Total_Impact_USD) | Lower is better | Weekly | Operations Manager
KPI006 | Target Savings | Validated Stage 2G.10.1 baseline | Higher is better | Monthly | Performance Manager
KPI007 | Average ROP | AVG(ROP_ft_hr) | Higher is better | Daily | Drilling Engineer
KPI008 | Cost per Foot | SUM(Daily_Cost_USD)/SUM(Daily_Footage_ft) | Lower is better | Daily | Drilling Engineer
KPI009 | NPT Hours per Drilling Day | SUM(Duration_hr)/COUNT(DISTINCT Date) | Lower is better | Daily | Drilling Manager
KPI010 | Savings Realization | Realized Savings / Target Savings | Higher is better | Monthly | Performance Manager

## KPI_Rig
Rig_ID | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Wells | Drilling_Days | Footage_ft | Avg_ROP_ft_hr | Drilling_Cost_USD | NPT_Hours_per_Drilling_Day | Cost_per_Foot_USD | Target_Savings_USD | Target_Savings_pct | Performance_Rank
R002 | 282 | 1610 | 30858241 | 45702204 | 76560445 | 20 | 442 | 383889.4 | 33.5415 | 258293934.08 | 3.6425 | 672.8342 | 11910364.2365 | 15.5568 | 1
R004 | 199 | 1186 | 24214105 | 37256294 | 61470399 | 16 | 318 | 301996.1 | 33.9592 | 211397181.03 | 3.7296 | 699.9997 | 9562834.2005 | 15.5568 | 2
R003 | 116 | 694 | 13880000 | 20516458 | 34396458 | 8 | 196 | 154500.2 | 33.6875 | 107400401.4 | 3.5408 | 695.1473 | 5350992.1896 | 15.5568 | 3
R001 | 80 | 518 | 10252062 | 15470814 | 25722876 | 6 | 174 | 111693.1 | 33.3442 | 77620939.53 | 2.977 | 694.9484 | 4001659.3735 | 15.5568 | 4

## KPI_Well
Well_ID | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Rigs | Drilling_Days | Footage_ft | Avg_ROP_ft_hr | Drilling_Cost_USD | NPT_Hours_per_Drilling_Day | Cost_per_Foot_USD | Target_Savings_USD | Performance_Rank
W007 | 16 | 128 | 2533329 | 4282582 | 6815911 | 1 | 33 | 21584.9 | 34.2727 | 14628770.85 | 3.8788 | 677.7317 | 1060338.4373 | 1
W040 | 21 | 130 | 2491660 | 4128450 | 6620110 | 1 | 28 | 18509.8 | 34.2754 | 12137950.94 | 4.6429 | 655.7581 | 1029878.0445 | 2
W019 | 13 | 114 | 2280000 | 3281717 | 5561717 | 1 | 25 | 15697.8 | 33.8384 | 10717808.92 | 4.56 | 682.7587 | 865225.8389 | 3
W036 | 19 | 108 | 2069994 | 3341514 | 5411508 | 1 | 25 | 16733 | 33.9652 | 11091091.98 | 4.32 | 662.8275 | 841858.1077 | 4
W003 | 13 | 88 | 1796663 | 3429015 | 5225678 | 1 | 28 | 18763 | 34.6875 | 12784056.41 | 3.1429 | 681.3439 | 812948.8845 | 5
W011 | 16 | 104 | 2123328 | 3064293 | 5187621 | 1 | 36 | 22974 | 33.9056 | 16212768.29 | 2.8889 | 705.7007 | 807028.4287 | 6
W046 | 16 | 102 | 2040000 | 2992158 | 5032158 | 1 | 29 | 19388.9 | 34.8452 | 12933266.13 | 3.5172 | 667.0449 | 782843.3426 | 7
W013 | 20 | 96 | 1920000 | 2963822 | 4883822 | 1 | 36 | 22553.7 | 32.7356 | 16182108.87 | 2.6667 | 717.4924 | 759766.9905 | 8
W023 | 14 | 84 | 1714995 | 3113218 | 4828213 | 1 | 32 | 21362.9 | 34.8016 | 14445134.24 | 2.625 | 676.1785 | 751116.0031 | 9
W010 | 16 | 106 | 2031661 | 2703200 | 4734861 | 1 | 29 | 18581.1 | 33.2452 | 12551454.43 | 3.6552 | 675.4958 | 736593.4082 | 10
W009 | 15 | 100 | 1979163 | 2690209 | 4669372 | 1 | 27 | 16290.9 | 31.3663 | 11956185.14 | 3.7037 | 733.918 | 726405.4079 | 11
W001 | 19 | 88 | 1796660 | 2808881 | 4605541 | 1 | 26 | 16495 | 32.8035 | 12003516.78 | 3.3846 | 727.7064 | 716475.3394 | 12
W020 | 20 | 90 | 1800000 | 2765483 | 4565483 | 1 | 26 | 17159.9 | 34.2012 | 11719190.56 | 3.4615 | 682.9405 | 710243.5918 | 13
W045 | 10 | 80 | 1633331 | 2920236 | 4553567 | 1 | 25 | 15766.1 | 32.642 | 11426115.78 | 3.2 | 724.7268 | 708389.8421 | 14
W002 | 13 | 88 | 1741664 | 2804697 | 4546361 | 1 | 28 | 18303.9 | 32.635 | 12906810.88 | 3.1429 | 705.1399 | 707268.8183 | 15
W021 | 16 | 94 | 1801664 | 2704639 | 4506303 | 1 | 30 | 19096.8 | 33.28 | 13145292.25 | 3.1333 | 688.3505 | 701037.0706 | 16
W026 | 11 | 90 | 1837497 | 2615327 | 4452824 | 1 | 31 | 20855 | 34.7661 | 14459113.13 | 2.9032 | 693.3164 | 692717.4433 | 17
W015 | 14 | 76 | 1520000 | 2865282 | 4385282 | 1 | 25 | 16635.9 | 34.4632 | 11401518.43 | 3.04 | 685.3563 | 682210.0616 | 18
W043 | 18 | 94 | 1801662 | 2548737 | 4350399 | 1 | 30 | 19217.9 | 33.4967 | 12906481.26 | 3.1333 | 671.5865 | 676783.379 | 19
W032 | 15 | 86 | 1755829 | 2495861 | 4251690 | 1 | 31 | 20171.8 | 34.539 | 13999009.8 | 2.7742 | 693.9891 | 661427.4058 | 20
W033 | 16 | 90 | 1724995 | 2518455 | 4243450 | 1 | 25 | 16706.9 | 35.1348 | 10913961.71 | 3.6 | 653.2607 | 660145.5245 | 21
W006 | 15 | 84 | 1609994 | 2621287 | 4231281 | 1 | 30 | 20616.1 | 35.1587 | 13143205.35 | 2.8 | 637.5214 | 658252.4161 | 22
W048 | 14 | 86 | 1648329 | 2560594 | 4208923 | 1 | 30 | 17931 | 32.5013 | 12603788.4 | 2.8667 | 702.9049 | 654774.2241 | 23
W028 | 15 | 90 | 1724995 | 2418055 | 4143050 | 1 | 33 | 21527.8 | 33.4239 | 14462989.11 | 2.7273 | 671.8285 | 644526.4856 | 24
W030 | 15 | 90 | 1724996 | 2412390 | 4137386 | 1 | 33 | 20756.7 | 32.873 | 14266132.13 | 2.7273 | 687.3025 | 643645.3478 | 25
W047 | 13 | 78 | 1592495 | 2325588 | 3918083 | 1 | 25 | 17327 | 35.1512 | 11659169.74 | 3.12 | 672.8903 | 609528.7931 | 26
W050 | 11 | 74 | 1510831 | 2383689 | 3894520 | 1 | 22 | 15197 | 36.1468 | 10027597.8 | 3.3636 | 659.8406 | 605863.1416 | 27
W018 | 14 | 88 | 1796662 | 2059142 | 3855804 | 1 | 26 | 18151.7 | 34.8804 | 12308393.58 | 3.3846 | 678.0849 | 599840.1663 | 28
W034 | 12 | 74 | 1464578 | 2192968 | 3657546 | 1 | 28 | 17777 | 33.6807 | 12356618.88 | 2.6429 | 695.0902 | 568997.5427 | 29
W035 | 12 | 92 | 1840000 | 1755897 | 3595897 | 1 | 33 | 20790.7 | 33.3033 | 14687778.32 | 2.7879 | 706.4591 | 559406.9239 | 30
W038 | 15 | 68 | 1388328 | 2167309 | 3555637 | 1 | 34 | 21390.1 | 33.4735 | 15149998.79 | 2 | 708.2715 | 553143.7515 | 31
W041 | 14 | 76 | 1456662 | 2055484 | 3512146 | 1 | 25 | 15201.9 | 32.0492 | 10742273.1 | 3.04 | 706.6402 | 546377.9385 | 32
W022 | 13 | 74 | 1464580 | 1977792 | 3442372 | 1 | 30 | 19737.2 | 33.7763 | 13405027.07 | 2.4667 | 679.1757 | 535523.3288 | 33
W044 | 12 | 64 | 1280000 | 2137944 | 3417944 | 1 | 31 | 19496.2 | 33.1719 | 13817299.17 | 2.0645 | 708.7176 | 531723.1108 | 34
W029 | 14 | 70 | 1341662 | 2007400 | 3349062 | 1 | 28 | 18474 | 33.8211 | 12278777.35 | 2.5 | 664.6518 | 521007.2678 | 35
W024 | 12 | 68 | 1303329 | 1939009 | 3242338 | 1 | 32 | 20685.1 | 33.7209 | 13722096.47 | 2.125 | 663.3807 | 504404.4161 | 36
W012 | 11 | 64 | 1306664 | 1927076 | 3233740 | 1 | 29 | 18457.2 | 33.4397 | 13227460.52 | 2.2069 | 716.6559 | 503066.8414 | 37
W027 | 10 | 66 | 1264997 | 1957712 | 3222709 | 1 | 34 | 22391.9 | 34.2441 | 14655693.1 | 1.9412 | 654.5087 | 501350.7696 | 38
W037 | 9 | 72 | 1379996 | 1814397 | 3194393 | 1 | 32 | 20535.1 | 33.7097 | 13749815.59 | 2.25 | 669.5763 | 496945.7028 | 39
W005 | 13 | 64 | 1226662 | 1917071 | 3143733 | 1 | 27 | 16853.1 | 32.0207 | 11873271.59 | 2.3704 | 704.5156 | 489064.622 | 40
W039 | 13 | 70 | 1341663 | 1781728 | 3123391 | 1 | 29 | 19931 | 35.1524 | 12786789.7 | 2.4138 | 641.5528 | 485900.0553 | 41
W031 | 11 | 60 | 1149994 | 1882761 | 3032755 | 1 | 31 | 20249.1 | 33.7687 | 13420380.1 | 1.9355 | 662.7643 | 471799.9835 | 42
W049 | 9 | 60 | 1200000 | 1754155 | 2954155 | 1 | 36 | 22777.1 | 33.4886 | 15941431 | 1.6667 | 699.8885 | 459572.3296 | 43
W025 | 11 | 54 | 1102497 | 1756149 | 2858646 | 1 | 26 | 15854.2 | 32.405 | 11627789.13 | 2.0769 | 733.4201 | 444714.1743 | 44
W017 | 11 | 54 | 1068748 | 1522566 | 2591314 | 1 | 28 | 17999.2 | 34.0668 | 12367526.71 | 1.9286 | 687.1154 | 403125.8386 | 45
W016 | 10 | 50 | 1020830 | 1523000 | 2543830 | 1 | 29 | 18696.2 | 33.2086 | 13214359.14 | 1.7241 | 706.7938 | 395738.8421 | 46
W042 | 8 | 52 | 1061665 | 1336502 | 2398167 | 1 | 28 | 18254.8 | 34.3746 | 12572413.42 | 1.8571 | 688.7182 | 373078.3235 | 47
W004 | 11 | 52 | 996663 | 1337831 | 2334494 | 1 | 33 | 20231.9 | 33.7436 | 13777407.37 | 1.5758 | 680.9745 | 363172.8348 | 48
W014 | 8 | 38 | 775830 | 1331008 | 2106838 | 1 | 35 | 22280.1 | 32.6689 | 16280284.48 | 1.0857 | 730.7097 | 327756.8197 | 49
W008 | 10 | 40 | 766663 | 1051490 | 1818153 | 1 | 32 | 19659.2 | 31.3706 | 14065082.15 | 1.25 | 715.4453 | 282846.6379 | 50

## KPI_Root_Cause
NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Wells | Rigs | Impact_Share_pct | Target_Savings_USD | Priority
Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | 6 | 50 | 1009582 | 1789153 | 2798735 | 6 | 3 | 1.4124 | 435393.9329 | CRITICAL
Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | 4 | 44 | 876666 | 1780955 | 2657621 | 4 | 3 | 1.3412 | 413441.0937 | CRITICAL
Weather | Poor Visibility | Heavy Rain | Weather | 5 | 46 | 906666 | 1675572 | 2582238 | 5 | 3 | 1.3032 | 401713.9023 | CRITICAL
Mechanical | BOP Repair | Equipment Wear | Maintenance Team | 5 | 48 | 923332 | 1450100 | 2373432 | 5 | 2 | 1.1978 | 369230.3462 | CRITICAL
Drilling | Fishing Operation | Formation Instability | Operator | 7 | 42 | 829581 | 1528764 | 2358345 | 7 | 4 | 1.1902 | 366883.29 | CRITICAL
Weather | Poor Visibility | Strong Wind | Marine Operations | 3 | 34 | 685000 | 1588104 | 2273104 | 3 | 3 | 1.1472 | 353622.5082 | CRITICAL
Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | 5 | 50 | 984166 | 1229748 | 2213914 | 5 | 3 | 1.1173 | 344414.4313 | CRITICAL
Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | 5 | 42 | 820000 | 1392195 | 2212195 | 5 | 2 | 1.1164 | 344147.0098 | CRITICAL
Drilling | Lost Circulation | Formation Instability | Directional Drilling | 5 | 48 | 954998 | 1220391 | 2175389 | 5 | 3 | 1.0978 | 338421.1697 | CRITICAL
Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | 3 | 34 | 682916 | 1409351 | 2092267 | 3 | 3 | 1.0559 | 325490.0367 | CRITICAL
Drilling | Bit Failure | Bit Wear | Mud Engineering | 3 | 38 | 753333 | 1251096 | 2004429 | 3 | 2 | 1.0116 | 311825.2444 | CRITICAL
Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | 7 | 38 | 753332 | 1249861 | 2003193 | 6 | 3 | 1.0109 | 311632.9622 | CRITICAL
Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | 3 | 38 | 765833 | 1234524 | 2000357 | 3 | 2 | 1.0095 | 311191.7711 | CRITICAL
Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | 3 | 30 | 601249 | 1353499 | 1954748 | 3 | 2 | 0.9865 | 304096.4648 | CRITICAL
Weather | Strong Wind | Strong Wind | Marine Operations | 8 | 40 | 789164 | 1106026 | 1895190 | 8 | 4 | 0.95644 | 294831.1389 | CRITICAL
Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | 4 | 34 | 660833 | 1223235 | 1884068 | 4 | 3 | 0.95083 | 293100.9103 | CRITICAL
Weather | Heavy Rain | Heavy Rain | Weather | 5 | 42 | 837499 | 1007895 | 1845394 | 4 | 3 | 0.93131 | 287084.469 | CRITICAL
Weather | Lightning | Heavy Rain | Marine Operations | 4 | 40 | 774166 | 1046611 | 1820777 | 4 | 2 | 0.91889 | 283254.8487 | CRITICAL
Weather | Heavy Rain | Strong Wind | Marine Operations | 3 | 32 | 618333 | 1063440 | 1681773 | 3 | 2 | 0.84874 | 261630.2582 | CRITICAL
Weather | Lightning | Lightning | Weather | 9 | 36 | 706247 | 974259 | 1680506 | 8 | 3 | 0.8481 | 261433.1534 | CRITICAL
Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | 6 | 34 | 672499 | 982945 | 1655444 | 5 | 3 | 0.83545 | 257534.3053 | CRITICAL
Weather | Heavy Rain | Storm | Weather | 3 | 34 | 686666 | 963834 | 1650500 | 3 | 2 | 0.83295 | 256765.1765 | CRITICAL
Weather | Lightning | High Waves | Weather | 2 | 36 | 710000 | 933604 | 1643604 | 2 | 2 | 0.82947 | 255692.3788 | CRITICAL
Weather | Lightning | Lightning | Marine Operations | 7 | 30 | 598749 | 1024066 | 1622815 | 7 | 4 | 0.81898 | 252458.2732 | CRITICAL
Drilling | Fishing Operation | Differential Sticking | Directional Drilling | 3 | 32 | 618333 | 999052 | 1617385 | 3 | 2 | 0.81624 | 251613.5383 | CRITICAL
Logistics | Waiting on Materials | Material Shortage | Procurement | 5 | 32 | 620832 | 989870 | 1610702 | 5 | 2 | 0.81287 | 250573.8766 | CRITICAL
Weather | Poor Visibility | Heavy Rain | Marine Operations | 4 | 32 | 643332 | 956728 | 1600060 | 4 | 3 | 0.8075 | 248918.3207 | CRITICAL
Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | 5 | 32 | 639582 | 929609 | 1569191 | 5 | 4 | 0.79192 | 244116.0885 | CRITICAL
Drilling | Well Control | Bit Wear | Directional Drilling | 3 | 26 | 518333 | 1045460 | 1563793 | 3 | 2 | 0.7892 | 243276.3318 | CRITICAL
Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | 3 | 28 | 551666 | 1009356 | 1561022 | 3 | 2 | 0.7878 | 242845.2525 | CRITICAL
Drilling | Well Control | Bit Wear | Mud Engineering | 3 | 26 | 521666 | 1012986 | 1534652 | 3 | 2 | 0.77449 | 238742.9213 | CRITICAL
Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | 6 | 30 | 594998 | 924767 | 1519765 | 5 | 3 | 0.76698 | 236426.9788 | CRITICAL
Drilling | Bit Failure | Differential Sticking | Directional Drilling | 5 | 30 | 586665 | 930846 | 1517511 | 5 | 2 | 0.76584 | 236076.3282 | CRITICAL
Drilling | Hole Cleaning | Bit Wear | Operator | 6 | 36 | 714166 | 768741 | 1482907 | 5 | 2 | 0.74838 | 230693.0491 | CRITICAL
Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | 2 | 24 | 480000 | 995042 | 1475042 | 2 | 1 | 0.74441 | 229469.5059 | CRITICAL
Drilling | Stuck Pipe | Bit Wear | Mud Engineering | 3 | 36 | 695000 | 730621 | 1425621 | 3 | 2 | 0.71946 | 221781.174 | CRITICAL
Drilling | Stuck Pipe | Unexpected Pressure | Operator | 4 | 30 | 579999 | 830678 | 1410677 | 4 | 2 | 0.71192 | 219456.3641 | CRITICAL
Weather | High Waves | Strong Wind | Marine Operations | 2 | 30 | 605000 | 781140 | 1386140 | 2 | 2 | 0.69954 | 215639.1892 | CRITICAL
Drilling | Lost Circulation | Formation Instability | Mud Engineering | 6 | 30 | 586665 | 798737 | 1385402 | 6 | 3 | 0.69917 | 215524.3799 | CRITICAL
Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | 3 | 28 | 541666 | 837609 | 1379275 | 3 | 2 | 0.69608 | 214571.2141 | CRITICAL
Logistics | Delayed Helicopter | Customs Clearance | Procurement | 2 | 26 | 498333 | 854721 | 1353054 | 2 | 1 | 0.68284 | 210492.0625 | CRITICAL
Drilling | Lost Circulation | Formation Instability | Operator | 3 | 22 | 440000 | 882159 | 1322159 | 2 | 1 | 0.66725 | 205685.7855 | CRITICAL
Weather | Heavy Rain | Lightning | Marine Operations | 4 | 20 | 400832 | 836814 | 1237646 | 4 | 2 | 0.6246 | 192538.2573 | CRITICAL
Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | 5 | 20 | 397498 | 832915 | 1230413 | 5 | 4 | 0.62095 | 191413.0331 | CRITICAL
Weather | High Waves | Lightning | Weather | 4 | 22 | 440832 | 760122 | 1200954 | 4 | 3 | 0.60608 | 186830.1519 | CRITICAL
Weather | Lightning | Strong Wind | Weather | 2 | 24 | 490000 | 710103 | 1200103 | 2 | 1 | 0.60565 | 186697.7635 | CRITICAL
Weather | High Waves | High Waves | Marine Operations | 4 | 24 | 472499 | 722142 | 1194641 | 4 | 2 | 0.6029 | 185848.0504 | CRITICAL
Drilling | Bit Failure | Differential Sticking | Mud Engineering | 5 | 26 | 510832 | 677064 | 1187896 | 5 | 3 | 0.59949 | 184798.7435 | CRITICAL
Drilling | Fishing Operation | Formation Instability | Directional Drilling | 4 | 24 | 465833 | 710577 | 1176410 | 4 | 3 | 0.5937 | 183011.8881 | CRITICAL
Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | 4 | 26 | 508332 | 667160 | 1175492 | 4 | 2 | 0.59323 | 182869.0765 | CRITICAL
Drilling | Well Control | Unexpected Pressure | Directional Drilling | 7 | 22 | 434998 | 711366 | 1146364 | 7 | 3 | 0.57853 | 178337.6884 | CRITICAL
Personnel | Crew Change | Medical Emergency | Medical Team | 1 | 18 | 367500 | 774135 | 1141635 | 1 | 1 | 0.57615 | 177602.0068 | CRITICAL
Mechanical | Power System Failure | Equipment Wear | OEM Vendor | 3 | 26 | 505833 | 624770 | 1130603 | 3 | 2 | 0.57058 | 175885.7794 | CRITICAL
Weather | High Waves | Strong Wind | Weather | 4 | 22 | 445416 | 678421 | 1123837 | 4 | 3 | 0.56716 | 174833.2055 | CRITICAL
Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 26 | 498333 | 625181 | 1123514 | 2 | 1 | 0.567 | 174782.957 | CRITICAL
Weather | High Waves | Lightning | Marine Operations | 4 | 20 | 389582 | 721737 | 1111319 | 4 | 2 | 0.56085 | 172885.8038 | CRITICAL
Mechanical | Generator Failure | Equipment Wear | Maintenance Team | 1 | 18 | 356250 | 753050 | 1109300 | 1 | 1 | 0.55983 | 172571.7118 | CRITICAL
Drilling | Stuck Pipe | Formation Instability | Operator | 5 | 22 | 432915 | 662663 | 1095578 | 5 | 3 | 0.5529 | 170437.0061 | CRITICAL
Drilling | Lost Circulation | Bit Wear | Operator | 4 | 20 | 399999 | 695367 | 1095366 | 4 | 3 | 0.5528 | 170404.0256 | CRITICAL
Drilling | Bit Failure | Unexpected Pressure | Operator | 3 | 22 | 444166 | 649187 | 1093353 | 3 | 2 | 0.55178 | 170090.867 | CRITICAL
Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | 3 | 22 | 441666 | 645962 | 1087628 | 3 | 2 | 0.54889 | 169200.2395 | CRITICAL
Mechanical | BOP Repair | Electrical Failure | OEM Vendor | 4 | 22 | 439166 | 630032 | 1069198 | 4 | 2 | 0.53959 | 166333.1192 | CRITICAL
Drilling | Fishing Operation | Unexpected Pressure | Operator | 5 | 24 | 473332 | 592187 | 1065519 | 5 | 2 | 0.53773 | 165760.7841 | CRITICAL
Logistics | Waiting on Cement | Port Congestion | Supply Chain | 2 | 18 | 360000 | 705290 | 1065290 | 2 | 2 | 0.53762 | 165725.159 | CRITICAL
Logistics | Fuel Supply Delay | Customs Clearance | Procurement | 3 | 18 | 352499 | 693425 | 1045924 | 3 | 3 | 0.52784 | 162712.4268 | CRITICAL
Weather | Heavy Rain | Strong Wind | Weather | 4 | 22 | 436666 | 601439 | 1038105 | 4 | 3 | 0.5239 | 161496.0397 | CRITICAL
Weather | Poor Visibility | Strong Wind | Weather | 5 | 24 | 471248 | 566798 | 1038046 | 5 | 4 | 0.52387 | 161486.8612 | CRITICAL
Weather | High Waves | Storm | Marine Operations | 4 | 20 | 408332 | 625479 | 1033811 | 4 | 1 | 0.52173 | 160828.0302 | CRITICAL
Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | 1 | 18 | 360000 | 663187 | 1023187 | 1 | 1 | 0.51637 | 159175.2745 | HIGH
Drilling | Stuck Pipe | Differential Sticking | Operator | 4 | 26 | 513332 | 495054 | 1008386 | 4 | 2 | 0.5089 | 156872.7108 | HIGH
Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | 3 | 22 | 421666 | 581674 | 1003340 | 3 | 1 | 0.50635 | 156087.7141 | HIGH
Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | 4 | 20 | 404166 | 598675 | 1002841 | 4 | 3 | 0.5061 | 156010.0856 | HIGH
Drilling | Stuck Pipe | Bit Wear | Operator | 2 | 16 | 325000 | 676961 | 1001961 | 2 | 2 | 0.50566 | 155873.1857 | HIGH
Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | 3 | 28 | 543333 | 444184 | 987517 | 3 | 2 | 0.49837 | 153626.1598 | HIGH
Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | 3 | 16 | 306665 | 637880 | 944545 | 3 | 1 | 0.47668 | 146941.0867 | HIGH
Weather | High Waves | Heavy Rain | Marine Operations | 4 | 18 | 354166 | 583664 | 937830 | 4 | 3 | 0.47329 | 145896.4468 | HIGH
Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | 3 | 22 | 435000 | 500897 | 935897 | 3 | 2 | 0.47232 | 145595.7336 | HIGH
Weather | Lightning | High Waves | Marine Operations | 5 | 20 | 392081 | 542232 | 934313 | 5 | 3 | 0.47152 | 145349.3137 | HIGH
Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | 4 | 24 | 463332 | 470318 | 933650 | 4 | 2 | 0.47118 | 145246.1721 | HIGH
Weather | Strong Wind | High Waves | Marine Operations | 4 | 18 | 356248 | 571296 | 927544 | 4 | 3 | 0.4681 | 144296.2732 | HIGH
Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | 3 | 18 | 354999 | 571010 | 926009 | 3 | 2 | 0.46733 | 144057.4761 | HIGH
Logistics | Waiting on Cement | Port Congestion | Marine Logistics | 1 | 18 | 345000 | 573898 | 918898 | 1 | 1 | 0.46374 | 142951.2312 | HIGH
Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | 3 | 20 | 383332 | 534598 | 917930 | 3 | 1 | 0.46325 | 142800.6413 | HIGH
Weather | Heavy Rain | High Waves | Marine Operations | 4 | 16 | 315833 | 574551 | 890384 | 4 | 3 | 0.44935 | 138515.362 | HIGH
Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | 1 | 24 | 490000 | 397460 | 887460 | 1 | 1 | 0.44787 | 138060.4808 | HIGH
Drilling | Fishing Operation | Bit Wear | Directional Drilling | 2 | 14 | 280000 | 601833 | 881833 | 2 | 1 | 0.44503 | 137185.099 | HIGH
Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | 4 | 26 | 503332 | 377984 | 881316 | 4 | 2 | 0.44477 | 137104.6703 | HIGH
Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | 2 | 20 | 385833 | 495197 | 881030 | 2 | 2 | 0.44463 | 137060.1778 | HIGH
Drilling | Hole Cleaning | Unexpected Pressure | Operator | 4 | 20 | 399582 | 479851 | 879433 | 4 | 3 | 0.44382 | 136811.7355 | HIGH
Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | 2 | 16 | 321666 | 547435 | 869101 | 2 | 2 | 0.43861 | 135204.4057 | HIGH
Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | 5 | 18 | 363332 | 504214 | 867546 | 5 | 3 | 0.43782 | 134962.4973 | HIGH
Weather | Lightning | Storm | Weather | 2 | 16 | 326666 | 540736 | 867402 | 2 | 1 | 0.43775 | 134940.0955 | HIGH
Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | 2 | 16 | 326666 | 538360 | 865026 | 2 | 1 | 0.43655 | 134570.4657 | HIGH
Drilling | Fishing Operation | Differential Sticking | Operator | 4 | 22 | 444999 | 407026 | 852025 | 4 | 2 | 0.42999 | 132547.9246 | HIGH
Drilling | Lost Circulation | Bit Wear | Directional Drilling | 2 | 14 | 285000 | 566293 | 851293 | 2 | 2 | 0.42962 | 132434.0487 | HIGH
Drilling | Well Control | Formation Instability | Mud Engineering | 5 | 18 | 351665 | 466385 | 818050 | 4 | 3 | 0.41284 | 127262.4978 | HIGH
Drilling | Well Control | Formation Instability | Operator | 3 | 16 | 314166 | 495832 | 809998 | 3 | 2 | 0.40878 | 126009.8633 | HIGH
Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | 2 | 22 | 437916 | 362099 | 800015 | 2 | 2 | 0.40374 | 124456.8268 | HIGH
Logistics | Waiting on Materials | Port Congestion | Marine Logistics | 2 | 16 | 316666 | 482000 | 798666 | 2 | 2 | 0.40306 | 124246.9654 | HIGH
Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | 1 | 18 | 356250 | 426483 | 782733 | 1 | 1 | 0.39502 | 121768.2986 | HIGH
Weather | Lightning | Storm | Marine Operations | 3 | 16 | 316665 | 461207 | 777872 | 3 | 3 | 0.39257 | 121012.082 | HIGH
Weather | Heavy Rain | High Waves | Weather | 3 | 12 | 237499 | 534451 | 771950 | 3 | 3 | 0.38958 | 120090.8076 | HIGH
Logistics | Delayed Helicopter | Port Congestion | Supply Chain | 2 | 16 | 306666 | 462230 | 768896 | 2 | 1 | 0.38804 | 119615.7026 | HIGH
Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | 3 | 12 | 236666 | 520254 | 756920 | 3 | 2 | 0.38199 | 117752.6188 | HIGH
Personnel | Safety Stand Down | Medical Emergency | Rig Management | 1 | 18 | 367500 | 388821 | 756321 | 1 | 1 | 0.38169 | 117659.4335 | HIGH
Weather | Strong Wind | High Waves | Weather | 2 | 14 | 272083 | 483655 | 755738 | 2 | 2 | 0.3814 | 117568.7373 | HIGH
Drilling | Stuck Pipe | Formation Instability | Directional Drilling | 3 | 16 | 322916 | 419311 | 742227 | 3 | 3 | 0.37458 | 115466.8565 | HIGH
Personnel | Medical Evacuation | Training Requirement | HR | 4 | 18 | 352499 | 387418 | 739917 | 4 | 2 | 0.37341 | 115107.4941 | HIGH
Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | 4 | 14 | 283331 | 449372 | 732703 | 4 | 2 | 0.36977 | 113985.2258 | HIGH
Drilling | Lost Circulation | Differential Sticking | Mud Engineering | 2 | 12 | 233750 | 493668 | 727418 | 2 | 2 | 0.3671 | 113163.0483 | HIGH
Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | 4 | 18 | 364999 | 361231 | 726230 | 4 | 2 | 0.3665 | 112978.2333 | HIGH
Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | 3 | 12 | 229999 | 484817 | 714816 | 3 | 1 | 0.36074 | 111202.5789 | HIGH
Personnel | Safety Stand Down | Crew Rotation | Medical Team | 3 | 16 | 317083 | 394125 | 711208 | 3 | 3 | 0.35892 | 110641.2891 | HIGH
Drilling | Hole Cleaning | Bit Wear | Directional Drilling | 2 | 12 | 229999 | 474568 | 704567 | 2 | 1 | 0.35557 | 109608.1612 | HIGH
Weather | Poor Visibility | Lightning | Weather | 3 | 14 | 268332 | 430551 | 698883 | 3 | 1 | 0.3527 | 108723.912 | HIGH
Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | 3 | 16 | 316666 | 380857 | 697523 | 3 | 2 | 0.35202 | 108512.3394 | HIGH
Drilling | Hole Cleaning | Differential Sticking | Operator | 3 | 16 | 316666 | 370500 | 687166 | 3 | 2 | 0.34679 | 106901.1204 | HIGH
Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | 2 | 12 | 234999 | 450541 | 685540 | 2 | 2 | 0.34597 | 106648.1667 | HIGH
Weather | Poor Visibility | Lightning | Marine Operations | 4 | 16 | 309165 | 371867 | 681032 | 4 | 2 | 0.34369 | 105946.8656 | HIGH
Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | 3 | 16 | 318333 | 362244 | 680577 | 3 | 3 | 0.34347 | 105876.0821 | HIGH
Drilling | Lost Circulation | Bit Wear | Mud Engineering | 4 | 14 | 277499 | 398891 | 676390 | 4 | 3 | 0.34135 | 105224.7184 | HIGH
Weather | Strong Wind | Heavy Rain | Weather | 2 | 18 | 355000 | 316484 | 671484 | 2 | 2 | 0.33888 | 104461.5012 | HIGH
Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | 2 | 14 | 273333 | 397753 | 671086 | 2 | 2 | 0.33868 | 104399.5851 | HIGH
Mechanical | Power System Failure | Electrical Failure | OEM Vendor | 2 | 12 | 230000 | 432865 | 662865 | 2 | 1 | 0.33453 | 103120.6596 | HIGH
Weather | Strong Wind | Storm | Weather | 4 | 16 | 317499 | 334476 | 651975 | 4 | 3 | 0.32903 | 101426.5228 | HIGH
Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | 2 | 14 | 268333 | 377403 | 645736 | 2 | 1 | 0.32588 | 100455.9334 | HIGH
Personnel | Safety Stand Down | Training Requirement | Rig Management | 3 | 18 | 352499 | 292861 | 645360 | 3 | 2 | 0.32569 | 100397.4397 | HIGH
Logistics | Fuel Supply Delay | Material Shortage | Procurement | 2 | 12 | 241250 | 399607 | 640857 | 2 | 2 | 0.32342 | 99696.9165 | HIGH
Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | 3 | 14 | 275832 | 362592 | 638424 | 3 | 3 | 0.32219 | 99318.4193 | HIGH
Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | 1 | 12 | 230000 | 407608 | 637608 | 1 | 1 | 0.32178 | 99191.4757 | HIGH
Mechanical | BOP Repair | OEM Defect | Drilling Contractor | 2 | 10 | 203333 | 426701 | 630034 | 2 | 2 | 0.31796 | 98013.2028 | HIGH
Logistics | Waiting on Cement | Customs Clearance | Procurement | 2 | 12 | 233333 | 392072 | 625405 | 2 | 2 | 0.31562 | 97293.078 | HIGH
Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | 3 | 12 | 232499 | 389631 | 622130 | 3 | 2 | 0.31397 | 96783.5924 | HIGH
Logistics | Waiting on Cement | Late Supply Vessel | Procurement | 2 | 12 | 233750 | 387953 | 621703 | 2 | 2 | 0.31375 | 96717.1648 | HIGH
Logistics | Waiting on Materials | Port Congestion | Supply Chain | 2 | 14 | 268333 | 348193 | 616526 | 2 | 1 | 0.31114 | 95911.7887 | HIGH
Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | 3 | 10 | 197499 | 412127 | 609626 | 3 | 3 | 0.30766 | 94838.3687 | MEDIUM
Personnel | Crew Change | Crew Rotation | Rig Management | 1 | 18 | 367500 | 236304 | 603804 | 1 | 1 | 0.30472 | 93932.6511 | MEDIUM
Logistics | Waiting on Cement | Material Shortage | Marine Logistics | 3 | 14 | 277500 | 307302 | 584802 | 3 | 3 | 0.29513 | 90976.5457 | MEDIUM
Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | 4 | 14 | 278333 | 299723 | 578056 | 4 | 2 | 0.29173 | 89927.0832 | MEDIUM
Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | 3 | 16 | 322916 | 253533 | 576449 | 3 | 2 | 0.29092 | 89677.0853 | MEDIUM
Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | 2 | 14 | 272083 | 294780 | 566863 | 2 | 2 | 0.28608 | 88185.8093 | MEDIUM
Weather | Heavy Rain | Lightning | Weather | 3 | 10 | 199165 | 365446 | 564611 | 3 | 3 | 0.28494 | 87835.4699 | MEDIUM
Drilling | Stuck Pipe | Bit Wear | Directional Drilling | 4 | 14 | 278332 | 272689 | 551021 | 4 | 2 | 0.27808 | 85721.2992 | MEDIUM
Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | 3 | 14 | 280832 | 265682 | 546514 | 3 | 2 | 0.27581 | 85020.1537 | MEDIUM
Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | 3 | 10 | 193333 | 344893 | 538226 | 3 | 2 | 0.27163 | 83730.8051 | MEDIUM
Mechanical | Power System Failure | OEM Defect | OEM Vendor | 2 | 10 | 191666 | 339541 | 531207 | 2 | 1 | 0.26808 | 82638.8725 | MEDIUM
Drilling | Well Control | Unexpected Pressure | Mud Engineering | 2 | 10 | 204166 | 316845 | 521011 | 2 | 1 | 0.26294 | 81052.7 | MEDIUM
Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | 2 | 8 | 158332 | 360014 | 518346 | 2 | 2 | 0.26159 | 80638.111 | MEDIUM
Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | 2 | 14 | 275000 | 241750 | 516750 | 2 | 2 | 0.26079 | 80389.8243 | MEDIUM
Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | 1 | 8 | 158333 | 357164 | 515497 | 1 | 1 | 0.26015 | 80194.8974 | MEDIUM
Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | 2 | 10 | 200416 | 310047 | 510463 | 2 | 2 | 0.25761 | 79411.7675 | MEDIUM
Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | 2 | 10 | 201666 | 304834 | 506500 | 2 | 2 | 0.25561 | 78795.2511 | MEDIUM
Drilling | Bit Failure | Formation Instability | Directional Drilling | 3 | 12 | 238750 | 263155 | 501905 | 3 | 2 | 0.2533 | 78080.4156 | MEDIUM
Weather | Poor Visibility | Storm | Weather | 3 | 12 | 239999 | 260713 | 500712 | 3 | 3 | 0.25269 | 77894.8228 | MEDIUM
Drilling | Lost Circulation | Differential Sticking | Directional Drilling | 2 | 10 | 191666 | 299995 | 491661 | 2 | 1 | 0.24813 | 76486.7758 | MEDIUM
Drilling | Lost Circulation | Differential Sticking | Operator | 2 | 10 | 194166 | 295847 | 490013 | 2 | 2 | 0.24729 | 76230.3995 | MEDIUM
Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | 3 | 10 | 196665 | 288719 | 485384 | 3 | 2 | 0.24496 | 75510.2747 | MEDIUM
Weather | High Waves | Heavy Rain | Weather | 2 | 10 | 196666 | 280380 | 477046 | 2 | 2 | 0.24075 | 74213.1478 | MEDIUM
Weather | Poor Visibility | High Waves | Marine Operations | 3 | 12 | 229998 | 243433 | 473431 | 3 | 1 | 0.23893 | 73650.769 | MEDIUM
Logistics | Delayed Helicopter | Port Congestion | Procurement | 3 | 10 | 195833 | 277135 | 472968 | 3 | 3 | 0.23869 | 73578.741 | MEDIUM
Weather | Heavy Rain | Heavy Rain | Marine Operations | 2 | 8 | 158332 | 312744 | 471076 | 2 | 2 | 0.23774 | 73284.4061 | MEDIUM
Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | 2 | 10 | 195416 | 263218 | 458634 | 2 | 2 | 0.23146 | 71348.8276 | MEDIUM
Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | 3 | 10 | 194165 | 241772 | 435937 | 3 | 2 | 0.22 | 67817.8981 | MEDIUM
Logistics | Waiting on Materials | Port Congestion | Procurement | 2 | 10 | 199166 | 235314 | 434480 | 2 | 2 | 0.21927 | 67591.2353 | MEDIUM
Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | 2 | 10 | 199166 | 234328 | 433494 | 2 | 2 | 0.21877 | 67437.8451 | MEDIUM
Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | 1 | 8 | 153333 | 279943 | 433276 | 1 | 1 | 0.21866 | 67403.9313 | MEDIUM
Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | 2 | 10 | 200833 | 230960 | 431793 | 2 | 2 | 0.21791 | 67173.2238 | MEDIUM
Weather | Poor Visibility | Storm | Marine Operations | 3 | 10 | 200416 | 231216 | 431632 | 3 | 3 | 0.21783 | 67148.1773 | MEDIUM
Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | 1 | 8 | 153333 | 276056 | 429389 | 1 | 1 | 0.2167 | 66799.238 | MEDIUM
Mechanical | Power System Failure | Electrical Failure | Maintenance Team | 2 | 8 | 160833 | 262056 | 422889 | 2 | 2 | 0.21342 | 65788.0453 | MEDIUM
Logistics | Waiting on Cement | Customs Clearance | Supply Chain | 1 | 6 | 120000 | 295691 | 415691 | 1 | 1 | 0.20979 | 64668.266 | MEDIUM
Drilling | Hole Cleaning | Formation Instability | Operator | 3 | 8 | 159582 | 255813 | 415395 | 3 | 3 | 0.20964 | 64622.2178 | MEDIUM
Mechanical | BOP Repair | Equipment Wear | OEM Vendor | 1 | 8 | 153333 | 252476 | 405809 | 1 | 1 | 0.2048 | 63130.9418 | MEDIUM
Logistics | Waiting on Boat | Customs Clearance | Procurement | 2 | 6 | 119999 | 282138 | 402137 | 2 | 2 | 0.20295 | 62559.6957 | MEDIUM
Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | 2 | 8 | 160833 | 234484 | 395317 | 2 | 2 | 0.1995 | 61498.7212 | MEDIUM
Weather | Heavy Rain | Storm | Marine Operations | 2 | 6 | 119999 | 275086 | 395085 | 2 | 2 | 0.19939 | 61462.6294 | MEDIUM
Drilling | Bit Failure | Differential Sticking | Operator | 1 | 6 | 120000 | 273652 | 393652 | 1 | 1 | 0.19866 | 61239.7002 | MEDIUM
Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | 1 | 6 | 120000 | 270679 | 390679 | 1 | 1 | 0.19716 | 60777.1962 | MEDIUM
Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | 1 | 6 | 115000 | 272813 | 387813 | 1 | 1 | 0.19572 | 60331.338 | MEDIUM
Weather | Lightning | Strong Wind | Marine Operations | 2 | 8 | 155833 | 227263 | 383096 | 2 | 2 | 0.19334 | 59597.5232 | MEDIUM
Logistics | Waiting on Boat | Port Congestion | Supply Chain | 1 | 6 | 122500 | 257837 | 380337 | 1 | 1 | 0.19194 | 59168.3108 | MEDIUM
Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | 2 | 8 | 155833 | 224020 | 379853 | 2 | 2 | 0.1917 | 59093.0158 | MEDIUM
Logistics | Waiting on Boat | Port Congestion | Procurement | 1 | 6 | 122500 | 255221 | 377721 | 1 | 1 | 0.19062 | 58761.3446 | MEDIUM
Personnel | Medical Evacuation | Medical Emergency | HR | 1 | 6 | 122500 | 253590 | 376090 | 1 | 1 | 0.1898 | 58507.613 | MEDIUM
Drilling | Hole Cleaning | Formation Instability | Mud Engineering | 2 | 6 | 114999 | 255620 | 370619 | 2 | 1 | 0.18704 | 57656.4998 | MEDIUM
Drilling | Well Control | Formation Instability | Directional Drilling | 1 | 6 | 115000 | 253781 | 368781 | 1 | 1 | 0.18611 | 57370.5656 | MEDIUM
Drilling | Fishing Operation | Bit Wear | Mud Engineering | 2 | 6 | 121666 | 244186 | 365852 | 2 | 2 | 0.18463 | 56914.9066 | MEDIUM
Drilling | Bit Failure | Formation Instability | Mud Engineering | 3 | 10 | 199165 | 165341 | 364506 | 3 | 2 | 0.18395 | 56705.5119 | MEDIUM
Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | 1 | 12 | 240000 | 123301 | 363301 | 1 | 1 | 0.18335 | 56518.0523 | MEDIUM
Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | 1 | 6 | 122500 | 226126 | 348626 | 1 | 1 | 0.17594 | 54235.0902 | MEDIUM
Drilling | Bit Failure | Bit Wear | Directional Drilling | 1 | 6 | 118750 | 226214 | 344964 | 1 | 1 | 0.17409 | 53665.3998 | MEDIUM
Weather | Strong Wind | Storm | Marine Operations | 2 | 8 | 153333 | 190713 | 344046 | 2 | 1 | 0.17363 | 53522.5883 | MEDIUM
Personnel | Crew Change | Medical Emergency | Rig Management | 2 | 6 | 114999 | 212937 | 327936 | 2 | 1 | 0.1655 | 51016.3859 | MEDIUM
Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | 1 | 8 | 163333 | 152781 | 316114 | 1 | 1 | 0.15953 | 49177.2596 | MEDIUM
Drilling | Bit Failure | Bit Wear | Operator | 2 | 8 | 159583 | 152895 | 312478 | 2 | 2 | 0.1577 | 48611.6139 | MEDIUM
Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | 1 | 6 | 115000 | 196670 | 311670 | 1 | 1 | 0.15729 | 48485.9149 | MEDIUM
Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | 2 | 6 | 114999 | 187090 | 302089 | 2 | 1 | 0.15245 | 46995.4168 | MEDIUM
Drilling | Well Control | Unexpected Pressure | Operator | 2 | 8 | 153332 | 141593 | 294925 | 2 | 1 | 0.14884 | 45880.9268 | MEDIUM
Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | 1 | 6 | 115000 | 177855 | 292855 | 1 | 1 | 0.14779 | 45558.9008 | MEDIUM
Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | 1 | 4 | 81666 | 198934 | 280600 | 1 | 1 | 0.14161 | 43652.4135 | MEDIUM
Personnel | Safety Stand Down | Training Requirement | Medical Team | 2 | 6 | 119999 | 160592 | 280591 | 2 | 2 | 0.14161 | 43651.0134 | MEDIUM
Logistics | Delayed Helicopter | Material Shortage | Supply Chain | 1 | 4 | 81666 | 198718 | 280384 | 1 | 1 | 0.1415 | 43618.8108 | MEDIUM
Logistics | Waiting on Boat | Port Congestion | Marine Logistics | 1 | 4 | 80000 | 183601 | 263601 | 1 | 1 | 0.13303 | 41007.9111 | LOW
Weather | Strong Wind | Heavy Rain | Marine Operations | 2 | 6 | 118749 | 138316 | 257065 | 1 | 1 | 0.12973 | 39991.1179 | LOW
Weather | Poor Visibility | High Waves | Weather | 1 | 6 | 118750 | 138221 | 256971 | 1 | 1 | 0.12968 | 39976.4945 | LOW
Personnel | Medical Evacuation | Training Requirement | Medical Team | 2 | 4 | 80833 | 169277 | 250110 | 2 | 2 | 0.12622 | 38909.1416 | LOW
Logistics | Delayed Helicopter | Material Shortage | Procurement | 1 | 4 | 76666 | 169001 | 245667 | 1 | 1 | 0.12398 | 38217.9525 | LOW
Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | 1 | 4 | 76666 | 165696 | 242362 | 1 | 1 | 0.12231 | 37703.7999 | LOW
Logistics | Waiting on Materials | Material Shortage | Supply Chain | 1 | 6 | 118750 | 120114 | 238864 | 1 | 1 | 0.12055 | 37159.6226 | LOW
Weather | Strong Wind | Lightning | Marine Operations | 1 | 6 | 115000 | 123339 | 238339 | 1 | 1 | 0.12028 | 37077.9493 | LOW
Drilling | Fishing Operation | Differential Sticking | Mud Engineering | 1 | 4 | 76666 | 157410 | 234076 | 1 | 1 | 0.11813 | 36414.7625 | LOW
Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | 1 | 4 | 81666 | 152013 | 233679 | 1 | 1 | 0.11793 | 36353.0019 | LOW
Personnel | Crew Change | Medical Emergency | HR | 1 | 6 | 115000 | 117452 | 232452 | 1 | 1 | 0.11731 | 36162.1198 | LOW
Logistics | Waiting on Materials | Customs Clearance | Procurement | 2 | 6 | 117499 | 113974 | 231473 | 2 | 2 | 0.11682 | 36009.8187 | LOW
Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | 2 | 4 | 81666 | 148998 | 230664 | 2 | 1 | 0.11641 | 35883.9641 | LOW
Mechanical | Generator Failure | OEM Defect | Drilling Contractor | 1 | 4 | 76666 | 152544 | 229210 | 1 | 1 | 0.11567 | 35657.768 | LOW
Drilling | Hole Cleaning | Formation Instability | Directional Drilling | 1 | 6 | 120000 | 106088 | 226088 | 1 | 1 | 0.1141 | 35172.0844 | LOW
Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | 2 | 6 | 114999 | 108729 | 223728 | 2 | 1 | 0.11291 | 34804.9436 | LOW
Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | 1 | 4 | 80000 | 143184 | 223184 | 1 | 1 | 0.11263 | 34720.3145 | LOW
Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | 2 | 6 | 119166 | 98637 | 217803 | 2 | 2 | 0.10992 | 33883.2025 | LOW
Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | 2 | 4 | 76666 | 140554 | 217220 | 2 | 1 | 0.10962 | 33792.5063 | LOW
Personnel | Training | Crew Rotation | Medical Team | 1 | 6 | 122500 | 90710 | 213210 | 1 | 1 | 0.1076 | 33168.6781 | LOW
Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | 1 | 6 | 122500 | 88110 | 210610 | 1 | 1 | 0.10629 | 32764.201 | LOW
Logistics | Waiting on Materials | Customs Clearance | Supply Chain | 1 | 4 | 76666 | 128931 | 205597 | 1 | 1 | 0.10376 | 31984.3381 | LOW
Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | 2 | 6 | 116666 | 86992 | 203658 | 2 | 2 | 0.10278 | 31682.6915 | LOW
Weather | Lightning | Heavy Rain | Weather | 2 | 4 | 78333 | 123696 | 202029 | 2 | 2 | 0.10196 | 31429.271 | LOW
Logistics | Waiting on Boat | Customs Clearance | Supply Chain | 1 | 4 | 80000 | 121829 | 201829 | 1 | 1 | 0.10186 | 31398.1574 | LOW
Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | 1 | 6 | 122500 | 78520 | 201020 | 1 | 1 | 0.10145 | 31272.3028 | LOW
Mechanical | Generator Failure | Equipment Wear | OEM Vendor | 2 | 6 | 117499 | 82412 | 199911 | 2 | 2 | 0.10089 | 31099.7778 | LOW
Weather | High Waves | Storm | Weather | 1 | 4 | 81666 | 110150 | 191816 | 1 | 1 | 0.096803 | 29840.4539 | LOW
Weather | High Waves | High Waves | Weather | 1 | 6 | 115000 | 70319 | 185319 | 1 | 1 | 0.093525 | 28829.7278 | LOW
Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | 1 | 6 | 118750 | 64902 | 183652 | 1 | 1 | 0.092683 | 28570.3958 | LOW
Logistics | Waiting on Boat | Material Shortage | Procurement | 2 | 4 | 80416 | 102981 | 183397 | 2 | 2 | 0.092555 | 28530.7259 | LOW
Drilling | Stuck Pipe | Formation Instability | Mud Engineering | 1 | 4 | 80000 | 91574 | 171574 | 1 | 1 | 0.086588 | 26691.444 | LOW
Mechanical | BOP Repair | OEM Defect | Maintenance Team | 1 | 4 | 76666 | 90633 | 167299 | 1 | 1 | 0.08443 | 26026.3903 | LOW
Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | 2 | 4 | 78333 | 85214 | 163547 | 2 | 2 | 0.082537 | 25442.6988 | LOW
Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | 1 | 4 | 81666 | 77766 | 159432 | 1 | 1 | 0.08046 | 24802.536 | LOW
Personnel | Crew Change | Training Requirement | Rig Management | 1 | 4 | 76666 | 79447 | 156113 | 1 | 1 | 0.078785 | 24286.2054 | LOW
Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | 1 | 4 | 81666 | 71396 | 153062 | 1 | 1 | 0.077245 | 23811.5671 | LOW
Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | 1 | 4 | 79166 | 68905 | 148071 | 1 | 1 | 0.074727 | 23035.1266 | LOW
Drilling | Well Control | Differential Sticking | Operator | 1 | 4 | 76666 | 70081 | 146747 | 1 | 1 | 0.074058 | 22829.1544 | LOW
Logistics | Waiting on Boat | Material Shortage | Supply Chain | 1 | 4 | 81666 | 64854 | 146520 | 1 | 1 | 0.073944 | 22793.8404 | LOW
Personnel | Safety Stand Down | Medical Emergency | Medical Team | 1 | 4 | 81666 | 60840 | 142506 | 1 | 1 | 0.071918 | 22169.39 | LOW
Logistics | Waiting on Cement | Port Congestion | Procurement | 1 | 4 | 81666 | 60188 | 141854 | 1 | 1 | 0.071589 | 22067.9596 | LOW
Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | 1 | 4 | 81666 | 55857 | 137523 | 1 | 1 | 0.069403 | 21394.1941 | LOW
Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | 1 | 2 | 40000 | 88171 | 128171 | 1 | 1 | 0.064684 | 19939.3211 | LOW
Drilling | Well Control | Bit Wear | Operator | 1 | 2 | 40000 | 85472 | 125472 | 1 | 1 | 0.063322 | 19519.4427 | LOW
Drilling | Bit Failure | Formation Instability | Operator | 1 | 2 | 40000 | 85034 | 125034 | 1 | 1 | 0.063101 | 19451.3039 | LOW
Personnel | Training | Training Requirement | Medical Team | 1 | 2 | 39583 | 85410 | 124993 | 1 | 1 | 0.06308 | 19444.9256 | LOW
Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | 1 | 2 | 38333 | 83567 | 121900 | 1 | 1 | 0.061519 | 18963.7534 | LOW
Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | 1 | 2 | 38333 | 82613 | 120946 | 1 | 1 | 0.061038 | 18815.3414 | LOW
Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | 1 | 2 | 40000 | 79766 | 119766 | 1 | 1 | 0.060442 | 18631.7711 | LOW
Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | 1 | 2 | 38333 | 81222 | 119555 | 1 | 1 | 0.060336 | 18598.9462 | LOW
Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | 1 | 2 | 40833 | 67554 | 108387 | 1 | 1 | 0.054699 | 16861.5615 | LOW
Logistics | Waiting on Cement | Material Shortage | Supply Chain | 1 | 2 | 40833 | 60855 | 101688 | 1 | 1 | 0.051319 | 15819.4106 | LOW
Drilling | Lost Circulation | Unexpected Pressure | Operator | 1 | 2 | 40833 | 59674 | 100507 | 1 | 1 | 0.050723 | 15635.6847 | LOW
Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | 1 | 2 | 38333 | 59428 | 97761 | 1 | 1 | 0.049337 | 15208.4946 | LOW
Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | 1 | 2 | 40833 | 55477 | 96310 | 1 | 1 | 0.048605 | 14982.7653 | LOW
Personnel | Safety Stand Down | Training Requirement | HR | 1 | 2 | 40000 | 53981 | 93981 | 1 | 1 | 0.047429 | 14620.4472 | LOW
Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | 1 | 2 | 40833 | 48689 | 89522 | 1 | 1 | 0.045179 | 13926.7689 | LOW
Drilling | Fishing Operation | Bit Wear | Operator | 1 | 2 | 38333 | 49722 | 88055 | 1 | 1 | 0.044439 | 13698.5505 | LOW
Weather | Strong Wind | Lightning | Weather | 1 | 2 | 40833 | 43926 | 84759 | 1 | 1 | 0.042775 | 13185.798 | LOW
Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | 1 | 2 | 40000 | 42480 | 82480 | 1 | 1 | 0.041625 | 12831.2583 | LOW
Mechanical | Generator Failure | Electrical Failure | OEM Vendor | 1 | 2 | 38333 | 43940 | 82273 | 1 | 1 | 0.041521 | 12799.0557 | LOW
Personnel | Safety Stand Down | Crew Rotation | Rig Management | 1 | 2 | 38333 | 43207 | 81540 | 1 | 1 | 0.041151 | 12685.0242 | LOW
Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | 1 | 2 | 39583 | 39917 | 79500 | 1 | 1 | 0.040121 | 12367.6653 | LOW
Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | 1 | 2 | 40000 | 33971 | 73971 | 1 | 1 | 0.037331 | 11507.5292 | LOW
Drilling | Well Control | Differential Sticking | Mud Engineering | 1 | 2 | 40000 | 30168 | 70168 | 1 | 1 | 0.035412 | 10915.9036 | LOW
Personnel | Safety Stand Down | Medical Emergency | HR | 1 | 2 | 40000 | 25522 | 65522 | 1 | 1 | 0.033067 | 10193.1341 | LOW

## KPI_Monthly
Month | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Drilling_Days | Footage_ft | Avg_ROP_ft_hr | Drilling_Cost_USD | NPT_Hours_per_Drilling_Day | Cost_per_Foot_USD | Target_Savings_USD
2023-01 | 7 | 24 | 466247 | 452038 | 918285 | 11 | 22698.9 | 40.5377 | 12936968.02 | 2.1818 | 569.9381 | 142855.868
2023-02 | 11 | 80 | 1564580 | 2707775 | 4272355 | 26 | 38368.7 | 30.1543 | 28982940.26 | 3.0769 | 755.3798 | 664642.2209
2023-03 | 24 | 178 | 3454161 | 6044361 | 9498522 | 30 | 32950.8 | 34.9135 | 21746915.53 | 5.9333 | 659.9814 | 1477667.1782
2023-04 | 28 | 152 | 2994574 | 3852413 | 6846987 | 30 | 59853.1 | 35.1316 | 40261376.27 | 5.0667 | 672.6699 | 1065172.8721
2023-05 | 36 | 202 | 4030405 | 5558193 | 9588598 | 31 | 64675 | 31.2898 | 48171226.55 | 6.5161 | 744.8199 | 1491680.1319
2023-06 | 28 | 146 | 2954157 | 4798401 | 7752558 | 26 | 29058.8 | 34.362 | 19470867.8 | 5.6154 | 670.0506 | 1206050.8471
2023-07 | 37 | 248 | 4937906 | 7155038 | 12092944 | 31 | 48647.1 | 33.4841 | 33608210.64 | 8 | 690.8574 | 1881276.5225
2023-08 | 23 | 120 | 2364159 | 3258288 | 5622447 | 31 | 26569.3 | 32.4316 | 19298177.6 | 3.871 | 726.3337 | 874673.4906
2023-09 | 22 | 140 | 2787495 | 4366027 | 7153522 | 29 | 39553.2 | 35.4039 | 25497665.16 | 4.8276 | 644.6423 | 1112859.9448
2023-10 | 26 | 176 | 3558326 | 6268603 | 9826929 | 31 | 57333.4 | 33.6441 | 40105928.2 | 5.6774 | 699.5212 | 1528756.8367
2023-11 | 38 | 232 | 4563323 | 6762862 | 11326185 | 29 | 37031.8 | 35.5977 | 24010569.94 | 8 | 648.3771 | 1761993.269
2023-12 | 30 | 152 | 3044160 | 4213835 | 7257995 | 29 | 32244.5 | 33.1127 | 22859570.23 | 5.2414 | 708.9448 | 1129112.6126
2024-01 | 23 | 136 | 2680831 | 4287967 | 6968798 | 31 | 30516.3 | 34.0196 | 20667146.98 | 4.3871 | 677.2494 | 1084122.78
2024-02 | 24 | 136 | 2668329 | 4535986 | 7204315 | 28 | 21738.1 | 32.9791 | 15082629.83 | 4.8571 | 693.8339 | 1120761.7161
2024-03 | 16 | 90 | 1802497 | 3087259 | 4889756 | 30 | 26851.2 | 33.6666 | 18559083.74 | 3 | 691.1827 | 760690.1317
2024-04 | 32 | 166 | 3262077 | 4902668 | 8164745 | 30 | 73305.5 | 36.6055 | 45746366.29 | 5.5333 | 624.0509 | 1270174.0024
2024-05 | 47 | 322 | 6335405 | 9203469 | 15538874 | 31 | 81874.1 | 32.504 | 58039986.55 | 10.3871 | 708.8931 | 2417353.3626
2024-06 | 45 | 262 | 5089157 | 7281705 | 12370862 | 27 | 27248.3 | 28.9906 | 22021295.55 | 9.7037 | 808.1714 | 1924511.7023
2024-07 | 32 | 186 | 3709578 | 5238043 | 8947621 | 18 | 33191.5 | 38.6036 | 20095303.34 | 10.3333 | 605.4352 | 1391964.5472
2024-08 | 11 | 96 | 1919999 | 2204311 | 4124310 | 16 | 20437 | 28.1351 | 17218392.98 | 6 | 842.5108 | 641611.1391
2024-09 | 18 | 78 | 1537494 | 2137474 | 3674968 | 25 | 16488.1 | 33.786 | 10919375.29 | 3.12 | 662.2579 | 571707.8504
2024-10 | 18 | 84 | 1682493 | 2351460 | 4033953 | 30 | 30021.4 | 35.983 | 19567628.46 | 2.8 | 651.7893 | 627554.4708
2024-11 | 16 | 118 | 2343747 | 3266634 | 5610381 | 30 | 48442.3 | 34.2578 | 32291856.02 | 3.9333 | 666.6045 | 872796.4057
2024-12 | 38 | 198 | 3872906 | 6551205 | 10424111 | 31 | 50341.8 | 33.2095 | 34811438.08 | 6.3871 | 691.5017 | 1621659.3157
2025-01 | 35 | 194 | 3804572 | 6043872 | 9848444 | 5 | 2638.6 | 22.27 | 2741536.73 | 38.8 | 1039.0119 | 1532103.8847
2025-02 | 12 | 92 | 1775830 | 2415883 | 4191713 | 0 | 0 | 0 | 0 |  |  | 652096.8968

## KPI_Savings
Scenario | Savings_USD | Savings_pct_of_Impact | Baseline_Source
Conservative | 15412920 | 7.7784 | Validated Stage 2G.10.1
Target | 30825850 | 15.5568 | Validated Stage 2G.10.1
Stretch | 46238770 | 23.3352 | Validated Stage 2G.10.1

## KPI_Action
NPT_Category | Root_Cause | Responsible_Party | Corrective_Action | Action_Status | NPT_Events | NPT_Hours | Total_Impact | Target_Savings_USD | Action_Rank
Drilling | Bit Wear | Directional Drilling | Condition Hole | Closed | 5 | 48 | 2941304 | 457573.1237 | 1
Logistics | Customs Clearance | Supply Chain | Air Freight Materials | Closed | 5 | 46 | 2647056 | 411797.5165 | 2
Drilling | Formation Instability | Operator | Adjust Drilling Parameters | Closed | 5 | 42 | 2500695 | 389028.4114 | 3
Drilling | Bit Wear | Mud Engineering | Adjust Drilling Parameters | Closed | 5 | 46 | 2496596 | 388390.7377 | 4
Mechanical | Electrical Failure | Drilling Contractor | OEM Inspection | Closed | 6 | 44 | 2422522 | 376867.185 | 5
Drilling | Differential Sticking | Mud Engineering | Increase Mud Weight | Closed | 6 | 42 | 2256061 | 350971.1608 | 6
Weather | Strong Wind | Marine Operations | Suspend Operations | Closed | 4 | 36 | 2155954 | 335397.7033 | 7
Drilling | Bit Wear | Mud Engineering | Increase Mud Weight | Closed | 5 | 42 | 2045202 | 318168.2233 | 8
Weather | Storm | Weather | Resume Operations | Closed | 3 | 40 | 1973347 | 306989.8762 | 9
Mechanical | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Open | 2 | 36 | 1941595 | 302050.2774 | 10
Drilling | Unexpected Pressure | Operator | Condition Hole | Closed | 6 | 42 | 1904173 | 296228.6073 | 11
Mechanical | Equipment Wear | Maintenance Team | OEM Inspection | Closed | 4 | 34 | 1901925 | 295878.8902 | 12
Weather | Strong Wind | Marine Operations | Wait on Weather | Closed | 4 | 40 | 1900596 | 295672.1402 | 13
Logistics | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | Closed | 5 | 36 | 1875259 | 291730.5108 | 14
Logistics | Customs Clearance | Supply Chain | Expedite Shipment | Closed | 4 | 32 | 1857668 | 288993.9121 | 15
Drilling | Formation Instability | Directional Drilling | Run Fishing Tools | Closed | 4 | 40 | 1740814 | 270815.1554 | 16
Drilling | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Closed | 5 | 34 | 1718483 | 267341.1638 | 17
Mechanical | Poor Preventive Maintenance | OEM Vendor | Repair Component | Closed | 4 | 38 | 1713621 | 266584.7916 | 18
Weather | Strong Wind | Weather | Suspend Operations | Closed | 5 | 38 | 1696351 | 263898.1302 | 19
Weather | Lightning | Marine Operations | Resume Operations | Closed | 7 | 34 | 1693212 | 263409.8019 | 20
Drilling | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | Closed | 6 | 32 | 1649679 | 256637.4551 | 21
Drilling | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Closed | 4 | 38 | 1600380 | 248968.1025 | 22
Mechanical | Hydraulic Failure | Drilling Contractor | Repair Component | Closed | 3 | 28 | 1576514 | 245255.3138 | 23
Weather | Storm | Marine Operations | Wait on Weather | Closed | 5 | 30 | 1565240 | 243501.4389 | 24
Weather | Strong Wind | Marine Operations | Resume Operations | Closed | 5 | 26 | 1543499 | 240119.2324 | 25
Weather | High Waves | Weather | Resume Operations | Closed | 3 | 32 | 1519307 | 236355.7286 | 26
Weather | Strong Wind | Weather | Wait on Weather | Closed | 5 | 30 | 1509791 | 234875.3424 | 27
Weather | High Waves | Marine Operations | Resume Operations | Closed | 5 | 28 | 1455207 | 226383.8123 | 28
Weather | Heavy Rain | Weather | Wait on Weather | Closed | 4 | 32 | 1448389 | 225323.1489 | 29
Weather | Heavy Rain | Marine Operations | Suspend Operations | Closed | 4 | 32 | 1428987 | 222304.8163 | 30
Mechanical | Equipment Wear | Drilling Contractor | Repair Component | Closed | 4 | 28 | 1419575 | 220840.6092 | 31
Mechanical | Poor Preventive Maintenance | Drilling Contractor | Repair Component | Closed | 2 | 24 | 1416581 | 220374.8382 | 32
Drilling | Differential Sticking | Operator | Run Fishing Tools | Closed | 4 | 36 | 1415526 | 220210.7139 | 33
Drilling | Formation Instability | Directional Drilling | Condition Hole | Closed | 4 | 32 | 1409701 | 219304.5296 | 34
Mechanical | Equipment Wear | Drilling Contractor | Replace Equipment | Closed | 6 | 28 | 1404184 | 218446.2603 | 35
Mechanical | Equipment Wear | Maintenance Team | Replace Equipment | In Progress | 1 | 24 | 1403802 | 218386.8333 | 36
Mechanical | Equipment Wear | Maintenance Team | Repair Component | Closed | 3 | 24 | 1367890 | 212800.071 | 37
Logistics | Material Shortage | Procurement | Expedite Shipment | Closed | 5 | 28 | 1358697 | 211369.9334 | 38
Mechanical | Hydraulic Failure | OEM Vendor | OEM Inspection | In Progress | 3 | 24 | 1302904 | 202690.3214 | 39
Logistics | Material Shortage | Marine Logistics | Mobilize Supply Vessel | Closed | 3 | 24 | 1288494 | 200448.5849 | 40
Drilling | Formation Instability | Mud Engineering | Adjust Drilling Parameters | Closed | 5 | 26 | 1287431 | 200283.216 | 41
Personnel | Medical Emergency | Medical Team | Medical Clearance | Closed | 2 | 22 | 1284141 | 199771.3968 | 42
Drilling | Differential Sticking | Mud Engineering | Run Fishing Tools | Closed | 4 | 32 | 1276897 | 198644.4614 | 43
Mechanical | Equipment Wear | OEM Vendor | Replace Equipment | Closed | 2 | 20 | 1267723 | 197217.2795 | 44
Drilling | Bit Wear | Mud Engineering | Condition Hole | Closed | 3 | 26 | 1260705 | 196125.5025 | 45
Drilling | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | Open | 1 | 18 | 1230862 | 191482.8832 | 46
Logistics | Customs Clearance | Procurement | Expedite Shipment | In Progress | 1 | 24 | 1223810 | 190385.8168 | 47
Weather | Heavy Rain | Weather | Suspend Operations | Closed | 3 | 22 | 1220410 | 189856.8852 | 48
Logistics | Port Congestion | Supply Chain | Mobilize Supply Vessel | Open | 3 | 22 | 1200866 | 186816.4619 | 49
Drilling | Bit Wear | Operator | Run Fishing Tools | Closed | 2 | 24 | 1190338 | 185178.6408 | 50
Logistics | Port Congestion | Marine Logistics | Mobilize Supply Vessel | Closed | 2 | 22 | 1182499 | 183959.1423 | 51
Drilling | Formation Instability | Operator | Adjust Drilling Parameters | In Progress | 4 | 20 | 1169931 | 182003.9622 | 52
Weather | Heavy Rain | Weather | Suspend Operations | In Progress | 1 | 18 | 1133348 | 176312.8138 | 53
Logistics | Late Supply Vessel | Marine Logistics | Expedite Shipment | Closed | 6 | 20 | 1116140 | 173635.7977 | 54
Weather | Lightning | Weather | Suspend Operations | Closed | 7 | 20 | 1100557 | 171211.5797 | 55
Weather | Heavy Rain | Marine Operations | Suspend Operations | In Progress | 2 | 24 | 1085839 | 168921.9282 | 56
Mechanical | Electrical Failure | Drilling Contractor | Preventive Maintenance | Closed | 3 | 20 | 1062946 | 165360.5073 | 57
Logistics | Late Supply Vessel | Supply Chain | Air Freight Materials | Closed | 2 | 22 | 1049218 | 163224.8682 | 58
Mechanical | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | Closed | 3 | 24 | 1041690 | 162053.7514 | 59
Weather | Lightning | Weather | Resume Operations | Closed | 4 | 20 | 1018406 | 158431.5034 | 60
Logistics | Port Congestion | Supply Chain | Expedite Shipment | Closed | 2 | 18 | 1013657 | 157692.7104 | 61
Weather | Lightning | Weather | Wait on Weather | Closed | 5 | 22 | 990711 | 154123.0444 | 62
Drilling | Unexpected Pressure | Mud Engineering | Increase Mud Weight | Closed | 3 | 20 | 981213 | 152645.4584 | 63
Mechanical | Equipment Wear | OEM Vendor | Preventive Maintenance | Closed | 2 | 20 | 944371 | 146914.0179 | 64
Drilling | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | In Progress | 1 | 18 | 910252 | 141606.1893 | 65
Weather | High Waves | Marine Operations | Wait on Weather | In Progress | 3 | 16 | 896056 | 139397.7443 | 66
Logistics | Port Congestion | Supply Chain | Air Freight Materials | Open | 1 | 24 | 887460 | 138060.4808 | 67
Drilling | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Closed | 3 | 16 | 884221 | 137556.5956 | 68
Mechanical | Equipment Wear | OEM Vendor | Replace Equipment | Open | 2 | 16 | 882113 | 137228.6581 | 69
Mechanical | Hydraulic Failure | OEM Vendor | OEM Inspection | Closed | 2 | 20 | 881030 | 137060.1778 | 70
Logistics | Customs Clearance | Procurement | Air Freight Materials | Closed | 3 | 14 | 873117 | 135829.1673 | 71
Mechanical | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | Open | 3 | 18 | 858605 | 133571.5628 | 72
Mechanical | Electrical Failure | OEM Vendor | Repair Component | Closed | 4 | 20 | 852884 | 132681.5576 | 73
Weather | Lightning | Marine Operations | Wait on Weather | In Progress | 2 | 14 | 851110 | 132405.5797 | 74
Mechanical | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Open | 1 | 18 | 848296 | 131967.8111 | 75
Weather | High Waves | Marine Operations | Suspend Operations | Closed | 4 | 18 | 841682 | 130938.8835 | 76
Weather | Lightning | Marine Operations | Suspend Operations | Closed | 2 | 14 | 828675 | 128915.409 | 77
Weather | Strong Wind | Marine Operations | Suspend Operations | In Progress | 1 | 12 | 825843 | 128474.8401 | 78
Drilling | Bit Wear | Operator | Run Fishing Tools | Open | 3 | 16 | 817774 | 127219.561 | 79
Drilling | Differential Sticking | Operator | Condition Hole | Closed | 4 | 16 | 815336 | 126840.2859 | 80
Mechanical | Hydraulic Failure | Maintenance Team | Replace Equipment | Closed | 2 | 16 | 800436 | 124522.321 | 81
Logistics | Material Shortage | Marine Logistics | Expedite Shipment | Closed | 4 | 18 | 793604 | 123459.4796 | 82
Mechanical | OEM Defect | Maintenance Team | Replace Equipment | Closed | 1 | 18 | 763285 | 118742.8099 | 83
Mechanical | Poor Preventive Maintenance | Maintenance Team | Repair Component | In Progress | 2 | 12 | 762321 | 118592.8422 | 84
Personnel | Medical Emergency | Rig Management | Crew Replacement | In Progress | 1 | 18 | 756321 | 117659.4335 | 85
Weather | Heavy Rain | Marine Operations | Resume Operations | Closed | 4 | 14 | 750919 | 116819.0546 | 86
Drilling | Differential Sticking | Operator | Adjust Drilling Parameters | Closed | 3 | 18 | 748274 | 116407.5769 | 87
Drilling | Bit Wear | Operator | Adjust Drilling Parameters | In Progress | 3 | 16 | 741593 | 115368.2263 | 88
Mechanical | Equipment Wear | Drilling Contractor | Repair Component | In Progress | 2 | 14 | 738959 | 114958.4599 | 89
Drilling | Differential Sticking | Mud Engineering | Condition Hole | In Progress | 1 | 18 | 735612 | 114437.7734 | 90
Drilling | Unexpected Pressure | Mud Engineering | Condition Hole | Closed | 4 | 16 | 727528 | 113180.1608 | 91
Mechanical | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | Closed | 2 | 16 | 726803 | 113067.3739 | 92
Mechanical | Hydraulic Failure | Drilling Contractor | Repair Component | In Progress | 2 | 14 | 723367 | 112532.8418 | 93
Weather | Heavy Rain | Marine Operations | Wait on Weather | In Progress | 1 | 12 | 723028 | 112480.1042 | 94
Drilling | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | In Progress | 3 | 18 | 712472 | 110837.9272 | 95
Weather | Heavy Rain | Weather | Resume Operations | Closed | 3 | 20 | 712142 | 110786.5897 | 96
Mechanical | Electrical Failure | OEM Vendor | Preventive Maintenance | Closed | 3 | 18 | 711334 | 110660.8907 | 97
Drilling | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Closed | 4 | 16 | 709641 | 110397.5138 | 98
Logistics | Port Congestion | Marine Logistics | Expedite Shipment | Closed | 2 | 14 | 705796 | 109799.3544 | 99
Weather | High Waves | Weather | Wait on Weather | Closed | 2 | 14 | 685861 | 106698.104 | 100
Personnel | Crew Rotation | Rig Management | Medical Clearance | Closed | 2 | 20 | 685344 | 106617.6753 | 101
Mechanical | Electrical Failure | OEM Vendor | OEM Inspection | Closed | 2 | 14 | 682934 | 106242.7562 | 102
Drilling | Bit Wear | Operator | Condition Hole | Closed | 4 | 14 | 678898 | 105614.8832 | 103
Drilling | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Closed | 4 | 14 | 675160 | 105033.3696 | 104
Drilling | Unexpected Pressure | Operator | Increase Mud Weight | Closed | 3 | 18 | 669500 | 104152.8541 | 105
Mechanical | Electrical Failure | Drilling Contractor | Repair Component | Closed | 2 | 16 | 668721 | 104031.6665 | 106
Drilling | Unexpected Pressure | Operator | Adjust Drilling Parameters | Closed | 4 | 14 | 665427 | 103519.2251 | 107
Drilling | Bit Wear | Directional Drilling | Increase Mud Weight | Closed | 2 | 12 | 664429 | 103363.9682 | 108
Mechanical | Equipment Wear | OEM Vendor | Repair Component | Closed | 3 | 16 | 664269 | 103339.0773 | 109
Mechanical | Hydraulic Failure | Drilling Contractor | Replace Equipment | Open | 2 | 14 | 660890 | 102813.4126 | 110
Drilling | Formation Instability | Mud Engineering | Run Fishing Tools | Closed | 4 | 14 | 659598 | 102612.4186 | 111
Drilling | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | Closed | 2 | 14 | 658638 | 102463.0732 | 112
Drilling | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 10 | 654502 | 101819.6435 | 113
Logistics | Late Supply Vessel | Procurement | Expedite Shipment | Closed | 4 | 12 | 643719 | 100142.1525 | 114
Mechanical | OEM Defect | Drilling Contractor | OEM Inspection | Closed | 2 | 10 | 630034 | 98013.2028 | 115
Personnel | Crew Rotation | Medical Team | Crew Replacement | Closed | 2 | 14 | 620573 | 96541.3728 | 116
Drilling | Formation Instability | Operator | Increase Mud Weight | Closed | 3 | 16 | 619715 | 96407.8954 | 117
Logistics | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | Closed | 1 | 12 | 617611 | 96080.5801 | 118
Mechanical | Equipment Wear | OEM Vendor | OEM Inspection | Closed | 2 | 10 | 615566 | 95762.4433 | 119
Weather | Storm | Weather | Suspend Operations | Closed | 4 | 12 | 613859 | 95496.8885 | 120
Weather | High Waves | Weather | Suspend Operations | Closed | 2 | 14 | 608320 | 94635.1967 | 121
Mechanical | OEM Defect | Drilling Contractor | Repair Component | Closed | 4 | 14 | 598875 | 93165.8558 | 122
Drilling | Unexpected Pressure | Mud Engineering | Run Fishing Tools | In Progress | 2 | 12 | 592778 | 92217.357 | 123
Mechanical | Electrical Failure | Drilling Contractor | Replace Equipment | Closed | 2 | 10 | 587653 | 91420.0704 | 124
Weather | Lightning | Marine Operations | Wait on Weather | Closed | 4 | 14 | 586436 | 91230.744 | 125
Weather | Storm | Marine Operations | Resume Operations | In Progress | 2 | 12 | 573989 | 89294.3877 | 126
Weather | Strong Wind | Marine Operations | Resume Operations | Open | 1 | 18 | 560297 | 87164.349 | 127
Logistics | Customs Clearance | Marine Logistics | Air Freight Materials | Closed | 2 | 14 | 559945 | 87109.5891 | 128
Mechanical | Hydraulic Failure | Maintenance Team | OEM Inspection | Closed | 2 | 12 | 544245 | 84667.1696 | 129
Weather | High Waves | Weather | Suspend Operations | Open | 1 | 8 | 543123 | 84492.6222 | 130
Drilling | Formation Instability | Operator | Run Fishing Tools | Closed | 4 | 10 | 539910 | 83992.7818 | 131
Logistics | Port Congestion | Procurement | Mobilize Supply Vessel | Closed | 3 | 10 | 536596 | 83477.2291 | 132
Drilling | Bit Wear | Directional Drilling | Adjust Drilling Parameters | Closed | 2 | 10 | 533802 | 83042.5718 | 133
Drilling | Formation Instability | Operator | Condition Hole | In Progress | 3 | 10 | 532190 | 82791.796 | 134
Weather | Heavy Rain | Marine Operations | Suspend Operations | Open | 1 | 8 | 524772 | 81637.7917 | 135
Drilling | Formation Instability | Directional Drilling | Adjust Drilling Parameters | Open | 2 | 10 | 524233 | 81553.9405 | 136
Mechanical | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | Closed | 3 | 12 | 523356 | 81417.5072 | 137
Drilling | Unexpected Pressure | Directional Drilling | Condition Hole | Closed | 3 | 12 | 516077 | 80285.1269 | 138
Logistics | Customs Clearance | Procurement | Mobilize Supply Vessel | Closed | 2 | 10 | 514866 | 80096.7339 | 139
Mechanical | OEM Defect | OEM Vendor | OEM Inspection | Closed | 2 | 8 | 507810 | 78999.0453 | 140
Drilling | Differential Sticking | Operator | Increase Mud Weight | Closed | 3 | 12 | 506910 | 78859.034 | 141
Drilling | Formation Instability | Directional Drilling | Increase Mud Weight | Closed | 2 | 14 | 505704 | 78671.4188 | 142
Mechanical | Poor Preventive Maintenance | Maintenance Team | Repair Component | Closed | 3 | 12 | 503984 | 78403.8417 | 143
Drilling | Unexpected Pressure | Operator | Run Fishing Tools | Open | 1 | 8 | 495628 | 77103.9145 | 144
Mechanical | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | Closed | 2 | 8 | 491097 | 76399.0354 | 145
Drilling | Differential Sticking | Directional Drilling | Condition Hole | Open | 1 | 8 | 488768 | 76036.7172 | 146
Logistics | Material Shortage | Procurement | Expedite Shipment | In Progress | 2 | 10 | 475501 | 73972.795 | 147
Logistics | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | In Progress | 2 | 10 | 474827 | 73867.9421 | 148
Drilling | Unexpected Pressure | Directional Drilling | Increase Mud Weight | In Progress | 2 | 12 | 474423 | 73805.0926 | 149
Weather | Heavy Rain | Weather | Wait on Weather | Open | 1 | 12 | 469440 | 73029.8967 | 150
Mechanical | Hydraulic Failure | Maintenance Team | Replace Equipment | In Progress | 2 | 14 | 466630 | 72592.7503 | 151
Mechanical | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | Closed | 2 | 10 | 462706 | 71982.301 | 152
Weather | Lightning | Weather | Wait on Weather | In Progress | 2 | 10 | 458870 | 71385.5417 | 153
Weather | Heavy Rain | Weather | Resume Operations | In Progress | 2 | 8 | 457277 | 71137.7217 | 154
Logistics | Port Congestion | Procurement | Expedite Shipment | Closed | 2 | 10 | 455947 | 70930.8161 | 155
Mechanical | OEM Defect | OEM Vendor | Repair Component | Closed | 2 | 10 | 454661 | 70730.7555 | 156
Weather | High Waves | Marine Operations | Wait on Weather | Closed | 3 | 12 | 450998 | 70160.9095 | 157
Mechanical | Equipment Wear | Maintenance Team | Repair Component | In Progress | 1 | 12 | 449568 | 69938.4471 | 158
Mechanical | Equipment Wear | Maintenance Team | OEM Inspection | In Progress | 1 | 8 | 447806 | 69664.336 | 159
Drilling | Unexpected Pressure | Operator | Increase Mud Weight | Open | 1 | 8 | 439871 | 68429.903 | 160
Mechanical | OEM Defect | Drilling Contractor | Preventive Maintenance | Closed | 2 | 10 | 435704 | 67781.6507 | 161
Drilling | Differential Sticking | Directional Drilling | Run Fishing Tools | Closed | 2 | 8 | 433799 | 67485.2934 | 162
Mechanical | Hydraulic Failure | Drilling Contractor | Replace Equipment | Closed | 2 | 10 | 433547 | 67446.0903 | 163
Weather | Strong Wind | Marine Operations | Wait on Weather | In Progress | 2 | 8 | 433113 | 67378.5737 | 164
Logistics | Customs Clearance | Procurement | Expedite Shipment | Closed | 1 | 8 | 432665 | 67308.8792 | 165
Logistics | Material Shortage | Procurement | Air Freight Materials | Closed | 1 | 6 | 424036 | 65966.4819 | 166
Mechanical | Electrical Failure | Maintenance Team | OEM Inspection | Closed | 2 | 8 | 422889 | 65788.0453 | 167
Drilling | Bit Wear | Directional Drilling | Run Fishing Tools | Closed | 3 | 8 | 422578 | 65739.6636 | 168
Mechanical | Electrical Failure | OEM Vendor | Replace Equipment | Closed | 2 | 8 | 421811 | 65620.3428 | 169
Mechanical | Equipment Wear | Drilling Contractor | OEM Inspection | Closed | 3 | 8 | 414429 | 64471.939 | 170
Mechanical | OEM Defect | OEM Vendor | Replace Equipment | Closed | 1 | 8 | 414076 | 64417.0235 | 171
Personnel | Training Requirement | HR | Medical Clearance | Closed | 2 | 8 | 413001 | 64249.7877 | 172
Drilling | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | In Progress | 1 | 6 | 409922 | 63770.7935 | 173
Drilling | Differential Sticking | Directional Drilling | Run Fishing Tools | In Progress | 1 | 6 | 398656 | 62018.1631 | 174
Logistics | Port Congestion | Supply Chain | Mobilize Supply Vessel | Closed | 1 | 8 | 392444 | 61051.774 | 175
Logistics | Customs Clearance | Supply Chain | Mobilize Supply Vessel | Closed | 1 | 6 | 390341 | 60724.6142 | 176
Logistics | Customs Clearance | Marine Logistics | Expedite Shipment | Closed | 2 | 6 | 388306 | 60408.0331 | 177
Weather | Strong Wind | Weather | Resume Operations | Open | 1 | 6 | 388120 | 60379.0974 | 178
Logistics | Late Supply Vessel | Procurement | Air Freight Materials | Closed | 2 | 8 | 379170 | 58986.7628 | 179
Personnel | Medical Emergency | HR | Crew Replacement | Closed | 1 | 6 | 376090 | 58507.613 | 180
Mechanical | Hydraulic Failure | Drilling Contractor | Repair Component | Open | 1 | 6 | 365352 | 56837.1225 | 181
Drilling | Differential Sticking | Directional Drilling | Condition Hole | In Progress | 1 | 8 | 364022 | 56630.2169 | 182
Mechanical | Hydraulic Failure | Maintenance Team | Preventive Maintenance | Open | 1 | 12 | 363301 | 56518.0523 | 183
Drilling | Formation Instability | Operator | Condition Hole | Closed | 1 | 6 | 362949 | 56463.2924 | 184
Mechanical | Electrical Failure | OEM Vendor | Replace Equipment | Open | 1 | 6 | 362320 | 56365.44 | 185
Logistics | Late Supply Vessel | Marine Logistics | Air Freight Materials | Closed | 2 | 10 | 360764 | 56123.376 | 186
Weather | Strong Wind | Weather | Resume Operations | Closed | 1 | 8 | 358157 | 55717.8099 | 187
Weather | Storm | Marine Operations | Suspend Operations | In Progress | 2 | 8 | 357570 | 55626.4915 | 188
Weather | Lightning | Weather | Suspend Operations | Open | 1 | 6 | 351890 | 54742.8646 | 189
Logistics | Port Congestion | Procurement | Expedite Shipment | Open | 1 | 8 | 351618 | 54700.55 | 190
Drilling | Differential Sticking | Directional Drilling | Increase Mud Weight | Closed | 1 | 6 | 343111 | 53377.1321 | 191
Logistics | Material Shortage | Supply Chain | Expedite Shipment | In Progress | 2 | 8 | 340552 | 52979.0333 | 192
Weather | Heavy Rain | Weather | Wait on Weather | In Progress | 2 | 8 | 337185 | 52455.2354 | 193
Weather | Storm | Weather | Wait on Weather | In Progress | 1 | 6 | 337173 | 52453.3686 | 194
Weather | Storm | Marine Operations | Resume Operations | Closed | 3 | 6 | 327667 | 50974.5381 | 195
Personnel | Training Requirement | HR | Safety Briefing | Closed | 2 | 10 | 326916 | 50857.7064 | 196
Drilling | Unexpected Pressure | Mud Engineering | Run Fishing Tools | Open | 1 | 8 | 324904 | 50544.7034 | 197
Drilling | Formation Instability | Mud Engineering | Run Fishing Tools | Open | 2 | 10 | 323370 | 50306.0619 | 198
Mechanical | Equipment Wear | Maintenance Team | Replace Equipment | Closed | 2 | 6 | 322428 | 50159.5167 | 199
Weather | Storm | Weather | Resume Operations | Open | 1 | 8 | 318983 | 49623.5845 | 200
Drilling | Differential Sticking | Mud Engineering | Condition Hole | Closed | 1 | 6 | 317496 | 49392.2548 | 201
Weather | High Waves | Marine Operations | Suspend Operations | In Progress | 2 | 6 | 316171 | 49186.127 | 202
Weather | Storm | Weather | Wait on Weather | Closed | 2 | 8 | 310807 | 48351.6596 | 203
Weather | Lightning | Weather | Suspend Operations | In Progress | 1 | 6 | 309279 | 48113.9515 | 204
Drilling | Differential Sticking | Directional Drilling | Condition Hole | Closed | 2 | 6 | 309204 | 48102.2839 | 205
Logistics | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | In Progress | 1 | 6 | 308615 | 48010.6543 | 206
Mechanical | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | Open | 2 | 8 | 307463 | 47831.4398 | 207
Drilling | Differential Sticking | Directional Drilling | Run Fishing Tools | Open | 2 | 6 | 304780 | 47414.0506 | 208
Drilling | Bit Wear | Operator | Increase Mud Weight | Closed | 2 | 8 | 303591 | 47229.0801 | 209
Weather | Heavy Rain | Marine Operations | Resume Operations | Open | 2 | 8 | 302650 | 47082.6905 | 210
Drilling | Unexpected Pressure | Operator | Adjust Drilling Parameters | Open | 1 | 8 | 297440 | 46272.1806 | 211
Mechanical | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | Open | 1 | 6 | 293383 | 45641.0408 | 212
Mechanical | Hydraulic Failure | Maintenance Team | Repair Component | Closed | 1 | 4 | 280600 | 43652.4135 | 213
Logistics | Material Shortage | Supply Chain | Expedite Shipment | Closed | 1 | 4 | 280384 | 43618.8108 | 214
Mechanical | OEM Defect | Maintenance Team | Preventive Maintenance | Closed | 2 | 6 | 277804 | 43217.4451 | 215
Weather | Lightning | Marine Operations | Resume Operations | Open | 1 | 4 | 276806 | 43062.1881 | 216
Drilling | Bit Wear | Directional Drilling | Increase Mud Weight | In Progress | 1 | 6 | 276785 | 43058.9212 | 217
Drilling | Formation Instability | Operator | Condition Hole | Open | 1 | 6 | 276085 | 42950.0235 | 218
Weather | Lightning | Marine Operations | Resume Operations | In Progress | 1 | 6 | 271006 | 42159.893 | 219
Personnel | Training Requirement | Medical Team | Medical Clearance | Closed | 2 | 4 | 264071 | 41081.0281 | 220
Weather | Strong Wind | Weather | Wait on Weather | Open | 1 | 6 | 263523 | 40995.7768 | 221
Mechanical | Equipment Wear | Drilling Contractor | Repair Component | Open | 1 | 4 | 261526 | 40685.1073 | 222
Drilling | Unexpected Pressure | Mud Engineering | Condition Hole | In Progress | 1 | 6 | 261222 | 40637.8146 | 223
Weather | High Waves | Weather | Resume Operations | In Progress | 1 | 6 | 256971 | 39976.4945 | 224
Logistics | Port Congestion | Marine Logistics | Air Freight Materials | Closed | 2 | 6 | 256417 | 39890.3098 | 225
Logistics | Late Supply Vessel | Supply Chain | Expedite Shipment | Closed | 2 | 4 | 256404 | 39888.2874 | 226
Weather | High Waves | Marine Operations | Suspend Operations | Open | 2 | 6 | 254279 | 39557.7051 | 227
Mechanical | Hydraulic Failure | Drilling Contractor | OEM Inspection | In Progress | 1 | 6 | 252040 | 39209.3881 | 228
Mechanical | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | In Progress | 1 | 4 | 250433 | 38959.3902 | 229
Mechanical | Electrical Failure | Drilling Contractor | OEM Inspection | Open | 1 | 4 | 250300 | 38938.6996 | 230
Drilling | Bit Wear | Operator | Condition Hole | Open | 1 | 4 | 248562 | 38668.3222 | 231
Logistics | Material Shortage | Procurement | Mobilize Supply Vessel | Open | 1 | 4 | 245667 | 38217.9525 | 232
Personnel | Training Requirement | Rig Management | Medical Clearance | Closed | 1 | 8 | 245289 | 38159.1478 | 233
Drilling | Unexpected Pressure | Directional Drilling | Condition Hole | In Progress | 2 | 6 | 242740 | 37762.6046 | 234
Logistics | Material Shortage | Supply Chain | Expedite Shipment | Open | 1 | 4 | 242362 | 37703.7999 | 235
Logistics | Customs Clearance | Procurement | Air Freight Materials | Open | 1 | 4 | 239783 | 37302.5897 | 236
Drilling | Unexpected Pressure | Directional Drilling | Run Fishing Tools | Open | 1 | 8 | 239696 | 37289.0553 | 237
Mechanical | OEM Defect | OEM Vendor | Preventive Maintenance | In Progress | 1 | 6 | 239454 | 37251.4078 | 238
Mechanical | Equipment Wear | Drilling Contractor | OEM Inspection | In Progress | 1 | 4 | 236497 | 36791.3929 | 239
Mechanical | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | Closed | 2 | 6 | 235083 | 36571.4196 | 240
Mechanical | Electrical Failure | OEM Vendor | OEM Inspection | In Progress | 1 | 6 | 233378 | 36306.1759 | 241
Personnel | Medical Emergency | HR | Medical Clearance | In Progress | 1 | 6 | 232452 | 36162.1198 | 242
Logistics | Customs Clearance | Marine Logistics | Expedite Shipment | Open | 1 | 4 | 231017 | 35938.8796 | 243
Drilling | Formation Instability | Mud Engineering | Increase Mud Weight | In Progress | 1 | 4 | 230562 | 35868.0961 | 244
Logistics | Late Supply Vessel | Procurement | Mobilize Supply Vessel | Closed | 1 | 4 | 227308 | 35361.8775 | 245
Personnel | Medical Emergency | Rig Management | Safety Briefing | In Progress | 1 | 4 | 227010 | 35315.5182 | 246
Drilling | Formation Instability | Mud Engineering | Increase Mud Weight | Closed | 1 | 4 | 226267 | 35199.931 | 247
Logistics | Customs Clearance | Procurement | Expedite Shipment | Open | 2 | 4 | 224568 | 34935.6208 | 248
Logistics | Port Congestion | Supply Chain | Air Freight Materials | Closed | 1 | 6 | 224082 | 34860.0147 | 249
Personnel | Training Requirement | Rig Management | Safety Briefing | Closed | 1 | 6 | 223591 | 34783.6308 | 250
Personnel | Crew Rotation | Medical Team | Safety Briefing | In Progress | 1 | 6 | 213210 | 33168.6781 | 251
Mechanical | Electrical Failure | Drilling Contractor | OEM Inspection | In Progress | 1 | 6 | 208334 | 32410.128 | 252
Weather | High Waves | Marine Operations | Wait on Weather | Open | 1 | 4 | 205920 | 32034.5866 | 253
Mechanical | Hydraulic Failure | OEM Vendor | Preventive Maintenance | In Progress | 1 | 6 | 205497 | 31968.7813 | 254
Drilling | Unexpected Pressure | Operator | Increase Mud Weight | In Progress | 1 | 4 | 202954 | 31573.1715 | 255
Logistics | Customs Clearance | Supply Chain | Mobilize Supply Vessel | In Progress | 1 | 4 | 201829 | 31398.1574 | 256
Mechanical | Electrical Failure | Maintenance Team | Repair Component | In Progress | 1 | 6 | 201020 | 31272.3028 | 257
Weather | Strong Wind | Marine Operations | Resume Operations | In Progress | 1 | 4 | 200001 | 31113.7789 | 258
Mechanical | OEM Defect | Maintenance Team | Repair Component | Closed | 2 | 4 | 199844 | 31089.3547 | 259
Drilling | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | Open | 1 | 4 | 199028 | 30962.4111 | 260
Weather | Heavy Rain | Marine Operations | Wait on Weather | Closed | 1 | 4 | 196795 | 30615.0275 | 261
Drilling | Formation Instability | Mud Engineering | Condition Hole | Closed | 2 | 4 | 195946 | 30482.9502 | 262
Weather | Storm | Weather | Suspend Operations | In Progress | 1 | 4 | 190528 | 29640.0821 | 263
Weather | Strong Wind | Weather | Resume Operations | In Progress | 2 | 4 | 184149 | 28647.7131 | 264
Logistics | Late Supply Vessel | Procurement | Expedite Shipment | In Progress | 1 | 6 | 180226 | 28037.4194 | 265
Logistics | Material Shortage | Procurement | Mobilize Supply Vessel | Closed | 1 | 4 | 176722 | 27492.3087 | 266
Personnel | Training Requirement | Rig Management | Medical Clearance | In Progress | 1 | 4 | 176480 | 27454.6612 | 267
Personnel | Training Requirement | Medical Team | Medical Clearance | In Progress | 1 | 4 | 175762 | 27342.9633 | 268
Mechanical | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | In Progress | 1 | 4 | 172374 | 26815.8985 | 269
Mechanical | Equipment Wear | OEM Vendor | Replace Equipment | In Progress | 1 | 4 | 172131 | 26778.0955 | 270
Mechanical | Hydraulic Failure | Maintenance Team | OEM Inspection | In Progress | 1 | 4 | 168452 | 26205.7604 | 271
Mechanical | OEM Defect | Maintenance Team | Preventive Maintenance | Open | 1 | 4 | 167299 | 26026.3903 | 272
Personnel | Training Requirement | Rig Management | Crew Replacement | Closed | 1 | 4 | 156113 | 24286.2054 | 273
Mechanical | Electrical Failure | Maintenance Team | OEM Inspection | Open | 1 | 4 | 153062 | 23811.5671 | 274
Logistics | Customs Clearance | Procurement | Mobilize Supply Vessel | Open | 1 | 4 | 149184 | 23208.2739 | 275
Logistics | Material Shortage | Supply Chain | Air Freight Materials | Closed | 1 | 4 | 146520 | 22793.8404 | 276
Mechanical | OEM Defect | Drilling Contractor | Replace Equipment | In Progress | 1 | 4 | 144589 | 22493.4384 | 277
Mechanical | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | Open | 1 | 4 | 144441 | 22470.4143 | 278
Logistics | Material Shortage | Marine Logistics | Air Freight Materials | In Progress | 1 | 4 | 143153 | 22270.0426 | 279
Logistics | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | In Progress | 1 | 2 | 141074 | 21946.6165 | 280
Drilling | Formation Instability | Directional Drilling | Increase Mud Weight | In Progress | 1 | 2 | 136963 | 21307.076 | 281
Drilling | Bit Wear | Mud Engineering | Run Fishing Tools | In Progress | 1 | 4 | 136897 | 21296.8085 | 282
Weather | Lightning | Marine Operations | Wait on Weather | Open | 1 | 2 | 133395 | 20752.0089 | 283
Mechanical | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | Closed | 1 | 2 | 132117 | 20553.1929 | 284
Mechanical | Equipment Wear | OEM Vendor | Preventive Maintenance | Open | 1 | 4 | 131948 | 20526.9019 | 285
Weather | Lightning | Marine Operations | Suspend Operations | Open | 1 | 2 | 130889 | 20362.1552 | 286
Drilling | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | Open | 1 | 4 | 128909 | 20054.1303 | 287
Mechanical | Electrical Failure | OEM Vendor | Replace Equipment | In Progress | 1 | 2 | 128096 | 19927.6535 | 288
Drilling | Bit Wear | Operator | Increase Mud Weight | In Progress | 1 | 2 | 125483 | 19521.154 | 289
Drilling | Formation Instability | Operator | Increase Mud Weight | In Progress | 1 | 2 | 125034 | 19451.3039 | 290
Drilling | Unexpected Pressure | Directional Drilling | Increase Mud Weight | Open | 1 | 2 | 124705 | 19400.122 | 291
Mechanical | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | In Progress | 1 | 2 | 124400 | 19352.6737 | 292
Drilling | Formation Instability | Directional Drilling | Adjust Drilling Parameters | In Progress | 1 | 2 | 123601 | 19228.3748 | 293
Drilling | Formation Instability | Mud Engineering | Increase Mud Weight | Open | 1 | 4 | 122835 | 19109.2096 | 294
Mechanical | Hydraulic Failure | OEM Vendor | Replace Equipment | Closed | 1 | 2 | 121900 | 18963.7534 | 295
Mechanical | Equipment Wear | Drilling Contractor | Preventive Maintenance | In Progress | 1 | 2 | 121891 | 18962.3533 | 296
Mechanical | Electrical Failure | Maintenance Team | Preventive Maintenance | Open | 1 | 2 | 120946 | 18815.3414 | 297
Weather | Lightning | Marine Operations | Suspend Operations | In Progress | 1 | 2 | 119622 | 18609.3692 | 298
Weather | Storm | Weather | Suspend Operations | Open | 1 | 4 | 117708 | 18311.6119 | 299
Mechanical | Electrical Failure | OEM Vendor | Repair Component | Open | 1 | 2 | 111750 | 17384.737 | 300
Personnel | Training Requirement | Medical Team | Safety Briefing | Closed | 1 | 2 | 111032 | 17273.0391 | 301
Personnel | Training Requirement | Medical Team | Safety Briefing | In Progress | 1 | 2 | 104829 | 16308.0501 | 302
Personnel | Medical Emergency | Rig Management | Safety Briefing | Closed | 1 | 2 | 100926 | 15700.8677 | 303
Drilling | Unexpected Pressure | Operator | Run Fishing Tools | In Progress | 1 | 2 | 100507 | 15635.6847 | 304
Logistics | Late Supply Vessel | Supply Chain | Expedite Shipment | In Progress | 1 | 2 | 97761 | 15208.4946 | 305
Drilling | Formation Instability | Directional Drilling | Run Fishing Tools | In Progress | 1 | 2 | 95282 | 14822.8413 | 306
Mechanical | Electrical Failure | OEM Vendor | Preventive Maintenance | Open | 1 | 2 | 94282 | 14667.2732 | 307
Personnel | Training Requirement | HR | Crew Replacement | Closed | 1 | 2 | 93981 | 14620.4472 | 308
Mechanical | Equipment Wear | Maintenance Team | Preventive Maintenance | Closed | 1 | 2 | 92909 | 14453.6781 | 309
Mechanical | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | In Progress | 1 | 2 | 92820 | 14439.8326 | 310
Drilling | Differential Sticking | Operator | Increase Mud Weight | Open | 1 | 2 | 91943 | 14303.3993 | 311
Personnel | Crew Rotation | Medical Team | Safety Briefing | Closed | 1 | 2 | 90635 | 14099.9163 | 312
Weather | Storm | Marine Operations | Suspend Operations | Closed | 1 | 2 | 89808 | 13971.2614 | 313
Mechanical | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | Closed | 1 | 2 | 88341 | 13743.043 | 314
Logistics | Port Congestion | Procurement | Air Freight Materials | Closed | 1 | 2 | 82862 | 12890.6853 | 315
Logistics | Customs Clearance | Marine Logistics | Expedite Shipment | In Progress | 1 | 2 | 82480 | 12831.2583 | 316
Mechanical | Electrical Failure | OEM Vendor | OEM Inspection | Open | 1 | 2 | 82273 | 12799.0557 | 317
Mechanical | Hydraulic Failure | OEM Vendor | Preventive Maintenance | Closed | 1 | 2 | 79500 | 12367.6653 | 318
Logistics | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | Closed | 1 | 2 | 78248 | 12172.894 | 319
Weather | Heavy Rain | Marine Operations | Wait on Weather | Open | 1 | 2 | 73818 | 11483.7272 | 320
Drilling | Unexpected Pressure | Operator | Run Fishing Tools | Closed | 1 | 2 | 68914 | 10720.8212 | 321
Weather | Storm | Marine Operations | Suspend Operations | Open | 1 | 2 | 68172 | 10605.3896 | 322
Drilling | Bit Wear | Mud Engineering | Increase Mud Weight | Open | 1 | 2 | 67544 | 10507.6929 | 323
Personnel | Medical Emergency | HR | Safety Briefing | Closed | 1 | 2 | 65522 | 10193.1341 | 324
Drilling | Formation Instability | Mud Engineering | Condition Hole | In Progress | 1 | 2 | 64142 | 9978.4501 | 325
Drilling | Bit Wear | Directional Drilling | Run Fishing Tools | In Progress | 1 | 2 | 58573 | 9112.0913 | 326

## Data_Quality
Check | Actual | Expected | Status
NPT rows | 677 | 677 | PASS
Drilling rows | 1474 | 1474 | PASS
Unique NPT IDs | 677 | 677 | PASS
Duplicate NPT IDs | 0 | 0 | PASS
Null NPT IDs | 0 | 0 | PASS
Negative NPT Hours | 0 | 0 | PASS
Negative Direct Cost | 0 | 0 | PASS
Economic Difference vs Stage 2G.10.1 | 0 | 0 | PASS
Target Savings Positive | 30825850 | > 0 | PASS