## Executive_Scorecard
KPI | Value | Unit
NPT Events | 677 | events
NPT Hours | 4008 | hours
Direct NPT Cost | 79204408 | USD
Deferred Cost | 118945770 | USD
Total Economic Impact | 198150178 | USD
Validated Target Savings | 30825850 | USD
Validated Conservative Savings | 15412920 | USD
Validated Stretch Savings | 46238770 | USD
Target Savings Rate | 0.15557 | %
Unique Wells | 50 | wells
Unique Rigs | 4 | rigs
Total Footage | 952078.8 | ft
Average ROP | 33.6733 | ft/hr
Cost per Foot | 687.6662 | USD/ft
NPT Hours per Well | 80.16 | hr/well
Direct NPT Cost per Event | 116993.2171 | USD/event

## Management_Dashboard
Management_Area | Metric | Actual | Reference | Priority
Operational Exposure | Total NPT Hours | 4008 | 4,008 | HIGH
Economic Exposure | Total Economic Impact | 198150178 | 198150178 | CRITICAL
Savings Opportunity | Target Savings | 30825850 | 30825850 | CRITICAL
Rig Exposure | Highest NPT Rig | R002 | 76560445 | REVIEW
Root Cause Exposure | Highest Impact Root Cause | Differential Sticking | 4901437 | REVIEW
Initiative Portfolio | Critical Initiatives | 3 | 3 | CRITICAL

## Rig_Scorecard
Rank | Rig_ID | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Wells | Impact_per_NPT_Hour | Impact_per_Well | Impact_Share_pct | Management_Priority
1 | R002 | 282 | 1610 | 30858241 | 45702204 | 76560445 | 20 | 47553.0714 | 3828022.25 | 0.38638 | CRITICAL
2 | R004 | 199 | 1186 | 24214105 | 37256294 | 61470399 | 16 | 51830.016 | 3841899.9375 | 0.31022 | HIGH
3 | R003 | 116 | 694 | 13880000 | 20516458 | 34396458 | 8 | 49562.6196 | 4299557.25 | 0.17359 | MEDIUM
4 | R001 | 80 | 518 | 10252062 | 15470814 | 25722876 | 6 | 49658.0618 | 4287146 | 0.12982 | MEDIUM

## Well_Scorecard
Rank | Well_ID | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Rig_ID | Impact_Share_pct | Management_Priority
1 | W007 | 16 | 128 | 2533329 | 4282582 | 6815911 | R001 | 0.034398 | HIGH
2 | W040 | 21 | 130 | 2491660 | 4128450 | 6620110 | R002 | 0.03341 | HIGH
3 | W019 | 13 | 114 | 2280000 | 3281717 | 5561717 | R003 | 0.028068 | HIGH
4 | W036 | 19 | 108 | 2069994 | 3341514 | 5411508 | R002 | 0.02731 | HIGH
5 | W003 | 13 | 88 | 1796663 | 3429015 | 5225678 | R004 | 0.026372 | HIGH
6 | W011 | 16 | 104 | 2123328 | 3064293 | 5187621 | R004 | 0.02618 | HIGH
7 | W046 | 16 | 102 | 2040000 | 2992158 | 5032158 | R003 | 0.025396 | HIGH
8 | W013 | 20 | 96 | 1920000 | 2963822 | 4883822 | R003 | 0.024647 | HIGH
9 | W023 | 14 | 84 | 1714995 | 3113218 | 4828213 | R004 | 0.024366 | HIGH
10 | W010 | 16 | 106 | 2031661 | 2703200 | 4734861 | R002 | 0.023895 | HIGH
11 | W009 | 15 | 100 | 1979163 | 2690209 | 4669372 | R001 | 0.023565 | HIGH
12 | W001 | 19 | 88 | 1796660 | 2808881 | 4605541 | R004 | 0.023243 | HIGH
13 | W020 | 20 | 90 | 1800000 | 2765483 | 4565483 | R003 | 0.023041 | HIGH
14 | W045 | 10 | 80 | 1633331 | 2920236 | 4553567 | R004 | 0.02298 | HIGH
15 | W002 | 13 | 88 | 1741664 | 2804697 | 4546361 | R001 | 0.022944 | HIGH
16 | W021 | 16 | 94 | 1801664 | 2704639 | 4506303 | R002 | 0.022742 | HIGH
17 | W026 | 11 | 90 | 1837497 | 2615327 | 4452824 | R004 | 0.022472 | HIGH
18 | W015 | 14 | 76 | 1520000 | 2865282 | 4385282 | R003 | 0.022131 | HIGH
19 | W043 | 18 | 94 | 1801662 | 2548737 | 4350399 | R002 | 0.021955 | HIGH
20 | W032 | 15 | 86 | 1755829 | 2495861 | 4251690 | R004 | 0.021457 | HIGH
21 | W033 | 16 | 90 | 1724995 | 2518455 | 4243450 | R002 | 0.021415 | HIGH
22 | W006 | 15 | 84 | 1609994 | 2621287 | 4231281 | R002 | 0.021354 | HIGH
23 | W048 | 14 | 86 | 1648329 | 2560594 | 4208923 | R002 | 0.021241 | HIGH
24 | W028 | 15 | 90 | 1724995 | 2418055 | 4143050 | R002 | 0.020909 | HIGH
25 | W030 | 15 | 90 | 1724996 | 2412390 | 4137386 | R002 | 0.02088 | HIGH
26 | W047 | 13 | 78 | 1592495 | 2325588 | 3918083 | R004 | 0.019773 | MEDIUM
27 | W050 | 11 | 74 | 1510831 | 2383689 | 3894520 | R004 | 0.019654 | MEDIUM
28 | W018 | 14 | 88 | 1796662 | 2059142 | 3855804 | R004 | 0.019459 | MEDIUM
29 | W034 | 12 | 74 | 1464578 | 2192968 | 3657546 | R001 | 0.018458 | MEDIUM
30 | W035 | 12 | 92 | 1840000 | 1755897 | 3595897 | R003 | 0.018147 | MEDIUM
31 | W038 | 15 | 68 | 1388328 | 2167309 | 3555637 | R004 | 0.017944 | MEDIUM
32 | W041 | 14 | 76 | 1456662 | 2055484 | 3512146 | R002 | 0.017725 | MEDIUM
33 | W022 | 13 | 74 | 1464580 | 1977792 | 3442372 | R001 | 0.017373 | MEDIUM
34 | W044 | 12 | 64 | 1280000 | 2137944 | 3417944 | R003 | 0.017249 | MEDIUM
35 | W029 | 14 | 70 | 1341662 | 2007400 | 3349062 | R002 | 0.016902 | MEDIUM
36 | W024 | 12 | 68 | 1303329 | 1939009 | 3242338 | R002 | 0.016363 | MEDIUM
37 | W012 | 11 | 64 | 1306664 | 1927076 | 3233740 | R004 | 0.01632 | MEDIUM
38 | W027 | 10 | 66 | 1264997 | 1957712 | 3222709 | R002 | 0.016264 | MEDIUM
39 | W037 | 9 | 72 | 1379996 | 1814397 | 3194393 | R002 | 0.016121 | MEDIUM
40 | W005 | 13 | 64 | 1226662 | 1917071 | 3143733 | R002 | 0.015865 | MEDIUM
41 | W039 | 13 | 70 | 1341663 | 1781728 | 3123391 | R002 | 0.015763 | MEDIUM
42 | W031 | 11 | 60 | 1149994 | 1882761 | 3032755 | R002 | 0.015305 | MEDIUM
43 | W049 | 9 | 60 | 1200000 | 1754155 | 2954155 | R003 | 0.014909 | MEDIUM
44 | W025 | 11 | 54 | 1102497 | 1756149 | 2858646 | R004 | 0.014427 | MEDIUM
45 | W017 | 11 | 54 | 1068748 | 1522566 | 2591314 | R001 | 0.013078 | MEDIUM
46 | W016 | 10 | 50 | 1020830 | 1523000 | 2543830 | R004 | 0.012838 | MEDIUM
47 | W042 | 8 | 52 | 1061665 | 1336502 | 2398167 | R004 | 0.012103 | MEDIUM
48 | W004 | 11 | 52 | 996663 | 1337831 | 2334494 | R002 | 0.011781 | MEDIUM
49 | W014 | 8 | 38 | 775830 | 1331008 | 2106838 | R004 | 0.010633 | MEDIUM
50 | W008 | 10 | 40 | 766663 | 1051490 | 1818153 | R002 | 0.0091756 | LOW

## Root_Cause_Scorecard
Rank | NPT_Category | NPT_Subcategory | Root_Cause | NPT_Events | NPT_Hours | Direct_NPT_Cost | Deferred_Cost | Total_Impact | Wells | Rigs | Impact_Share_pct | Management_Priority
1 | Drilling | Hole Cleaning | Differential Sticking | 11 | 104 | 2066665 | 2834772 | 4901437 | 11 | 4 | 0.024736 | HIGH
2 | Drilling | Lost Circulation | Formation Instability | 14 | 100 | 1981663 | 2901287 | 4882950 | 12 | 4 | 0.024643 | HIGH
3 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 9 | 78 | 1543331 | 2977401 | 4520732 | 9 | 4 | 0.022815 | HIGH
4 | Mechanical | Top Drive Failure | Equipment Wear | 11 | 78 | 1558748 | 2885338 | 4444086 | 8 | 3 | 0.022428 | HIGH
5 | Weather | Poor Visibility | Heavy Rain | 9 | 78 | 1549998 | 2632300 | 4182298 | 8 | 4 | 0.021107 | HIGH
6 | Drilling | Stuck Pipe | Differential Sticking | 12 | 80 | 1569998 | 2407503 | 3977501 | 11 | 3 | 0.020073 | HIGH
7 | Logistics | Fuel Supply Delay | Customs Clearance | 10 | 70 | 1402081 | 2525058 | 3927139 | 10 | 4 | 0.019819 | MEDIUM
8 | Drilling | Stuck Pipe | Unexpected Pressure | 13 | 86 | 1682913 | 2230605 | 3913518 | 10 | 4 | 0.01975 | MEDIUM
9 | Drilling | Fishing Operation | Formation Instability | 11 | 66 | 1295414 | 2239341 | 3534755 | 10 | 4 | 0.017839 | MEDIUM
10 | Logistics | Delayed Helicopter | Customs Clearance | 7 | 60 | 1175832 | 2261890 | 3437722 | 7 | 3 | 0.017349 | MEDIUM
11 | Weather | Poor Visibility | Strong Wind | 8 | 58 | 1156248 | 2154902 | 3311150 | 7 | 4 | 0.01671 | MEDIUM
12 | Weather | Lightning | Lightning | 16 | 66 | 1304996 | 1998325 | 3303321 | 13 | 4 | 0.016671 | MEDIUM
13 | Drilling | Well Control | Bit Wear | 7 | 54 | 1079999 | 2143918 | 3223917 | 7 | 3 | 0.01627 | MEDIUM
14 | Drilling | Bit Failure | Differential Sticking | 11 | 62 | 1217497 | 1881562 | 3099059 | 9 | 3 | 0.01564 | MEDIUM
15 | Mechanical | Draw Works Failure | Hydraulic Failure | 8 | 62 | 1201249 | 1895418 | 3096667 | 8 | 4 | 0.015628 | MEDIUM
16 | Drilling | Stuck Pipe | Bit Wear | 9 | 66 | 1298332 | 1680271 | 2978603 | 9 | 3 | 0.015032 | MEDIUM
17 | Drilling | Hole Cleaning | Unexpected Pressure | 13 | 60 | 1191245 | 1693337 | 2884582 | 12 | 4 | 0.014558 | MEDIUM
18 | Mechanical | BOP Repair | Equipment Wear | 6 | 56 | 1076665 | 1702576 | 2779241 | 6 | 2 | 0.014026 | MEDIUM
19 | Drilling | Bit Failure | Unexpected Pressure | 9 | 54 | 1057497 | 1668602 | 2726099 | 8 | 2 | 0.013758 | MEDIUM
20 | Weather | Heavy Rain | Strong Wind | 7 | 54 | 1054999 | 1664879 | 2719878 | 7 | 3 | 0.013726 | MEDIUM
21 | Drilling | Fishing Operation | Differential Sticking | 8 | 58 | 1139998 | 1563488 | 2703486 | 8 | 3 | 0.013644 | MEDIUM
22 | Drilling | Bit Failure | Bit Wear | 6 | 52 | 1031666 | 1630205 | 2661871 | 5 | 3 | 0.013434 | MEDIUM
23 | Drilling | Lost Circulation | Bit Wear | 10 | 48 | 962498 | 1660551 | 2623049 | 9 | 3 | 0.013238 | MEDIUM
24 | Weather | Lightning | High Waves | 7 | 56 | 1102081 | 1475836 | 2577917 | 6 | 4 | 0.01301 | MEDIUM
25 | Mechanical | Generator Failure | Equipment Wear | 8 | 44 | 871247 | 1668377 | 2539624 | 7 | 4 | 0.012817 | MEDIUM
26 | Weather | High Waves | Strong Wind | 6 | 52 | 1050416 | 1459561 | 2509977 | 5 | 3 | 0.012667 | MEDIUM
27 | Mechanical | Power System Failure | Electrical Failure | 7 | 48 | 932499 | 1532530 | 2465029 | 7 | 2 | 0.01244 | MEDIUM
28 | Logistics | Waiting on Cement | Late Supply Vessel | 9 | 48 | 944582 | 1430326 | 2374908 | 8 | 4 | 0.011985 | MEDIUM
29 | Weather | Heavy Rain | Heavy Rain | 7 | 50 | 995831 | 1320639 | 2316470 | 6 | 3 | 0.01169 | MEDIUM
30 | Weather | High Waves | Lightning | 8 | 42 | 830414 | 1481859 | 2312273 | 8 | 4 | 0.011669 | MEDIUM
31 | Drilling | Hole Cleaning | Bit Wear | 8 | 48 | 944165 | 1243309 | 2187474 | 7 | 3 | 0.011039 | MEDIUM
32 | Logistics | Waiting on Cement | Port Congestion | 4 | 40 | 786666 | 1339376 | 2126042 | 4 | 2 | 0.010729 | MEDIUM
33 | Mechanical | BOP Repair | Electrical Failure | 5 | 40 | 799166 | 1293219 | 2092385 | 5 | 3 | 0.01056 | MEDIUM
34 | Weather | Heavy Rain | Storm | 5 | 40 | 806665 | 1238920 | 2045585 | 5 | 2 | 0.010323 | MEDIUM
35 | Mechanical | Mud Pump Failure | Equipment Wear | 4 | 32 | 641249 | 1387470 | 2028719 | 4 | 3 | 0.010238 | MEDIUM
36 | Weather | Lightning | Heavy Rain | 6 | 44 | 852499 | 1170307 | 2022806 | 5 | 3 | 0.010208 | MEDIUM
37 | Drilling | Stuck Pipe | Formation Instability | 9 | 42 | 835831 | 1173548 | 2009379 | 9 | 4 | 0.010141 | MEDIUM
38 | Drilling | Well Control | Formation Instability | 9 | 40 | 780831 | 1215998 | 1996829 | 8 | 3 | 0.010077 | MEDIUM
39 | Drilling | Well Control | Unexpected Pressure | 11 | 40 | 792496 | 1169804 | 1962300 | 10 | 3 | 0.0099031 | LOW
40 | Drilling | Lost Circulation | Unexpected Pressure | 8 | 50 | 979165 | 938555 | 1917720 | 8 | 3 | 0.0096781 | LOW
41 | Weather | Strong Wind | Strong Wind | 8 | 40 | 789164 | 1106026 | 1895190 | 8 | 4 | 0.0095644 | LOW
42 | Logistics | Fuel Supply Delay | Material Shortage | 7 | 36 | 722082 | 1163978 | 1886060 | 6 | 4 | 0.0095183 | LOW
43 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 8 | 46 | 906665 | 948398 | 1855063 | 7 | 3 | 0.0093619 | LOW
44 | Logistics | Waiting on Materials | Port Congestion | 6 | 40 | 784165 | 1065507 | 1849672 | 6 | 4 | 0.0093347 | LOW
45 | Logistics | Waiting on Materials | Material Shortage | 6 | 38 | 739582 | 1109984 | 1849566 | 6 | 3 | 0.0093342 | LOW
46 | Mechanical | Power System Failure | Equipment Wear | 6 | 42 | 822499 | 1005627 | 1828126 | 6 | 2 | 0.009226 | LOW
47 | Weather | Heavy Rain | Lightning | 7 | 30 | 599997 | 1202260 | 1802257 | 7 | 3 | 0.0090954 | LOW
48 | Logistics | Fuel Supply Delay | Late Supply Vessel | 7 | 42 | 835416 | 957166 | 1792582 | 7 | 4 | 0.0090466 | LOW
49 | Logistics | Waiting on Cement | Customs Clearance | 6 | 34 | 671666 | 1050007 | 1721673 | 6 | 4 | 0.0086887 | LOW
50 | Drilling | Lost Circulation | Differential Sticking | 6 | 32 | 619582 | 1089510 | 1709092 | 6 | 3 | 0.0086252 | LOW
51 | Personnel | Crew Change | Medical Emergency | 4 | 30 | 597499 | 1104524 | 1702023 | 4 | 2 | 0.0085896 | LOW
52 | Weather | Strong Wind | High Waves | 6 | 32 | 628331 | 1054951 | 1683282 | 6 | 3 | 0.008495 | LOW
53 | Weather | Heavy Rain | High Waves | 7 | 28 | 553332 | 1109002 | 1662334 | 7 | 4 | 0.0083893 | LOW
54 | Weather | Lightning | Storm | 5 | 32 | 643331 | 1001943 | 1645274 | 5 | 3 | 0.0083032 | LOW
55 | Mechanical | Rotary Table Failure | Electrical Failure | 7 | 36 | 716248 | 907156 | 1623404 | 7 | 3 | 0.0081928 | LOW
56 | Drilling | Fishing Operation | Unexpected Pressure | 8 | 38 | 754164 | 857869 | 1612033 | 8 | 3 | 0.0081354 | LOW
57 | Weather | Lightning | Strong Wind | 4 | 32 | 645833 | 937366 | 1583199 | 4 | 2 | 0.0079899 | LOW
58 | Mechanical | Power System Failure | Poor Preventive Maintenance | 6 | 34 | 669998 | 866201 | 1536199 | 6 | 3 | 0.0077527 | LOW
59 | Mechanical | Generator Failure | Poor Preventive Maintenance | 5 | 34 | 655832 | 767650 | 1423482 | 5 | 3 | 0.0071839 | LOW
60 | Weather | High Waves | Heavy Rain | 6 | 28 | 550832 | 864044 | 1414876 | 6 | 3 | 0.0071404 | LOW
61 | Logistics | Delayed Helicopter | Port Congestion | 7 | 30 | 580832 | 824579 | 1405411 | 6 | 3 | 0.0070927 | LOW
62 | Weather | High Waves | High Waves | 5 | 30 | 587499 | 792461 | 1379960 | 5 | 2 | 0.0069642 | LOW
63 | Weather | Poor Visibility | Lightning | 7 | 30 | 577497 | 802418 | 1379915 | 7 | 2 | 0.006964 | LOW
64 | Mechanical | BOP Repair | Hydraulic Failure | 4 | 26 | 508332 | 848294 | 1356626 | 4 | 3 | 0.0068465 | LOW
65 | Drilling | Fishing Operation | Bit Wear | 5 | 22 | 439999 | 895741 | 1335740 | 5 | 3 | 0.006741 | LOW
66 | Mechanical | Mud Pump Failure | Hydraulic Failure | 5 | 30 | 584166 | 745713 | 1329879 | 5 | 3 | 0.0067115 | LOW
67 | Logistics | Delayed Helicopter | Late Supply Vessel | 6 | 22 | 428331 | 875049 | 1303380 | 6 | 3 | 0.0065777 | LOW
68 | Mechanical | Draw Works Failure | Equipment Wear | 6 | 26 | 515831 | 748648 | 1264479 | 6 | 3 | 0.0063814 | LOW
69 | Logistics | Waiting on Boat | Late Supply Vessel | 4 | 24 | 487499 | 772844 | 1260343 | 4 | 2 | 0.0063605 | LOW
70 | Mechanical | BOP Repair | Poor Preventive Maintenance | 5 | 20 | 393331 | 857732 | 1251063 | 5 | 3 | 0.0063137 | LOW
71 | Weather | High Waves | Storm | 5 | 24 | 489998 | 735629 | 1225627 | 5 | 1 | 0.0061853 | LOW
72 | Mechanical | Top Drive Failure | OEM Defect | 6 | 26 | 525832 | 680599 | 1206431 | 6 | 2 | 0.0060885 | LOW
73 | Mechanical | Draw Works Failure | Electrical Failure | 6 | 26 | 528330 | 673549 | 1201879 | 6 | 2 | 0.0060655 | LOW
74 | Mechanical | Mud Pump Failure | OEM Defect | 4 | 28 | 540416 | 646576 | 1186992 | 4 | 2 | 0.0059904 | LOW
75 | Mechanical | Generator Failure | Hydraulic Failure | 4 | 24 | 481249 | 685879 | 1167128 | 4 | 2 | 0.0058901 | LOW
76 | Logistics | Delayed Helicopter | Material Shortage | 3 | 20 | 388332 | 775327 | 1163659 | 3 | 2 | 0.0058726 | LOW
77 | Mechanical | Top Drive Failure | Electrical Failure | 6 | 26 | 512081 | 583510 | 1095591 | 6 | 3 | 0.0055291 | LOW
78 | Mechanical | Rotary Table Failure | Hydraulic Failure | 3 | 26 | 508333 | 583307 | 1091640 | 3 | 2 | 0.0055092 | LOW
79 | Mechanical | Power System Failure | Hydraulic Failure | 3 | 18 | 349999 | 671660 | 1021659 | 3 | 2 | 0.005156 | LOW
80 | Logistics | Waiting on Boat | Port Congestion | 3 | 16 | 325000 | 696659 | 1021659 | 3 | 2 | 0.005156 | LOW
81 | Personnel | Safety Stand Down | Training Requirement | 6 | 26 | 512498 | 507434 | 1019932 | 6 | 3 | 0.0051473 | LOW
82 | Drilling | Hole Cleaning | Formation Instability | 6 | 20 | 394581 | 617521 | 1012102 | 5 | 4 | 0.0051078 | LOW
83 | Weather | Strong Wind | Storm | 6 | 24 | 470832 | 525189 | 996021 | 6 | 3 | 0.0050266 | LOW
84 | Drilling | Bit Failure | Formation Instability | 7 | 24 | 477915 | 513530 | 991445 | 7 | 3 | 0.0050035 | LOW
85 | Personnel | Medical Evacuation | Training Requirement | 6 | 22 | 433332 | 556695 | 990027 | 6 | 3 | 0.0049963 | LOW
86 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 3 | 18 | 361666 | 627201 | 988867 | 3 | 3 | 0.0049905 | LOW
87 | Personnel | Safety Stand Down | Medical Emergency | 3 | 24 | 489166 | 475183 | 964349 | 3 | 2 | 0.0048668 | LOW
88 | Weather | Poor Visibility | Storm | 6 | 22 | 440415 | 491929 | 932344 | 5 | 3 | 0.0047052 | LOW
89 | Weather | Strong Wind | Heavy Rain | 4 | 24 | 473749 | 454800 | 928549 | 3 | 3 | 0.0046861 | LOW
90 | Mechanical | Mud Pump Failure | Electrical Failure | 4 | 16 | 308333 | 617706 | 926039 | 4 | 2 | 0.0046734 | LOW
91 | Mechanical | Top Drive Failure | Hydraulic Failure | 4 | 24 | 477499 | 441196 | 918695 | 4 | 3 | 0.0046364 | LOW
92 | Logistics | Fuel Supply Delay | Port Congestion | 1 | 24 | 490000 | 397460 | 887460 | 1 | 1 | 0.0044787 | LOW
93 | Mechanical | Draw Works Failure | OEM Defect | 5 | 20 | 394581 | 487681 | 882262 | 5 | 3 | 0.0044525 | LOW
94 | Logistics | Waiting on Materials | Late Supply Vessel | 4 | 16 | 314165 | 541644 | 855809 | 4 | 3 | 0.004319 | LOW
95 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 2 | 22 | 437916 | 362099 | 800015 | 2 | 2 | 0.0040374 | LOW
96 | Mechanical | BOP Repair | OEM Defect | 3 | 14 | 279999 | 517334 | 797333 | 3 | 3 | 0.0040239 | LOW
97 | Personnel | Safety Stand Down | Crew Rotation | 4 | 18 | 355416 | 437332 | 792748 | 4 | 3 | 0.0040007 | LOW
98 | Weather | Poor Visibility | High Waves | 4 | 18 | 348748 | 381654 | 730402 | 4 | 2 | 0.0036861 | LOW
99 | Logistics | Waiting on Cement | Material Shortage | 4 | 16 | 318333 | 368157 | 686490 | 4 | 3 | 0.0034645 | LOW
100 | Logistics | Waiting on Boat | Customs Clearance | 3 | 10 | 199999 | 403967 | 603966 | 3 | 3 | 0.003048 | LOW
101 | Personnel | Crew Change | Crew Rotation | 1 | 18 | 367500 | 236304 | 603804 | 1 | 1 | 0.0030472 | LOW
102 | Logistics | Waiting on Materials | Customs Clearance | 4 | 12 | 234998 | 310459 | 545457 | 4 | 2 | 0.0027527 | LOW
103 | Mechanical | Power System Failure | OEM Defect | 2 | 10 | 191666 | 339541 | 531207 | 2 | 1 | 0.0026808 | LOW
104 | Mechanical | Rotary Table Failure | Equipment Wear | 3 | 10 | 200832 | 176403 | 377235 | 3 | 3 | 0.0019038 | LOW
105 | Personnel | Medical Evacuation | Medical Emergency | 1 | 6 | 122500 | 253590 | 376090 | 1 | 1 | 0.001898 | LOW
106 | Mechanical | Generator Failure | Electrical Failure | 2 | 8 | 153333 | 221795 | 375128 | 2 | 1 | 0.0018931 | LOW
107 | Logistics | Waiting on Boat | Material Shortage | 3 | 8 | 162082 | 167835 | 329917 | 2 | 2 | 0.001665 | LOW
108 | Weather | Strong Wind | Lightning | 2 | 8 | 155833 | 167265 | 323098 | 2 | 2 | 0.0016306 | LOW
109 | Mechanical | Generator Failure | OEM Defect | 1 | 4 | 76666 | 152544 | 229210 | 1 | 1 | 0.0011567 | LOW
110 | Drilling | Well Control | Differential Sticking | 2 | 6 | 116666 | 100249 | 216915 | 2 | 2 | 0.0010947 | LOW
111 | Personnel | Training | Crew Rotation | 1 | 6 | 122500 | 90710 | 213210 | 1 | 1 | 0.001076 | LOW
112 | Personnel | Crew Change | Training Requirement | 1 | 4 | 76666 | 79447 | 156113 | 1 | 1 | 0.00078785 | LOW
113 | Personnel | Training | Training Requirement | 1 | 2 | 39583 | 85410 | 124993 | 1 | 1 | 0.0006308 | LOW

## Initiative_Scorecard
Rank | NPT_Category | NPT_Subcategory | Root_Cause | Responsible_Party | Corrective_Action | NPT_Events | Baseline_NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_Share_pct | Management_Priority
1 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Air Freight Materials | 3 | 36 | 2025768 | 315144.9125 | 0.010223 | MEDIUM
2 | Drilling | Hole Cleaning | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 3 | 38 | 2000357 | 311191.7711 | 0.010095 | MEDIUM
3 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | OEM Inspection | 2 | 32 | 1995386 | 310418.442 | 0.01007 | MEDIUM
4 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 32 | 1986528 | 309040.4196 | 0.010025 | MEDIUM
5 | Weather | Poor Visibility | Heavy Rain | Weather | Suspend Operations | 2 | 30 | 1924964 | 299463.024 | 0.0097147 | LOW
6 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 26 | 1687808 | 262569.1118 | 0.0085178 | LOW
7 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Replace Equipment | 2 | 28 | 1606675 | 249947.4038 | 0.0081084 | LOW
8 | Drilling | Fishing Operation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 26 | 1550070 | 241141.4705 | 0.0078227 | LOW
9 | Logistics | Delayed Helicopter | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 24 | 1475042 | 229469.5059 | 0.0074441 | LOW
10 | Logistics | Waiting on Materials | Material Shortage | Procurement | Expedite Shipment | 4 | 28 | 1433980 | 223081.5679 | 0.0072368 | LOW
11 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Repair Component | 2 | 24 | 1416581 | 220374.8382 | 0.007149 | LOW
12 | Drilling | Well Control | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 2 | 22 | 1397755 | 217446.1129 | 0.007054 | LOW
13 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Suspend Operations | 3 | 28 | 1371759 | 213401.9641 | 0.0069228 | LOW
14 | Weather | Heavy Rain | Strong Wind | Marine Operations | Wait on Weather | 2 | 26 | 1338154 | 208174.0975 | 0.0067532 | LOW
15 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Increase Mud Weight | 3 | 24 | 1332986 | 207370.1215 | 0.0067272 | LOW
16 | Drilling | Lost Circulation | Formation Instability | Operator | Adjust Drilling Parameters | 3 | 22 | 1322159 | 205685.7855 | 0.0066725 | LOW
17 | Weather | Heavy Rain | Heavy Rain | Weather | Wait on Weather | 3 | 26 | 1246345 | 193891.5443 | 0.0062899 | LOW
18 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Expedite Shipment | 1 | 24 | 1223810 | 190385.8168 | 0.0061762 | LOW
19 | Weather | Poor Visibility | Strong Wind | Marine Operations | Suspend Operations | 1 | 18 | 1219350 | 189691.983 | 0.0061537 | LOW
20 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 2 | 20 | 1212253 | 188587.9161 | 0.0061178 | LOW
21 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Increase Mud Weight | 2 | 26 | 1204623 | 187400.9314 | 0.0060793 | LOW
22 | Drilling | Well Control | Bit Wear | Directional Drilling | Condition Hole | 1 | 18 | 1154940 | 179671.8406 | 0.0058286 | LOW
23 | Weather | Lightning | High Waves | Weather | Resume Operations | 1 | 24 | 1154701 | 179634.6598 | 0.0058274 | LOW
24 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Run Fishing Tools | 2 | 28 | 1145945 | 178272.5054 | 0.0057832 | LOW
25 | Personnel | Crew Change | Medical Emergency | Medical Team | Medical Clearance | 1 | 18 | 1141635 | 177602.0068 | 0.0057615 | LOW
26 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Repair Component | 4 | 22 | 1113727 | 173260.4118 | 0.0056206 | LOW
27 | Mechanical | Generator Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 18 | 1109300 | 172571.7118 | 0.0055983 | LOW
28 | Weather | Heavy Rain | Storm | Weather | Resume Operations | 1 | 24 | 1104657 | 171849.409 | 0.0055748 | LOW
29 | Mechanical | Generator Failure | Hydraulic Failure | Drilling Contractor | Repair Component | 3 | 22 | 1087628 | 169200.2395 | 0.0054889 | LOW
30 | Logistics | Waiting on Cement | Port Congestion | Supply Chain | Mobilize Supply Vessel | 2 | 18 | 1065290 | 165725.159 | 0.0053762 | LOW
31 | Weather | Poor Visibility | Strong Wind | Marine Operations | Resume Operations | 2 | 16 | 1053754 | 163930.5252 | 0.005318 | LOW
32 | Drilling | Bit Failure | Unexpected Pressure | Operator | Condition Hole | 2 | 20 | 1024439 | 159370.0458 | 0.00517 | LOW
33 | Mechanical | BOP Repair | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 18 | 1023187 | 159175.2745 | 0.0051637 | LOW
34 | Weather | Strong Wind | Strong Wind | Marine Operations | Wait on Weather | 4 | 22 | 995555 | 154876.6163 | 0.0050242 | LOW
35 | Weather | Lightning | Heavy Rain | Marine Operations | Suspend Operations | 2 | 24 | 959820 | 149317.3897 | 0.0048439 | LOW
36 | Logistics | Delayed Helicopter | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 3 | 16 | 944545 | 146941.0867 | 0.0047668 | LOW
37 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 2 | 20 | 944371 | 146914.0179 | 0.0047659 | LOW
38 | Logistics | Waiting on Cement | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 18 | 918898 | 142951.2312 | 0.0046374 | LOW
39 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 18 | 910252 | 141606.1893 | 0.0045937 | LOW
40 | Mechanical | Top Drive Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 3 | 16 | 889466 | 138372.5504 | 0.0044888 | LOW
41 | Logistics | Fuel Supply Delay | Port Congestion | Supply Chain | Air Freight Materials | 1 | 24 | 887460 | 138060.4808 | 0.0044787 | LOW
42 | Mechanical | Rotary Table Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 2 | 20 | 881030 | 137060.1778 | 0.0044463 | LOW
43 | Logistics | Waiting on Boat | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 2 | 16 | 865026 | 134570.4657 | 0.0043655 | LOW
44 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 16 | 863558 | 134342.0917 | 0.0043581 | LOW
45 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 18 | 848296 | 131967.8111 | 0.0042811 | LOW
46 | Weather | Lightning | Lightning | Weather | Suspend Operations | 5 | 16 | 835484 | 129974.6723 | 0.0042164 | LOW
47 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 3 | 18 | 829534 | 129049.0421 | 0.0041864 | LOW
48 | Weather | High Waves | Strong Wind | Marine Operations | Suspend Operations | 1 | 12 | 825843 | 128474.8401 | 0.0041678 | LOW
49 | Weather | Lightning | Strong Wind | Weather | Suspend Operations | 1 | 18 | 813357 | 126532.4166 | 0.0041048 | LOW
50 | Drilling | Fishing Operation | Formation Instability | Operator | Condition Hole | 4 | 16 | 808275 | 125741.8195 | 0.0040791 | LOW
51 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 2 | 22 | 800015 | 124456.8268 | 0.0040374 | LOW
52 | Drilling | Bit Failure | Bit Wear | Mud Engineering | Condition Hole | 1 | 12 | 799806 | 124424.3131 | 0.0040364 | LOW
53 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Condition Hole | 3 | 14 | 797972 | 124139.0012 | 0.0040271 | LOW
54 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Condition Hole | 1 | 12 | 784466 | 122037.8982 | 0.0039589 | LOW
55 | Logistics | Fuel Supply Delay | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 18 | 782733 | 121768.2986 | 0.0039502 | LOW
56 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Replace Equipment | 1 | 18 | 763285 | 118742.8099 | 0.0038521 | LOW
57 | Weather | High Waves | Lightning | Weather | Resume Operations | 2 | 14 | 762121 | 118561.7286 | 0.0038462 | LOW
58 | Drilling | Stuck Pipe | Differential Sticking | Directional Drilling | Run Fishing Tools | 3 | 12 | 756920 | 117752.6188 | 0.0038199 | LOW
59 | Personnel | Safety Stand Down | Medical Emergency | Rig Management | Crew Replacement | 1 | 18 | 756321 | 117659.4335 | 0.0038169 | LOW
60 | Drilling | Stuck Pipe | Bit Wear | Operator | Run Fishing Tools | 1 | 12 | 753399 | 117204.8635 | 0.0038022 | LOW
61 | Weather | Lightning | Lightning | Marine Operations | Wait on Weather | 3 | 14 | 743179 | 115614.9573 | 0.0037506 | LOW
62 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Condition Hole | 1 | 18 | 735612 | 114437.7734 | 0.0037124 | LOW
63 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 18 | 725594 | 112879.292 | 0.0036618 | LOW
64 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 2 | 12 | 724267 | 112672.8531 | 0.0036551 | LOW
65 | Weather | Lightning | Heavy Rain | Marine Operations | Wait on Weather | 1 | 12 | 723028 | 112480.1042 | 0.0036489 | LOW
66 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Condition Hole | 2 | 16 | 701596 | 109145.9684 | 0.0035407 | LOW
67 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Condition Hole | 2 | 16 | 699182 | 108770.4269 | 0.0035285 | LOW
68 | Drilling | Stuck Pipe | Differential Sticking | Operator | Run Fishing Tools | 2 | 20 | 692021 | 107656.4036 | 0.0034924 | LOW
69 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 10 | 688998 | 107186.1212 | 0.0034772 | LOW
70 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Expedite Shipment | 3 | 12 | 687915 | 107017.6409 | 0.0034717 | LOW
71 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 2 | 20 | 681870 | 106077.2317 | 0.0034412 | LOW
72 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 16 | 678675 | 105580.1915 | 0.0034251 | LOW
73 | Weather | Lightning | Storm | Weather | Resume Operations | 1 | 12 | 676874 | 105300.0134 | 0.003416 | LOW
74 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 18 | 674096 | 104867.8451 | 0.0034019 | LOW
75 | Weather | Strong Wind | Heavy Rain | Weather | Wait on Weather | 2 | 18 | 671484 | 104461.5012 | 0.0033888 | LOW
76 | Mechanical | Power System Failure | Electrical Failure | OEM Vendor | Replace Equipment | 2 | 12 | 662865 | 103120.6596 | 0.0033453 | LOW
77 | Weather | Heavy Rain | High Waves | Weather | Suspend Operations | 2 | 10 | 662540 | 103070.1 | 0.0033436 | LOW
78 | Weather | Heavy Rain | Strong Wind | Weather | Suspend Operations | 2 | 14 | 662374 | 103044.2757 | 0.0033428 | LOW
79 | Weather | High Waves | High Waves | Marine Operations | Resume Operations | 1 | 12 | 659330 | 102570.7263 | 0.0033274 | LOW
80 | Weather | Heavy Rain | Lightning | Marine Operations | Resume Operations | 2 | 10 | 654240 | 101778.8846 | 0.0033017 | LOW
81 | Drilling | Hole Cleaning | Bit Wear | Operator | Adjust Drilling Parameters | 2 | 14 | 653538 | 101669.6758 | 0.0032982 | LOW
82 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 3 | 18 | 650525 | 101200.9491 | 0.003283 | LOW
83 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 1 | 12 | 648094 | 100822.763 | 0.0032707 | LOW
84 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Increase Mud Weight | 2 | 12 | 642825 | 100003.0746 | 0.0032441 | LOW
85 | Weather | High Waves | Storm | Marine Operations | Wait on Weather | 1 | 12 | 639548 | 99493.2779 | 0.0032276 | LOW
86 | Logistics | Delayed Helicopter | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 12 | 637608 | 99191.4757 | 0.0032178 | LOW
87 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Expedite Shipment | 1 | 12 | 633320 | 98524.3996 | 0.0031962 | LOW
88 | Weather | High Waves | Strong Wind | Weather | Wait on Weather | 2 | 14 | 632812 | 98445.371 | 0.0031936 | LOW
89 | Mechanical | BOP Repair | OEM Defect | Drilling Contractor | OEM Inspection | 2 | 10 | 630034 | 98013.2028 | 0.0031796 | LOW
90 | Drilling | Well Control | Formation Instability | Operator | Adjust Drilling Parameters | 2 | 10 | 620732 | 96566.1082 | 0.0031326 | LOW
91 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Crew Replacement | 2 | 14 | 620573 | 96541.3728 | 0.0031318 | LOW
92 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 12 | 614455 | 95589.6071 | 0.003101 | LOW
93 | Weather | High Waves | Lightning | Marine Operations | Wait on Weather | 2 | 12 | 613679 | 95468.8862 | 0.003097 | LOW
94 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 12 | 613627 | 95460.7967 | 0.0030968 | LOW
95 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | Repair Component | 2 | 16 | 611277 | 95095.2116 | 0.0030849 | LOW
96 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 12 | 606765 | 94393.2883 | 0.0030621 | LOW
97 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 16 | 603848 | 93939.4961 | 0.0030474 | LOW
98 | Personnel | Crew Change | Crew Rotation | Rig Management | Medical Clearance | 1 | 18 | 603804 | 93932.6511 | 0.0030472 | LOW
99 | Weather | Lightning | High Waves | Marine Operations | Suspend Operations | 3 | 12 | 603759 | 93925.6505 | 0.003047 | LOW
100 | Weather | Strong Wind | Strong Wind | Marine Operations | Suspend Operations | 2 | 12 | 592985 | 92249.5596 | 0.0029926 | LOW
101 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Preventive Maintenance | 2 | 14 | 590628 | 91882.8856 | 0.0029807 | LOW
102 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 2 | 14 | 590044 | 91792.0338 | 0.0029778 | LOW
103 | Weather | Lightning | Lightning | Weather | Wait on Weather | 2 | 14 | 588737 | 91588.7063 | 0.0029712 | LOW
104 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Expedite Shipment | 2 | 10 | 574944 | 89442.9552 | 0.0029016 | LOW
105 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Increase Mud Weight | 3 | 12 | 570436 | 88741.6542 | 0.0028788 | LOW
106 | Drilling | Lost Circulation | Bit Wear | Operator | Run Fishing Tools | 1 | 8 | 568521 | 88443.7412 | 0.0028691 | LOW
107 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Replace Equipment | 2 | 12 | 566196 | 88082.0454 | 0.0028574 | LOW
108 | Weather | High Waves | Strong Wind | Marine Operations | Resume Operations | 1 | 18 | 560297 | 87164.349 | 0.0028276 | LOW
109 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 3 | 12 | 560259 | 87158.4375 | 0.0028274 | LOW
110 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 8 | 553128 | 86049.0812 | 0.0027915 | LOW
111 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Increase Mud Weight | 2 | 12 | 550011 | 85564.1754 | 0.0027757 | LOW
112 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 2 | 12 | 549958 | 85555.9303 | 0.0027755 | LOW
113 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 3 | 10 | 542032 | 84322.8974 | 0.0027355 | LOW
114 | Weather | High Waves | High Waves | Marine Operations | Wait on Weather | 3 | 12 | 535311 | 83277.3241 | 0.0027015 | LOW
115 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 10 | 534644 | 83173.5601 | 0.0026982 | LOW
116 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 12 | 531067 | 82617.093 | 0.0026801 | LOW
117 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 2 | 8 | 525857 | 81806.5831 | 0.0026538 | LOW
118 | Weather | High Waves | Heavy Rain | Marine Operations | Suspend Operations | 1 | 8 | 524772 | 81637.7917 | 0.0026484 | LOW
119 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Condition Hole | 1 | 12 | 523344 | 81415.6404 | 0.0026411 | LOW
120 | Drilling | Fishing Operation | Differential Sticking | Operator | Adjust Drilling Parameters | 2 | 12 | 521909 | 81192.4002 | 0.0026339 | LOW
121 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Repair Component | 3 | 12 | 519736 | 80854.3507 | 0.0026229 | LOW
122 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 8 | 517088 | 80442.4063 | 0.0026096 | LOW
123 | Mechanical | BOP Repair | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 8 | 515497 | 80194.8974 | 0.0026015 | LOW
124 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Expedite Shipment | 2 | 8 | 510936 | 79485.3512 | 0.0025785 | LOW
125 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 10 | 505330 | 78613.2364 | 0.0025502 | LOW
126 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 8 | 501153 | 77963.4284 | 0.0025292 | LOW
127 | Weather | Strong Wind | High Waves | Weather | Wait on Weather | 1 | 8 | 500542 | 77868.3762 | 0.0025261 | LOW
128 | Drilling | Hole Cleaning | Bit Wear | Operator | Run Fishing Tools | 2 | 14 | 499197 | 77659.1371 | 0.0025193 | LOW
129 | Weather | High Waves | Lightning | Marine Operations | Resume Operations | 2 | 8 | 497640 | 77416.9176 | 0.0025114 | LOW
130 | Weather | Lightning | Lightning | Marine Operations | Suspend Operations | 2 | 8 | 496272 | 77204.1004 | 0.0025045 | LOW
131 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 8 | 495628 | 77103.9145 | 0.0025013 | LOW
132 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 12 | 495392 | 77067.2004 | 0.0025001 | LOW
133 | Weather | Poor Visibility | Strong Wind | Weather | Wait on Weather | 2 | 10 | 490233 | 76264.6245 | 0.002474 | LOW
134 | Weather | Lightning | High Waves | Weather | Suspend Operations | 1 | 12 | 488903 | 76057.7189 | 0.0024673 | LOW
135 | Logistics | Fuel Supply Delay | Customs Clearance | Procurement | Air Freight Materials | 1 | 8 | 470980 | 73269.4716 | 0.0023769 | LOW
136 | Weather | Poor Visibility | Lightning | Marine Operations | Resume Operations | 2 | 12 | 467441 | 72718.916 | 0.002359 | LOW
137 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 8 | 466975 | 72646.4213 | 0.0023567 | LOW
138 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 12 | 461255 | 71756.5716 | 0.0023278 | LOW
139 | Mechanical | Top Drive Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 10 | 458634 | 71348.8276 | 0.0023146 | LOW
140 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 8 | 456648 | 71039.8693 | 0.0023046 | LOW
141 | Weather | Heavy Rain | Lightning | Marine Operations | Suspend Operations | 1 | 8 | 452025 | 70320.6779 | 0.0022812 | LOW
142 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Condition Hole | 1 | 8 | 442510 | 68840.4473 | 0.0022332 | LOW
143 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 8 | 440239 | 68487.1521 | 0.0022217 | LOW
144 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 2 | 8 | 439448 | 68364.0977 | 0.0022178 | LOW
145 | Mechanical | Mud Pump Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 8 | 433276 | 67403.9313 | 0.0021866 | LOW
146 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 8 | 431142 | 67071.9489 | 0.0021758 | LOW
147 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 8 | 430846 | 67025.9008 | 0.0021743 | LOW
148 | Weather | Poor Visibility | Strong Wind | Weather | Resume Operations | 2 | 10 | 430098 | 66909.5358 | 0.0021706 | LOW
149 | Mechanical | Power System Failure | Hydraulic Failure | OEM Vendor | OEM Inspection | 1 | 8 | 429389 | 66799.238 | 0.002167 | LOW
150 | Weather | Lightning | Storm | Marine Operations | Wait on Weather | 2 | 8 | 426642 | 66371.8924 | 0.0021531 | LOW
151 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Air Freight Materials | 1 | 6 | 424036 | 65966.4819 | 0.00214 | LOW
152 | Mechanical | Power System Failure | Electrical Failure | Maintenance Team | OEM Inspection | 2 | 8 | 422889 | 65788.0453 | 0.0021342 | LOW
153 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 8 | 422843 | 65780.8891 | 0.002134 | LOW
154 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Medical Clearance | 2 | 12 | 421769 | 65613.809 | 0.0021285 | LOW
155 | Logistics | Waiting on Cement | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 6 | 415691 | 64668.266 | 0.0020979 | LOW
156 | Drilling | Fishing Operation | Bit Wear | Directional Drilling | Condition Hole | 1 | 6 | 414858 | 64538.6777 | 0.0020937 | LOW
157 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | Preventive Maintenance | 2 | 8 | 414852 | 64537.7443 | 0.0020936 | LOW
158 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | Replace Equipment | 1 | 8 | 414076 | 64417.0235 | 0.0020897 | LOW
159 | Weather | High Waves | Heavy Rain | Marine Operations | Resume Operations | 3 | 10 | 413058 | 64258.6551 | 0.0020846 | LOW
160 | Personnel | Medical Evacuation | Training Requirement | HR | Medical Clearance | 2 | 8 | 413001 | 64249.7877 | 0.0020843 | LOW
161 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | OEM Vendor | Repair Component | 1 | 8 | 412453 | 64164.5364 | 0.0020815 | LOW
162 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 8 | 412023 | 64097.6421 | 0.0020793 | LOW
163 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 6 | 409922 | 63770.7935 | 0.0020687 | LOW
164 | Mechanical | BOP Repair | Equipment Wear | OEM Vendor | Repair Component | 1 | 8 | 405809 | 63130.9418 | 0.002048 | LOW
165 | Logistics | Waiting on Boat | Customs Clearance | Procurement | Air Freight Materials | 2 | 6 | 402137 | 62559.6957 | 0.0020295 | LOW
166 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 8 | 400816 | 62354.1902 | 0.0020228 | LOW
167 | Weather | Strong Wind | High Waves | Marine Operations | Wait on Weather | 1 | 6 | 398600 | 62009.4513 | 0.0020116 | LOW
168 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Condition Hole | 2 | 10 | 397925 | 61904.4428 | 0.0020082 | LOW
169 | Drilling | Bit Failure | Differential Sticking | Operator | Condition Hole | 1 | 6 | 393652 | 61239.7002 | 0.0019866 | LOW
170 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 8 | 392444 | 61051.774 | 0.0019805 | LOW
171 | Mechanical | Top Drive Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 6 | 390679 | 60777.1962 | 0.0019716 | LOW
172 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 6 | 390341 | 60724.6142 | 0.0019699 | LOW
173 | Weather | Poor Visibility | Heavy Rain | Weather | Resume Operations | 2 | 10 | 390215 | 60705.0126 | 0.0019693 | LOW
174 | Weather | High Waves | Strong Wind | Weather | Resume Operations | 1 | 6 | 388120 | 60379.0974 | 0.0019587 | LOW
175 | Mechanical | Mud Pump Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 6 | 387813 | 60331.338 | 0.0019572 | LOW
176 | Weather | Lightning | Strong Wind | Weather | Wait on Weather | 1 | 6 | 386746 | 60165.3468 | 0.0019518 | LOW
177 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 8 | 385622 | 59990.4883 | 0.0019461 | LOW
178 | Weather | Lightning | Lightning | Marine Operations | Resume Operations | 2 | 8 | 383364 | 59639.2155 | 0.0019347 | LOW
179 | Weather | Lightning | Strong Wind | Marine Operations | Resume Operations | 2 | 8 | 383096 | 59597.5232 | 0.0019334 | LOW
180 | Logistics | Fuel Supply Delay | Customs Clearance | Supply Chain | Expedite Shipment | 2 | 8 | 382626 | 59524.4062 | 0.001931 | LOW
181 | Drilling | Stuck Pipe | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 12 | 380405 | 59178.8894 | 0.0019198 | LOW
182 | Logistics | Waiting on Boat | Port Congestion | Supply Chain | Expedite Shipment | 1 | 6 | 380337 | 59168.3108 | 0.0019194 | LOW
183 | Weather | Heavy Rain | Heavy Rain | Weather | Resume Operations | 1 | 12 | 378994 | 58959.3828 | 0.0019127 | LOW
184 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 8 | 378432 | 58871.9535 | 0.0019098 | LOW
185 | Logistics | Waiting on Boat | Port Congestion | Procurement | Mobilize Supply Vessel | 1 | 6 | 377721 | 58761.3446 | 0.0019062 | LOW
186 | Personnel | Medical Evacuation | Medical Emergency | HR | Crew Replacement | 1 | 6 | 376090 | 58507.613 | 0.001898 | LOW
187 | Drilling | Hole Cleaning | Differential Sticking | Mud Engineering | Increase Mud Weight | 1 | 6 | 373064 | 58036.8639 | 0.0018827 | LOW
188 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 2 | 8 | 370834 | 57689.947 | 0.0018715 | LOW
189 | Drilling | Hole Cleaning | Differential Sticking | Operator | Run Fishing Tools | 1 | 8 | 368858 | 57382.5444 | 0.0018615 | LOW
190 | Drilling | Well Control | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 6 | 368781 | 57370.5656 | 0.0018611 | LOW
191 | Drilling | Bit Failure | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 8 | 367972 | 57244.711 | 0.001857 | LOW
192 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 6 | 366820 | 57065.4965 | 0.0018512 | LOW
193 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Repair Component | 1 | 6 | 365352 | 56837.1225 | 0.0018438 | LOW
194 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Condition Hole | 1 | 8 | 364022 | 56630.2169 | 0.0018371 | LOW
195 | Mechanical | Top Drive Failure | Hydraulic Failure | Maintenance Team | Preventive Maintenance | 1 | 12 | 363301 | 56518.0523 | 0.0018335 | LOW
196 | Drilling | Stuck Pipe | Formation Instability | Operator | Condition Hole | 1 | 6 | 362949 | 56463.2924 | 0.0018317 | LOW
197 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Condition Hole | 1 | 12 | 362340 | 56368.5514 | 0.0018286 | LOW
198 | Logistics | Waiting on Cement | Late Supply Vessel | Marine Logistics | Air Freight Materials | 2 | 10 | 360764 | 56123.376 | 0.0018207 | LOW
199 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Adjust Drilling Parameters | 2 | 10 | 360223 | 56039.2137 | 0.0018179 | LOW
200 | Drilling | Lost Circulation | Differential Sticking | Operator | Run Fishing Tools | 1 | 8 | 354647 | 55171.7659 | 0.0017898 | LOW
201 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 6 | 354358 | 55126.8067 | 0.0017883 | LOW
202 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Run Fishing Tools | 1 | 6 | 353029 | 54920.0566 | 0.0017816 | LOW
203 | Weather | Poor Visibility | Lightning | Weather | Suspend Operations | 1 | 6 | 351890 | 54742.8646 | 0.0017759 | LOW
204 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 6 | 351864 | 54738.8198 | 0.0017757 | LOW
205 | Logistics | Waiting on Materials | Port Congestion | Procurement | Expedite Shipment | 1 | 8 | 351618 | 54700.55 | 0.0017745 | LOW
206 | Weather | Lightning | Storm | Marine Operations | Resume Operations | 1 | 8 | 351230 | 54640.1896 | 0.0017725 | LOW
207 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 12 | 351023 | 54607.987 | 0.0017715 | LOW
208 | Mechanical | Top Drive Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 6 | 348626 | 54235.0902 | 0.0017594 | LOW
209 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Expedite Shipment | 1 | 6 | 348024 | 54141.4382 | 0.0017564 | LOW
210 | Weather | Poor Visibility | Lightning | Weather | Wait on Weather | 2 | 8 | 346993 | 53981.0475 | 0.0017512 | LOW
211 | Drilling | Stuck Pipe | Formation Instability | Operator | Increase Mud Weight | 1 | 8 | 346314 | 53875.4167 | 0.0017477 | LOW
212 | Drilling | Lost Circulation | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 8 | 345853 | 53803.6998 | 0.0017454 | LOW
213 | Drilling | Bit Failure | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 6 | 344964 | 53665.3998 | 0.0017409 | LOW
214 | Weather | Strong Wind | Storm | Marine Operations | Suspend Operations | 2 | 8 | 344046 | 53522.5883 | 0.0017363 | LOW
215 | Weather | Heavy Rain | Strong Wind | Marine Operations | Suspend Operations | 1 | 6 | 343619 | 53456.1607 | 0.0017341 | LOW
216 | Drilling | Fishing Operation | Differential Sticking | Directional Drilling | Increase Mud Weight | 1 | 6 | 343111 | 53377.1321 | 0.0017316 | LOW
217 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | Repair Component | 2 | 10 | 343071 | 53370.9093 | 0.0017314 | LOW
218 | Weather | Heavy Rain | Lightning | Weather | Wait on Weather | 2 | 6 | 341516 | 53129.0009 | 0.0017235 | LOW
219 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 6 | 340265 | 52934.3852 | 0.0017172 | LOW
220 | Drilling | Stuck Pipe | Bit Wear | Mud Engineering | Increase Mud Weight | 1 | 6 | 337687 | 52533.3306 | 0.0017042 | LOW
221 | Weather | Heavy Rain | Storm | Weather | Wait on Weather | 1 | 6 | 337173 | 52453.3686 | 0.0017016 | LOW
222 | Weather | Heavy Rain | High Waves | Marine Operations | Wait on Weather | 1 | 6 | 335006 | 52116.2525 | 0.0016907 | LOW
223 | Drilling | Hole Cleaning | Formation Instability | Operator | Run Fishing Tools | 2 | 6 | 331260 | 51533.4943 | 0.0016718 | LOW
224 | Drilling | Hole Cleaning | Bit Wear | Operator | Condition Hole | 2 | 8 | 330172 | 51364.2362 | 0.0016663 | LOW
225 | Drilling | Stuck Pipe | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 8 | 329802 | 51306.676 | 0.0016644 | LOW
226 | Personnel | Crew Change | Medical Emergency | Rig Management | Safety Briefing | 2 | 6 | 327936 | 51016.3859 | 0.001655 | LOW
227 | Personnel | Medical Evacuation | Training Requirement | HR | Safety Briefing | 2 | 10 | 326916 | 50857.7064 | 0.0016498 | LOW
228 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 8 | 323949 | 50396.1358 | 0.0016349 | LOW
229 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 6 | 322678 | 50198.4087 | 0.0016285 | LOW
230 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Repair Component | 1 | 8 | 322359 | 50148.7825 | 0.0016268 | LOW
231 | Drilling | Well Control | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 6 | 319465 | 49698.5684 | 0.0016122 | LOW
232 | Weather | Strong Wind | Storm | Weather | Resume Operations | 1 | 8 | 318983 | 49623.5845 | 0.0016098 | LOW
233 | Mechanical | Draw Works Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 2 | 6 | 317851 | 49447.4814 | 0.0016041 | LOW
234 | Drilling | Lost Circulation | Differential Sticking | Mud Engineering | Condition Hole | 1 | 6 | 317496 | 49392.2548 | 0.0016023 | LOW
235 | Weather | Strong Wind | High Waves | Marine Operations | Suspend Operations | 2 | 8 | 317064 | 49325.0493 | 0.0016001 | LOW
236 | Mechanical | Draw Works Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 8 | 316114 | 49177.2596 | 0.0015953 | LOW
237 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Expedite Shipment | 1 | 6 | 314093 | 48862.8565 | 0.0015851 | LOW
238 | Mechanical | Power System Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 6 | 311670 | 48485.9149 | 0.0015729 | LOW
239 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Mobilize Supply Vessel | 1 | 6 | 308615 | 48010.6543 | 0.0015575 | LOW
240 | Drilling | Stuck Pipe | Unexpected Pressure | Mud Engineering | Adjust Drilling Parameters | 1 | 6 | 307708 | 47869.554 | 0.0015529 | LOW
241 | Weather | Strong Wind | Strong Wind | Marine Operations | Resume Operations | 2 | 6 | 306650 | 47704.963 | 0.0015476 | LOW
242 | Mechanical | BOP Repair | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 8 | 305734 | 47562.4626 | 0.0015429 | LOW
243 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 8 | 305647 | 47548.9281 | 0.0015425 | LOW
244 | Drilling | Lost Circulation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 8 | 305177 | 47475.8111 | 0.0015401 | LOW
245 | Drilling | Well Control | Formation Instability | Mud Engineering | Run Fishing Tools | 3 | 8 | 304293 | 47338.2889 | 0.0015357 | LOW
246 | Weather | Poor Visibility | Storm | Weather | Suspend Operations | 2 | 6 | 303851 | 47269.5278 | 0.0015334 | LOW
247 | Drilling | Lost Circulation | Bit Wear | Operator | Increase Mud Weight | 2 | 8 | 303591 | 47229.0801 | 0.0015321 | LOW
248 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 2 | 6 | 302089 | 46995.4168 | 0.0015245 | LOW
249 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Adjust Drilling Parameters | 1 | 6 | 299818 | 46642.1216 | 0.0015131 | LOW
250 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Mobilize Supply Vessel | 1 | 6 | 296528 | 46130.3025 | 0.0014965 | LOW
251 | Mechanical | Draw Works Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 6 | 293383 | 45641.0408 | 0.0014806 | LOW
252 | Mechanical | Generator Failure | Electrical Failure | Drilling Contractor | OEM Inspection | 1 | 6 | 292855 | 45558.9008 | 0.0014779 | LOW
253 | Weather | Heavy Rain | High Waves | Marine Operations | Suspend Operations | 2 | 6 | 289788 | 45081.7734 | 0.0014625 | LOW
254 | Logistics | Waiting on Cement | Material Shortage | Marine Logistics | Expedite Shipment | 2 | 8 | 288274 | 44846.2433 | 0.0014548 | LOW
255 | Drilling | Well Control | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 6 | 287490 | 44724.2778 | 0.0014509 | LOW
256 | Weather | Heavy Rain | Storm | Marine Operations | Wait on Weather | 1 | 4 | 283956 | 44174.5001 | 0.001433 | LOW
257 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 6 | 283515 | 44105.8946 | 0.0014308 | LOW
258 | Mechanical | Draw Works Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 8 | 283348 | 44079.9147 | 0.00143 | LOW
259 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 6 | 282458 | 43941.4591 | 0.0014255 | LOW
260 | Mechanical | Power System Failure | Hydraulic Failure | Maintenance Team | Repair Component | 1 | 4 | 280600 | 43652.4135 | 0.0014161 | LOW
261 | Logistics | Delayed Helicopter | Material Shortage | Supply Chain | Expedite Shipment | 1 | 4 | 280384 | 43618.8108 | 0.001415 | LOW
262 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Increase Mud Weight | 1 | 6 | 276785 | 43058.9212 | 0.0013968 | LOW
263 | Mechanical | Generator Failure | Poor Preventive Maintenance | Maintenance Team | Repair Component | 1 | 8 | 275218 | 42815.1459 | 0.0013889 | LOW
264 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Resume Operations | 1 | 4 | 274281 | 42669.3786 | 0.0013842 | LOW
265 | Logistics | Waiting on Cement | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 6 | 273679 | 42575.7266 | 0.0013812 | LOW
266 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 4 | 271009 | 42160.3597 | 0.0013677 | LOW
267 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Condition Hole | 2 | 6 | 269378 | 41906.6281 | 0.0013595 | LOW
268 | Weather | High Waves | Heavy Rain | Weather | Resume Operations | 1 | 4 | 268307 | 41740.0147 | 0.0013541 | LOW
269 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 4 | 267913 | 41678.7208 | 0.0013521 | LOW
270 | Drilling | Hole Cleaning | Unexpected Pressure | Mud Engineering | Increase Mud Weight | 1 | 4 | 267388 | 41597.0476 | 0.0013494 | LOW
271 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 4 | 267293 | 41582.2686 | 0.0013489 | LOW
272 | Weather | Poor Visibility | Heavy Rain | Weather | Wait on Weather | 1 | 6 | 267059 | 41545.8657 | 0.0013478 | LOW
273 | Drilling | Bit Failure | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 6 | 267051 | 41544.6211 | 0.0013477 | LOW
274 | Mechanical | Mud Pump Failure | Equipment Wear | OEM Vendor | OEM Inspection | 1 | 4 | 266940 | 41527.3531 | 0.0013472 | LOW
275 | Weather | High Waves | Lightning | Weather | Suspend Operations | 1 | 4 | 266498 | 41458.5919 | 0.0013449 | LOW
276 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Air Freight Materials | 1 | 4 | 266485 | 41456.5696 | 0.0013449 | LOW
277 | Weather | Heavy Rain | High Waves | Marine Operations | Resume Operations | 1 | 4 | 265590 | 41317.3361 | 0.0013403 | LOW
278 | Drilling | Stuck Pipe | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 6 | 265582 | 41316.0915 | 0.0013403 | LOW
279 | Drilling | Fishing Operation | Differential Sticking | Operator | Increase Mud Weight | 1 | 8 | 264193 | 41100.0074 | 0.0013333 | LOW
280 | Logistics | Waiting on Boat | Port Congestion | Marine Logistics | Mobilize Supply Vessel | 1 | 4 | 263601 | 41007.9111 | 0.0013303 | LOW
281 | Weather | Heavy Rain | Strong Wind | Weather | Wait on Weather | 1 | 6 | 263523 | 40995.7768 | 0.0013299 | LOW
282 | Drilling | Hole Cleaning | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 4 | 262057 | 40767.7139 | 0.0013225 | LOW
283 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 6 | 260730 | 40561.275 | 0.0013158 | LOW
284 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 4 | 260558 | 40534.5173 | 0.001315 | LOW
285 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 6 | 257968 | 40131.5959 | 0.0013019 | LOW
286 | Weather | Poor Visibility | High Waves | Weather | Resume Operations | 1 | 6 | 256971 | 39976.4945 | 0.0012968 | LOW
287 | Weather | Lightning | Lightning | Weather | Resume Operations | 2 | 6 | 256285 | 39869.7748 | 0.0012934 | LOW
288 | Mechanical | Mud Pump Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 8 | 256020 | 39828.5492 | 0.0012921 | LOW
289 | Weather | Strong Wind | High Waves | Weather | Resume Operations | 1 | 6 | 255196 | 39700.3611 | 0.0012879 | LOW
290 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | OEM Inspection | 1 | 6 | 252040 | 39209.3881 | 0.001272 | LOW
291 | Mechanical | BOP Repair | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 4 | 250433 | 38959.3902 | 0.0012639 | LOW
292 | Drilling | Stuck Pipe | Bit Wear | Operator | Condition Hole | 1 | 4 | 248562 | 38668.3222 | 0.0012544 | LOW
293 | Logistics | Delayed Helicopter | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 4 | 245667 | 38217.9525 | 0.0012398 | LOW
294 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 8 | 245257 | 38154.1696 | 0.0012377 | LOW
295 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 4 | 243632 | 37901.3714 | 0.0012295 | LOW
296 | Logistics | Fuel Supply Delay | Material Shortage | Supply Chain | Expedite Shipment | 1 | 4 | 242362 | 37703.7999 | 0.0012231 | LOW
297 | Drilling | Hole Cleaning | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 2 | 6 | 241752 | 37608.9033 | 0.00122 | LOW
298 | Logistics | Waiting on Cement | Customs Clearance | Procurement | Air Freight Materials | 1 | 4 | 239783 | 37302.5897 | 0.0012101 | LOW
299 | Mechanical | Draw Works Failure | OEM Defect | OEM Vendor | Preventive Maintenance | 1 | 6 | 239454 | 37251.4078 | 0.0012084 | LOW
300 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 6 | 239340 | 37233.673 | 0.0012079 | LOW
301 | Logistics | Waiting on Materials | Material Shortage | Supply Chain | Expedite Shipment | 1 | 6 | 238864 | 37159.6226 | 0.0012055 | LOW
302 | Weather | Strong Wind | Lightning | Marine Operations | Resume Operations | 1 | 6 | 238339 | 37077.9493 | 0.0012028 | LOW
303 | Mechanical | Power System Failure | Electrical Failure | Drilling Contractor | Replace Equipment | 1 | 4 | 235789 | 36681.2507 | 0.00119 | LOW
304 | Drilling | Fishing Operation | Differential Sticking | Mud Engineering | Adjust Drilling Parameters | 1 | 4 | 234076 | 36414.7625 | 0.0011813 | LOW
305 | Logistics | Waiting on Materials | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 4 | 233679 | 36353.0019 | 0.0011793 | LOW
306 | Mechanical | Rotary Table Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 6 | 233378 | 36306.1759 | 0.0011778 | LOW
307 | Personnel | Crew Change | Medical Emergency | HR | Medical Clearance | 1 | 6 | 232452 | 36162.1198 | 0.0011731 | LOW
308 | Drilling | Lost Circulation | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 8 | 230791 | 35903.7212 | 0.0011647 | LOW
309 | Logistics | Delayed Helicopter | Late Supply Vessel | Procurement | Expedite Shipment | 2 | 4 | 230664 | 35883.9641 | 0.0011641 | LOW
310 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 4 | 230562 | 35868.0961 | 0.0011636 | LOW
311 | Mechanical | Generator Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 4 | 229210 | 35657.768 | 0.0011567 | LOW
312 | Weather | Poor Visibility | Heavy Rain | Marine Operations | Resume Operations | 1 | 4 | 228301 | 35516.3566 | 0.0011522 | LOW
313 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Mobilize Supply Vessel | 1 | 6 | 227412 | 35378.0565 | 0.0011477 | LOW
314 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Mobilize Supply Vessel | 1 | 4 | 227308 | 35361.8775 | 0.0011472 | LOW
315 | Drilling | Hole Cleaning | Differential Sticking | Operator | Adjust Drilling Parameters | 1 | 6 | 226365 | 35215.1767 | 0.0011424 | LOW
316 | Drilling | Well Control | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 4 | 226267 | 35199.931 | 0.0011419 | LOW
317 | Drilling | Hole Cleaning | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 6 | 226088 | 35172.0844 | 0.001141 | LOW
318 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Increase Mud Weight | 1 | 4 | 225101 | 35018.5386 | 0.001136 | LOW
319 | Logistics | Waiting on Materials | Port Congestion | Supply Chain | Air Freight Materials | 1 | 6 | 224082 | 34860.0147 | 0.0011309 | LOW
320 | Personnel | Safety Stand Down | Training Requirement | Rig Management | Safety Briefing | 1 | 6 | 223591 | 34783.6308 | 0.0011284 | LOW
321 | Drilling | Lost Circulation | Bit Wear | Operator | Condition Hole | 1 | 4 | 223254 | 34731.2043 | 0.0011267 | LOW
322 | Mechanical | Power System Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 4 | 223184 | 34720.3145 | 0.0011263 | LOW
323 | Weather | Heavy Rain | Lightning | Weather | Suspend Operations | 1 | 4 | 223095 | 34706.469 | 0.0011259 | LOW
324 | Weather | High Waves | Storm | Marine Operations | Resume Operations | 1 | 4 | 222759 | 34654.1981 | 0.0011242 | LOW
325 | Weather | Heavy Rain | Heavy Rain | Weather | Suspend Operations | 1 | 4 | 220055 | 34233.5419 | 0.0011105 | LOW
326 | Logistics | Waiting on Cement | Customs Clearance | Marine Logistics | Mobilize Supply Vessel | 2 | 4 | 219322 | 34119.5105 | 0.0011068 | LOW
327 | Weather | Strong Wind | Storm | Weather | Suspend Operations | 2 | 6 | 219046 | 34076.5737 | 0.0011055 | LOW
328 | Logistics | Fuel Supply Delay | Material Shortage | Procurement | Expedite Shipment | 1 | 6 | 216821 | 33730.4346 | 0.0010942 | LOW
329 | Weather | Poor Visibility | Storm | Marine Operations | Resume Operations | 2 | 4 | 216538 | 33686.4088 | 0.0010928 | LOW
330 | Weather | Poor Visibility | Storm | Marine Operations | Wait on Weather | 1 | 6 | 215094 | 33461.7685 | 0.0010855 | LOW
331 | Personnel | Training | Crew Rotation | Medical Team | Safety Briefing | 1 | 6 | 213210 | 33168.6781 | 0.001076 | LOW
332 | Weather | Strong Wind | High Waves | Marine Operations | Resume Operations | 1 | 4 | 211880 | 32961.7726 | 0.0010693 | LOW
333 | Mechanical | Rotary Table Failure | Hydraulic Failure | Maintenance Team | Replace Equipment | 1 | 6 | 210610 | 32764.201 | 0.0010629 | LOW
334 | Drilling | Stuck Pipe | Differential Sticking | Operator | Condition Hole | 1 | 4 | 209014 | 32515.9143 | 0.0010548 | LOW
335 | Weather | High Waves | Heavy Rain | Weather | Suspend Operations | 1 | 6 | 208739 | 32473.1331 | 0.0010534 | LOW
336 | Weather | Heavy Rain | Storm | Weather | Suspend Operations | 1 | 4 | 208670 | 32462.3989 | 0.0010531 | LOW
337 | Drilling | Stuck Pipe | Formation Instability | Operator | Run Fishing Tools | 2 | 4 | 208650 | 32459.2875 | 0.001053 | LOW
338 | Mechanical | Top Drive Failure | OEM Defect | Drilling Contractor | Preventive Maintenance | 1 | 6 | 206494 | 32123.8827 | 0.0010421 | LOW
339 | Logistics | Waiting on Materials | Customs Clearance | Supply Chain | Air Freight Materials | 1 | 4 | 205597 | 31984.3381 | 0.0010376 | LOW
340 | Mechanical | Draw Works Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 6 | 205497 | 31968.7813 | 0.0010371 | LOW
341 | Logistics | Waiting on Boat | Customs Clearance | Supply Chain | Mobilize Supply Vessel | 1 | 4 | 201829 | 31398.1574 | 0.0010186 | LOW
342 | Weather | Poor Visibility | High Waves | Marine Operations | Suspend Operations | 1 | 4 | 201521 | 31350.2424 | 0.001017 | LOW
343 | Mechanical | Top Drive Failure | Electrical Failure | Maintenance Team | Repair Component | 1 | 6 | 201020 | 31272.3028 | 0.0010145 | LOW
344 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 6 | 200527 | 31195.6077 | 0.001012 | LOW
345 | Weather | Poor Visibility | Storm | Weather | Wait on Weather | 1 | 6 | 196861 | 30625.295 | 0.00099349 | LOW
346 | Weather | Heavy Rain | Heavy Rain | Marine Operations | Wait on Weather | 1 | 4 | 196795 | 30615.0275 | 0.00099316 | LOW
347 | Drilling | Lost Circulation | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 4 | 191843 | 29844.6542 | 0.00096817 | LOW
348 | Weather | High Waves | Storm | Weather | Resume Operations | 1 | 4 | 191816 | 29840.4539 | 0.00096803 | LOW
349 | Weather | Lightning | Storm | Weather | Suspend Operations | 1 | 4 | 190528 | 29640.0821 | 0.00096153 | LOW
350 | Drilling | Well Control | Formation Instability | Operator | Increase Mud Weight | 1 | 6 | 189266 | 29443.7552 | 0.00095516 | LOW
351 | Drilling | Bit Failure | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 4 | 188959 | 29395.9957 | 0.00095362 | LOW
352 | Drilling | Bit Failure | Differential Sticking | Directional Drilling | Run Fishing Tools | 1 | 4 | 188472 | 29320.2341 | 0.00095116 | LOW
353 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Condition Hole | 1 | 4 | 187175 | 29118.4622 | 0.00094461 | LOW
354 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Repair Component | 1 | 4 | 187135 | 29112.2395 | 0.00094441 | LOW
355 | Drilling | Bit Failure | Bit Wear | Operator | Run Fishing Tools | 1 | 6 | 186995 | 29090.46 | 0.0009437 | LOW
356 | Mechanical | Power System Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 6 | 186232 | 28971.7615 | 0.00093985 | LOW
357 | Weather | High Waves | High Waves | Weather | Wait on Weather | 1 | 6 | 185319 | 28829.7278 | 0.00093525 | LOW
358 | Logistics | Waiting on Materials | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 4 | 184211 | 28657.3583 | 0.00092965 | LOW
359 | Mechanical | Mud Pump Failure | OEM Defect | OEM Vendor | Repair Component | 1 | 6 | 183652 | 28570.3958 | 0.00092683 | LOW
360 | Logistics | Waiting on Boat | Material Shortage | Procurement | Expedite Shipment | 2 | 4 | 183397 | 28530.7259 | 0.00092555 | LOW
361 | Weather | Strong Wind | Heavy Rain | Marine Operations | Suspend Operations | 1 | 4 | 183247 | 28507.3907 | 0.00092479 | LOW
362 | Drilling | Well Control | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 4 | 179258 | 27886.8294 | 0.00090466 | LOW
363 | Drilling | Stuck Pipe | Formation Instability | Operator | Adjust Drilling Parameters | 1 | 4 | 177665 | 27639.0094 | 0.00089662 | LOW
364 | Logistics | Waiting on Materials | Material Shortage | Procurement | Mobilize Supply Vessel | 1 | 4 | 176722 | 27492.3087 | 0.00089186 | LOW
365 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Medical Clearance | 1 | 4 | 175762 | 27342.9633 | 0.00088701 | LOW
366 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | Replace Equipment | 1 | 4 | 175170 | 27250.867 | 0.00088403 | LOW
367 | Mechanical | Rotary Table Failure | Electrical Failure | Drilling Contractor | Repair Component | 1 | 4 | 173329 | 26964.4661 | 0.00087474 | LOW
368 | Weather | High Waves | Lightning | Weather | Wait on Weather | 1 | 4 | 172335 | 26809.8314 | 0.00086972 | LOW
369 | Drilling | Stuck Pipe | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 4 | 171574 | 26691.444 | 0.00086588 | LOW
370 | Weather | High Waves | Storm | Marine Operations | Suspend Operations | 2 | 4 | 171504 | 26680.5543 | 0.00086553 | LOW
371 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 4 | 169940 | 26437.2457 | 0.00085763 | LOW
372 | Mechanical | BOP Repair | Hydraulic Failure | Maintenance Team | OEM Inspection | 1 | 4 | 168452 | 26205.7604 | 0.00085012 | LOW
373 | Weather | Lightning | High Waves | Marine Operations | Resume Operations | 1 | 4 | 168104 | 26151.6227 | 0.00084837 | LOW
374 | Drilling | Well Control | Unexpected Pressure | Mud Engineering | Condition Hole | 1 | 4 | 167982 | 26132.6434 | 0.00084775 | LOW
375 | Mechanical | BOP Repair | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 4 | 167299 | 26026.3903 | 0.0008443 | LOW
376 | Weather | Lightning | High Waves | Marine Operations | Wait on Weather | 1 | 4 | 162450 | 25272.0405 | 0.00081983 | LOW
377 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Condition Hole | 1 | 4 | 159637 | 24834.4274 | 0.00080564 | LOW
378 | Mechanical | Rotary Table Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 4 | 159432 | 24802.536 | 0.0008046 | LOW
379 | Logistics | Delayed Helicopter | Port Congestion | Procurement | Mobilize Supply Vessel | 2 | 4 | 158875 | 24715.8845 | 0.00080179 | LOW
380 | Personnel | Crew Change | Training Requirement | Rig Management | Crew Replacement | 1 | 4 | 156113 | 24286.2054 | 0.00078785 | LOW
381 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Adjust Drilling Parameters | 1 | 4 | 155786 | 24235.3346 | 0.0007862 | LOW
382 | Mechanical | BOP Repair | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 4 | 155480 | 24187.7308 | 0.00078466 | LOW
383 | Mechanical | Draw Works Failure | Electrical Failure | Maintenance Team | OEM Inspection | 1 | 4 | 153062 | 23811.5671 | 0.00077245 | LOW
384 | Mechanical | Top Drive Failure | Hydraulic Failure | Drilling Contractor | Preventive Maintenance | 1 | 4 | 151036 | 23496.3861 | 0.00076223 | LOW
385 | Weather | Poor Visibility | High Waves | Marine Operations | Resume Operations | 1 | 4 | 150303 | 23382.3546 | 0.00075853 | LOW
386 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 4 | 149184 | 23208.2739 | 0.00075288 | LOW
387 | Mechanical | Draw Works Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 4 | 148071 | 23035.1266 | 0.00074727 | LOW
388 | Drilling | Well Control | Differential Sticking | Operator | Condition Hole | 1 | 4 | 146747 | 22829.1544 | 0.00074058 | LOW
389 | Logistics | Waiting on Boat | Material Shortage | Supply Chain | Air Freight Materials | 1 | 4 | 146520 | 22793.8404 | 0.00073944 | LOW
390 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Replace Equipment | 1 | 4 | 144589 | 22493.4384 | 0.00072969 | LOW
391 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Condition Hole | 1 | 4 | 144530 | 22484.2599 | 0.0007294 | LOW
392 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | Drilling Contractor | Replace Equipment | 1 | 4 | 144441 | 22470.4143 | 0.00072895 | LOW
393 | Logistics | Fuel Supply Delay | Material Shortage | Marine Logistics | Air Freight Materials | 1 | 4 | 143153 | 22270.0426 | 0.00072245 | LOW
394 | Personnel | Safety Stand Down | Medical Emergency | Medical Team | Medical Clearance | 1 | 4 | 142506 | 22169.39 | 0.00071918 | LOW
395 | Logistics | Waiting on Cement | Port Congestion | Procurement | Expedite Shipment | 1 | 4 | 141854 | 22067.9596 | 0.00071589 | LOW
396 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Medical Clearance | 1 | 2 | 139078 | 21636.1025 | 0.00070188 | LOW
397 | Weather | Lightning | Heavy Rain | Marine Operations | Resume Operations | 1 | 4 | 137929 | 21457.3548 | 0.00069608 | LOW
398 | Mechanical | Power System Failure | Poor Preventive Maintenance | OEM Vendor | OEM Inspection | 1 | 4 | 137523 | 21394.1941 | 0.00069403 | LOW
399 | Drilling | Fishing Operation | Formation Instability | Directional Drilling | Increase Mud Weight | 1 | 2 | 136963 | 21307.076 | 0.00069121 | LOW
400 | Drilling | Well Control | Bit Wear | Mud Engineering | Run Fishing Tools | 1 | 4 | 136897 | 21296.8085 | 0.00069087 | LOW
401 | Mechanical | Power System Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 2 | 135824 | 21129.8839 | 0.00068546 | LOW
402 | Logistics | Delayed Helicopter | Port Congestion | Supply Chain | Mobilize Supply Vessel | 1 | 4 | 135576 | 21091.303 | 0.00068421 | LOW
403 | Mechanical | Power System Failure | Poor Preventive Maintenance | Maintenance Team | Preventive Maintenance | 1 | 4 | 135471 | 21074.9683 | 0.00068368 | LOW
404 | Drilling | Lost Circulation | Differential Sticking | Operator | Increase Mud Weight | 1 | 2 | 135366 | 21058.6337 | 0.00068315 | LOW
405 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | Maintenance Team | OEM Inspection | 1 | 2 | 132117 | 20553.1929 | 0.00066675 | LOW
406 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Preventive Maintenance | 1 | 4 | 131948 | 20526.9019 | 0.0006659 | LOW
407 | Weather | Lightning | Heavy Rain | Weather | Resume Operations | 1 | 2 | 131903 | 20519.9013 | 0.00066567 | LOW
408 | Weather | Heavy Rain | Lightning | Marine Operations | Wait on Weather | 1 | 2 | 131381 | 20438.6947 | 0.00066304 | LOW
409 | Weather | Poor Visibility | Lightning | Marine Operations | Suspend Operations | 1 | 2 | 130889 | 20362.1552 | 0.00066055 | LOW
410 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Preventive Maintenance | 1 | 2 | 129733 | 20182.3185 | 0.00065472 | LOW
411 | Drilling | Stuck Pipe | Bit Wear | Directional Drilling | Run Fishing Tools | 2 | 4 | 129706 | 20178.1181 | 0.00065458 | LOW
412 | Logistics | Delayed Helicopter | Customs Clearance | Procurement | Mobilize Supply Vessel | 1 | 2 | 129244 | 20106.2457 | 0.00065225 | LOW
413 | Drilling | Fishing Operation | Unexpected Pressure | Directional Drilling | Adjust Drilling Parameters | 1 | 4 | 128909 | 20054.1303 | 0.00065056 | LOW
414 | Logistics | Waiting on Materials | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 2 | 128233 | 19948.9663 | 0.00064715 | LOW
415 | Logistics | Delayed Helicopter | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 2 | 128171 | 19939.3211 | 0.00064684 | LOW
416 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 2 | 128096 | 19927.6535 | 0.00064646 | LOW
417 | Mechanical | Mud Pump Failure | Hydraulic Failure | Drilling Contractor | Replace Equipment | 1 | 2 | 127813 | 19883.6277 | 0.00064503 | LOW
418 | Drilling | Bit Failure | Bit Wear | Operator | Increase Mud Weight | 1 | 2 | 125483 | 19521.154 | 0.00063327 | LOW
419 | Drilling | Well Control | Bit Wear | Operator | Condition Hole | 1 | 2 | 125472 | 19519.4427 | 0.00063322 | LOW
420 | Drilling | Bit Failure | Formation Instability | Operator | Increase Mud Weight | 1 | 2 | 125034 | 19451.3039 | 0.00063101 | LOW
421 | Personnel | Training | Training Requirement | Medical Team | Medical Clearance | 1 | 2 | 124993 | 19444.9256 | 0.0006308 | LOW
422 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 4 | 124894 | 19429.5244 | 0.0006303 | LOW
423 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Preventive Maintenance | 1 | 2 | 124400 | 19352.6737 | 0.00062781 | LOW
424 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 2 | 123601 | 19228.3748 | 0.00062377 | LOW
425 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Increase Mud Weight | 1 | 4 | 122835 | 19109.2096 | 0.00061991 | LOW
426 | Mechanical | Top Drive Failure | Hydraulic Failure | OEM Vendor | Replace Equipment | 1 | 2 | 121900 | 18963.7534 | 0.00061519 | LOW
427 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Preventive Maintenance | 1 | 2 | 121891 | 18962.3533 | 0.00061514 | LOW
428 | Weather | Poor Visibility | High Waves | Marine Operations | Wait on Weather | 1 | 4 | 121607 | 18918.172 | 0.00061371 | LOW
429 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Replace Equipment | 1 | 2 | 121266 | 18865.1232 | 0.00061199 | LOW
430 | Mechanical | Rotary Table Failure | Electrical Failure | Maintenance Team | Preventive Maintenance | 1 | 2 | 120946 | 18815.3414 | 0.00061038 | LOW
431 | Mechanical | Top Drive Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 4 | 120706 | 18778.0051 | 0.00060916 | LOW
432 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 2 | 119766 | 18631.7711 | 0.00060442 | LOW
433 | Mechanical | Draw Works Failure | Equipment Wear | Maintenance Team | Replace Equipment | 1 | 2 | 119555 | 18598.9462 | 0.00060336 | LOW
434 | Weather | Poor Visibility | Strong Wind | Weather | Suspend Operations | 1 | 4 | 117715 | 18312.7008 | 0.00059407 | LOW
435 | Mechanical | Power System Failure | OEM Defect | OEM Vendor | OEM Inspection | 1 | 2 | 117131 | 18221.8491 | 0.00059112 | LOW
436 | Mechanical | Generator Failure | Equipment Wear | Drilling Contractor | Replace Equipment | 1 | 2 | 115946 | 18037.5008 | 0.00058514 | LOW
437 | Drilling | Well Control | Unexpected Pressure | Operator | Condition Hole | 1 | 4 | 115667 | 17994.0973 | 0.00058373 | LOW
438 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | OEM Inspection | 1 | 4 | 115317 | 17939.6485 | 0.00058197 | LOW
439 | Drilling | Bit Failure | Formation Instability | Directional Drilling | Adjust Drilling Parameters | 1 | 2 | 114203 | 17766.3456 | 0.00057635 | LOW
440 | Weather | Strong Wind | Storm | Weather | Wait on Weather | 1 | 2 | 113946 | 17726.3646 | 0.00057505 | LOW
441 | Weather | Heavy Rain | Strong Wind | Weather | Resume Operations | 1 | 2 | 112208 | 17455.9872 | 0.00056628 | LOW
442 | Mechanical | BOP Repair | Electrical Failure | OEM Vendor | Repair Component | 1 | 2 | 111750 | 17384.737 | 0.00056397 | LOW
443 | Weather | Heavy Rain | Storm | Marine Operations | Resume Operations | 1 | 2 | 111129 | 17288.1292 | 0.00056083 | LOW
444 | Personnel | Medical Evacuation | Training Requirement | Medical Team | Safety Briefing | 1 | 2 | 111032 | 17273.0391 | 0.00056034 | LOW
445 | Mechanical | Mud Pump Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 2 | 110322 | 17162.5858 | 0.00055676 | LOW
446 | Drilling | Hole Cleaning | Formation Instability | Mud Engineering | Condition Hole | 1 | 2 | 110061 | 17121.9825 | 0.00055544 | LOW
447 | Drilling | Well Control | Unexpected Pressure | Directional Drilling | Run Fishing Tools | 1 | 2 | 109853 | 17089.6243 | 0.00055439 | LOW
448 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Increase Mud Weight | 1 | 2 | 109837 | 17087.1352 | 0.00055431 | LOW
449 | Weather | Heavy Rain | High Waves | Weather | Resume Operations | 1 | 2 | 109410 | 17020.7076 | 0.00055216 | LOW
450 | Logistics | Waiting on Materials | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 2 | 108387 | 16861.5615 | 0.00054699 | LOW
451 | Logistics | Fuel Supply Delay | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 2 | 107844 | 16777.088 | 0.00054425 | LOW
452 | Drilling | Stuck Pipe | Differential Sticking | Operator | Increase Mud Weight | 1 | 2 | 107351 | 16700.3929 | 0.00054177 | LOW
453 | Drilling | Lost Circulation | Bit Wear | Mud Engineering | Adjust Drilling Parameters | 1 | 2 | 105954 | 16483.0642 | 0.00053472 | LOW
454 | Logistics | Fuel Supply Delay | Late Supply Vessel | Procurement | Air Freight Materials | 1 | 2 | 105491 | 16411.0362 | 0.00053238 | LOW
455 | Personnel | Safety Stand Down | Training Requirement | Medical Team | Safety Briefing | 1 | 2 | 104829 | 16308.0501 | 0.00052904 | LOW
456 | Weather | High Waves | Strong Wind | Weather | Suspend Operations | 1 | 2 | 102905 | 16008.737 | 0.00051933 | LOW
457 | Logistics | Waiting on Cement | Material Shortage | Supply Chain | Expedite Shipment | 1 | 2 | 101688 | 15819.4106 | 0.00051319 | LOW
458 | Drilling | Lost Circulation | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 2 | 100507 | 15635.6847 | 0.00050723 | LOW
459 | Logistics | Delayed Helicopter | Customs Clearance | Marine Logistics | Air Freight Materials | 1 | 2 | 98690 | 15353.0174 | 0.00049806 | LOW
460 | Drilling | Fishing Operation | Bit Wear | Mud Engineering | Condition Hole | 1 | 2 | 98559 | 15332.638 | 0.0004974 | LOW
461 | Logistics | Waiting on Cement | Late Supply Vessel | Supply Chain | Expedite Shipment | 1 | 2 | 97761 | 15208.4946 | 0.00049337 | LOW
462 | Mechanical | Top Drive Failure | Equipment Wear | Maintenance Team | Repair Component | 1 | 2 | 96881 | 15071.5947 | 0.00048893 | LOW
463 | Mechanical | Generator Failure | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 2 | 96310 | 14982.7653 | 0.00048605 | LOW
464 | Drilling | Stuck Pipe | Formation Instability | Directional Drilling | Run Fishing Tools | 1 | 2 | 95282 | 14822.8413 | 0.00048086 | LOW
465 | Mechanical | Mud Pump Failure | Electrical Failure | OEM Vendor | Preventive Maintenance | 1 | 2 | 94282 | 14667.2732 | 0.00047581 | LOW
466 | Personnel | Safety Stand Down | Training Requirement | HR | Crew Replacement | 1 | 2 | 93981 | 14620.4472 | 0.00047429 | LOW
467 | Mechanical | Rotary Table Failure | Equipment Wear | Maintenance Team | Preventive Maintenance | 1 | 2 | 92909 | 14453.6781 | 0.00046888 | LOW
468 | Mechanical | BOP Repair | Poor Preventive Maintenance | OEM Vendor | Replace Equipment | 1 | 2 | 92820 | 14439.8326 | 0.00046843 | LOW
469 | Drilling | Hole Cleaning | Differential Sticking | Operator | Increase Mud Weight | 1 | 2 | 91943 | 14303.3993 | 0.00046401 | LOW
470 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Expedite Shipment | 1 | 2 | 91341 | 14209.7473 | 0.00046097 | LOW
471 | Personnel | Safety Stand Down | Crew Rotation | Medical Team | Safety Briefing | 1 | 2 | 90635 | 14099.9163 | 0.00045741 | LOW
472 | Mechanical | Top Drive Failure | OEM Defect | Maintenance Team | Repair Component | 1 | 2 | 89522 | 13926.7689 | 0.00045179 | LOW
473 | Drilling | Well Control | Bit Wear | Directional Drilling | Run Fishing Tools | 1 | 2 | 89388 | 13905.9228 | 0.00045111 | LOW
474 | Mechanical | Generator Failure | Poor Preventive Maintenance | Drilling Contractor | Preventive Maintenance | 1 | 2 | 88341 | 13743.043 | 0.00044583 | LOW
475 | Drilling | Fishing Operation | Bit Wear | Operator | Adjust Drilling Parameters | 1 | 2 | 88055 | 13698.5505 | 0.00044439 | LOW
476 | Logistics | Waiting on Boat | Late Supply Vessel | Marine Logistics | Expedite Shipment | 1 | 2 | 86702 | 13488.0668 | 0.00043756 | LOW
477 | Drilling | Bit Failure | Formation Instability | Mud Engineering | Condition Hole | 1 | 2 | 85885 | 13360.9677 | 0.00043343 | LOW
478 | Weather | Strong Wind | Lightning | Weather | Suspend Operations | 1 | 2 | 84759 | 13185.798 | 0.00042775 | LOW
479 | Drilling | Hole Cleaning | Formation Instability | Operator | Increase Mud Weight | 1 | 2 | 84135 | 13088.7235 | 0.0004246 | LOW
480 | Logistics | Waiting on Materials | Port Congestion | Procurement | Air Freight Materials | 1 | 2 | 82862 | 12890.6853 | 0.00041818 | LOW
481 | Weather | Poor Visibility | Lightning | Marine Operations | Wait on Weather | 1 | 2 | 82702 | 12865.7944 | 0.00041737 | LOW
482 | Logistics | Fuel Supply Delay | Customs Clearance | Marine Logistics | Expedite Shipment | 1 | 2 | 82480 | 12831.2583 | 0.00041625 | LOW
483 | Logistics | Waiting on Materials | Customs Clearance | Procurement | Expedite Shipment | 1 | 2 | 82289 | 12801.5447 | 0.00041529 | LOW
484 | Mechanical | Generator Failure | Electrical Failure | OEM Vendor | OEM Inspection | 1 | 2 | 82273 | 12799.0557 | 0.00041521 | LOW
485 | Personnel | Safety Stand Down | Crew Rotation | Rig Management | Medical Clearance | 1 | 2 | 81540 | 12685.0242 | 0.00041151 | LOW
486 | Mechanical | Generator Failure | Hydraulic Failure | OEM Vendor | Preventive Maintenance | 1 | 2 | 79500 | 12367.6653 | 0.00040121 | LOW
487 | Mechanical | Draw Works Failure | OEM Defect | Drilling Contractor | Repair Component | 1 | 2 | 79139 | 12311.5052 | 0.00039939 | LOW
488 | Mechanical | Draw Works Failure | Equipment Wear | Drilling Contractor | OEM Inspection | 1 | 2 | 75654 | 11769.3503 | 0.0003818 | LOW
489 | Mechanical | Mud Pump Failure | Equipment Wear | Maintenance Team | OEM Inspection | 1 | 2 | 73971 | 11507.5292 | 0.00037331 | LOW
490 | Weather | Strong Wind | Heavy Rain | Marine Operations | Wait on Weather | 1 | 2 | 73818 | 11483.7272 | 0.00037254 | LOW
491 | Mechanical | Draw Works Failure | Equipment Wear | OEM Vendor | Repair Component | 1 | 2 | 72228 | 11236.3739 | 0.00036451 | LOW
492 | Logistics | Delayed Helicopter | Port Congestion | Marine Logistics | Air Freight Materials | 1 | 2 | 72206 | 11232.9514 | 0.0003644 | LOW
493 | Drilling | Well Control | Differential Sticking | Mud Engineering | Run Fishing Tools | 1 | 2 | 70168 | 10915.9036 | 0.00035412 | LOW
494 | Weather | Lightning | Heavy Rain | Weather | Wait on Weather | 1 | 2 | 70126 | 10909.3697 | 0.0003539 | LOW
495 | Drilling | Bit Failure | Unexpected Pressure | Operator | Run Fishing Tools | 1 | 2 | 68914 | 10720.8212 | 0.00034779 | LOW
496 | Drilling | Hole Cleaning | Unexpected Pressure | Operator | Adjust Drilling Parameters | 1 | 2 | 68000 | 10578.6319 | 0.00034317 | LOW
497 | Mechanical | Generator Failure | Equipment Wear | OEM Vendor | Replace Equipment | 1 | 2 | 67963 | 10572.8759 | 0.00034299 | LOW
498 | Drilling | Lost Circulation | Bit Wear | Directional Drilling | Adjust Drilling Parameters | 1 | 2 | 66827 | 10396.1505 | 0.00033725 | LOW
499 | Drilling | Fishing Operation | Differential Sticking | Operator | Condition Hole | 1 | 2 | 65923 | 10255.517 | 0.00033269 | LOW
500 | Personnel | Safety Stand Down | Medical Emergency | HR | Safety Briefing | 1 | 2 | 65522 | 10193.1341 | 0.00033067 | LOW
501 | Drilling | Lost Circulation | Formation Instability | Mud Engineering | Condition Hole | 1 | 2 | 64142 | 9978.4501 | 0.0003237 | LOW
502 | Drilling | Fishing Operation | Unexpected Pressure | Operator | Condition Hole | 1 | 2 | 62471 | 9718.4958 | 0.00031527 | LOW

## Economic_Scorecard
Metric | Value_USD | Reference_USD | Share_of_Total_Impact
Direct NPT Cost | 79204408 | 198150178 | 0.39972
Deferred Cost | 118945770 | 198150178 | 0.60028
Total Economic Impact | 198150178 | 198150178 | 1
Conservative Savings | 15412920 | 198150178 | 0.077784
Target Savings | 30825850 | 198150178 | 0.15557
Stretch Savings | 46238770 | 198150178 | 0.23335

## KPI_Framework
KPI | Domain | Definition | Direction | Baseline | Target | Frequency | Owner
NPT Hours | Operational Efficiency | Total non-productive time | Minimize | 4008 | < 3,000 hr | Monthly | Wells / Operations
NPT Cost | Economic Performance | Direct NPT cost | Minimize | 79204408 | < $60M | Monthly | Finance / Wells
Total Economic Impact | Economic Exposure | NPT + deferred impact | Minimize | 198150178 | < $150M | Monthly | Management
Average ROP | Drilling Performance | Average drilling rate | Maximize | 33.6733 | > 35 ft/hr | Weekly | Drilling
Cost per Foot | Cost Efficiency | Daily drilling cost / footage | Minimize | 687.6662 | < $600/ft | Weekly | Finance / Drilling
Target Savings | Improvement | Validated target savings | Maximize | 30825850 | > $30M | Monthly | Management
NPT Hours per Well | Well Performance | NPT hours normalized by wells | Minimize | 80.16 | < 60 hr/well | Per Well | Well Engineering

## Decision_Register
Decision_ID | Decision_Area | Decision | Economic_or_Operational_Value | Priority | Rationale | Owner | Time_Horizon
DEC-001 | Rig Performance | Intervene on Rig R002 | 76560445 | CRITICAL | Rig with highest economic exposure | Rig Management | Immediate
DEC-002 | Root Cause | Address Differential Sticking | 4901437 | CRITICAL | Highest-impact root cause | Operations / Engineering | Immediate
DEC-003 | Savings | Execute validated target savings portfolio | 30825850 | CRITICAL | Validated improvement opportunity | Management | 90 Days
DEC-004 | NPT Reduction | Reduce total NPT exposure | 4008 | HIGH | 4,008 baseline NPT hours | Operations | 90 Days
DEC-005 | Drilling Performance | Improve average ROP | 33.6733 | HIGH | Average ROP below strategic target | Drilling Engineering | 90 Days

## Data_Quality
Check | Actual | Expected | Status
NPT rows | 677 | 677 | PASS
Drilling rows | 1474 | 1474 | PASS
Unique NPT IDs | 677 | 677 | PASS
Duplicate NPT IDs | 0 | 0 | PASS
Economic Reconciliation | 0 | 0 | PASS
Target Savings Positive | 30825850 | > 0 | PASS
Rig Scorecard | 4 | 4 | PASS
Well Scorecard | 50 | 50 | PASS