## Control_Tower
Stage | Control_Tower | Overall_Status | NPT_Events | NPT_Hours | Direct_NPT_Cost_USD | Deferred_Cost_USD | Total_Economic_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Wells | Rigs | Drilling_Days | Total_Footage_ft | Average_ROP_ft_hr | Cost_per_Foot_USD | Critical_KPIs | Red_Rigs | Critical_Wells | Critical_Root_Causes | Top_Rig | Top_Root_Cause | Top_Initiative | Executive_Priority
STAGE 2G.15 | Operational Performance Control Tower | RED | 677 | 4008 | 79204408 | 118945770 | 198150178 | 30825850 | 6390128.6372 | 50 | 4 | 666 | 952078.8 | 33.6733 | 687.6662 | 4 | 2 | 25 | 18 | R002 | Differential Sticking | INIT-002 | Protect target savings and eliminate top rig/root-cause exposure.

## KPI_Status
KPI | Actual | Target | Direction | Status | Indicator_Type | Management_Objective
NPT Hours | 4008 | 3000 | MINIMIZE | RED | Lagging | Reduce operational downtime
Direct NPT Cost | 79204408 | 60000000 | MINIMIZE | RED | Lagging | Reduce direct NPT expenditure
Total Economic Impact | 198150178 | 150000000 | MINIMIZE | RED | Lagging | Reduce total operational exposure
Average ROP | 33.6733 | 35 | MAXIMIZE | AMBER | Leading | Improve drilling performance
Cost per Foot | 687.6662 | 600 | MINIMIZE | RED | Lagging | Improve cost efficiency
Target Savings | 30825850 | 30825850 | MAXIMIZE | AMBER | Leading | Protect validated savings opportunity

## Rig_Alerts
Rig_ID | NPT_Events | NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Wells_Exposed | Impact_Share_pct | Alert_Level | Management_Priority
R002 | 282 | 1610 | 76560445 | 11910364.2365 | 2665717.783 | 20 | 38.6376 | RED | CRITICAL
R004 | 199 | 1186 | 61470399 | 9562834.2005 | 1950075.5887 | 16 | 31.0221 | RED | CRITICAL
R003 | 116 | 694 | 34396458 | 5350992.1896 | 997525.5545 | 8 | 17.3588 | AMBER | HIGH
R001 | 80 | 518 | 25722876 | 4001659.3735 | 776809.711 | 6 | 12.9815 | YELLOW | MEDIUM

## Well_Alerts
Well_ID | NPT_Events | NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Rigs_Exposed | Impact_Share_pct | Alert_Level | Management_Priority
W007 | 16 | 128 | 6815911 | 1060338.4373 | 57881.218 | 1 | 3.4398 | RED | CRITICAL
W040 | 21 | 130 | 6620110 | 1029878.0445 | 315799.932 | 1 | 3.341 | RED | CRITICAL
W019 | 13 | 114 | 5561717 | 865225.8389 | 61507.2774 | 1 | 2.8068 | RED | CRITICAL
W036 | 19 | 108 | 5411508 | 841858.1077 | 62910.0351 | 1 | 2.731 | RED | CRITICAL
W003 | 13 | 88 | 5225678 | 812948.8845 | 230965.8378 | 1 | 2.6372 | RED | CRITICAL
W011 | 16 | 104 | 5187621 | 807028.4287 | 306938.9277 | 1 | 2.618 | RED | CRITICAL
W046 | 16 | 102 | 5032158 | 782843.3426 | 180294.5798 | 1 | 2.5396 | RED | CRITICAL
W013 | 20 | 96 | 4883822 | 759766.9905 | 151663.2791 | 1 | 2.4647 | RED | CRITICAL
W023 | 14 | 84 | 4828213 | 751116.0031 | 110384.6795 | 1 | 2.4366 | RED | CRITICAL
W010 | 16 | 106 | 4734861 | 736593.4082 | 90460.0596 | 1 | 2.3895 | RED | CRITICAL
W009 | 15 | 100 | 4669372 | 726405.4079 | 241535.2134 | 1 | 2.3565 | RED | CRITICAL
W001 | 19 | 88 | 4605541 | 716475.3394 | 160685.1409 | 1 | 2.3243 | RED | CRITICAL
W020 | 20 | 90 | 4565483 | 710243.5918 | 122685.3727 | 1 | 2.3041 | RED | CRITICAL
W045 | 10 | 80 | 4553567 | 708389.8421 | 14982.7653 | 1 | 2.298 | RED | CRITICAL
W002 | 13 | 88 | 4546361 | 707268.8183 | 176545.1548 | 1 | 2.2944 | RED | CRITICAL
W021 | 16 | 94 | 4506303 | 701037.0706 | 67414.8211 | 1 | 2.2742 | RED | CRITICAL
W026 | 11 | 90 | 4452824 | 692717.4433 | 159874.0087 | 1 | 2.2472 | RED | CRITICAL
W015 | 14 | 76 | 4385282 | 682210.0616 | 146050.1481 | 1 | 2.2131 | RED | CRITICAL
W043 | 18 | 94 | 4350399 | 676783.379 | 173507.7651 | 1 | 2.1955 | RED | CRITICAL
W032 | 15 | 86 | 4251690 | 661427.4058 | 24276.8713 | 1 | 2.1457 | RED | CRITICAL
W033 | 16 | 90 | 4243450 | 660145.5245 | 270607.9386 | 1 | 2.1415 | RED | CRITICAL
W006 | 15 | 84 | 4231281 | 658252.4161 | 107490.9569 | 1 | 2.1354 | RED | CRITICAL
W048 | 14 | 86 | 4208923 | 654774.2241 | 66949.1279 | 1 | 2.1241 | RED | CRITICAL
W028 | 15 | 90 | 4143050 | 644526.4856 | 106004.5036 | 1 | 2.0909 | RED | CRITICAL
W030 | 15 | 90 | 4137386 | 643645.3478 | 101422.3225 | 1 | 2.088 | RED | CRITICAL
W047 | 13 | 78 | 3918083 | 609528.7931 | 73265.5046 | 1 | 1.9773 | AMBER | HIGH
W050 | 11 | 74 | 3894520 | 605863.1416 | 206260.9208 | 1 | 1.9654 | AMBER | HIGH
W018 | 14 | 88 | 3855804 | 599840.1663 | 164382.7617 | 1 | 1.9459 | AMBER | HIGH
W034 | 12 | 74 | 3657546 | 568997.5427 | 47892.8892 | 1 | 1.8458 | AMBER | HIGH
W035 | 12 | 92 | 3595897 | 559406.9239 | 87164.349 | 1 | 1.8147 | AMBER | HIGH
W038 | 15 | 68 | 3555637 | 553143.7515 | 193295.0184 | 1 | 1.7944 | AMBER | HIGH
W041 | 14 | 76 | 3512146 | 546377.9385 | 151204.1198 | 1 | 1.7725 | AMBER | HIGH
W022 | 13 | 74 | 3442372 | 535523.3288 | 210817.3554 | 1 | 1.7373 | AMBER | HIGH
W044 | 12 | 64 | 3417944 | 531723.1108 | 109017.0802 | 1 | 1.7249 | AMBER | HIGH
W029 | 14 | 70 | 3349062 | 521007.2678 | 133093.5797 | 1 | 1.6902 | AMBER | HIGH
W024 | 12 | 68 | 3242338 | 504404.4161 | 66080.2022 | 1 | 1.6363 | AMBER | HIGH
W012 | 11 | 64 | 3233740 | 503066.8414 | 26379.8411 | 1 | 1.632 | AMBER | HIGH
W027 | 10 | 66 | 3222709 | 501350.7696 | 263882.9623 | 1 | 1.6264 | AMBER | HIGH
W037 | 9 | 72 | 3194393 | 496945.7028 | 151845.6049 | 1 | 1.6121 | AMBER | HIGH
W005 | 13 | 64 | 3143733 | 489064.622 | 26226.6843 | 1 | 1.5865 | AMBER | HIGH
W039 | 13 | 70 | 3123391 | 485900.0553 | 176957.0992 | 1 | 1.5763 | AMBER | HIGH
W031 | 11 | 60 | 3032755 | 471799.9835 | 180855.3251 | 1 | 1.5305 | AMBER | HIGH
W049 | 9 | 60 | 2954155 | 459572.3296 | 139143.4682 | 1 | 1.4909 | AMBER | HIGH
W025 | 11 | 54 | 2858646 | 444714.1743 | 123367.9278 | 1 | 1.4427 | AMBER | HIGH
W017 | 11 | 54 | 2591314 | 403125.8386 | 42137.8801 | 1 | 1.3078 | AMBER | HIGH
W016 | 10 | 50 | 2543830 | 395738.8421 | 41345.1828 | 1 | 1.2838 | AMBER | HIGH
W042 | 8 | 52 | 2398167 | 373078.3235 | 102868.4059 | 1 | 1.2103 | AMBER | HIGH
W004 | 11 | 52 | 2334494 | 363172.8348 | 50318.1962 | 1 | 1.1781 | AMBER | HIGH
W014 | 8 | 38 | 2106838 | 327756.8197 | 10801.7944 | 1 | 1.0633 | AMBER | HIGH
W008 | 10 | 40 | 1818153 | 282846.6379 | 102686.5468 | 1 | 0.91756 | YELLOW | MEDIUM

## Root_Cause_Alerts
Root_Cause | NPT_Events | NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Wells_Exposed | Rigs_Exposed | Impact_Share_pct | Alert_Level | Management_Priority
Differential Sticking | 50 | 342 | 16607490 | 2583595.9411 | 548468.6184 | 29 | 4 | 8.3813 | RED | CRITICAL
Equipment Wear | 44 | 288 | 15261510 | 2374204.3675 | 476180.6261 | 25 | 4 | 7.702 | RED | CRITICAL
Unexpected Pressure | 62 | 328 | 15016252 | 2336050.0424 | 551291.2464 | 35 | 4 | 7.5782 | RED | CRITICAL
Bit Wear | 45 | 290 | 15010654 | 2335179.1721 | 280574.1767 | 31 | 4 | 7.5754 | RED | CRITICAL
Formation Instability | 56 | 292 | 14427460 | 2244452.7799 | 386645.1856 | 33 | 4 | 7.2811 | RED | CRITICAL
Poor Preventive Maintenance | 38 | 252 | 12375421 | 1925220.9374 | 746971.824 | 30 | 4 | 6.2455 | RED | CRITICAL
Strong Wind | 33 | 236 | 12019394 | 1869834.4875 | 316346.6762 | 25 | 4 | 6.0658 | RED | CRITICAL
Heavy Rain | 32 | 224 | 10864999 | 1690247.4315 | 503888.0078 | 22 | 4 | 5.4832 | RED | CRITICAL
Customs Clearance | 30 | 186 | 10235957 | 1592388.5523 | 259666.2885 | 24 | 4 | 5.1658 | RED | CRITICAL
Hydraulic Failure | 31 | 210 | 9982294 | 1552926.6772 | 504409.5499 | 22 | 4 | 5.0377 | RED | CRITICAL
Electrical Failure | 37 | 200 | 9779455 | 1521371.396 | 242740.2441 | 24 | 4 | 4.9354 | RED | CRITICAL
Lightning | 40 | 176 | 9120864 | 1418915.6345 | 295256.3844 | 30 | 4 | 4.603 | RED | CRITICAL
High Waves | 29 | 164 | 8033895 | 1249817.9143 | 270365.0968 | 22 | 4 | 4.0544 | RED | CRITICAL
Late Supply Vessel | 30 | 152 | 7587022 | 1180298.7233 | 82562.2552 | 23 | 4 | 3.8289 | RED | CRITICAL
Port Congestion | 21 | 150 | 7290244 | 1134129.5288 | 379577.4927 | 18 | 4 | 3.6792 | RED | CRITICAL
Storm | 27 | 142 | 6844851 | 1064840.5786 | 192047.751 | 20 | 4 | 3.4544 | RED | CRITICAL
Material Shortage | 23 | 118 | 5915692 | 920293.063 | 150532.6878 | 18 | 4 | 2.9855 | RED | CRITICAL
OEM Defect | 21 | 102 | 4833435 | 751928.3798 | 55898.8134 | 17 | 4 | 2.4393 | RED | CRITICAL
Medical Emergency | 8 | 60 | 3042462 | 473310.0832 | 94568.5358 | 6 | 3 | 1.5354 | AMBER | HIGH
Training Requirement | 14 | 54 | 2291065 | 356416.6671 | 35552.8373 | 14 | 4 | 1.1562 | AMBER | HIGH
Crew Rotation | 6 | 42 | 1609762 | 250427.6426 | 16584.3391 | 6 | 4 | 0.81239 | YELLOW | MEDIUM

## Initiative_Status
Initiative_ID | Initiative_Name | Initiative_Priority | NPT_Events | NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Wells_Exposed | Rigs_Exposed | Savings_Protection_pct | Management_Status
INIT-002 | Mechanical Reliability Program | CRITICAL | 171 | 1052 | 52232115 | 8125651.7578 | 2026201.0575 | 48 | 4 | 75.0641 | GREEN
INIT-003 | Weather & Marine Operations Resilience | CRITICAL | 161 | 942 | 46884003 | 7293656.0465 | 1577903.9161 | 48 | 4 | 78.3661 | GREEN
INIT-001 | Drilling Dysfunction Reduction Program | CRITICAL | 168 | 962 | 46051202 | 7164098.7634 | 1486405.0504 | 49 | 4 | 79.252 | GREEN
INIT-004 | Supply Chain & Logistics Optimization | HIGH | 104 | 606 | 31028915 | 4827109.8674 | 872338.7243 | 46 | 4 | 81.9283 | GREEN
INIT-006 | Drilling Performance Optimization | LOW | 45 | 290 | 15010654 | 2335179.1721 | 280574.1767 | 31 | 4 | 87.9849 | GREEN
INIT-005 | People, Competency & Operational Readiness | LOW | 28 | 156 | 6943289 | 1080154.3929 | 146705.7122 | 24 | 4 | 86.4181 | GREEN

## Savings_At_Risk
Initiative_ID | Initiative_Name | Initiative_Priority | Action_Status_Normalized | NPT_Events | NPT_Hours | Target_Savings_USD | Savings_At_Risk_USD | Risk_pct
INIT-002 | Mechanical Reliability Program | CRITICAL | Open | 26 | 172 | 1306950.3051 | 1306950.3051 | 100
INIT-001 | Drilling Dysfunction Reduction Program | CRITICAL | Open | 19 | 114 | 873212.706 | 873212.706 | 100
INIT-003 | Weather & Marine Operations Resilience | CRITICAL | In Progress | 33 | 194 | 1605171.74 | 802585.87 | 50
INIT-003 | Weather & Marine Operations Resilience | CRITICAL | Open | 19 | 106 | 775318.0461 | 775318.0461 | 100
INIT-002 | Mechanical Reliability Program | CRITICAL | In Progress | 30 | 190 | 1438501.5048 | 719250.7524 | 50
INIT-001 | Drilling Dysfunction Reduction Program | CRITICAL | In Progress | 30 | 160 | 1226384.6889 | 613192.3444 | 50
INIT-004 | Supply Chain & Logistics Optimization | HIGH | Open | 12 | 78 | 586884.6092 | 586884.6092 | 100
INIT-004 | Supply Chain & Logistics Optimization | HIGH | In Progress | 14 | 78 | 570908.2303 | 285454.1151 | 50
INIT-006 | Drilling Performance Optimization | LOW | Open | 5 | 22 | 176395.5761 | 176395.5761 | 100
INIT-005 | People, Competency & Operational Readiness | LOW | In Progress | 7 | 44 | 293411.4243 | 146705.7122 | 50
INIT-006 | Drilling Performance Optimization | LOW | In Progress | 7 | 30 | 208357.2012 | 104178.6006 | 50
INIT-001 | Drilling Dysfunction Reduction Program | CRITICAL | Closed | 119 | 688 | 5064501.3685 | 0 | 0
INIT-002 | Mechanical Reliability Program | CRITICAL | Closed | 115 | 690 | 5380199.9479 | 0 | 0
INIT-003 | Weather & Marine Operations Resilience | CRITICAL | Closed | 109 | 642 | 4913166.2603 | 0 | 0
INIT-004 | Supply Chain & Logistics Optimization | HIGH | Closed | 78 | 450 | 3669317.028 | 0 | 0
INIT-005 | People, Competency & Operational Readiness | LOW | Closed | 21 | 112 | 786742.9686 | 0 | 0
INIT-006 | Drilling Performance Optimization | LOW | Closed | 33 | 238 | 1950426.3948 | 0 | 0

## Management_Escalation
Priority | Alert_Type | Object | Exposure_USD_or_Value | Target | Status | Recommended_Action
1 | KPI | NPT Hours | 4008 | 3000 | RED | Reduce operational downtime through top NPT drivers.
2 | RIG | R002 | 76560445 |  | RED | Escalate rig-level reliability and execution review.
3 | ROOT CAUSE | Differential Sticking | 16607490 |  | RED | Launch focused root-cause elimination action.
4 | INITIATIVE | INIT-002 | 8125651.7578 |  | CRITICAL | Protect the largest savings opportunity.
5 | SAVINGS AT RISK | INIT-002 | 1306950.3051 |  | RED | Prioritize closure of open actions threatening savings.

## Action_Ownership
Responsible_Party | NPT_Events | NPT_Hours | Total_Impact_USD | Target_Savings_USD | Savings_At_Risk_USD | Open_Actions | In_Progress_Actions | Closed_Actions | Savings_Risk_pct
OEM Vendor | 59 | 376 | 18331322 | 2851769.2388 | 936782.8166 | 14 | 10 | 35 | 32.8492
Marine Operations | 88 | 490 | 25000021 | 3889206.1825 | 911267.0008 | 12 | 20 | 56 | 23.4307
Directional Drilling | 71 | 428 | 21180149 | 3294955.8897 | 768325.6482 | 9 | 15 | 47 | 23.3182
Weather | 73 | 452 | 21883982 | 3404449.864 | 666636.9153 | 7 | 13 | 53 | 19.5813
Operator | 72 | 386 | 18655151 | 2902146.7064 | 648119.9535 | 9 | 14 | 49 | 22.3324
Maintenance Team | 47 | 308 | 14900279 | 2318008.3412 | 573873.7475 | 5 | 10 | 32 | 24.7572
Drilling Contractor | 65 | 368 | 19000514 | 2955874.1779 | 515544.4934 | 7 | 10 | 48 | 17.4414
Supply Chain | 32 | 236 | 12321042 | 1916761.2988 | 449307.5563 | 5 | 6 | 21 | 23.441
Mud Engineering | 70 | 438 | 21226556 | 3302175.3393 | 350533.6254 | 6 | 8 | 56 | 10.6152
Procurement | 36 | 180 | 9196062 | 1430614.0457 | 334563.0026 | 6 | 4 | 26 | 23.386
Rig Management | 9 | 66 | 2571074 | 399977.1399 | 90214.8065 | 0 | 3 | 6 | 22.555
Marine Logistics | 36 | 190 | 9511811 | 1479734.5229 | 88468.1654 | 1 | 4 | 31 | 5.9787
Medical Team | 11 | 56 | 2864253 | 445586.4447 | 38409.8458 | 0 | 3 | 8 | 8.6201
HR | 8 | 34 | 1507962 | 234590.8083 | 18081.0599 | 0 | 1 | 7 | 7.7075

## Assumptions
Assumption | Value | Basis
Economic baseline | Stage 2G.10.1 validated economic baseline | Reference
Target savings | 30825850 | Validated Stage 2G.10.1
Target savings rate | 0.15557 | Validated target savings / total impact
KPI minimize threshold | Green <= target; Amber <= 110%; Red > 110% | Management assumption
KPI maximize threshold | Green >= target; Amber >= 95%; Red < 95% | Management assumption
Rig alert threshold | Red >=25% impact share; Amber >=15%; Yellow >=10% | Management assumption
Well/root cause alert threshold | Red >=2%; Amber >=1%; Yellow >=0.5% impact share | Management assumption
Open action risk | 100% of target savings at risk | Management assumption
In-progress action risk | 50% of target savings at risk | Management assumption
Closed action risk | 0% of target savings at risk | Management assumption
Unknown action risk | 75% of target savings at risk | Management assumption
Important economic caveat | NPT reduction scenarios and economic savings are separate concepts | Stage 2G.14 methodology

## Data_Quality
Check | Actual | Expected | Status
NPT row count | 677 | 677 | PASS
Drilling row count | 1474 | 1474 | PASS
Unique NPT IDs | 677 | 677 | PASS
Duplicate NPT IDs | 0 | 0 | PASS
Economic reconciliation | 0 | 0 | PASS
Target savings reconciliation | -3.7253e-09 | 0 | PASS
Target savings positive | 30825850 | >0 | PASS
Rig count | 4 | 4 | PASS
Well count | 50 | 50 | PASS
Initiative count | 6 | 6 | PASS