## Executive_Summary
KPI | Value
Total Drilling Records | 1474
Total Wells | 50
Total Rigs | 4
Calendar Days | 666
Well-Days | 1474
Rig-Days | 1130
Total Footage (ft) | 952078.8
Total Drilling Hours | 28270.76
Average ROP (ft/hr) | 33.6733
Total Drilling Cost (USD) | 654712456.04
Total NPT Events | 677
Total NPT Hours | 4008
Total NPT Cost (USD) | 79204408
NPT Hours / Well-Day | 2.7191
NPT Cost / Well-Day (USD) | 53734.3338
NPT Events / 100 Well-Days | 45.9294
NPT Hours / 1,000 ft | 4.2097
NPT Cost / ft (USD) | 83.191
Lost Days / Well-Day | 0.11314
NPT Cost / Drilling Cost (%) | 12.0976
Best Rig | R001
Worst Rig | R003
Highest Risk Well | W040

## Overall_Efficiency
Metric | Value
Total Drilling Records | 1474
Total Wells | 50
Total Rigs | 4
Calendar Days | 666
Well-Days | 1474
Rig-Days | 1130
Total Footage (ft) | 952078.8
Total Drilling Hours | 28270.76
Average ROP (ft/hr) | 33.6733
Total Drilling Cost (USD) | 654712456.04
Total NPT Events | 677
Total NPT Hours | 4008
Total NPT Cost (USD) | 79204408
Total Lost Drilling Days | 166.77
NPT Hours / Well-Day | 2.7191
NPT Cost / Well-Day | 53734.3338
NPT Events / 100 Well-Days | 45.9294
NPT Hours / 1,000 ft | 4.2097
NPT Cost / ft | 83.191
Lost Days / Well-Day | 0.11314
NPT Cost / Drilling Cost (%) | 12.0976

## Rig_Performance
Rig_ID | Wells | Drilling_Days | Well_Days | Footage_ft | Drilling_Hours | Drilling_Cost_USD | Avg_ROP_ft_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | Lost_Drilling_Days | NPT_Hours_per_Drilling_Day | NPT_Cost_per_Drilling_Day_USD | NPT_Events_per_100_Drilling_Days | NPT_Hours_per_1000_ft | NPT_Cost_per_ft_USD | Lost_Days_per_Drilling_Day | NPT_Cost_pct_of_Drilling_Cost | NPT_Hours_per_Drilling_Day_Score | NPT_Cost_per_Drilling_Day_USD_Score | NPT_Cost_per_ft_USD_Score | Lost_Days_per_Drilling_Day_Score | Rig_Performance_Score | Performance_Class
R001 | 6 | 174 | 174 | 111693.1 | 3350.83 | 77620939.53 | 33.3442 | 80 | 518 | 10252062 | 21.55 | 2.977 | 58919.8966 | 45.977 | 4.6377 | 91.7878 | 0.12385 | 13.2079 | 100 | 100 | 0 | 100 | 75 | Excellent
R002 | 20 | 442 | 596 | 383889.4 | 11455.94 | 258293934.08 | 33.5415 | 282 | 1610 | 30858241 | 67 | 3.6425 | 69815.0249 | 63.8009 | 4.1939 | 80.3832 | 0.15158 | 11.9469 | 11.5642 | 36.7485 | 98.2515 | 11.7691 | 39.5833 | Poor
R004 | 16 | 318 | 463 | 301996.1 | 8873.07 | 211397181.03 | 33.9592 | 199 | 1186 | 24214105 | 49.38 | 3.7296 | 76144.9843 | 62.5786 | 3.9272 | 80.1802 | 0.15528 | 11.4543 | 0 | 0 | 100 | 0 | 25 | Poor
R003 | 8 | 196 | 241 | 154500.2 | 4590.92 | 107400401.4 | 33.6875 | 116 | 694 | 13880000 | 28.84 | 3.5408 | 70816.3265 | 59.1837 | 4.4919 | 89.8381 | 0.14714 | 12.9236 | 25.0806 | 30.9354 | 16.7969 | 25.8973 | 24.6776 | Poor

## Well_Performance
Well_ID | Rig_ID | Drilling_Days | Footage_ft | Drilling_Hours | Drilling_Cost_USD | Avg_ROP_ft_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | Lost_Drilling_Days | Avg_Productivity_Loss_pct | NPT_Hours_per_Drilling_Day | NPT_Cost_per_Drilling_Day_USD | NPT_Events_per_100_Drilling_Days | NPT_Hours_per_1000_ft | NPT_Cost_per_ft_USD | Lost_Days_per_Drilling_Day
W001 | R004 | 26 | 16495 | 503.52 | 12003516.78 | 32.8035 | 19 | 88 | 1796660 | 3.67 | 19.3 | 3.3846 | 69102.3077 | 73.0769 | 5.3349 | 108.9215 | 0.14115
W002 | R001 | 28 | 18303.9 | 560.67 | 12906810.88 | 32.635 | 13 | 88 | 1741664 | 3.66 | 28.2 | 3.1429 | 62202.2857 | 46.4286 | 4.8077 | 95.1526 | 0.13071
W003 | R004 | 28 | 18763 | 543.01 | 12784056.41 | 34.6875 | 13 | 88 | 1796663 | 3.67 | 28.2077 | 3.1429 | 64166.5357 | 46.4286 | 4.6901 | 95.7556 | 0.13107
W004 | R002 | 33 | 20231.9 | 606.2 | 13777407.37 | 33.7436 | 11 | 52 | 996663 | 2.16 | 19.6909 | 1.5758 | 30201.9091 | 33.3333 | 2.5702 | 49.262 | 0.065455
W005 | R002 | 27 | 16853.1 | 525.2 | 11873271.59 | 32.0207 | 13 | 64 | 1226662 | 2.67 | 20.5154 | 2.3704 | 45431.9259 | 48.1481 | 3.7975 | 72.7855 | 0.098889
W006 | R002 | 30 | 20616.1 | 583.51 | 13143205.35 | 35.1587 | 15 | 84 | 1609994 | 3.5 | 23.3333 | 2.8 | 53666.4667 | 50 | 4.0745 | 78.094 | 0.11667
W007 | R001 | 33 | 21584.9 | 632.93 | 14628770.85 | 34.2727 | 16 | 128 | 2533329 | 5.32 | 33.325 | 3.8788 | 76767.5455 | 48.4848 | 5.9301 | 117.3658 | 0.16121
W008 | R002 | 32 | 19659.2 | 624.56 | 14065082.15 | 31.3706 | 10 | 40 | 766663 | 1.66 | 16.66 | 1.25 | 23958.2188 | 31.25 | 2.0347 | 38.9977 | 0.051875
W009 | R001 | 27 | 16290.9 | 516.8 | 11956185.14 | 31.3663 | 15 | 100 | 1979163 | 4.17 | 27.78 | 3.7037 | 73302.3333 | 55.5556 | 6.1384 | 121.4889 | 0.15444
W010 | R002 | 29 | 18581.1 | 559.41 | 12551454.43 | 33.2452 | 16 | 106 | 2031661 | 4.41 | 27.6 | 3.6552 | 70057.2759 | 55.1724 | 5.7047 | 109.3402 | 0.15207
W011 | R004 | 36 | 22974 | 679.83 | 16212768.29 | 33.9056 | 16 | 104 | 2123328 | 4.34 | 27.0875 | 2.8889 | 58981.3333 | 44.4444 | 4.5269 | 92.4231 | 0.12056
W012 | R004 | 29 | 18457.2 | 554.47 | 13227460.52 | 33.4397 | 11 | 64 | 1306664 | 2.66 | 24.2364 | 2.2069 | 45057.3793 | 37.931 | 3.4675 | 70.7943 | 0.091724
W013 | R003 | 36 | 22553.7 | 688.1 | 16182108.87 | 32.7356 | 20 | 96 | 1920000 | 3.98 | 19.99 | 2.6667 | 53333.3333 | 55.5556 | 4.2565 | 85.1302 | 0.11056
W014 | R004 | 35 | 22280.1 | 681.68 | 16280284.48 | 32.6689 | 8 | 38 | 775830 | 1.59 | 19.8 | 1.0857 | 22166.5714 | 22.8571 | 1.7056 | 34.8217 | 0.045429
W015 | R003 | 25 | 16635.9 | 485.12 | 11401518.43 | 34.4632 | 14 | 76 | 1520000 | 3.16 | 22.6143 | 3.04 | 60800 | 56 | 4.5684 | 91.3687 | 0.1264
W016 | R004 | 29 | 18696.2 | 555.32 | 13214359.14 | 33.2086 | 10 | 50 | 1020830 | 2.08 | 20.83 | 1.7241 | 35201.0345 | 34.4828 | 2.6743 | 54.6009 | 0.071724
W017 | R001 | 28 | 17999.2 | 531.17 | 12367526.71 | 34.0668 | 11 | 54 | 1068748 | 2.24 | 20.4455 | 1.9286 | 38169.5714 | 39.2857 | 3.0001 | 59.3775 | 0.08
W018 | R004 | 26 | 18151.7 | 521.53 | 12308393.58 | 34.8804 | 14 | 88 | 1796662 | 3.67 | 26.1929 | 3.3846 | 69102.3846 | 53.8462 | 4.848 | 98.9804 | 0.14115
W019 | R003 | 25 | 15697.8 | 460.33 | 10717808.92 | 33.8384 | 13 | 114 | 2280000 | 4.75 | 36.5385 | 4.56 | 91200 | 52 | 7.2622 | 145.2433 | 0.19
W020 | R003 | 26 | 17159.9 | 503.49 | 11719190.56 | 34.2012 | 20 | 90 | 1800000 | 3.73 | 18.74 | 3.4615 | 69230.7692 | 76.9231 | 5.2448 | 104.8957 | 0.14346
W021 | R002 | 30 | 19096.8 | 580.87 | 13145292.25 | 33.28 | 16 | 94 | 1801664 | 3.9 | 24.4688 | 3.1333 | 60055.4667 | 53.3333 | 4.9223 | 94.3438 | 0.13
W022 | R001 | 30 | 19737.2 | 582.1 | 13405027.07 | 33.7763 | 13 | 74 | 1464580 | 3.07 | 23.7077 | 2.4667 | 48819.3333 | 43.3333 | 3.7493 | 74.204 | 0.10233
W023 | R004 | 32 | 21362.9 | 611.37 | 14445134.24 | 34.8016 | 14 | 84 | 1714995 | 3.51 | 25.0071 | 2.625 | 53593.5938 | 43.75 | 3.9321 | 80.2791 | 0.10969
W024 | R002 | 32 | 20685.1 | 607.96 | 13722096.47 | 33.7209 | 12 | 68 | 1303329 | 2.83 | 23.6083 | 2.125 | 40729.0312 | 37.5 | 3.2874 | 63.0081 | 0.088438
W025 | R004 | 26 | 15854.2 | 487.21 | 11627789.13 | 32.405 | 11 | 54 | 1102497 | 2.25 | 20.4545 | 2.0769 | 42403.7308 | 42.3077 | 3.406 | 69.5397 | 0.086538
W026 | R004 | 31 | 20855 | 600.04 | 14459113.13 | 34.7661 | 11 | 90 | 1837497 | 3.74 | 34.0818 | 2.9032 | 59274.0968 | 35.4839 | 4.3155 | 88.1082 | 0.12065
W027 | R002 | 34 | 22391.9 | 653.12 | 14655693.1 | 34.2441 | 10 | 66 | 1264997 | 2.74 | 27.49 | 1.9412 | 37205.7941 | 29.4118 | 2.9475 | 56.4935 | 0.080588
W028 | R002 | 33 | 21527.8 | 647.66 | 14462989.11 | 33.4239 | 15 | 90 | 1724995 | 3.75 | 25 | 2.7273 | 52272.5758 | 45.4545 | 4.1806 | 80.1287 | 0.11364
W029 | R002 | 28 | 18474 | 541.95 | 12278777.35 | 33.8211 | 14 | 70 | 1341662 | 2.91 | 20.8286 | 2.5 | 47916.5 | 50 | 3.7891 | 72.6243 | 0.10393
W030 | R002 | 33 | 20756.7 | 632.02 | 14266132.13 | 32.873 | 15 | 90 | 1724996 | 3.73 | 24.9867 | 2.7273 | 52272.6061 | 45.4545 | 4.3359 | 83.1055 | 0.11303
W031 | R002 | 31 | 20249.1 | 600.42 | 13420380.1 | 33.7687 | 11 | 60 | 1149994 | 2.52 | 22.7455 | 1.9355 | 37096.5806 | 35.4839 | 2.9631 | 56.7924 | 0.08129
W032 | R004 | 31 | 20171.8 | 582.1 | 13999009.8 | 34.539 | 15 | 86 | 1755829 | 3.57 | 23.88 | 2.7742 | 56639.6452 | 48.3871 | 4.2634 | 87.0437 | 0.11516
W033 | R002 | 25 | 16706.9 | 479.76 | 10913961.71 | 35.1348 | 16 | 90 | 1724995 | 3.74 | 23.4312 | 3.6 | 68999.8 | 64 | 5.387 | 103.2505 | 0.1496
W034 | R001 | 28 | 17777 | 527.16 | 12356618.88 | 33.6807 | 12 | 74 | 1464578 | 3.09 | 25.7 | 2.6429 | 52306.3571 | 42.8571 | 4.1627 | 82.3861 | 0.11036
W035 | R003 | 33 | 20790.7 | 625.48 | 14687778.32 | 33.3033 | 12 | 92 | 1840000 | 3.82 | 31.9333 | 2.7879 | 55757.5758 | 36.3636 | 4.4251 | 88.5011 | 0.11576
W036 | R002 | 25 | 16733 | 494.14 | 11091091.98 | 33.9652 | 19 | 108 | 2069994 | 4.51 | 23.6895 | 4.32 | 82799.76 | 76 | 6.4543 | 123.7073 | 0.1804
W037 | R002 | 32 | 20535.1 | 608.83 | 13749815.59 | 33.7097 | 9 | 72 | 1379996 | 3.01 | 33.3444 | 2.25 | 43124.875 | 28.125 | 3.5062 | 67.2018 | 0.094063
W038 | R004 | 34 | 21390.1 | 634.15 | 15149998.79 | 33.4735 | 15 | 68 | 1388328 | 2.83 | 18.8867 | 2 | 40833.1765 | 44.1176 | 3.179 | 64.9052 | 0.083235
W039 | R002 | 29 | 19931 | 564.51 | 12786789.7 | 35.1524 | 13 | 70 | 1341663 | 2.92 | 22.4385 | 2.4138 | 46264.2414 | 44.8276 | 3.5121 | 67.3154 | 0.10069
W040 | R002 | 28 | 18509.8 | 540.17 | 12137950.94 | 34.2754 | 21 | 130 | 2491660 | 5.42 | 25.7952 | 4.6429 | 88987.8571 | 75 | 7.0233 | 134.613 | 0.19357
W041 | R002 | 25 | 15201.9 | 476.36 | 10742273.1 | 32.0492 | 14 | 76 | 1456662 | 3.14 | 22.6 | 3.04 | 58266.48 | 56 | 4.9994 | 95.821 | 0.1256
W042 | R004 | 28 | 18254.8 | 528.41 | 12572413.42 | 34.3746 | 8 | 52 | 1061665 | 2.16 | 27.075 | 1.8571 | 37916.6071 | 28.5714 | 2.8486 | 58.1581 | 0.077143
W043 | R002 | 30 | 19217.9 | 571.39 | 12906481.26 | 33.4967 | 18 | 94 | 1801662 | 3.9 | 21.75 | 3.1333 | 60055.4 | 60 | 4.8913 | 93.7492 | 0.13
W044 | R003 | 31 | 19496.2 | 592.45 | 13817299.17 | 33.1719 | 12 | 64 | 1280000 | 2.65 | 22.2083 | 2.0645 | 41290.3226 | 38.7097 | 3.2827 | 65.6538 | 0.085484
W045 | R004 | 25 | 15766.1 | 478.29 | 11426115.78 | 32.642 | 10 | 80 | 1633331 | 3.32 | 33.32 | 3.2 | 65333.24 | 40 | 5.0742 | 103.5977 | 0.1328
W046 | R003 | 29 | 19388.9 | 555.4 | 12933266.13 | 34.8452 | 16 | 102 | 2040000 | 4.25 | 26.5625 | 3.5172 | 70344.8276 | 55.1724 | 5.2607 | 105.2148 | 0.14655
W047 | R004 | 25 | 17327 | 492.27 | 11659169.74 | 35.1512 | 13 | 78 | 1592495 | 3.24 | 24.9923 | 3.12 | 63699.8 | 52 | 4.5016 | 91.9083 | 0.1296
W048 | R002 | 30 | 17931 | 557.9 | 12603788.4 | 32.5013 | 14 | 86 | 1648329 | 3.58 | 25.5929 | 2.8667 | 54944.3 | 46.6667 | 4.7962 | 91.9262 | 0.11933
W049 | R003 | 36 | 22777.1 | 680.55 | 15941431 | 33.4886 | 9 | 60 | 1200000 | 2.5 | 27.7778 | 1.6667 | 33333.3333 | 25 | 2.6342 | 52.6845 | 0.069444
W050 | R004 | 22 | 15197 | 419.87 | 10027597.8 | 36.1468 | 11 | 74 | 1510831 | 3.08 | 28.0273 | 3.3636 | 68674.1364 | 50 | 4.8694 | 99.4164 | 0.14

## High_Risk_Wells
Well_ID | Rig_ID | Drilling_Days | Footage_ft | Drilling_Hours | Drilling_Cost_USD | Avg_ROP_ft_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | Lost_Drilling_Days | Avg_Productivity_Loss_pct | NPT_Hours_per_Drilling_Day | NPT_Cost_per_Drilling_Day_USD | NPT_Events_per_100_Drilling_Days | NPT_Hours_per_1000_ft | NPT_Cost_per_ft_USD | Lost_Days_per_Drilling_Day | Risk_Score | Risk_Class
W040 | R002 | 28 | 18509.8 | 540.17 | 12137950.94 | 34.2754 | 21 | 130 | 2491660 | 5.42 | 25.7952 | 4.6429 | 88987.8571 | 75 | 7.0233 | 134.613 | 0.19357 | 99 | High
W019 | R003 | 25 | 15697.8 | 460.33 | 10717808.92 | 33.8384 | 13 | 114 | 2280000 | 4.75 | 36.5385 | 4.56 | 91200 | 52 | 7.2622 | 145.2433 | 0.19 | 99 | High
W036 | R002 | 25 | 16733 | 494.14 | 11091091.98 | 33.9652 | 19 | 108 | 2069994 | 4.51 | 23.6895 | 4.32 | 82799.76 | 76 | 6.4543 | 123.7073 | 0.1804 | 96 | High
W007 | R001 | 33 | 21584.9 | 632.93 | 14628770.85 | 34.2727 | 16 | 128 | 2533329 | 5.32 | 33.325 | 3.8788 | 76767.5455 | 48.4848 | 5.9301 | 117.3658 | 0.16121 | 93.5 | High
W009 | R001 | 27 | 16290.9 | 516.8 | 11956185.14 | 31.3663 | 15 | 100 | 1979163 | 4.17 | 27.78 | 3.7037 | 73302.3333 | 55.5556 | 6.1384 | 121.4889 | 0.15444 | 92.5 | High
W010 | R002 | 29 | 18581.1 | 559.41 | 12551454.43 | 33.2452 | 16 | 106 | 2031661 | 4.41 | 27.6 | 3.6552 | 70057.2759 | 55.1724 | 5.7047 | 109.3402 | 0.15207 | 89.5 | High
W046 | R003 | 29 | 19388.9 | 555.4 | 12933266.13 | 34.8452 | 16 | 102 | 2040000 | 4.25 | 26.5625 | 3.5172 | 70344.8276 | 55.1724 | 5.2607 | 105.2148 | 0.14655 | 87 | High
W020 | R003 | 26 | 17159.9 | 503.49 | 11719190.56 | 34.2012 | 20 | 90 | 1800000 | 3.73 | 18.74 | 3.4615 | 69230.7692 | 76.9231 | 5.2448 | 104.8957 | 0.14346 | 84.5 | High
W033 | R002 | 25 | 16706.9 | 479.76 | 10913961.71 | 35.1348 | 16 | 90 | 1724995 | 3.74 | 23.4312 | 3.6 | 68999.8 | 64 | 5.387 | 103.2505 | 0.1496 | 84 | High
W001 | R004 | 26 | 16495 | 503.52 | 12003516.78 | 32.8035 | 19 | 88 | 1796660 | 3.67 | 19.3 | 3.3846 | 69102.3077 | 73.0769 | 5.3349 | 108.9215 | 0.14115 | 83 | High
W018 | R004 | 26 | 18151.7 | 521.53 | 12308393.58 | 34.8804 | 14 | 88 | 1796662 | 3.67 | 26.1929 | 3.3846 | 69102.3846 | 53.8462 | 4.848 | 98.9804 | 0.14115 | 80.5 | High
W050 | R004 | 22 | 15197 | 419.87 | 10027597.8 | 36.1468 | 11 | 74 | 1510831 | 3.08 | 28.0273 | 3.3636 | 68674.1364 | 50 | 4.8694 | 99.4164 | 0.14 | 78 | High
W045 | R004 | 25 | 15766.1 | 478.29 | 11426115.78 | 32.642 | 10 | 80 | 1633331 | 3.32 | 33.32 | 3.2 | 65333.24 | 40 | 5.0742 | 103.5977 | 0.1328 | 77.5 | High
W003 | R004 | 28 | 18763 | 543.01 | 12784056.41 | 34.6875 | 13 | 88 | 1796663 | 3.67 | 28.2077 | 3.1429 | 64166.5357 | 46.4286 | 4.6901 | 95.7556 | 0.13107 | 73.25 | Medium
W002 | R001 | 28 | 18303.9 | 560.67 | 12906810.88 | 32.635 | 13 | 88 | 1741664 | 3.66 | 28.2 | 3.1429 | 62202.2857 | 46.4286 | 4.8077 | 95.1526 | 0.13071 | 71.25 | Medium
W021 | R002 | 30 | 19096.8 | 580.87 | 13145292.25 | 33.28 | 16 | 94 | 1801664 | 3.9 | 24.4688 | 3.1333 | 60055.4667 | 53.3333 | 4.9223 | 94.3438 | 0.13 | 68 | Medium
W043 | R002 | 30 | 19217.9 | 571.39 | 12906481.26 | 33.4967 | 18 | 94 | 1801662 | 3.9 | 21.75 | 3.1333 | 60055.4 | 60 | 4.8913 | 93.7492 | 0.13 | 67 | Medium
W047 | R004 | 25 | 17327 | 492.27 | 11659169.74 | 35.1512 | 13 | 78 | 1592495 | 3.24 | 24.9923 | 3.12 | 63699.8 | 52 | 4.5016 | 91.9083 | 0.1296 | 66 | Medium
W041 | R002 | 25 | 15201.9 | 476.36 | 10742273.1 | 32.0492 | 14 | 76 | 1456662 | 3.14 | 22.6 | 3.04 | 58266.48 | 56 | 4.9994 | 95.821 | 0.1256 | 64.25 | Medium
W015 | R003 | 25 | 16635.9 | 485.12 | 11401518.43 | 34.4632 | 14 | 76 | 1520000 | 3.16 | 22.6143 | 3.04 | 60800 | 56 | 4.5684 | 91.3687 | 0.1264 | 63.25 | Medium
W011 | R004 | 36 | 22974 | 679.83 | 16212768.29 | 33.9056 | 16 | 104 | 2123328 | 4.34 | 27.0875 | 2.8889 | 58981.3333 | 44.4444 | 4.5269 | 92.4231 | 0.12056 | 60 | Medium
W026 | R004 | 31 | 20855 | 600.04 | 14459113.13 | 34.7661 | 11 | 90 | 1837497 | 3.74 | 34.0818 | 2.9032 | 59274.0968 | 35.4839 | 4.3155 | 88.1082 | 0.12065 | 59 | Medium
W048 | R002 | 30 | 17931 | 557.9 | 12603788.4 | 32.5013 | 14 | 86 | 1648329 | 3.58 | 25.5929 | 2.8667 | 54944.3 | 46.6667 | 4.7962 | 91.9262 | 0.11933 | 56.5 | Medium
W035 | R003 | 33 | 20790.7 | 625.48 | 14687778.32 | 33.3033 | 12 | 92 | 1840000 | 3.82 | 31.9333 | 2.7879 | 55757.5758 | 36.3636 | 4.4251 | 88.5011 | 0.11576 | 53.5 | Medium
W032 | R004 | 31 | 20171.8 | 582.1 | 13999009.8 | 34.539 | 15 | 86 | 1755829 | 3.57 | 23.88 | 2.7742 | 56639.6452 | 48.3871 | 4.2634 | 87.0437 | 0.11516 | 52 | Medium
W006 | R002 | 30 | 20616.1 | 583.51 | 13143205.35 | 35.1587 | 15 | 84 | 1609994 | 3.5 | 23.3333 | 2.8 | 53666.4667 | 50 | 4.0745 | 78.094 | 0.11667 | 49.5 | Low
W013 | R003 | 36 | 22553.7 | 688.1 | 16182108.87 | 32.7356 | 20 | 96 | 1920000 | 3.98 | 19.99 | 2.6667 | 53333.3333 | 55.5556 | 4.2565 | 85.1302 | 0.11056 | 46 | Low
W030 | R002 | 33 | 20756.7 | 632.02 | 14266132.13 | 32.873 | 15 | 90 | 1724996 | 3.73 | 24.9867 | 2.7273 | 52272.6061 | 45.4545 | 4.3359 | 83.1055 | 0.11303 | 45.75 | Low
W028 | R002 | 33 | 21527.8 | 647.66 | 14462989.11 | 33.4239 | 15 | 90 | 1724995 | 3.75 | 25 | 2.7273 | 52272.5758 | 45.4545 | 4.1806 | 80.1287 | 0.11364 | 44.25 | Low
W034 | R001 | 28 | 17777 | 527.16 | 12356618.88 | 33.6807 | 12 | 74 | 1464578 | 3.09 | 25.7 | 2.6429 | 52306.3571 | 42.8571 | 4.1627 | 82.3861 | 0.11036 | 43.5 | Low
W023 | R004 | 32 | 21362.9 | 611.37 | 14445134.24 | 34.8016 | 14 | 84 | 1714995 | 3.51 | 25.0071 | 2.625 | 53593.5938 | 43.75 | 3.9321 | 80.2791 | 0.10969 | 43 | Low
W022 | R001 | 30 | 19737.2 | 582.1 | 13405027.07 | 33.7763 | 13 | 74 | 1464580 | 3.07 | 23.7077 | 2.4667 | 48819.3333 | 43.3333 | 3.7493 | 74.204 | 0.10233 | 37 | Low
W029 | R002 | 28 | 18474 | 541.95 | 12278777.35 | 33.8211 | 14 | 70 | 1341662 | 2.91 | 20.8286 | 2.5 | 47916.5 | 50 | 3.7891 | 72.6243 | 0.10393 | 36.5 | Low
W005 | R002 | 27 | 16853.1 | 525.2 | 11873271.59 | 32.0207 | 13 | 64 | 1226662 | 2.67 | 20.5154 | 2.3704 | 45431.9259 | 48.1481 | 3.7975 | 72.7855 | 0.098889 | 33 | Low
W039 | R002 | 29 | 19931 | 564.51 | 12786789.7 | 35.1524 | 13 | 70 | 1341663 | 2.92 | 22.4385 | 2.4138 | 46264.2414 | 44.8276 | 3.5121 | 67.3154 | 0.10069 | 32.5 | Low
W012 | R004 | 29 | 18457.2 | 554.47 | 13227460.52 | 33.4397 | 11 | 64 | 1306664 | 2.66 | 24.2364 | 2.2069 | 45057.3793 | 37.931 | 3.4675 | 70.7943 | 0.091724 | 29.5 | Low
W037 | R002 | 32 | 20535.1 | 608.83 | 13749815.59 | 33.7097 | 9 | 72 | 1379996 | 3.01 | 33.3444 | 2.25 | 43124.875 | 28.125 | 3.5062 | 67.2018 | 0.094063 | 28.5 | Low
W025 | R004 | 26 | 15854.2 | 487.21 | 11627789.13 | 32.405 | 11 | 54 | 1102497 | 2.25 | 20.4545 | 2.0769 | 42403.7308 | 42.3077 | 3.406 | 69.5397 | 0.086538 | 26 | Low
W024 | R002 | 32 | 20685.1 | 607.96 | 13722096.47 | 33.7209 | 12 | 68 | 1303329 | 2.83 | 23.6083 | 2.125 | 40729.0312 | 37.5 | 3.2874 | 63.0081 | 0.088438 | 23 | Very Low
W044 | R003 | 31 | 19496.2 | 592.45 | 13817299.17 | 33.1719 | 12 | 64 | 1280000 | 2.65 | 22.2083 | 2.0645 | 41290.3226 | 38.7097 | 3.2827 | 65.6538 | 0.085484 | 23 | Very Low
W038 | R004 | 34 | 21390.1 | 634.15 | 15149998.79 | 33.4735 | 15 | 68 | 1388328 | 2.83 | 18.8867 | 2 | 40833.1765 | 44.1176 | 3.179 | 64.9052 | 0.083235 | 21 | Very Low
W017 | R001 | 28 | 17999.2 | 531.17 | 12367526.71 | 34.0668 | 11 | 54 | 1068748 | 2.24 | 20.4455 | 1.9286 | 38169.5714 | 39.2857 | 3.0001 | 59.3775 | 0.08 | 16 | Very Low
W031 | R002 | 31 | 20249.1 | 600.42 | 13420380.1 | 33.7687 | 11 | 60 | 1149994 | 2.52 | 22.7455 | 1.9355 | 37096.5806 | 35.4839 | 2.9631 | 56.7924 | 0.08129 | 15 | Very Low
W027 | R002 | 34 | 22391.9 | 653.12 | 14655693.1 | 34.2441 | 10 | 66 | 1264997 | 2.74 | 27.49 | 1.9412 | 37205.7941 | 29.4118 | 2.9475 | 56.4935 | 0.080588 | 15 | Very Low
W042 | R004 | 28 | 18254.8 | 528.41 | 12572413.42 | 34.3746 | 8 | 52 | 1061665 | 2.16 | 27.075 | 1.8571 | 37916.6071 | 28.5714 | 2.8486 | 58.1581 | 0.077143 | 14 | Very Low
W016 | R004 | 29 | 18696.2 | 555.32 | 13214359.14 | 33.2086 | 10 | 50 | 1020830 | 2.08 | 20.83 | 1.7241 | 35201.0345 | 34.4828 | 2.6743 | 54.6009 | 0.071724 | 10 | Very Low
W049 | R003 | 36 | 22777.1 | 680.55 | 15941431 | 33.4886 | 9 | 60 | 1200000 | 2.5 | 27.7778 | 1.6667 | 33333.3333 | 25 | 2.6342 | 52.6845 | 0.069444 | 8 | Very Low
W004 | R002 | 33 | 20231.9 | 606.2 | 13777407.37 | 33.7436 | 11 | 52 | 996663 | 2.16 | 19.6909 | 1.5758 | 30201.9091 | 33.3333 | 2.5702 | 49.262 | 0.065455 | 6 | Very Low
W008 | R002 | 32 | 19659.2 | 624.56 | 14065082.15 | 31.3706 | 10 | 40 | 766663 | 1.66 | 16.66 | 1.25 | 23958.2188 | 31.25 | 2.0347 | 38.9977 | 0.051875 | 4 | Very Low
W014 | R004 | 35 | 22280.1 | 681.68 | 16280284.48 | 32.6689 | 8 | 38 | 775830 | 1.59 | 19.8 | 1.0857 | 22166.5714 | 22.8571 | 1.7056 | 34.8217 | 0.045429 | 2 | Very Low

## Rig_Root_Cause
Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Events | NPT_Hours | NPT_Cost_USD | Lost_Days | Cost_Share_pct
R001 | Drilling | Bit Failure | Bit Wear | 2 | 12 | 237500 | 0.5 | 2.3166
R001 | Drilling | Bit Failure | Formation Instability | 3 | 14 | 277082 | 0.59 | 2.7027
R001 | Drilling | Fishing Operation | Formation Instability | 2 | 22 | 435416 | 0.92 | 4.2471
R001 | Drilling | Hole Cleaning | Bit Wear | 4 | 28 | 554166 | 1.16 | 5.4054
R001 | Drilling | Hole Cleaning | Differential Sticking | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Drilling | Hole Cleaning | Formation Instability | 1 | 2 | 39583 | 0.08 | 0.3861
R001 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 10 | 197916 | 0.41 | 1.9305
R001 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Drilling | Lost Circulation | Formation Instability | 1 | 24 | 475000 | 1 | 4.6332
R001 | Drilling | Stuck Pipe | Formation Instability | 2 | 4 | 79166 | 0.16 | 0.7722
R001 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Drilling | Well Control | Bit Wear | 2 | 20 | 395833 | 0.83 | 3.861
R001 | Logistics | Fuel Supply Delay | Customs Clearance | 3 | 18 | 356249 | 0.75 | 3.4749
R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Logistics | Fuel Supply Delay | Material Shortage | 2 | 10 | 197916 | 0.42 | 1.9305
R001 | Logistics | Waiting on Boat | Material Shortage | 1 | 2 | 39583 | 0.08 | 0.3861
R001 | Logistics | Waiting on Cement | Customs Clearance | 1 | 12 | 237500 | 0.5 | 2.3166
R001 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Logistics | Waiting on Materials | Port Congestion | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Mechanical | Draw Works Failure | OEM Defect | 2 | 10 | 197916 | 0.42 | 1.9305
R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Mechanical | Generator Failure | Equipment Wear | 3 | 22 | 435416 | 0.91 | 4.2471
R001 | Mechanical | Generator Failure | Hydraulic Failure | 2 | 14 | 277083 | 0.58 | 2.7027
R001 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Mechanical | Top Drive Failure | Electrical Failure | 2 | 10 | 197916 | 0.42 | 1.9305
R001 | Mechanical | Top Drive Failure | Equipment Wear | 2 | 6 | 118749 | 0.25 | 1.1583
R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 2 | 24 | 475000 | 1 | 4.6332
R001 | Personnel | Safety Stand Down | Crew Rotation | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Personnel | Training | Training Requirement | 1 | 2 | 39583 | 0.08 | 0.3861
R001 | Weather | Heavy Rain | High Waves | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Weather | Heavy Rain | Lightning | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Weather | High Waves | Lightning | 2 | 10 | 197916 | 0.41 | 1.9305
R001 | Weather | High Waves | Strong Wind | 1 | 2 | 39583 | 0.08 | 0.3861
R001 | Weather | Lightning | High Waves | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Weather | Lightning | Lightning | 2 | 8 | 158333 | 0.33 | 1.5444
R001 | Weather | Lightning | Storm | 1 | 8 | 158333 | 0.33 | 1.5444
R001 | Weather | Poor Visibility | Heavy Rain | 1 | 4 | 79166 | 0.17 | 0.7722
R001 | Weather | Poor Visibility | High Waves | 1 | 6 | 118750 | 0.25 | 1.1583
R001 | Weather | Poor Visibility | Storm | 2 | 6 | 118749 | 0.25 | 1.1583
R001 | Weather | Poor Visibility | Strong Wind | 2 | 14 | 277083 | 0.58 | 2.7027
R001 | Weather | Strong Wind | Heavy Rain | 2 | 6 | 118749 | 0.25 | 1.1583
R001 | Weather | Strong Wind | High Waves | 3 | 16 | 316666 | 0.67 | 3.0888
R001 | Weather | Strong Wind | Strong Wind | 1 | 4 | 79166 | 0.17 | 0.7722
R002 | Drilling | Bit Failure | Bit Wear | 1 | 18 | 345000 | 0.75 | 1.118
R002 | Drilling | Bit Failure | Differential Sticking | 6 | 30 | 574997 | 1.25 | 1.8633
R002 | Drilling | Bit Failure | Unexpected Pressure | 8 | 36 | 689997 | 1.49 | 2.236
R002 | Drilling | Fishing Operation | Bit Wear | 1 | 2 | 38333 | 0.08 | 0.12422
R002 | Drilling | Fishing Operation | Differential Sticking | 3 | 30 | 574999 | 1.25 | 1.8634
R002 | Drilling | Fishing Operation | Formation Instability | 4 | 28 | 536666 | 1.17 | 1.7391
R002 | Drilling | Fishing Operation | Unexpected Pressure | 4 | 12 | 229998 | 0.5 | 0.74534
R002 | Drilling | Hole Cleaning | Bit Wear | 2 | 12 | 229999 | 0.5 | 0.74534
R002 | Drilling | Hole Cleaning | Differential Sticking | 4 | 34 | 651666 | 1.41 | 2.1118
R002 | Drilling | Hole Cleaning | Formation Instability | 3 | 8 | 153332 | 0.33 | 0.49689
R002 | Drilling | Hole Cleaning | Unexpected Pressure | 6 | 20 | 383331 | 0.83 | 1.2422
R002 | Drilling | Lost Circulation | Bit Wear | 2 | 10 | 191666 | 0.42 | 0.62112
R002 | Drilling | Lost Circulation | Differential Sticking | 4 | 24 | 459999 | 1 | 1.4907
R002 | Drilling | Lost Circulation | Formation Instability | 6 | 28 | 536664 | 1.18 | 1.7391
R002 | Drilling | Lost Circulation | Unexpected Pressure | 4 | 28 | 536666 | 1.16 | 1.7391
R002 | Drilling | Stuck Pipe | Bit Wear | 4 | 36 | 689999 | 1.5 | 2.236
R002 | Drilling | Stuck Pipe | Differential Sticking | 8 | 42 | 804998 | 1.75 | 2.6087
R002 | Drilling | Stuck Pipe | Formation Instability | 4 | 14 | 268332 | 0.58 | 0.86956
R002 | Drilling | Stuck Pipe | Unexpected Pressure | 7 | 50 | 958331 | 2.09 | 3.1056
R002 | Drilling | Well Control | Differential Sticking | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Drilling | Well Control | Formation Instability | 6 | 28 | 536665 | 1.17 | 1.7391
R002 | Drilling | Well Control | Unexpected Pressure | 5 | 18 | 344997 | 0.76 | 1.118
R002 | Logistics | Delayed Helicopter | Customs Clearance | 3 | 30 | 574999 | 1.25 | 1.8634
R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 3 | 16 | 306665 | 0.67 | 0.99379
R002 | Logistics | Delayed Helicopter | Material Shortage | 2 | 16 | 306666 | 0.67 | 0.99379
R002 | Logistics | Delayed Helicopter | Port Congestion | 4 | 24 | 459999 | 1 | 1.4907
R002 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 8 | 153333 | 0.33 | 0.49689
R002 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 0.12422
R002 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Logistics | Waiting on Boat | Customs Clearance | 1 | 2 | 38333 | 0.08 | 0.12422
R002 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 0.12422
R002 | Logistics | Waiting on Cement | Customs Clearance | 1 | 8 | 153333 | 0.33 | 0.49689
R002 | Logistics | Waiting on Cement | Late Supply Vessel | 5 | 20 | 383332 | 0.83 | 1.2422
R002 | Logistics | Waiting on Cement | Material Shortage | 1 | 6 | 115000 | 0.25 | 0.37267
R002 | Logistics | Waiting on Cement | Port Congestion | 2 | 24 | 460000 | 1 | 1.4907
R002 | Logistics | Waiting on Materials | Customs Clearance | 2 | 8 | 153332 | 0.34 | 0.49689
R002 | Logistics | Waiting on Materials | Late Supply Vessel | 2 | 8 | 153333 | 0.33 | 0.49689
R002 | Logistics | Waiting on Materials | Material Shortage | 4 | 26 | 498332 | 1.09 | 1.6149
R002 | Logistics | Waiting on Materials | Port Congestion | 3 | 18 | 344999 | 0.75 | 1.118
R002 | Mechanical | BOP Repair | Electrical Failure | 1 | 8 | 153333 | 0.33 | 0.49689
R002 | Mechanical | BOP Repair | Equipment Wear | 5 | 52 | 996665 | 2.17 | 3.2298
R002 | Mechanical | BOP Repair | Hydraulic Failure | 2 | 16 | 306666 | 0.66 | 0.99379
R002 | Mechanical | BOP Repair | OEM Defect | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 3 | 8 | 153332 | 0.33 | 0.49689
R002 | Mechanical | Draw Works Failure | Equipment Wear | 3 | 8 | 153332 | 0.33 | 0.49689
R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 5 | 46 | 881666 | 1.91 | 2.8571
R002 | Mechanical | Draw Works Failure | OEM Defect | 2 | 6 | 114999 | 0.25 | 0.37267
R002 | Mechanical | Generator Failure | Electrical Failure | 2 | 8 | 153333 | 0.33 | 0.49689
R002 | Mechanical | Generator Failure | Equipment Wear | 2 | 8 | 153332 | 0.34 | 0.49689
R002 | Mechanical | Generator Failure | OEM Defect | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 3 | 30 | 574999 | 1.25 | 1.8634
R002 | Mechanical | Mud Pump Failure | Electrical Failure | 3 | 14 | 268333 | 0.58 | 0.86957
R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 3 | 20 | 383333 | 0.83 | 1.2422
R002 | Mechanical | Mud Pump Failure | OEM Defect | 3 | 22 | 421666 | 0.91 | 1.3665
R002 | Mechanical | Power System Failure | Electrical Failure | 5 | 38 | 728333 | 1.58 | 2.3603
R002 | Mechanical | Power System Failure | Equipment Wear | 3 | 28 | 536666 | 1.16 | 1.7391
R002 | Mechanical | Power System Failure | Hydraulic Failure | 2 | 14 | 268333 | 0.58 | 0.86957
R002 | Mechanical | Power System Failure | OEM Defect | 2 | 10 | 191666 | 0.41 | 0.62112
R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 3 | 18 | 344999 | 0.75 | 1.118
R002 | Mechanical | Rotary Table Failure | Electrical Failure | 3 | 12 | 229999 | 0.5 | 0.74534
R002 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 18 | 345000 | 0.75 | 1.118
R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 3 | 22 | 421666 | 0.91 | 1.3665
R002 | Mechanical | Top Drive Failure | Electrical Failure | 3 | 10 | 191665 | 0.42 | 0.62111
R002 | Mechanical | Top Drive Failure | Equipment Wear | 4 | 24 | 459999 | 0.99 | 1.4907
R002 | Mechanical | Top Drive Failure | Hydraulic Failure | 2 | 6 | 114999 | 0.25 | 0.37267
R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 5 | 26 | 498331 | 1.08 | 1.6149
R002 | Personnel | Crew Change | Medical Emergency | 3 | 12 | 229999 | 0.5 | 0.74534
R002 | Personnel | Crew Change | Training Requirement | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Personnel | Medical Evacuation | Training Requirement | 3 | 12 | 229999 | 0.49 | 0.74534
R002 | Personnel | Safety Stand Down | Crew Rotation | 2 | 4 | 76666 | 0.16 | 0.24845
R002 | Personnel | Safety Stand Down | Training Requirement | 3 | 14 | 268332 | 0.58 | 0.86956
R002 | Weather | Heavy Rain | Heavy Rain | 2 | 16 | 306666 | 0.67 | 0.99379
R002 | Weather | Heavy Rain | High Waves | 2 | 8 | 153333 | 0.33 | 0.49689
R002 | Weather | Heavy Rain | Lightning | 2 | 8 | 153333 | 0.33 | 0.49689
R002 | Weather | Heavy Rain | Storm | 2 | 8 | 153333 | 0.33 | 0.49689
R002 | Weather | Heavy Rain | Strong Wind | 3 | 34 | 651666 | 1.41 | 2.1118
R002 | Weather | High Waves | Heavy Rain | 3 | 12 | 229999 | 0.5 | 0.74534
R002 | Weather | High Waves | High Waves | 3 | 20 | 383333 | 0.83 | 1.2422
R002 | Weather | High Waves | Lightning | 3 | 14 | 268332 | 0.59 | 0.86956
R002 | Weather | Lightning | Heavy Rain | 4 | 36 | 689999 | 1.5 | 2.236
R002 | Weather | Lightning | High Waves | 4 | 22 | 421665 | 0.92 | 1.3665
R002 | Weather | Lightning | Lightning | 8 | 28 | 536664 | 1.15 | 1.7391
R002 | Weather | Lightning | Storm | 1 | 4 | 76666 | 0.17 | 0.24845
R002 | Weather | Lightning | Strong Wind | 1 | 6 | 115000 | 0.25 | 0.37267
R002 | Weather | Poor Visibility | Heavy Rain | 3 | 24 | 460000 | 1 | 1.4907
R002 | Weather | Poor Visibility | High Waves | 3 | 12 | 229998 | 0.51 | 0.74534
R002 | Weather | Poor Visibility | Lightning | 6 | 28 | 536664 | 1.17 | 1.7391
R002 | Weather | Poor Visibility | Storm | 2 | 4 | 76666 | 0.16 | 0.24845
R002 | Weather | Poor Visibility | Strong Wind | 2 | 12 | 229999 | 0.5 | 0.74534
R002 | Weather | Strong Wind | Heavy Rain | 1 | 6 | 115000 | 0.25 | 0.37267
R002 | Weather | Strong Wind | High Waves | 2 | 12 | 229999 | 0.5 | 0.74534
R002 | Weather | Strong Wind | Lightning | 1 | 6 | 115000 | 0.25 | 0.37267
R002 | Weather | Strong Wind | Storm | 3 | 12 | 229999 | 0.5 | 0.74534
R002 | Weather | Strong Wind | Strong Wind | 4 | 18 | 344999 | 0.75 | 1.118
R003 | Drilling | Bit Failure | Differential Sticking | 4 | 26 | 520000 | 1.08 | 3.7464
R003 | Drilling | Bit Failure | Formation Instability | 3 | 8 | 160000 | 0.33 | 1.1527
R003 | Drilling | Fishing Operation | Bit Wear | 3 | 16 | 320000 | 0.66 | 2.3055
R003 | Drilling | Fishing Operation | Differential Sticking | 3 | 16 | 320000 | 0.66 | 2.3055
R003 | Drilling | Fishing Operation | Formation Instability | 2 | 8 | 160000 | 0.34 | 1.1527
R003 | Drilling | Fishing Operation | Unexpected Pressure | 2 | 16 | 320000 | 0.66 | 2.3055
R003 | Drilling | Hole Cleaning | Bit Wear | 2 | 8 | 160000 | 0.34 | 1.1527
R003 | Drilling | Hole Cleaning | Differential Sticking | 3 | 28 | 560000 | 1.17 | 4.0346
R003 | Drilling | Hole Cleaning | Formation Instability | 1 | 6 | 120000 | 0.25 | 0.86455
R003 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 6 | 120000 | 0.25 | 0.86455
R003 | Drilling | Lost Circulation | Bit Wear | 4 | 12 | 240000 | 0.49 | 1.7291
R003 | Drilling | Lost Circulation | Formation Instability | 4 | 24 | 480000 | 1 | 3.4582
R003 | Drilling | Lost Circulation | Unexpected Pressure | 2 | 16 | 320000 | 0.66 | 2.3055
R003 | Drilling | Stuck Pipe | Bit Wear | 2 | 10 | 200000 | 0.42 | 1.4409
R003 | Drilling | Stuck Pipe | Differential Sticking | 3 | 26 | 520000 | 1.08 | 3.7464
R003 | Drilling | Stuck Pipe | Formation Instability | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 16 | 320000 | 0.67 | 2.3055
R003 | Drilling | Well Control | Bit Wear | 3 | 24 | 480000 | 1 | 3.4582
R003 | Drilling | Well Control | Differential Sticking | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Drilling | Well Control | Formation Instability | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Drilling | Well Control | Unexpected Pressure | 2 | 4 | 80000 | 0.16 | 0.57637
R003 | Logistics | Delayed Helicopter | Customs Clearance | 3 | 28 | 560000 | 1.17 | 4.0346
R003 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Logistics | Delayed Helicopter | Port Congestion | 2 | 4 | 80000 | 0.16 | 0.57637
R003 | Logistics | Fuel Supply Delay | Customs Clearance | 3 | 14 | 280000 | 0.58 | 2.0173
R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 4 | 20 | 400000 | 0.83 | 2.8818
R003 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Logistics | Waiting on Boat | Customs Clearance | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Logistics | Waiting on Boat | Port Congestion | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Logistics | Waiting on Cement | Customs Clearance | 3 | 12 | 240000 | 0.5 | 1.7291
R003 | Logistics | Waiting on Cement | Late Supply Vessel | 2 | 16 | 320000 | 0.67 | 2.3055
R003 | Logistics | Waiting on Cement | Material Shortage | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Logistics | Waiting on Materials | Port Congestion | 1 | 12 | 240000 | 0.5 | 1.7291
R003 | Mechanical | BOP Repair | Electrical Failure | 1 | 18 | 360000 | 0.75 | 2.5937
R003 | Mechanical | BOP Repair | Equipment Wear | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 6 | 120000 | 0.25 | 0.86455
R003 | Mechanical | BOP Repair | OEM Defect | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 160000 | 0.33 | 1.1527
R003 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Generator Failure | Equipment Wear | 1 | 8 | 160000 | 0.33 | 1.1527
R003 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Mud Pump Failure | Electrical Failure | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 8 | 160000 | 0.33 | 1.1527
R003 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 2 | 12 | 240000 | 0.5 | 1.7291
R003 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 12 | 240000 | 0.5 | 1.7291
R003 | Mechanical | Top Drive Failure | OEM Defect | 2 | 12 | 240000 | 0.5 | 1.7291
R003 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 4 | 80000 | 0.17 | 0.57637
R003 | Personnel | Medical Evacuation | Training Requirement | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Personnel | Safety Stand Down | Crew Rotation | 1 | 8 | 160000 | 0.33 | 1.1527
R003 | Personnel | Safety Stand Down | Medical Emergency | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Personnel | Safety Stand Down | Training Requirement | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Weather | Heavy Rain | Heavy Rain | 1 | 12 | 240000 | 0.5 | 1.7291
R003 | Weather | Heavy Rain | High Waves | 2 | 8 | 160000 | 0.34 | 1.1527
R003 | Weather | Heavy Rain | Strong Wind | 2 | 12 | 240000 | 0.5 | 1.7291
R003 | Weather | High Waves | Heavy Rain | 2 | 14 | 280000 | 0.58 | 2.0173
R003 | Weather | High Waves | Lightning | 1 | 8 | 160000 | 0.33 | 1.1527
R003 | Weather | High Waves | Strong Wind | 2 | 24 | 480000 | 1 | 3.4582
R003 | Weather | Lightning | Heavy Rain | 1 | 2 | 40000 | 0.08 | 0.28818
R003 | Weather | Lightning | High Waves | 1 | 24 | 480000 | 1 | 3.4582
R003 | Weather | Lightning | Lightning | 1 | 6 | 120000 | 0.25 | 0.86455
R003 | Weather | Poor Visibility | Heavy Rain | 2 | 24 | 480000 | 1 | 3.4582
R003 | Weather | Poor Visibility | Strong Wind | 2 | 10 | 200000 | 0.42 | 1.4409
R003 | Weather | Strong Wind | Heavy Rain | 1 | 12 | 240000 | 0.5 | 1.7291
R003 | Weather | Strong Wind | Storm | 2 | 10 | 200000 | 0.41 | 1.4409
R003 | Weather | Strong Wind | Strong Wind | 1 | 6 | 120000 | 0.25 | 0.86455
R004 | Drilling | Bit Failure | Bit Wear | 3 | 22 | 449166 | 0.91 | 1.855
R004 | Drilling | Bit Failure | Differential Sticking | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Drilling | Bit Failure | Formation Instability | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Drilling | Bit Failure | Unexpected Pressure | 1 | 18 | 367500 | 0.75 | 1.5177
R004 | Drilling | Fishing Operation | Bit Wear | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Drilling | Fishing Operation | Differential Sticking | 2 | 12 | 244999 | 0.5 | 1.0118
R004 | Drilling | Fishing Operation | Formation Instability | 3 | 8 | 163332 | 0.33 | 0.67453
R004 | Drilling | Fishing Operation | Unexpected Pressure | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Drilling | Hole Cleaning | Differential Sticking | 3 | 38 | 775833 | 1.58 | 3.2041
R004 | Drilling | Hole Cleaning | Formation Instability | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Drilling | Hole Cleaning | Unexpected Pressure | 4 | 24 | 489998 | 1 | 2.0236
R004 | Drilling | Lost Circulation | Bit Wear | 4 | 26 | 530832 | 1.08 | 2.1922
R004 | Drilling | Lost Circulation | Differential Sticking | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Drilling | Lost Circulation | Formation Instability | 3 | 24 | 489999 | 0.99 | 2.0236
R004 | Drilling | Lost Circulation | Unexpected Pressure | 2 | 6 | 122499 | 0.25 | 0.5059
R004 | Drilling | Stuck Pipe | Bit Wear | 3 | 20 | 408333 | 0.83 | 1.6863
R004 | Drilling | Stuck Pipe | Differential Sticking | 1 | 12 | 245000 | 0.5 | 1.0118
R004 | Drilling | Stuck Pipe | Formation Instability | 2 | 20 | 408333 | 0.83 | 1.6863
R004 | Drilling | Stuck Pipe | Unexpected Pressure | 3 | 14 | 285832 | 0.59 | 1.1804
R004 | Drilling | Well Control | Bit Wear | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Drilling | Well Control | Formation Instability | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Drilling | Well Control | Unexpected Pressure | 4 | 18 | 367499 | 0.75 | 1.5177
R004 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Logistics | Delayed Helicopter | Late Supply Vessel | 2 | 4 | 81666 | 0.16 | 0.33727
R004 | Logistics | Delayed Helicopter | Material Shortage | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Logistics | Delayed Helicopter | Port Congestion | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Logistics | Fuel Supply Delay | Customs Clearance | 3 | 30 | 612499 | 1.25 | 2.5295
R004 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Logistics | Fuel Supply Delay | Material Shortage | 3 | 18 | 367500 | 0.75 | 1.5177
R004 | Logistics | Fuel Supply Delay | Port Congestion | 1 | 24 | 490000 | 1 | 2.0236
R004 | Logistics | Waiting on Boat | Customs Clearance | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Logistics | Waiting on Boat | Late Supply Vessel | 3 | 22 | 449166 | 0.92 | 1.855
R004 | Logistics | Waiting on Boat | Material Shortage | 2 | 6 | 122499 | 0.25 | 0.5059
R004 | Logistics | Waiting on Boat | Port Congestion | 2 | 12 | 245000 | 0.5 | 1.0118
R004 | Logistics | Waiting on Cement | Customs Clearance | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Logistics | Waiting on Cement | Material Shortage | 2 | 8 | 163333 | 0.33 | 0.67454
R004 | Logistics | Waiting on Cement | Port Congestion | 2 | 16 | 326666 | 0.67 | 1.3491
R004 | Logistics | Waiting on Materials | Customs Clearance | 2 | 4 | 81666 | 0.16 | 0.33727
R004 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Logistics | Waiting on Materials | Port Congestion | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Mechanical | BOP Repair | Electrical Failure | 3 | 14 | 285833 | 0.58 | 1.1804
R004 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | BOP Repair | OEM Defect | 1 | 8 | 163333 | 0.33 | 0.67454
R004 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | Draw Works Failure | Electrical Failure | 5 | 22 | 449164 | 0.92 | 1.855
R004 | Mechanical | Draw Works Failure | Equipment Wear | 2 | 10 | 204166 | 0.41 | 0.84317
R004 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Mechanical | Draw Works Failure | OEM Defect | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 163333 | 0.33 | 0.67454
R004 | Mechanical | Generator Failure | Equipment Wear | 2 | 6 | 122499 | 0.25 | 0.5059
R004 | Mechanical | Generator Failure | Hydraulic Failure | 2 | 10 | 204166 | 0.41 | 0.84317
R004 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Mechanical | Mud Pump Failure | Equipment Wear | 2 | 12 | 244999 | 0.5 | 1.0118
R004 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | Power System Failure | Electrical Failure | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Mechanical | Power System Failure | Equipment Wear | 3 | 14 | 285833 | 0.58 | 1.1804
R004 | Mechanical | Power System Failure | Hydraulic Failure | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 2 | 12 | 244999 | 0.5 | 1.0118
R004 | Mechanical | Rotary Table Failure | Electrical Failure | 3 | 18 | 367499 | 0.75 | 1.5177
R004 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 2 | 8 | 163333 | 0.33 | 0.67454
R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 3 | 12 | 244999 | 0.5 | 1.0118
R004 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Mechanical | Top Drive Failure | Equipment Wear | 5 | 48 | 980000 | 2 | 4.0472
R004 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Mechanical | Top Drive Failure | OEM Defect | 4 | 14 | 285832 | 0.58 | 1.1804
R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 24 | 490000 | 1 | 2.0236
R004 | Personnel | Crew Change | Crew Rotation | 1 | 18 | 367500 | 0.75 | 1.5177
R004 | Personnel | Crew Change | Medical Emergency | 1 | 18 | 367500 | 0.75 | 1.5177
R004 | Personnel | Medical Evacuation | Medical Emergency | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Personnel | Medical Evacuation | Training Requirement | 2 | 8 | 163333 | 0.33 | 0.67454
R004 | Personnel | Safety Stand Down | Medical Emergency | 2 | 22 | 449166 | 0.92 | 1.855
R004 | Personnel | Safety Stand Down | Training Requirement | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Personnel | Training | Crew Rotation | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Weather | Heavy Rain | Heavy Rain | 4 | 22 | 449165 | 0.92 | 1.855
R004 | Weather | Heavy Rain | High Waves | 2 | 4 | 81666 | 0.16 | 0.33727
R004 | Weather | Heavy Rain | Lightning | 4 | 18 | 367498 | 0.75 | 1.5177
R004 | Weather | Heavy Rain | Storm | 3 | 32 | 653332 | 1.34 | 2.6981
R004 | Weather | Heavy Rain | Strong Wind | 2 | 8 | 163333 | 0.33 | 0.67454
R004 | Weather | High Waves | Heavy Rain | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Weather | High Waves | High Waves | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Weather | High Waves | Lightning | 2 | 10 | 204166 | 0.42 | 0.84317
R004 | Weather | High Waves | Storm | 5 | 24 | 489998 | 1 | 2.0236
R004 | Weather | High Waves | Strong Wind | 3 | 26 | 530833 | 1.08 | 2.1922
R004 | Weather | Lightning | Heavy Rain | 1 | 6 | 122500 | 0.25 | 0.5059
R004 | Weather | Lightning | High Waves | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Weather | Lightning | Lightning | 5 | 24 | 489999 | 1 | 2.0236
R004 | Weather | Lightning | Storm | 3 | 20 | 408332 | 0.84 | 1.6863
R004 | Weather | Lightning | Strong Wind | 3 | 26 | 530833 | 1.08 | 2.1922
R004 | Weather | Poor Visibility | Heavy Rain | 3 | 26 | 530832 | 1.09 | 2.1922
R004 | Weather | Poor Visibility | Lightning | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Weather | Poor Visibility | Storm | 2 | 12 | 245000 | 0.5 | 1.0118
R004 | Weather | Poor Visibility | Strong Wind | 2 | 22 | 449166 | 0.92 | 1.855
R004 | Weather | Strong Wind | High Waves | 1 | 4 | 81666 | 0.17 | 0.33727
R004 | Weather | Strong Wind | Lightning | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Weather | Strong Wind | Storm | 1 | 2 | 40833 | 0.08 | 0.16863
R004 | Weather | Strong Wind | Strong Wind | 2 | 12 | 244999 | 0.5 | 1.0118

## Top_Rig_Root_Causes
Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Events | NPT_Hours | NPT_Cost_USD | Lost_Days | Cost_Share_pct
R001 | Drilling | Hole Cleaning | Bit Wear | 4 | 28 | 554166 | 1.16 | 5.4054
R001 | Drilling | Lost Circulation | Formation Instability | 1 | 24 | 475000 | 1 | 4.6332
R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 2 | 24 | 475000 | 1 | 4.6332
R001 | Drilling | Fishing Operation | Formation Instability | 2 | 22 | 435416 | 0.92 | 4.2471
R001 | Mechanical | Generator Failure | Equipment Wear | 3 | 22 | 435416 | 0.91 | 4.2471
R001 | Drilling | Well Control | Bit Wear | 2 | 20 | 395833 | 0.83 | 3.861
R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 3.4749
R001 | Logistics | Fuel Supply Delay | Customs Clearance | 3 | 18 | 356249 | 0.75 | 3.4749
R002 | Mechanical | BOP Repair | Equipment Wear | 5 | 52 | 996665 | 2.17 | 3.2298
R002 | Drilling | Stuck Pipe | Unexpected Pressure | 7 | 50 | 958331 | 2.09 | 3.1056
R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 5 | 46 | 881666 | 1.91 | 2.8571
R002 | Drilling | Stuck Pipe | Differential Sticking | 8 | 42 | 804998 | 1.75 | 2.6087
R002 | Mechanical | Power System Failure | Electrical Failure | 5 | 38 | 728333 | 1.58 | 2.3603
R002 | Drilling | Stuck Pipe | Bit Wear | 4 | 36 | 689999 | 1.5 | 2.236
R002 | Weather | Lightning | Heavy Rain | 4 | 36 | 689999 | 1.5 | 2.236
R002 | Drilling | Bit Failure | Unexpected Pressure | 8 | 36 | 689997 | 1.49 | 2.236
R002 | Drilling | Hole Cleaning | Differential Sticking | 4 | 34 | 651666 | 1.41 | 2.1118
R002 | Weather | Heavy Rain | Strong Wind | 3 | 34 | 651666 | 1.41 | 2.1118
R003 | Drilling | Hole Cleaning | Differential Sticking | 3 | 28 | 560000 | 1.17 | 4.0346
R003 | Logistics | Delayed Helicopter | Customs Clearance | 3 | 28 | 560000 | 1.17 | 4.0346
R003 | Drilling | Bit Failure | Differential Sticking | 4 | 26 | 520000 | 1.08 | 3.7464
R003 | Drilling | Stuck Pipe | Differential Sticking | 3 | 26 | 520000 | 1.08 | 3.7464
R003 | Drilling | Lost Circulation | Formation Instability | 4 | 24 | 480000 | 1 | 3.4582
R003 | Drilling | Well Control | Bit Wear | 3 | 24 | 480000 | 1 | 3.4582
R003 | Weather | High Waves | Strong Wind | 2 | 24 | 480000 | 1 | 3.4582
R003 | Weather | Lightning | High Waves | 1 | 24 | 480000 | 1 | 3.4582
R003 | Weather | Poor Visibility | Heavy Rain | 2 | 24 | 480000 | 1 | 3.4582
R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 4 | 20 | 400000 | 0.83 | 2.8818
R004 | Mechanical | Top Drive Failure | Equipment Wear | 5 | 48 | 980000 | 2 | 4.0472
R004 | Drilling | Hole Cleaning | Differential Sticking | 3 | 38 | 775833 | 1.58 | 3.2041
R004 | Weather | Heavy Rain | Storm | 3 | 32 | 653332 | 1.34 | 2.6981
R004 | Logistics | Fuel Supply Delay | Customs Clearance | 3 | 30 | 612499 | 1.25 | 2.5295
R004 | Weather | High Waves | Strong Wind | 3 | 26 | 530833 | 1.08 | 2.1922
R004 | Weather | Lightning | Strong Wind | 3 | 26 | 530833 | 1.08 | 2.1922
R004 | Drilling | Lost Circulation | Bit Wear | 4 | 26 | 530832 | 1.08 | 2.1922
R004 | Weather | Poor Visibility | Heavy Rain | 3 | 26 | 530832 | 1.09 | 2.1922
R004 | Logistics | Fuel Supply Delay | Port Congestion | 1 | 24 | 490000 | 1 | 2.0236
R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 24 | 490000 | 1 | 2.0236

## Well_Root_Cause
Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Events | NPT_Hours | NPT_Cost_USD | Lost_Days | Cost_Share_pct
W001 | R004 | Drilling | Fishing Operation | Differential Sticking | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Drilling | Lost Circulation | Differential Sticking | 1 | 2 | 40833 | 0.08 | 2.2727
W001 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Logistics | Delayed Helicopter | Material Shortage | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 2 | 40833 | 0.08 | 2.2727
W001 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Logistics | Waiting on Cement | Material Shortage | 1 | 2 | 40833 | 0.08 | 2.2727
W001 | R004 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Mechanical | BOP Repair | Electrical Failure | 1 | 2 | 40833 | 0.08 | 2.2727
W001 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Mechanical | Top Drive Failure | OEM Defect | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Weather | Heavy Rain | High Waves | 1 | 2 | 40833 | 0.08 | 2.2727
W001 | R004 | Weather | High Waves | High Waves | 1 | 4 | 81666 | 0.17 | 4.5454
W001 | R004 | Weather | High Waves | Lightning | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Weather | High Waves | Storm | 1 | 12 | 245000 | 0.5 | 13.6364
W001 | R004 | Weather | High Waves | Strong Wind | 1 | 8 | 163333 | 0.33 | 9.0909
W001 | R004 | Weather | Lightning | Heavy Rain | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Weather | Lightning | Storm | 1 | 4 | 81666 | 0.17 | 4.5454
W002 | R001 | Drilling | Bit Failure | Bit Wear | 2 | 12 | 237500 | 0.5 | 13.6364
W002 | R001 | Drilling | Hole Cleaning | Bit Wear | 1 | 8 | 158333 | 0.33 | 9.0909
W002 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 2 | 39583 | 0.08 | 2.2727
W002 | R001 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 6 | 118750 | 0.25 | 6.8182
W002 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 4 | 79166 | 0.17 | 4.5454
W002 | R001 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 6 | 118750 | 0.25 | 6.8182
W002 | R001 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 8 | 158333 | 0.33 | 9.0909
W002 | R001 | Mechanical | Generator Failure | Equipment Wear | 2 | 20 | 395833 | 0.83 | 22.7273
W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 12 | 237500 | 0.5 | 13.6364
W002 | R001 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 6 | 118750 | 0.25 | 6.8182
W002 | R001 | Weather | Poor Visibility | Heavy Rain | 1 | 4 | 79166 | 0.17 | 4.5454
W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 367500 | 0.75 | 20.4546
W003 | R004 | Logistics | Waiting on Boat | Customs Clearance | 1 | 4 | 81666 | 0.17 | 4.5454
W003 | R004 | Logistics | Waiting on Boat | Material Shortage | 2 | 6 | 122499 | 0.25 | 6.8181
W003 | R004 | Mechanical | BOP Repair | Electrical Failure | 1 | 6 | 122500 | 0.25 | 6.8182
W003 | R004 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 2.2727
W003 | R004 | Mechanical | Power System Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 6.8182
W003 | R004 | Mechanical | Power System Failure | Equipment Wear | 1 | 2 | 40833 | 0.08 | 2.2727
W003 | R004 | Mechanical | Power System Failure | Hydraulic Failure | 1 | 4 | 81666 | 0.17 | 4.5454
W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 2 | 30 | 612500 | 1.25 | 34.091
W003 | R004 | Personnel | Safety Stand Down | Training Requirement | 1 | 6 | 122500 | 0.25 | 6.8182
W003 | R004 | Weather | Strong Wind | Strong Wind | 1 | 4 | 81666 | 0.17 | 4.5454
W004 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 2 | 38333 | 0.08 | 3.8461
W004 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 3.8461
W004 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 4 | 76666 | 0.17 | 7.6923
W004 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 12 | 230000 | 0.5 | 23.077
W004 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 12 | 230000 | 0.5 | 23.077
W004 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 2 | 38333 | 0.08 | 3.8461
W004 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 2 | 38333 | 0.08 | 3.8461
W004 | R002 | Weather | Heavy Rain | Heavy Rain | 1 | 4 | 76666 | 0.17 | 7.6923
W004 | R002 | Weather | Lightning | High Waves | 1 | 4 | 76666 | 0.17 | 7.6923
W004 | R002 | Weather | Lightning | Lightning | 2 | 8 | 153333 | 0.33 | 15.3846
W005 | R002 | Drilling | Hole Cleaning | Formation Instability | 1 | 4 | 76666 | 0.17 | 6.25
W005 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 4 | 76666 | 0.17 | 6.25
W005 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 4 | 76666 | 0.17 | 6.25
W005 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 4 | 76666 | 0.17 | 6.25
W005 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 8 | 153333 | 0.33 | 12.5
W005 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 9.375
W005 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 115000 | 0.25 | 9.375
W005 | R002 | Personnel | Medical Evacuation | Training Requirement | 1 | 8 | 153333 | 0.33 | 12.5
W005 | R002 | Weather | Heavy Rain | Storm | 1 | 6 | 115000 | 0.25 | 9.375
W005 | R002 | Weather | Lightning | Lightning | 1 | 4 | 76666 | 0.17 | 6.25
W005 | R002 | Weather | Poor Visibility | Storm | 1 | 2 | 38333 | 0.08 | 3.125
W005 | R002 | Weather | Strong Wind | Storm | 1 | 2 | 38333 | 0.08 | 3.125
W005 | R002 | Weather | Strong Wind | Strong Wind | 1 | 6 | 115000 | 0.25 | 9.375
W006 | R002 | Drilling | Bit Failure | Bit Wear | 1 | 18 | 345000 | 0.75 | 21.4287
W006 | R002 | Drilling | Fishing Operation | Differential Sticking | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Logistics | Delayed Helicopter | Material Shortage | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Logistics | Waiting on Cement | Customs Clearance | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Logistics | Waiting on Materials | Port Congestion | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 1 | 2 | 38333 | 0.08 | 2.3809
W006 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 7.1429
W006 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 7.1429
W006 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Weather | High Waves | Lightning | 1 | 4 | 76666 | 0.17 | 4.7619
W006 | R002 | Weather | Lightning | Lightning | 1 | 2 | 38333 | 0.08 | 2.3809
W006 | R002 | Weather | Poor Visibility | Lightning | 1 | 2 | 38333 | 0.08 | 2.3809
W007 | R001 | Drilling | Hole Cleaning | Differential Sticking | 1 | 4 | 79166 | 0.17 | 3.125
W007 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 158333 | 0.33 | 6.25
W007 | R001 | Drilling | Stuck Pipe | Formation Instability | 1 | 2 | 39583 | 0.08 | 1.5625
W007 | R001 | Drilling | Well Control | Bit Wear | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 4 | 79166 | 0.17 | 3.125
W007 | R001 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 8 | 158333 | 0.33 | 6.25
W007 | R001 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 6 | 118750 | 0.25 | 4.6875
W007 | R001 | Mechanical | Generator Failure | Equipment Wear | 1 | 2 | 39583 | 0.08 | 1.5625
W007 | R001 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 2 | 39583 | 0.08 | 1.5625
W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Personnel | Training | Training Requirement | 1 | 2 | 39583 | 0.08 | 1.5625
W007 | R001 | Weather | Lightning | Lightning | 1 | 6 | 118750 | 0.25 | 4.6875
W007 | R001 | Weather | Lightning | Storm | 1 | 8 | 158333 | 0.33 | 6.25
W007 | R001 | Weather | Strong Wind | High Waves | 1 | 4 | 79166 | 0.17 | 3.125
W008 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 4 | 76666 | 0.17 | 10
W008 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 6 | 115000 | 0.25 | 15.0001
W008 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 6 | 115000 | 0.25 | 15.0001
W008 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 20.0001
W008 | R002 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 5
W008 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 5
W008 | R002 | Mechanical | BOP Repair | OEM Defect | 1 | 4 | 76666 | 0.17 | 10
W008 | R002 | Personnel | Safety Stand Down | Training Requirement | 1 | 2 | 38333 | 0.08 | 5
W008 | R002 | Weather | Lightning | Lightning | 1 | 2 | 38333 | 0.08 | 5
W008 | R002 | Weather | Poor Visibility | High Waves | 1 | 4 | 76666 | 0.17 | 10
W009 | R001 | Drilling | Bit Failure | Formation Instability | 1 | 4 | 79166 | 0.17 | 4
W009 | R001 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Drilling | Lost Circulation | Formation Instability | 1 | 24 | 475000 | 1 | 24
W009 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Logistics | Waiting on Cement | Customs Clearance | 1 | 12 | 237500 | 0.5 | 12
W009 | R001 | Mechanical | Draw Works Failure | OEM Defect | 1 | 4 | 79166 | 0.17 | 4
W009 | R001 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 4 | 79166 | 0.17 | 4
W009 | R001 | Weather | Heavy Rain | High Waves | 1 | 8 | 158333 | 0.33 | 8
W009 | R001 | Weather | Heavy Rain | Lightning | 1 | 4 | 79166 | 0.17 | 4
W009 | R001 | Weather | High Waves | Lightning | 1 | 2 | 39583 | 0.08 | 2
W009 | R001 | Weather | Lightning | High Waves | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Weather | Poor Visibility | Storm | 1 | 2 | 39583 | 0.08 | 2
W009 | R001 | Weather | Strong Wind | High Waves | 1 | 6 | 118750 | 0.25 | 6
W010 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 1.8868
W010 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 1.8868
W010 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 8 | 153333 | 0.33 | 7.5472
W010 | R002 | Drilling | Lost Circulation | Bit Wear | 1 | 4 | 76666 | 0.17 | 3.7736
W010 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 6 | 115000 | 0.25 | 5.6604
W010 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 4 | 76666 | 0.17 | 3.7736
W010 | R002 | Drilling | Well Control | Formation Instability | 1 | 4 | 76666 | 0.17 | 3.7736
W010 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 1.8868
W010 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 7.5472
W010 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 4 | 76666 | 0.17 | 3.7736
W010 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 7.5472
W010 | R002 | Weather | Heavy Rain | Strong Wind | 1 | 24 | 460000 | 1 | 22.6416
W010 | R002 | Weather | Lightning | Heavy Rain | 2 | 20 | 383333 | 0.83 | 18.868
W010 | R002 | Weather | Strong Wind | Storm | 1 | 6 | 115000 | 0.25 | 5.6604
W010 | R002 | Weather | Strong Wind | Strong Wind | 1 | 4 | 76666 | 0.17 | 3.7736
W011 | R004 | Drilling | Bit Failure | Bit Wear | 1 | 12 | 245000 | 0.5 | 11.5385
W011 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 12 | 245000 | 0.5 | 11.5385
W011 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 163333 | 0.33 | 7.6923
W011 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 2 | 40833 | 0.08 | 1.9231
W011 | R004 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 3.8461
W011 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 4 | 81666 | 0.17 | 3.8461
W011 | R004 | Mechanical | Generator Failure | Equipment Wear | 1 | 2 | 40833 | 0.08 | 1.9231
W011 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 1.9231
W011 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 5.7692
W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 24 | 490000 | 1 | 23.077
W011 | R004 | Personnel | Training | Crew Rotation | 1 | 6 | 122500 | 0.25 | 5.7692
W011 | R004 | Weather | Lightning | Lightning | 2 | 10 | 204166 | 0.42 | 9.6154
W011 | R004 | Weather | Lightning | Storm | 1 | 4 | 81666 | 0.17 | 3.8461
W011 | R004 | Weather | Poor Visibility | Heavy Rain | 1 | 4 | 81666 | 0.17 | 3.8461
W011 | R004 | Weather | Poor Visibility | Strong Wind | 1 | 4 | 81666 | 0.17 | 3.8461
W012 | R004 | Drilling | Bit Failure | Unexpected Pressure | 1 | 18 | 367500 | 0.75 | 28.1251
W012 | R004 | Drilling | Fishing Operation | Formation Instability | 1 | 4 | 81666 | 0.17 | 6.25
W012 | R004 | Drilling | Stuck Pipe | Bit Wear | 1 | 2 | 40833 | 0.08 | 3.125
W012 | R004 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 2 | 40833 | 0.08 | 3.125
W012 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 12 | 245000 | 0.5 | 18.75
W012 | R004 | Logistics | Waiting on Boat | Port Congestion | 1 | 6 | 122500 | 0.25 | 9.375
W012 | R004 | Logistics | Waiting on Cement | Customs Clearance | 1 | 2 | 40833 | 0.08 | 3.125
W012 | R004 | Logistics | Waiting on Materials | Customs Clearance | 1 | 2 | 40833 | 0.08 | 3.125
W012 | R004 | Mechanical | Power System Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 9.375
W012 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 6.25
W012 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 9.375
W013 | R003 | Drilling | Bit Failure | Formation Instability | 1 | 2 | 40000 | 0.08 | 2.0833
W013 | R003 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 160000 | 0.33 | 8.3333
W013 | R003 | Drilling | Fishing Operation | Formation Instability | 1 | 4 | 80000 | 0.17 | 4.1667
W013 | R003 | Drilling | Hole Cleaning | Differential Sticking | 1 | 6 | 120000 | 0.25 | 6.25
W013 | R003 | Drilling | Lost Circulation | Bit Wear | 2 | 4 | 80000 | 0.16 | 4.1667
W013 | R003 | Drilling | Lost Circulation | Formation Instability | 2 | 18 | 360000 | 0.75 | 18.75
W013 | R003 | Drilling | Stuck Pipe | Differential Sticking | 1 | 6 | 120000 | 0.25 | 6.25
W013 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 2 | 40000 | 0.08 | 2.0833
W013 | R003 | Logistics | Waiting on Cement | Customs Clearance | 1 | 4 | 80000 | 0.17 | 4.1667
W013 | R003 | Logistics | Waiting on Cement | Material Shortage | 1 | 2 | 40000 | 0.08 | 2.0833
W013 | R003 | Mechanical | BOP Repair | Equipment Wear | 1 | 4 | 80000 | 0.17 | 4.1667
W013 | R003 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 2 | 40000 | 0.08 | 2.0833
W013 | R003 | Personnel | Safety Stand Down | Crew Rotation | 1 | 8 | 160000 | 0.33 | 8.3333
W013 | R003 | Personnel | Safety Stand Down | Medical Emergency | 1 | 2 | 40000 | 0.08 | 2.0833
W013 | R003 | Weather | Heavy Rain | High Waves | 1 | 4 | 80000 | 0.17 | 4.1667
W013 | R003 | Weather | Heavy Rain | Strong Wind | 1 | 6 | 120000 | 0.25 | 6.25
W013 | R003 | Weather | Lightning | Lightning | 1 | 6 | 120000 | 0.25 | 6.25
W013 | R003 | Weather | Strong Wind | Storm | 1 | 8 | 160000 | 0.33 | 8.3333
W014 | R004 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 15.7895
W014 | R004 | Drilling | Stuck Pipe | Bit Wear | 1 | 12 | 245000 | 0.5 | 31.5791
W014 | R004 | Logistics | Waiting on Cement | Port Congestion | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Mechanical | Power System Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Personnel | Medical Evacuation | Training Requirement | 1 | 2 | 40833 | 0.08 | 5.2631
W014 | R004 | Weather | Heavy Rain | High Waves | 1 | 2 | 40833 | 0.08 | 5.2631
W015 | R003 | Drilling | Fishing Operation | Differential Sticking | 1 | 2 | 40000 | 0.08 | 2.6316
W015 | R003 | Drilling | Fishing Operation | Formation Instability | 1 | 4 | 80000 | 0.17 | 5.2632
W015 | R003 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 6 | 120000 | 0.25 | 7.8947
W015 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 10.5263
W015 | R003 | Drilling | Stuck Pipe | Bit Wear | 1 | 4 | 80000 | 0.17 | 5.2632
W015 | R003 | Drilling | Well Control | Formation Instability | 1 | 2 | 40000 | 0.08 | 2.6316
W015 | R003 | Drilling | Well Control | Unexpected Pressure | 1 | 2 | 40000 | 0.08 | 2.6316
W015 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 18 | 360000 | 0.75 | 23.6842
W015 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 4 | 80000 | 0.17 | 5.2632
W015 | R003 | Logistics | Waiting on Cement | Customs Clearance | 1 | 6 | 120000 | 0.25 | 7.8947
W015 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 4 | 80000 | 0.17 | 5.2632
W015 | R003 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 6 | 120000 | 0.25 | 7.8947
W015 | R003 | Mechanical | Generator Failure | Equipment Wear | 1 | 8 | 160000 | 0.33 | 10.5263
W015 | R003 | Personnel | Safety Stand Down | Training Requirement | 1 | 2 | 40000 | 0.08 | 2.6316
W016 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 2 | 40833 | 0.08 | 4
W016 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 4 | 81666 | 0.17 | 8
W016 | R004 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 122500 | 0.25 | 12
W016 | R004 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 8 | 163333 | 0.33 | 16
W016 | R004 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 12
W016 | R004 | Weather | Heavy Rain | Heavy Rain | 1 | 4 | 81666 | 0.17 | 8
W016 | R004 | Weather | Heavy Rain | Lightning | 1 | 2 | 40833 | 0.08 | 4
W016 | R004 | Weather | Lightning | Strong Wind | 1 | 6 | 122500 | 0.25 | 12
W016 | R004 | Weather | Poor Visibility | Heavy Rain | 1 | 4 | 81666 | 0.17 | 8
W016 | R004 | Weather | Strong Wind | Strong Wind | 1 | 8 | 163333 | 0.33 | 16
W017 | R001 | Drilling | Bit Failure | Formation Instability | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Drilling | Fishing Operation | Formation Instability | 1 | 4 | 79166 | 0.17 | 7.4074
W017 | R001 | Drilling | Hole Cleaning | Formation Instability | 1 | 2 | 39583 | 0.08 | 3.7037
W017 | R001 | Drilling | Stuck Pipe | Formation Instability | 1 | 2 | 39583 | 0.08 | 3.7037
W017 | R001 | Drilling | Well Control | Bit Wear | 1 | 2 | 39583 | 0.08 | 3.7037
W017 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 8 | 158333 | 0.33 | 14.8148
W017 | R001 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Mechanical | Draw Works Failure | OEM Defect | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Personnel | Safety Stand Down | Crew Rotation | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Weather | Strong Wind | High Waves | 1 | 6 | 118750 | 0.25 | 11.1111
W018 | R004 | Drilling | Fishing Operation | Formation Instability | 2 | 4 | 81666 | 0.16 | 4.5454
W018 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 163333 | 0.33 | 9.0909
W018 | R004 | Drilling | Stuck Pipe | Formation Instability | 1 | 12 | 245000 | 0.5 | 13.6364
W018 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 4.5454
W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | 1 | 24 | 490000 | 1 | 27.2728
W018 | R004 | Mechanical | Generator Failure | Equipment Wear | 1 | 4 | 81666 | 0.17 | 4.5454
W018 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 6.8182
W018 | R004 | Weather | Heavy Rain | Heavy Rain | 1 | 4 | 81666 | 0.17 | 4.5454
W018 | R004 | Weather | Heavy Rain | Storm | 1 | 4 | 81666 | 0.17 | 4.5454
W018 | R004 | Weather | Heavy Rain | Strong Wind | 1 | 2 | 40833 | 0.08 | 2.2727
W018 | R004 | Weather | Poor Visibility | Storm | 2 | 12 | 245000 | 0.5 | 13.6364
W018 | R004 | Weather | Strong Wind | High Waves | 1 | 4 | 81666 | 0.17 | 4.5454
W019 | R003 | Drilling | Hole Cleaning | Bit Wear | 1 | 4 | 80000 | 0.17 | 3.5088
W019 | R003 | Drilling | Lost Circulation | Bit Wear | 1 | 2 | 40000 | 0.08 | 1.7544
W019 | R003 | Drilling | Lost Circulation | Formation Instability | 2 | 6 | 120000 | 0.25 | 5.2632
W019 | R003 | Drilling | Stuck Pipe | Bit Wear | 1 | 6 | 120000 | 0.25 | 5.2632
W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 16 | 320000 | 0.67 | 14.0351
W019 | R003 | Drilling | Well Control | Bit Wear | 1 | 18 | 360000 | 0.75 | 15.7895
W019 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 6 | 120000 | 0.25 | 5.2632
W019 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 8 | 160000 | 0.33 | 7.0175
W019 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 12 | 240000 | 0.5 | 10.5263
W019 | R003 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 12 | 240000 | 0.5 | 10.5263
W019 | R003 | Weather | Lightning | High Waves | 1 | 24 | 480000 | 1 | 21.0526
W020 | R003 | Drilling | Bit Failure | Formation Instability | 1 | 4 | 80000 | 0.17 | 4.4444
W020 | R003 | Drilling | Fishing Operation | Differential Sticking | 1 | 6 | 120000 | 0.25 | 6.6667
W020 | R003 | Drilling | Hole Cleaning | Differential Sticking | 1 | 4 | 80000 | 0.17 | 4.4444
W020 | R003 | Drilling | Lost Circulation | Bit Wear | 1 | 6 | 120000 | 0.25 | 6.6667
W020 | R003 | Drilling | Stuck Pipe | Differential Sticking | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Logistics | Delayed Helicopter | Port Congestion | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 6 | 120000 | 0.25 | 6.6667
W020 | R003 | Mechanical | BOP Repair | Electrical Failure | 1 | 18 | 360000 | 0.75 | 20
W020 | R003 | Mechanical | BOP Repair | OEM Defect | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Mechanical | Mud Pump Failure | Electrical Failure | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 4 | 80000 | 0.17 | 4.4444
W020 | R003 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 2 | 12 | 240000 | 0.5 | 13.3333
W020 | R003 | Personnel | Medical Evacuation | Training Requirement | 1 | 2 | 40000 | 0.08 | 2.2222
W020 | R003 | Weather | Heavy Rain | High Waves | 1 | 4 | 80000 | 0.17 | 4.4444
W020 | R003 | Weather | High Waves | Heavy Rain | 1 | 8 | 160000 | 0.33 | 8.8889
W020 | R003 | Weather | Lightning | Heavy Rain | 1 | 2 | 40000 | 0.08 | 2.2222
W021 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.383
W021 | R002 | Drilling | Well Control | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.383
W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 2 | 8 | 153333 | 0.33 | 8.5106
W021 | R002 | Logistics | Waiting on Cement | Port Congestion | 1 | 18 | 345000 | 0.75 | 19.149
W021 | R002 | Logistics | Waiting on Materials | Port Congestion | 1 | 8 | 153333 | 0.33 | 8.5106
W021 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 4 | 76666 | 0.17 | 4.2553
W021 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 6.383
W021 | R002 | Mechanical | Draw Works Failure | OEM Defect | 1 | 2 | 38333 | 0.08 | 2.1276
W021 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 6.383
W021 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 12 | 230000 | 0.5 | 12.766
W021 | R002 | Mechanical | Power System Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 6.383
W021 | R002 | Mechanical | Power System Failure | OEM Defect | 1 | 2 | 38333 | 0.08 | 2.1276
W021 | R002 | Personnel | Medical Evacuation | Training Requirement | 1 | 2 | 38333 | 0.08 | 2.1276
W021 | R002 | Weather | Lightning | Lightning | 1 | 2 | 38333 | 0.08 | 2.1276
W021 | R002 | Weather | Strong Wind | Strong Wind | 1 | 6 | 115000 | 0.25 | 6.383
W022 | R001 | Drilling | Hole Cleaning | Bit Wear | 2 | 18 | 356250 | 0.75 | 24.3244
W022 | R001 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 118750 | 0.25 | 8.1081
W022 | R001 | Logistics | Waiting on Materials | Port Congestion | 1 | 8 | 158333 | 0.33 | 10.8108
W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 158333 | 0.33 | 10.8108
W022 | R001 | Weather | High Waves | Strong Wind | 1 | 2 | 39583 | 0.08 | 2.7027
W022 | R001 | Weather | Lightning | Lightning | 1 | 2 | 39583 | 0.08 | 2.7027
W022 | R001 | Weather | Poor Visibility | High Waves | 1 | 6 | 118750 | 0.25 | 8.1081
W022 | R001 | Weather | Poor Visibility | Strong Wind | 2 | 14 | 277083 | 0.58 | 18.9189
W022 | R001 | Weather | Strong Wind | Heavy Rain | 2 | 6 | 118749 | 0.25 | 8.1081
W022 | R001 | Weather | Strong Wind | Strong Wind | 1 | 4 | 79166 | 0.17 | 5.4054
W023 | R004 | Drilling | Fishing Operation | Bit Wear | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Drilling | Well Control | Bit Wear | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 7.1429
W023 | R004 | Logistics | Waiting on Boat | Port Congestion | 1 | 6 | 122500 | 0.25 | 7.1429
W023 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Mechanical | Draw Works Failure | OEM Defect | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 2.3809
W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 8 | 163333 | 0.33 | 9.5238
W023 | R004 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 2 | 40833 | 0.08 | 2.3809
W023 | R004 | Mechanical | Top Drive Failure | OEM Defect | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Personnel | Crew Change | Medical Emergency | 1 | 18 | 367500 | 0.75 | 21.4286
W023 | R004 | Personnel | Medical Evacuation | Medical Emergency | 1 | 6 | 122500 | 0.25 | 7.1429
W023 | R004 | Personnel | Safety Stand Down | Medical Emergency | 1 | 4 | 81666 | 0.17 | 4.7619
W023 | R004 | Weather | Lightning | Storm | 1 | 12 | 245000 | 0.5 | 14.2858
W024 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 2.9412
W024 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 115000 | 0.25 | 8.8236
W024 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 4 | 76666 | 0.17 | 5.8823
W024 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 2 | 38333 | 0.08 | 2.9412
W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 16 | 306666 | 0.67 | 23.5294
W024 | R002 | Drilling | Well Control | Differential Sticking | 1 | 4 | 76666 | 0.17 | 5.8823
W024 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 12 | 230000 | 0.5 | 17.6471
W024 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.7647
W024 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 2 | 38333 | 0.08 | 2.9412
W024 | R002 | Mechanical | Power System Failure | OEM Defect | 1 | 8 | 153333 | 0.33 | 11.7647
W024 | R002 | Weather | Poor Visibility | High Waves | 1 | 4 | 76666 | 0.17 | 5.8823
W025 | R004 | Drilling | Bit Failure | Differential Sticking | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 12 | 245000 | 0.5 | 22.2223
W025 | R004 | Drilling | Stuck Pipe | Bit Wear | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Drilling | Well Control | Formation Instability | 1 | 4 | 81666 | 0.17 | 7.4074
W025 | R004 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 4 | 81666 | 0.17 | 7.4074
W025 | R004 | Mechanical | Top Drive Failure | OEM Defect | 1 | 2 | 40833 | 0.08 | 3.7037
W025 | R004 | Weather | Heavy Rain | Storm | 1 | 4 | 81666 | 0.17 | 7.4074
W025 | R004 | Weather | High Waves | Storm | 1 | 2 | 40833 | 0.08 | 3.7037
W025 | R004 | Weather | High Waves | Strong Wind | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Weather | Strong Wind | Lightning | 1 | 2 | 40833 | 0.08 | 3.7037
W026 | R004 | Drilling | Bit Failure | Bit Wear | 1 | 8 | 163333 | 0.33 | 8.8889
W026 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 4.4444
W026 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 6 | 122500 | 0.25 | 6.6667
W026 | R004 | Logistics | Waiting on Materials | Customs Clearance | 1 | 2 | 40833 | 0.08 | 2.2222
W026 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 2 | 40833 | 0.08 | 2.2222
W026 | R004 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 2 | 40833 | 0.08 | 2.2222
W026 | R004 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 163333 | 0.33 | 8.8889
W026 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 4 | 81666 | 0.17 | 4.4444
W026 | R004 | Personnel | Safety Stand Down | Medical Emergency | 1 | 18 | 367500 | 0.75 | 20
W026 | R004 | Weather | Heavy Rain | Storm | 1 | 24 | 490000 | 1 | 26.6667
W026 | R004 | Weather | High Waves | Strong Wind | 1 | 12 | 245000 | 0.5 | 13.3334
W027 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 8 | 153333 | 0.33 | 12.1212
W027 | R002 | Drilling | Fishing Operation | Differential Sticking | 1 | 18 | 345000 | 0.75 | 27.2728
W027 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 2 | 38333 | 0.08 | 3.0303
W027 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 12.1212
W027 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 6 | 115000 | 0.25 | 9.0909
W027 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 4 | 76666 | 0.17 | 6.0606
W027 | R002 | Weather | High Waves | Heavy Rain | 1 | 2 | 38333 | 0.08 | 3.0303
W027 | R002 | Weather | Lightning | High Waves | 2 | 16 | 306666 | 0.67 | 24.2424
W027 | R002 | Weather | Poor Visibility | Storm | 1 | 2 | 38333 | 0.08 | 3.0303
W028 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 4 | 76666 | 0.17 | 4.4444
W028 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 2.2222
W028 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 6 | 115000 | 0.25 | 6.6667
W028 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 18 | 345000 | 0.75 | 20.0001
W028 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 12 | 230000 | 0.5 | 13.3334
W028 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 4 | 76666 | 0.17 | 4.4444
W028 | R002 | Mechanical | Power System Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W028 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 2 | 38333 | 0.08 | 2.2222
W028 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 8.8889
W028 | R002 | Personnel | Crew Change | Training Requirement | 1 | 4 | 76666 | 0.17 | 4.4444
W028 | R002 | Weather | High Waves | Lightning | 1 | 6 | 115000 | 0.25 | 6.6667
W028 | R002 | Weather | Lightning | Storm | 1 | 4 | 76666 | 0.17 | 4.4444
W028 | R002 | Weather | Strong Wind | Heavy Rain | 1 | 6 | 115000 | 0.25 | 6.6667
W028 | R002 | Weather | Strong Wind | Storm | 1 | 4 | 76666 | 0.17 | 4.4444
W028 | R002 | Weather | Strong Wind | Strong Wind | 1 | 2 | 38333 | 0.08 | 2.2222
W029 | R002 | Drilling | Hole Cleaning | Bit Wear | 1 | 4 | 76666 | 0.17 | 5.7143
W029 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 2 | 38333 | 0.08 | 2.8571
W029 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Drilling | Well Control | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 5.7143
W029 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 115000 | 0.25 | 8.5715
W029 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 4 | 76666 | 0.17 | 5.7143
W029 | R002 | Personnel | Crew Change | Medical Emergency | 1 | 6 | 115000 | 0.25 | 8.5715
W029 | R002 | Personnel | Medical Evacuation | Training Requirement | 1 | 2 | 38333 | 0.08 | 2.8571
W029 | R002 | Weather | Heavy Rain | Lightning | 1 | 6 | 115000 | 0.25 | 8.5715
W029 | R002 | Weather | Heavy Rain | Strong Wind | 1 | 2 | 38333 | 0.08 | 2.8571
W029 | R002 | Weather | Poor Visibility | Heavy Rain | 1 | 6 | 115000 | 0.25 | 8.5715
W029 | R002 | Weather | Strong Wind | High Waves | 1 | 4 | 76666 | 0.17 | 5.7143
W030 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 4.4444
W030 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 2.2222
W030 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 2 | 38333 | 0.08 | 2.2222
W030 | R002 | Drilling | Well Control | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.6667
W030 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 115000 | 0.25 | 6.6667
W030 | R002 | Logistics | Waiting on Cement | Material Shortage | 1 | 6 | 115000 | 0.25 | 6.6667
W030 | R002 | Mechanical | BOP Repair | Electrical Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Mechanical | Generator Failure | Electrical Failure | 1 | 2 | 38333 | 0.08 | 2.2222
W030 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 12 | 230000 | 0.5 | 13.3334
W030 | R002 | Mechanical | Power System Failure | Equipment Wear | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 2 | 38333 | 0.08 | 2.2222
W030 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 4 | 76666 | 0.17 | 4.4444
W030 | R002 | Personnel | Safety Stand Down | Training Requirement | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Weather | High Waves | High Waves | 1 | 12 | 230000 | 0.5 | 13.3334
W031 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 2 | 38333 | 0.08 | 3.3333
W031 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Logistics | Waiting on Materials | Customs Clearance | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 24 | 460000 | 1 | 40.0002
W031 | R002 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 2 | 38333 | 0.08 | 3.3333
W031 | R002 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Personnel | Safety Stand Down | Training Requirement | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Weather | High Waves | Heavy Rain | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Weather | Poor Visibility | Strong Wind | 1 | 4 | 76666 | 0.17 | 6.6666
W032 | R004 | Drilling | Bit Failure | Formation Instability | 1 | 2 | 40833 | 0.08 | 2.3256
W032 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 2 | 40833 | 0.08 | 2.3256
W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 2 | 12 | 245000 | 0.5 | 13.9535
W032 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 8 | 163333 | 0.33 | 9.3023
W032 | R004 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 8 | 163333 | 0.33 | 9.3023
W032 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 6.9768
W032 | R004 | Mechanical | Top Drive Failure | OEM Defect | 1 | 2 | 40833 | 0.08 | 2.3256
W032 | R004 | Personnel | Safety Stand Down | Training Requirement | 1 | 4 | 81666 | 0.17 | 4.6511
W032 | R004 | Weather | Heavy Rain | Lightning | 1 | 8 | 163333 | 0.33 | 9.3023
W032 | R004 | Weather | Heavy Rain | Strong Wind | 1 | 6 | 122500 | 0.25 | 6.9768
W032 | R004 | Weather | High Waves | Lightning | 1 | 4 | 81666 | 0.17 | 4.6511
W032 | R004 | Weather | High Waves | Storm | 1 | 2 | 40833 | 0.08 | 2.3256
W032 | R004 | Weather | Lightning | High Waves | 1 | 4 | 81666 | 0.17 | 4.6511
W032 | R004 | Weather | Lightning | Strong Wind | 1 | 18 | 367500 | 0.75 | 20.9303
W033 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.6667
W033 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 4 | 76666 | 0.17 | 4.4444
W033 | R002 | Logistics | Delayed Helicopter | Material Shortage | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 4 | 76666 | 0.17 | 4.4444
W033 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 2 | 38333 | 0.08 | 2.2222
W033 | R002 | Mechanical | Generator Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 6.6667
W033 | R002 | Mechanical | Generator Failure | Equipment Wear | 1 | 4 | 76666 | 0.17 | 4.4444
W033 | R002 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 2 | 38333 | 0.08 | 2.2222
W033 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Weather | Heavy Rain | Storm | 1 | 2 | 38333 | 0.08 | 2.2222
W033 | R002 | Weather | High Waves | High Waves | 1 | 2 | 38333 | 0.08 | 2.2222
W033 | R002 | Weather | Lightning | High Waves | 1 | 2 | 38333 | 0.08 | 2.2222
W033 | R002 | Weather | Poor Visibility | High Waves | 1 | 4 | 76666 | 0.17 | 4.4444
W033 | R002 | Weather | Poor Visibility | Lightning | 1 | 8 | 153333 | 0.33 | 8.8889
W033 | R002 | Weather | Strong Wind | High Waves | 1 | 8 | 153333 | 0.33 | 8.8889
W034 | R001 | Drilling | Bit Failure | Formation Instability | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Drilling | Fishing Operation | Formation Instability | 1 | 18 | 356250 | 0.75 | 24.3244
W034 | R001 | Drilling | Hole Cleaning | Bit Wear | 1 | 2 | 39583 | 0.08 | 2.7027
W034 | R001 | Logistics | Waiting on Boat | Material Shortage | 1 | 2 | 39583 | 0.08 | 2.7027
W034 | R001 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 24.3244
W034 | R001 | Mechanical | Rotary Table Failure | Equipment Wear | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 2 | 39583 | 0.08 | 2.7027
W034 | R001 | Weather | High Waves | Lightning | 1 | 8 | 158333 | 0.33 | 10.8108
W034 | R001 | Weather | Poor Visibility | Storm | 1 | 4 | 79166 | 0.17 | 5.4054
W035 | R003 | Drilling | Bit Failure | Differential Sticking | 3 | 24 | 480000 | 1 | 26.087
W035 | R003 | Drilling | Fishing Operation | Bit Wear | 1 | 2 | 40000 | 0.08 | 2.1739
W035 | R003 | Drilling | Stuck Pipe | Differential Sticking | 1 | 18 | 360000 | 0.75 | 19.5652
W035 | R003 | Drilling | Well Control | Differential Sticking | 1 | 2 | 40000 | 0.08 | 2.1739
W035 | R003 | Drilling | Well Control | Unexpected Pressure | 1 | 2 | 40000 | 0.08 | 2.1739
W035 | R003 | Logistics | Waiting on Cement | Customs Clearance | 1 | 2 | 40000 | 0.08 | 2.1739
W035 | R003 | Weather | High Waves | Heavy Rain | 1 | 6 | 120000 | 0.25 | 6.5217
W035 | R003 | Weather | High Waves | Strong Wind | 2 | 24 | 480000 | 1 | 26.087
W035 | R003 | Weather | Strong Wind | Heavy Rain | 1 | 12 | 240000 | 0.5 | 13.0435
W036 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 6 | 115000 | 0.25 | 5.5556
W036 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 115000 | 0.25 | 5.5556
W036 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 6 | 115000 | 0.25 | 5.5556
W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | 2 | 8 | 153333 | 0.33 | 7.4074
W036 | R002 | Drilling | Well Control | Formation Instability | 1 | 6 | 115000 | 0.25 | 5.5556
W036 | R002 | Logistics | Delayed Helicopter | Port Congestion | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 2 | 38333 | 0.08 | 1.8518
W036 | R002 | Logistics | Waiting on Boat | Customs Clearance | 1 | 2 | 38333 | 0.08 | 1.8518
W036 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 18 | 345000 | 0.75 | 16.6667
W036 | R002 | Mechanical | Draw Works Failure | OEM Defect | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Mechanical | Generator Failure | OEM Defect | 1 | 4 | 76666 | 0.17 | 3.7037
W036 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 2 | 38333 | 0.08 | 1.8518
W036 | R002 | Mechanical | Power System Failure | Equipment Wear | 1 | 18 | 345000 | 0.75 | 16.6667
W036 | R002 | Weather | Strong Wind | Lightning | 1 | 6 | 115000 | 0.25 | 5.5556
W037 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 11.1111
W037 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 5.5555
W037 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 12 | 230000 | 0.5 | 16.6667
W037 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 5.5555
W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 24 | 460000 | 1 | 33.3334
W037 | R002 | Mechanical | Generator Failure | Equipment Wear | 1 | 4 | 76666 | 0.17 | 5.5555
W037 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 4 | 76666 | 0.17 | 5.5555
W037 | R002 | Weather | Poor Visibility | Lightning | 1 | 4 | 76666 | 0.17 | 5.5555
W037 | R002 | Weather | Poor Visibility | Strong Wind | 1 | 8 | 153333 | 0.33 | 11.1111
W038 | R004 | Drilling | Hole Cleaning | Formation Instability | 1 | 4 | 81666 | 0.17 | 5.8823
W038 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 5.8823
W038 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 11.7647
W038 | R004 | Drilling | Well Control | Formation Instability | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Logistics | Delayed Helicopter | Port Congestion | 1 | 2 | 40833 | 0.08 | 2.9412
W038 | R004 | Logistics | Waiting on Materials | Port Congestion | 1 | 2 | 40833 | 0.08 | 2.9412
W038 | R004 | Mechanical | BOP Repair | Electrical Failure | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 5.8823
W038 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 8 | 163333 | 0.33 | 11.7647
W038 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Weather | Heavy Rain | Lightning | 1 | 4 | 81666 | 0.17 | 5.8823
W038 | R004 | Weather | High Waves | Heavy Rain | 1 | 2 | 40833 | 0.08 | 2.9412
W038 | R004 | Weather | High Waves | Storm | 1 | 4 | 81666 | 0.17 | 5.8823
W038 | R004 | Weather | Lightning | Lightning | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Weather | Poor Visibility | Lightning | 1 | 2 | 40833 | 0.08 | 2.9412
W039 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 4 | 76666 | 0.17 | 5.7143
W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 10 | 191666 | 0.42 | 14.2857
W039 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 2 | 38333 | 0.08 | 2.8571
W039 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 4 | 76666 | 0.17 | 5.7143
W039 | R002 | Logistics | Waiting on Materials | Port Congestion | 1 | 6 | 115000 | 0.25 | 8.5715
W039 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 8.5715
W039 | R002 | Personnel | Safety Stand Down | Crew Rotation | 1 | 2 | 38333 | 0.08 | 2.8571
W039 | R002 | Weather | Heavy Rain | Heavy Rain | 1 | 12 | 230000 | 0.5 | 17.1429
W039 | R002 | Weather | Heavy Rain | Lightning | 1 | 2 | 38333 | 0.08 | 2.8571
W039 | R002 | Weather | Lightning | Heavy Rain | 1 | 12 | 230000 | 0.5 | 17.1429
W039 | R002 | Weather | Lightning | Strong Wind | 1 | 6 | 115000 | 0.25 | 8.5715
W039 | R002 | Weather | Poor Visibility | Lightning | 1 | 4 | 76666 | 0.17 | 5.7143
W040 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 8 | 153333 | 0.33 | 6.1538
W040 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 3.0769
W040 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 12 | 230000 | 0.5 | 9.2308
W040 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 4 | 76666 | 0.17 | 3.0769
W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 10 | 191666 | 0.42 | 7.6923
W040 | R002 | Drilling | Well Control | Formation Instability | 2 | 6 | 114999 | 0.25 | 4.6154
W040 | R002 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 8 | 153333 | 0.33 | 6.1538
W040 | R002 | Logistics | Waiting on Cement | Port Congestion | 1 | 6 | 115000 | 0.25 | 4.6154
W040 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 4 | 76666 | 0.17 | 3.0769
W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 18 | 345000 | 0.75 | 13.8462
W040 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 2 | 38333 | 0.08 | 1.5385
W040 | R002 | Mechanical | Power System Failure | Equipment Wear | 1 | 2 | 38333 | 0.08 | 1.5385
W040 | R002 | Personnel | Crew Change | Medical Emergency | 1 | 4 | 76666 | 0.17 | 3.0769
W040 | R002 | Weather | Heavy Rain | High Waves | 1 | 6 | 115000 | 0.25 | 4.6154
W040 | R002 | Weather | Heavy Rain | Strong Wind | 1 | 8 | 153333 | 0.33 | 6.1538
W040 | R002 | Weather | High Waves | Heavy Rain | 1 | 6 | 115000 | 0.25 | 4.6154
W040 | R002 | Weather | High Waves | Lightning | 1 | 4 | 76666 | 0.17 | 3.0769
W040 | R002 | Weather | Poor Visibility | Heavy Rain | 2 | 18 | 345000 | 0.75 | 13.8462
W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | 2 | 10 | 191666 | 0.41 | 13.1579
W041 | R002 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 153333 | 0.33 | 10.5263
W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 345000 | 0.75 | 23.6843
W041 | R002 | Drilling | Hole Cleaning | Formation Instability | 2 | 4 | 76666 | 0.16 | 5.2631
W041 | R002 | Drilling | Well Control | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 5.2631
W041 | R002 | Logistics | Delayed Helicopter | Port Congestion | 1 | 2 | 38333 | 0.08 | 2.6316
W041 | R002 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 8 | 153333 | 0.33 | 10.5263
W041 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 7.8948
W041 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 4 | 76666 | 0.17 | 5.2631
W041 | R002 | Weather | Heavy Rain | High Waves | 1 | 2 | 38333 | 0.08 | 2.6316
W041 | R002 | Weather | Lightning | Lightning | 2 | 10 | 191666 | 0.41 | 13.1579
W042 | R004 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 163333 | 0.33 | 15.3846
W042 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 4 | 81666 | 0.17 | 7.6923
W042 | R004 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 2 | 40833 | 0.08 | 3.8461
W042 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 6 | 122500 | 0.25 | 11.5385
W042 | R004 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 6 | 122500 | 0.25 | 11.5385
W042 | R004 | Weather | Lightning | Lightning | 1 | 6 | 122500 | 0.25 | 11.5385
W042 | R004 | Weather | Lightning | Strong Wind | 1 | 2 | 40833 | 0.08 | 3.8461
W042 | R004 | Weather | Poor Visibility | Heavy Rain | 1 | 18 | 367500 | 0.75 | 34.6154
W043 | R002 | Drilling | Fishing Operation | Bit Wear | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 8.5106
W043 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 6 | 115000 | 0.25 | 6.383
W043 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.383
W043 | R002 | Drilling | Well Control | Unexpected Pressure | 2 | 6 | 114999 | 0.25 | 6.3829
W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | 2 | 18 | 345000 | 0.75 | 19.149
W043 | R002 | Logistics | Waiting on Materials | Customs Clearance | 1 | 4 | 76666 | 0.17 | 4.2553
W043 | R002 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 6.383
W043 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 18 | 345000 | 0.75 | 19.149
W043 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Personnel | Crew Change | Medical Emergency | 1 | 2 | 38333 | 0.08 | 2.1276
W043 | R002 | Weather | Lightning | Heavy Rain | 1 | 4 | 76666 | 0.17 | 4.2553
W043 | R002 | Weather | Poor Visibility | Lightning | 1 | 6 | 115000 | 0.25 | 6.383
W044 | R003 | Drilling | Bit Failure | Formation Instability | 1 | 2 | 40000 | 0.08 | 3.125
W044 | R003 | Drilling | Hole Cleaning | Formation Instability | 1 | 6 | 120000 | 0.25 | 9.375
W044 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 12.5
W044 | R003 | Drilling | Well Control | Bit Wear | 1 | 4 | 80000 | 0.17 | 6.25
W044 | R003 | Logistics | Delayed Helicopter | Late Supply Vessel | 1 | 2 | 40000 | 0.08 | 3.125
W044 | R003 | Logistics | Delayed Helicopter | Port Congestion | 1 | 2 | 40000 | 0.08 | 3.125
W044 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 2 | 40000 | 0.08 | 3.125
W044 | R003 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 4 | 80000 | 0.17 | 6.25
W044 | R003 | Weather | High Waves | Lightning | 1 | 8 | 160000 | 0.33 | 12.5
W044 | R003 | Weather | Poor Visibility | Heavy Rain | 1 | 18 | 360000 | 0.75 | 28.125
W044 | R003 | Weather | Poor Visibility | Strong Wind | 1 | 6 | 120000 | 0.25 | 9.375
W044 | R003 | Weather | Strong Wind | Storm | 1 | 2 | 40000 | 0.08 | 3.125
W045 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 10
W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 24 | 490000 | 1 | 30
W045 | R004 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 2 | 40833 | 0.08 | 2.5
W045 | R004 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 122500 | 0.25 | 7.5
W045 | R004 | Mechanical | BOP Repair | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 5
W045 | R004 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 2 | 40833 | 0.08 | 2.5
W045 | R004 | Weather | Heavy Rain | Heavy Rain | 2 | 14 | 285833 | 0.58 | 17.5
W045 | R004 | Weather | Lightning | Lightning | 1 | 2 | 40833 | 0.08 | 2.5
W045 | R004 | Weather | Poor Visibility | Strong Wind | 1 | 18 | 367500 | 0.75 | 22.5
W046 | R003 | Drilling | Bit Failure | Differential Sticking | 1 | 2 | 40000 | 0.08 | 1.9608
W046 | R003 | Drilling | Fishing Operation | Bit Wear | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Drilling | Hole Cleaning | Bit Wear | 1 | 4 | 80000 | 0.17 | 3.9216
W046 | R003 | Drilling | Stuck Pipe | Formation Instability | 1 | 4 | 80000 | 0.17 | 3.9216
W046 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 4 | 80000 | 0.17 | 3.9216
W046 | R003 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 6 | 120000 | 0.25 | 5.8824
W046 | R003 | Logistics | Waiting on Materials | Port Congestion | 1 | 12 | 240000 | 0.5 | 11.7647
W046 | R003 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Mechanical | Top Drive Failure | OEM Defect | 1 | 6 | 120000 | 0.25 | 5.8824
W046 | R003 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 4 | 80000 | 0.17 | 3.9216
W046 | R003 | Weather | Heavy Rain | Heavy Rain | 1 | 12 | 240000 | 0.5 | 11.7647
W046 | R003 | Weather | Poor Visibility | Heavy Rain | 1 | 6 | 120000 | 0.25 | 5.8824
W046 | R003 | Weather | Poor Visibility | Strong Wind | 1 | 4 | 80000 | 0.17 | 3.9216
W046 | R003 | Weather | Strong Wind | Strong Wind | 1 | 6 | 120000 | 0.25 | 5.8824
W047 | R004 | Drilling | Bit Failure | Bit Wear | 1 | 2 | 40833 | 0.08 | 2.5641
W047 | R004 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 5.1282
W047 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 2 | 40833 | 0.08 | 2.5641
W047 | R004 | Drilling | Well Control | Bit Wear | 1 | 6 | 122500 | 0.25 | 7.6923
W047 | R004 | Mechanical | BOP Repair | OEM Defect | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 5.1282
W047 | R004 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 4 | 81666 | 0.17 | 5.1282
W047 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Personnel | Crew Change | Crew Rotation | 1 | 18 | 367500 | 0.75 | 23.077
W047 | R004 | Weather | Heavy Rain | Lightning | 1 | 4 | 81666 | 0.17 | 5.1282
W047 | R004 | Weather | Strong Wind | Storm | 1 | 2 | 40833 | 0.08 | 2.5641
W048 | R002 | Drilling | Hole Cleaning | Bit Wear | 1 | 8 | 153333 | 0.33 | 9.3023
W048 | R002 | Drilling | Lost Circulation | Bit Wear | 1 | 6 | 115000 | 0.25 | 6.9768
W048 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 6 | 115000 | 0.25 | 6.9768
W048 | R002 | Drilling | Well Control | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 4.6511
W048 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 4 | 76666 | 0.17 | 4.6511
W048 | R002 | Mechanical | Mud Pump Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 6.9768
W048 | R002 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 18 | 345000 | 0.75 | 20.9303
W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 3 | 18 | 344999 | 0.74 | 20.9302
W048 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 4 | 76666 | 0.17 | 4.6511
W048 | R002 | Personnel | Safety Stand Down | Crew Rotation | 1 | 2 | 38333 | 0.08 | 2.3256
W048 | R002 | Weather | High Waves | High Waves | 1 | 6 | 115000 | 0.25 | 6.9768
W048 | R002 | Weather | Poor Visibility | Lightning | 1 | 4 | 76666 | 0.17 | 4.6511
W049 | R003 | Drilling | Fishing Operation | Bit Wear | 1 | 6 | 120000 | 0.25 | 10
W049 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 13.3333
W049 | R003 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 360000 | 0.75 | 30
W049 | R003 | Drilling | Well Control | Bit Wear | 1 | 2 | 40000 | 0.08 | 3.3333
W049 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 6 | 120000 | 0.25 | 10
W049 | R003 | Logistics | Waiting on Boat | Customs Clearance | 1 | 4 | 80000 | 0.17 | 6.6667
W049 | R003 | Logistics | Waiting on Boat | Port Congestion | 1 | 4 | 80000 | 0.17 | 6.6667
W049 | R003 | Mechanical | Top Drive Failure | OEM Defect | 1 | 6 | 120000 | 0.25 | 10
W049 | R003 | Weather | Heavy Rain | Strong Wind | 1 | 6 | 120000 | 0.25 | 10
W050 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 8 | 163333 | 0.33 | 10.8108
W050 | R004 | Drilling | Stuck Pipe | Differential Sticking | 1 | 12 | 245000 | 0.5 | 16.2162
W050 | R004 | Drilling | Stuck Pipe | Formation Instability | 1 | 8 | 163333 | 0.33 | 10.8108
W050 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 4 | 81666 | 0.17 | 5.4054
W050 | R004 | Logistics | Waiting on Cement | Material Shortage | 1 | 6 | 122500 | 0.25 | 8.1081
W050 | R004 | Logistics | Waiting on Cement | Port Congestion | 1 | 12 | 245000 | 0.5 | 16.2162
W050 | R004 | Mechanical | Power System Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 8.1081
W050 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 2 | 40833 | 0.08 | 2.7027
W050 | R004 | Personnel | Medical Evacuation | Training Requirement | 1 | 6 | 122500 | 0.25 | 8.1081
W050 | R004 | Weather | High Waves | High Waves | 1 | 6 | 122500 | 0.25 | 8.1081
W050 | R004 | Weather | High Waves | Storm | 1 | 4 | 81666 | 0.17 | 5.4054

## Top_Well_Root_Causes
Well_ID | Rig_ID | NPT_Category | NPT_Subcategory | Root_Cause | Events | NPT_Hours | NPT_Cost_USD | Lost_Days | Cost_Share_pct
W001 | R004 | Weather | High Waves | Storm | 1 | 12 | 245000 | 0.5 | 13.6364
W001 | R004 | Weather | High Waves | Strong Wind | 1 | 8 | 163333 | 0.33 | 9.0909
W001 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 1 | 6 | 122500 | 0.25 | 6.8182
W001 | R004 | Mechanical | Top Drive Failure | OEM Defect | 1 | 6 | 122500 | 0.25 | 6.8182
W002 | R001 | Mechanical | Generator Failure | Equipment Wear | 2 | 20 | 395833 | 0.83 | 22.7273
W002 | R001 | Drilling | Bit Failure | Bit Wear | 2 | 12 | 237500 | 0.5 | 13.6364
W002 | R001 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 12 | 237500 | 0.5 | 13.6364
W002 | R001 | Drilling | Hole Cleaning | Bit Wear | 1 | 8 | 158333 | 0.33 | 9.0909
W002 | R001 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 8 | 158333 | 0.33 | 9.0909
W003 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 2 | 30 | 612500 | 1.25 | 34.091
W003 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 367500 | 0.75 | 20.4546
W003 | R004 | Mechanical | BOP Repair | Electrical Failure | 1 | 6 | 122500 | 0.25 | 6.8182
W003 | R004 | Mechanical | Power System Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 6.8182
W003 | R004 | Personnel | Safety Stand Down | Training Requirement | 1 | 6 | 122500 | 0.25 | 6.8182
W004 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 12 | 230000 | 0.5 | 23.077
W004 | R002 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 12 | 230000 | 0.5 | 23.077
W004 | R002 | Weather | Lightning | Lightning | 2 | 8 | 153333 | 0.33 | 15.3846
W004 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 4 | 76666 | 0.17 | 7.6923
W004 | R002 | Weather | Heavy Rain | Heavy Rain | 1 | 4 | 76666 | 0.17 | 7.6923
W005 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 8 | 153333 | 0.33 | 12.5
W005 | R002 | Personnel | Medical Evacuation | Training Requirement | 1 | 8 | 153333 | 0.33 | 12.5
W005 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 6 | 115000 | 0.25 | 9.375
W005 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 115000 | 0.25 | 9.375
W005 | R002 | Weather | Heavy Rain | Storm | 1 | 6 | 115000 | 0.25 | 9.375
W006 | R002 | Drilling | Bit Failure | Bit Wear | 1 | 18 | 345000 | 0.75 | 21.4287
W006 | R002 | Logistics | Waiting on Cement | Customs Clearance | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 9.5238
W006 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 7.1429
W007 | R001 | Drilling | Well Control | Bit Wear | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 14.0625
W007 | R001 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 158333 | 0.33 | 6.25
W008 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 20.0001
W008 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 6 | 115000 | 0.25 | 15.0001
W008 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 6 | 115000 | 0.25 | 15.0001
W008 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 4 | 76666 | 0.17 | 10
W008 | R002 | Mechanical | BOP Repair | OEM Defect | 1 | 4 | 76666 | 0.17 | 10
W009 | R001 | Drilling | Lost Circulation | Formation Instability | 1 | 24 | 475000 | 1 | 24
W009 | R001 | Logistics | Waiting on Cement | Customs Clearance | 1 | 12 | 237500 | 0.5 | 12
W009 | R001 | Weather | Heavy Rain | High Waves | 1 | 8 | 158333 | 0.33 | 8
W009 | R001 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 118750 | 0.25 | 6
W009 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 6 | 118750 | 0.25 | 6
W010 | R002 | Weather | Heavy Rain | Strong Wind | 1 | 24 | 460000 | 1 | 22.6416
W010 | R002 | Weather | Lightning | Heavy Rain | 2 | 20 | 383333 | 0.83 | 18.868
W010 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 8 | 153333 | 0.33 | 7.5472
W010 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 7.5472
W010 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 7.5472
W011 | R004 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 24 | 490000 | 1 | 23.077
W011 | R004 | Drilling | Bit Failure | Bit Wear | 1 | 12 | 245000 | 0.5 | 11.5385
W011 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 12 | 245000 | 0.5 | 11.5385
W011 | R004 | Weather | Lightning | Lightning | 2 | 10 | 204166 | 0.42 | 9.6154
W011 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 163333 | 0.33 | 7.6923
W012 | R004 | Drilling | Bit Failure | Unexpected Pressure | 1 | 18 | 367500 | 0.75 | 28.1251
W012 | R004 | Logistics | Waiting on Boat | Late Supply Vessel | 1 | 12 | 245000 | 0.5 | 18.75
W012 | R004 | Logistics | Waiting on Boat | Port Congestion | 1 | 6 | 122500 | 0.25 | 9.375
W012 | R004 | Mechanical | Power System Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 9.375
W012 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 9.375
W013 | R003 | Drilling | Lost Circulation | Formation Instability | 2 | 18 | 360000 | 0.75 | 18.75
W013 | R003 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 160000 | 0.33 | 8.3333
W013 | R003 | Personnel | Safety Stand Down | Crew Rotation | 1 | 8 | 160000 | 0.33 | 8.3333
W013 | R003 | Weather | Strong Wind | Storm | 1 | 8 | 160000 | 0.33 | 8.3333
W013 | R003 | Drilling | Hole Cleaning | Differential Sticking | 1 | 6 | 120000 | 0.25 | 6.25
W014 | R004 | Drilling | Stuck Pipe | Bit Wear | 1 | 12 | 245000 | 0.5 | 31.5791
W014 | R004 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 15.7895
W014 | R004 | Logistics | Waiting on Cement | Port Congestion | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 10.5263
W014 | R004 | Mechanical | Power System Failure | Electrical Failure | 1 | 4 | 81666 | 0.17 | 10.5263
W015 | R003 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 18 | 360000 | 0.75 | 23.6842
W015 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 10.5263
W015 | R003 | Mechanical | Generator Failure | Equipment Wear | 1 | 8 | 160000 | 0.33 | 10.5263
W015 | R003 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 6 | 120000 | 0.25 | 7.8947
W015 | R003 | Logistics | Waiting on Cement | Customs Clearance | 1 | 6 | 120000 | 0.25 | 7.8947
W016 | R004 | Mechanical | Generator Failure | Hydraulic Failure | 1 | 8 | 163333 | 0.33 | 16
W016 | R004 | Weather | Strong Wind | Strong Wind | 1 | 8 | 163333 | 0.33 | 16
W016 | R004 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 122500 | 0.25 | 12
W016 | R004 | Mechanical | Top Drive Failure | Electrical Failure | 1 | 6 | 122500 | 0.25 | 12
W016 | R004 | Weather | Lightning | Strong Wind | 1 | 6 | 122500 | 0.25 | 12
W017 | R001 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 8 | 158333 | 0.33 | 14.8148
W017 | R001 | Drilling | Bit Failure | Formation Instability | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Mechanical | Draw Works Failure | OEM Defect | 1 | 6 | 118750 | 0.25 | 11.1111
W017 | R001 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 6 | 118750 | 0.25 | 11.1111
W018 | R004 | Logistics | Fuel Supply Delay | Port Congestion | 1 | 24 | 490000 | 1 | 27.2728
W018 | R004 | Drilling | Stuck Pipe | Formation Instability | 1 | 12 | 245000 | 0.5 | 13.6364
W018 | R004 | Weather | Poor Visibility | Storm | 2 | 12 | 245000 | 0.5 | 13.6364
W018 | R004 | Drilling | Hole Cleaning | Unexpected Pressure | 1 | 8 | 163333 | 0.33 | 9.0909
W018 | R004 | Mechanical | Top Drive Failure | Equipment Wear | 1 | 6 | 122500 | 0.25 | 6.8182
W019 | R003 | Weather | Lightning | High Waves | 1 | 24 | 480000 | 1 | 21.0526
W019 | R003 | Drilling | Well Control | Bit Wear | 1 | 18 | 360000 | 0.75 | 15.7895
W019 | R003 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 16 | 320000 | 0.67 | 14.0351
W019 | R003 | Logistics | Waiting on Cement | Late Supply Vessel | 1 | 12 | 240000 | 0.5 | 10.5263
W019 | R003 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 12 | 240000 | 0.5 | 10.5263
W020 | R003 | Mechanical | BOP Repair | Electrical Failure | 1 | 18 | 360000 | 0.75 | 20
W020 | R003 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 2 | 12 | 240000 | 0.5 | 13.3333
W020 | R003 | Weather | High Waves | Heavy Rain | 1 | 8 | 160000 | 0.33 | 8.8889
W020 | R003 | Drilling | Fishing Operation | Differential Sticking | 1 | 6 | 120000 | 0.25 | 6.6667
W020 | R003 | Drilling | Lost Circulation | Bit Wear | 1 | 6 | 120000 | 0.25 | 6.6667
W021 | R002 | Logistics | Waiting on Cement | Port Congestion | 1 | 18 | 345000 | 0.75 | 19.149
W021 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 12 | 230000 | 0.5 | 12.766
W021 | R002 | Logistics | Waiting on Cement | Late Supply Vessel | 2 | 8 | 153333 | 0.33 | 8.5106
W021 | R002 | Logistics | Waiting on Materials | Port Congestion | 1 | 8 | 153333 | 0.33 | 8.5106
W021 | R002 | Drilling | Lost Circulation | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.383
W022 | R001 | Drilling | Hole Cleaning | Bit Wear | 2 | 18 | 356250 | 0.75 | 24.3244
W022 | R001 | Weather | Poor Visibility | Strong Wind | 2 | 14 | 277083 | 0.58 | 18.9189
W022 | R001 | Logistics | Waiting on Materials | Port Congestion | 1 | 8 | 158333 | 0.33 | 10.8108
W022 | R001 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 158333 | 0.33 | 10.8108
W022 | R001 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 118750 | 0.25 | 8.1081
W023 | R004 | Personnel | Crew Change | Medical Emergency | 1 | 18 | 367500 | 0.75 | 21.4286
W023 | R004 | Weather | Lightning | Storm | 1 | 12 | 245000 | 0.5 | 14.2858
W023 | R004 | Mechanical | Mud Pump Failure | Equipment Wear | 1 | 8 | 163333 | 0.33 | 9.5238
W023 | R004 | Drilling | Well Control | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 7.1429
W023 | R004 | Logistics | Waiting on Boat | Port Congestion | 1 | 6 | 122500 | 0.25 | 7.1429
W024 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 16 | 306666 | 0.67 | 23.5294
W024 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 12 | 230000 | 0.5 | 17.6471
W024 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.7647
W024 | R002 | Mechanical | Power System Failure | OEM Defect | 1 | 8 | 153333 | 0.33 | 11.7647
W024 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 115000 | 0.25 | 8.8236
W025 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 12 | 245000 | 0.5 | 22.2223
W025 | R004 | Drilling | Bit Failure | Differential Sticking | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Drilling | Stuck Pipe | Bit Wear | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 6 | 122500 | 0.25 | 11.1111
W025 | R004 | Weather | High Waves | Strong Wind | 1 | 6 | 122500 | 0.25 | 11.1111
W026 | R004 | Weather | Heavy Rain | Storm | 1 | 24 | 490000 | 1 | 26.6667
W026 | R004 | Personnel | Safety Stand Down | Medical Emergency | 1 | 18 | 367500 | 0.75 | 20
W026 | R004 | Weather | High Waves | Strong Wind | 1 | 12 | 245000 | 0.5 | 13.3334
W026 | R004 | Drilling | Bit Failure | Bit Wear | 1 | 8 | 163333 | 0.33 | 8.8889
W026 | R004 | Mechanical | Draw Works Failure | Poor Preventive Maintenance | 1 | 8 | 163333 | 0.33 | 8.8889
W027 | R002 | Drilling | Fishing Operation | Differential Sticking | 1 | 18 | 345000 | 0.75 | 27.2728
W027 | R002 | Weather | Lightning | High Waves | 2 | 16 | 306666 | 0.67 | 24.2424
W027 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 8 | 153333 | 0.33 | 12.1212
W027 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 12.1212
W027 | R002 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 6 | 115000 | 0.25 | 9.0909
W028 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 18 | 345000 | 0.75 | 20.0001
W028 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 1 | 12 | 230000 | 0.5 | 13.3334
W028 | R002 | Mechanical | Power System Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W028 | R002 | Mechanical | Top Drive Failure | Poor Preventive Maintenance | 1 | 8 | 153333 | 0.33 | 8.8889
W028 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 6 | 115000 | 0.25 | 6.6667
W029 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 11.4286
W029 | R002 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 115000 | 0.25 | 8.5715
W029 | R002 | Personnel | Crew Change | Medical Emergency | 1 | 6 | 115000 | 0.25 | 8.5715
W030 | R002 | Mechanical | Power System Failure | Electrical Failure | 1 | 12 | 230000 | 0.5 | 13.3334
W030 | R002 | Weather | High Waves | High Waves | 1 | 12 | 230000 | 0.5 | 13.3334
W030 | R002 | Mechanical | BOP Repair | Electrical Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Mechanical | BOP Repair | Hydraulic Failure | 1 | 8 | 153333 | 0.33 | 8.8889
W030 | R002 | Mechanical | Power System Failure | Equipment Wear | 1 | 8 | 153333 | 0.33 | 8.8889
W031 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 24 | 460000 | 1 | 40.0002
W031 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 4 | 76666 | 0.17 | 6.6666
W031 | R002 | Logistics | Waiting on Materials | Customs Clearance | 1 | 4 | 76666 | 0.17 | 6.6666
W032 | R004 | Weather | Lightning | Strong Wind | 1 | 18 | 367500 | 0.75 | 20.9303
W032 | R004 | Logistics | Fuel Supply Delay | Material Shortage | 2 | 12 | 245000 | 0.5 | 13.9535
W032 | R004 | Mechanical | Draw Works Failure | Electrical Failure | 1 | 8 | 163333 | 0.33 | 9.3023
W032 | R004 | Mechanical | Draw Works Failure | Equipment Wear | 1 | 8 | 163333 | 0.33 | 9.3023
W032 | R004 | Weather | Heavy Rain | Lightning | 1 | 8 | 163333 | 0.33 | 9.3023
W033 | R002 | Logistics | Delayed Helicopter | Material Shortage | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Mechanical | BOP Repair | Equipment Wear | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 12 | 230000 | 0.5 | 13.3334
W033 | R002 | Weather | Poor Visibility | Lightning | 1 | 8 | 153333 | 0.33 | 8.8889
W033 | R002 | Weather | Strong Wind | High Waves | 1 | 8 | 153333 | 0.33 | 8.8889
W034 | R001 | Drilling | Fishing Operation | Formation Instability | 1 | 18 | 356250 | 0.75 | 24.3244
W034 | R001 | Mechanical | Mud Pump Failure | Poor Preventive Maintenance | 1 | 18 | 356250 | 0.75 | 24.3244
W034 | R001 | Weather | High Waves | Lightning | 1 | 8 | 158333 | 0.33 | 10.8108
W034 | R001 | Drilling | Bit Failure | Formation Instability | 1 | 4 | 79166 | 0.17 | 5.4054
W034 | R001 | Logistics | Waiting on Materials | Late Supply Vessel | 1 | 4 | 79166 | 0.17 | 5.4054
W035 | R003 | Drilling | Bit Failure | Differential Sticking | 3 | 24 | 480000 | 1 | 26.087
W035 | R003 | Weather | High Waves | Strong Wind | 2 | 24 | 480000 | 1 | 26.087
W035 | R003 | Drilling | Stuck Pipe | Differential Sticking | 1 | 18 | 360000 | 0.75 | 19.5652
W035 | R003 | Weather | Strong Wind | Heavy Rain | 1 | 12 | 240000 | 0.5 | 13.0435
W035 | R003 | Weather | High Waves | Heavy Rain | 1 | 6 | 120000 | 0.25 | 6.5217
W036 | R002 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 18 | 345000 | 0.75 | 16.6667
W036 | R002 | Mechanical | Power System Failure | Equipment Wear | 1 | 18 | 345000 | 0.75 | 16.6667
W036 | R002 | Drilling | Stuck Pipe | Differential Sticking | 2 | 8 | 153333 | 0.33 | 7.4074
W036 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 6 | 115000 | 0.25 | 5.5556
W036 | R002 | Drilling | Lost Circulation | Differential Sticking | 1 | 6 | 115000 | 0.25 | 5.5556
W037 | R002 | Logistics | Delayed Helicopter | Customs Clearance | 1 | 24 | 460000 | 1 | 33.3334
W037 | R002 | Drilling | Stuck Pipe | Bit Wear | 1 | 12 | 230000 | 0.5 | 16.6667
W037 | R002 | Drilling | Bit Failure | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 11.1111
W037 | R002 | Weather | Poor Visibility | Strong Wind | 1 | 8 | 153333 | 0.33 | 11.1111
W037 | R002 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 4 | 76666 | 0.17 | 5.5555
W038 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 11.7647
W038 | R004 | Mechanical | Rotary Table Failure | Electrical Failure | 1 | 8 | 163333 | 0.33 | 11.7647
W038 | R004 | Drilling | Well Control | Formation Instability | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Mechanical | BOP Repair | Electrical Failure | 1 | 6 | 122500 | 0.25 | 8.8236
W038 | R004 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 6 | 122500 | 0.25 | 8.8236
W039 | R002 | Weather | Heavy Rain | Heavy Rain | 1 | 12 | 230000 | 0.5 | 17.1429
W039 | R002 | Weather | Lightning | Heavy Rain | 1 | 12 | 230000 | 0.5 | 17.1429
W039 | R002 | Drilling | Hole Cleaning | Unexpected Pressure | 2 | 10 | 191666 | 0.42 | 14.2857
W039 | R002 | Logistics | Waiting on Materials | Port Congestion | 1 | 6 | 115000 | 0.25 | 8.5715
W039 | R002 | Mechanical | Mud Pump Failure | Hydraulic Failure | 1 | 6 | 115000 | 0.25 | 8.5715
W040 | R002 | Mechanical | Generator Failure | Poor Preventive Maintenance | 1 | 18 | 345000 | 0.75 | 13.8462
W040 | R002 | Weather | Poor Visibility | Heavy Rain | 2 | 18 | 345000 | 0.75 | 13.8462
W040 | R002 | Drilling | Fishing Operation | Formation Instability | 1 | 12 | 230000 | 0.5 | 9.2308
W040 | R002 | Drilling | Stuck Pipe | Unexpected Pressure | 2 | 10 | 191666 | 0.42 | 7.6923
W040 | R002 | Drilling | Bit Failure | Differential Sticking | 1 | 8 | 153333 | 0.33 | 6.1538
W041 | R002 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 345000 | 0.75 | 23.6843
W041 | R002 | Drilling | Bit Failure | Unexpected Pressure | 2 | 10 | 191666 | 0.41 | 13.1579
W041 | R002 | Weather | Lightning | Lightning | 2 | 10 | 191666 | 0.41 | 13.1579
W041 | R002 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 153333 | 0.33 | 10.5263
W041 | R002 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 8 | 153333 | 0.33 | 10.5263
W042 | R004 | Weather | Poor Visibility | Heavy Rain | 1 | 18 | 367500 | 0.75 | 34.6154
W042 | R004 | Drilling | Fishing Operation | Differential Sticking | 1 | 8 | 163333 | 0.33 | 15.3846
W042 | R004 | Mechanical | Rotary Table Failure | Poor Preventive Maintenance | 1 | 6 | 122500 | 0.25 | 11.5385
W042 | R004 | Mechanical | Top Drive Failure | Hydraulic Failure | 1 | 6 | 122500 | 0.25 | 11.5385
W042 | R004 | Weather | Lightning | Lightning | 1 | 6 | 122500 | 0.25 | 11.5385
W043 | R002 | Logistics | Delayed Helicopter | Port Congestion | 2 | 18 | 345000 | 0.75 | 19.149
W043 | R002 | Mechanical | Mud Pump Failure | OEM Defect | 1 | 18 | 345000 | 0.75 | 19.149
W043 | R002 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 153333 | 0.33 | 8.5106
W043 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 6 | 115000 | 0.25 | 6.383
W043 | R002 | Drilling | Stuck Pipe | Formation Instability | 1 | 6 | 115000 | 0.25 | 6.383
W044 | R003 | Weather | Poor Visibility | Heavy Rain | 1 | 18 | 360000 | 0.75 | 28.125
W044 | R003 | Drilling | Lost Circulation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 12.5
W044 | R003 | Weather | High Waves | Lightning | 1 | 8 | 160000 | 0.33 | 12.5
W044 | R003 | Drilling | Hole Cleaning | Formation Instability | 1 | 6 | 120000 | 0.25 | 9.375
W044 | R003 | Weather | Poor Visibility | Strong Wind | 1 | 6 | 120000 | 0.25 | 9.375
W045 | R004 | Logistics | Fuel Supply Delay | Customs Clearance | 1 | 24 | 490000 | 1 | 30
W045 | R004 | Weather | Poor Visibility | Strong Wind | 1 | 18 | 367500 | 0.75 | 22.5
W045 | R004 | Weather | Heavy Rain | Heavy Rain | 2 | 14 | 285833 | 0.58 | 17.5
W045 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 10
W045 | R004 | Logistics | Waiting on Materials | Material Shortage | 1 | 6 | 122500 | 0.25 | 7.5
W046 | R003 | Logistics | Waiting on Materials | Port Congestion | 1 | 12 | 240000 | 0.5 | 11.7647
W046 | R003 | Weather | Heavy Rain | Heavy Rain | 1 | 12 | 240000 | 0.5 | 11.7647
W046 | R003 | Drilling | Fishing Operation | Bit Wear | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 7.8431
W046 | R003 | Mechanical | Draw Works Failure | Hydraulic Failure | 1 | 8 | 160000 | 0.33 | 7.8431
W047 | R004 | Personnel | Crew Change | Crew Rotation | 1 | 18 | 367500 | 0.75 | 23.077
W047 | R004 | Drilling | Hole Cleaning | Differential Sticking | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Drilling | Lost Circulation | Formation Instability | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Mechanical | BOP Repair | OEM Defect | 1 | 8 | 163333 | 0.33 | 10.2564
W047 | R004 | Mechanical | Power System Failure | Poor Preventive Maintenance | 1 | 8 | 163333 | 0.33 | 10.2564
W048 | R002 | Mechanical | Rotary Table Failure | Hydraulic Failure | 1 | 18 | 345000 | 0.75 | 20.9303
W048 | R002 | Mechanical | Top Drive Failure | Equipment Wear | 3 | 18 | 344999 | 0.74 | 20.9302
W048 | R002 | Drilling | Hole Cleaning | Bit Wear | 1 | 8 | 153333 | 0.33 | 9.3023
W048 | R002 | Drilling | Lost Circulation | Bit Wear | 1 | 6 | 115000 | 0.25 | 6.9768
W048 | R002 | Drilling | Stuck Pipe | Differential Sticking | 1 | 6 | 115000 | 0.25 | 6.9768
W049 | R003 | Drilling | Hole Cleaning | Differential Sticking | 1 | 18 | 360000 | 0.75 | 30
W049 | R003 | Drilling | Fishing Operation | Unexpected Pressure | 1 | 8 | 160000 | 0.33 | 13.3333
W049 | R003 | Drilling | Fishing Operation | Bit Wear | 1 | 6 | 120000 | 0.25 | 10
W049 | R003 | Logistics | Fuel Supply Delay | Late Supply Vessel | 1 | 6 | 120000 | 0.25 | 10
W049 | R003 | Mechanical | Top Drive Failure | OEM Defect | 1 | 6 | 120000 | 0.25 | 10
W050 | R004 | Drilling | Stuck Pipe | Differential Sticking | 1 | 12 | 245000 | 0.5 | 16.2162
W050 | R004 | Logistics | Waiting on Cement | Port Congestion | 1 | 12 | 245000 | 0.5 | 16.2162
W050 | R004 | Drilling | Lost Circulation | Bit Wear | 1 | 8 | 163333 | 0.33 | 10.8108
W050 | R004 | Drilling | Stuck Pipe | Formation Instability | 1 | 8 | 163333 | 0.33 | 10.8108
W050 | R004 | Logistics | Waiting on Cement | Material Shortage | 1 | 6 | 122500 | 0.25 | 8.1081

## Category_by_Rig
Rig_ID | NPT_Category | Events | NPT_Hours | NPT_Cost_USD | Cost_Share_pct
R001 | Drilling | 22 | 152 | 3008328 | 29.3436
R001 | Logistics | 12 | 84 | 1662497 | 16.2162
R001 | Mechanical | 23 | 172 | 3404161 | 33.2046
R001 | Personnel | 2 | 8 | 158333 | 1.5444
R001 | Weather | 21 | 102 | 2018743 | 19.6911
R002 | Drilling | 93 | 512 | 9813301 | 31.8012
R002 | Logistics | 37 | 222 | 4254988 | 13.7888
R002 | Mechanical | 75 | 480 | 9199977 | 29.8137
R002 | Personnel | 12 | 46 | 881662 | 2.8571
R002 | Weather | 65 | 350 | 6708313 | 21.7391
R003 | Drilling | 49 | 278 | 5560000 | 40.0576
R003 | Logistics | 23 | 122 | 2440000 | 17.5793
R003 | Mechanical | 19 | 108 | 2160000 | 15.562
R003 | Personnel | 4 | 14 | 280000 | 2.0173
R003 | Weather | 21 | 172 | 3440000 | 24.7839
R004 | Drilling | 49 | 310 | 6329151 | 26.1383
R004 | Logistics | 32 | 178 | 3634158 | 15.0084
R004 | Mechanical | 54 | 292 | 5961649 | 24.6206
R004 | Personnel | 10 | 88 | 1796665 | 7.4199
R004 | Weather | 54 | 318 | 6492482 | 26.8128

## Rig_Exposure_QA
Rig_ID | First_Date | Last_Date | Calendar_Days | Wells | Rig_Days | Date_Range_Days
R001 | 2023-01-21 | 2024-11-22 | 174 | 6 | 174 | 672
R002 | 2023-01-21 | 2025-01-01 | 442 | 20 | 442 | 712
R003 | 2023-06-16 | 2024-11-17 | 196 | 8 | 196 | 521
R004 | 2023-03-29 | 2025-01-05 | 318 | 16 | 318 | 649

## Well_Exposure_QA
Well_ID | Rig_ID | First_Date | Last_Date | Drilling_Days | Well_Days | Date_Range_Days
W001 | R004 | 2023-04-13 | 2023-05-08 | 26 | 26 | 26
W002 | R001 | 2024-03-11 | 2024-04-07 | 28 | 28 | 28
W003 | R004 | 2023-09-28 | 2023-10-25 | 28 | 28 | 28
W004 | R002 | 2023-04-17 | 2023-05-20 | 33 | 33 | 34
W005 | R002 | 2023-03-13 | 2023-04-08 | 27 | 27 | 27
W006 | R002 | 2024-12-01 | 2025-01-01 | 30 | 30 | 32
W007 | R001 | 2023-01-21 | 2023-02-22 | 33 | 33 | 33
W008 | R002 | 2024-09-06 | 2024-10-07 | 32 | 32 | 32
W009 | R001 | 2023-05-02 | 2023-05-29 | 27 | 27 | 28
W010 | R002 | 2024-04-11 | 2024-05-09 | 29 | 29 | 29
W011 | R004 | 2023-08-04 | 2023-09-10 | 36 | 36 | 38
W012 | R004 | 2023-11-27 | 2023-12-25 | 29 | 29 | 29
W013 | R003 | 2024-04-03 | 2024-05-09 | 36 | 36 | 37
W014 | R004 | 2023-03-29 | 2023-05-03 | 35 | 35 | 36
W015 | R003 | 2024-01-08 | 2024-02-01 | 25 | 25 | 25
W016 | R004 | 2023-04-10 | 2023-05-10 | 29 | 29 | 31
W017 | R001 | 2024-10-26 | 2024-11-22 | 28 | 28 | 28
W018 | R004 | 2023-05-11 | 2023-06-05 | 26 | 26 | 26
W019 | R003 | 2024-10-23 | 2024-11-17 | 25 | 25 | 26
W020 | R003 | 2023-11-05 | 2023-11-30 | 26 | 26 | 26
W021 | R002 | 2023-12-10 | 2024-01-13 | 30 | 30 | 35
W022 | R001 | 2024-05-06 | 2024-06-05 | 30 | 30 | 31
W023 | R004 | 2024-02-18 | 2024-03-21 | 32 | 32 | 33
W024 | R002 | 2024-01-21 | 2024-02-22 | 32 | 32 | 33
W025 | R004 | 2023-07-11 | 2023-08-06 | 26 | 26 | 27
W026 | R004 | 2023-10-04 | 2023-11-04 | 31 | 31 | 32
W027 | R002 | 2023-06-10 | 2023-07-13 | 34 | 34 | 34
W028 | R002 | 2024-04-04 | 2024-05-08 | 33 | 33 | 35
W029 | R002 | 2023-11-10 | 2023-12-08 | 28 | 28 | 29
W030 | R002 | 2023-01-22 | 2023-02-25 | 33 | 33 | 35
W031 | R002 | 2023-09-10 | 2023-10-11 | 31 | 31 | 32
W032 | R004 | 2024-07-14 | 2024-08-15 | 31 | 31 | 33
W033 | R002 | 2024-04-19 | 2024-05-13 | 25 | 25 | 25
W034 | R001 | 2023-02-28 | 2023-03-28 | 28 | 28 | 29
W035 | R003 | 2024-05-25 | 2024-06-28 | 33 | 33 | 35
W036 | R002 | 2024-11-12 | 2024-12-09 | 25 | 25 | 28
W037 | R002 | 2024-04-20 | 2024-05-24 | 32 | 32 | 35
W038 | R004 | 2024-11-30 | 2025-01-05 | 34 | 34 | 37
W039 | R002 | 2023-07-09 | 2023-08-09 | 29 | 29 | 32
W040 | R002 | 2024-11-17 | 2024-12-14 | 28 | 28 | 28
W041 | R002 | 2024-07-16 | 2024-08-10 | 25 | 25 | 26
W042 | R004 | 2024-07-20 | 2024-08-16 | 28 | 28 | 28
W043 | R002 | 2023-09-01 | 2023-10-02 | 30 | 30 | 32
W044 | R003 | 2024-05-19 | 2024-06-18 | 31 | 31 | 31
W045 | R004 | 2023-05-11 | 2023-06-05 | 25 | 25 | 26
W046 | R003 | 2024-04-29 | 2024-05-29 | 29 | 29 | 31
W047 | R004 | 2024-10-08 | 2024-11-03 | 25 | 25 | 27
W048 | R002 | 2023-01-21 | 2023-02-22 | 30 | 30 | 33
W049 | R003 | 2023-06-16 | 2023-07-24 | 36 | 36 | 39
W050 | R004 | 2023-10-01 | 2023-10-23 | 22 | 22 | 23

## Data_Quality
Check | Value
Daily records | 1474
Unique well-day combinations | 1474
Unique rig-day combinations | 1130
Null dates | 0
Null Well_ID | 0
Null Rig_ID | 0
Negative footage | 0
Negative drilling hours | 0
Negative NPT duration | 0
Negative NPT cost | 0
Duplicate well-day rows | 0