## Executive_Summary
Metric | Value
Total Wells | 50
Total Rigs | 4
Drilling Records | 1474
NPT Events | 677
NPT Hours | 4008
NPT Cost USD | 79204408
Total Drilling Cost USD | 654712456.04
Median Well ROP ft/hr | 33.7323
Median Rig ROP ft/hr | 33.6145
Top Root Cause | Drilling
Top Root Cause Score | 85.5603
Top Well Opportunity | W040
Top Well Score | 79.1745
Top Rig Opportunity | R002
Top Rig Score | 85.4019

## Root_Cause_Impact
NPT_Category | NPT_Events | NPT_Hours | NPT_Cost_USD | Avg_NPT_Duration_hr | Avg_Severity_Score | Cost_Impact_Score | NPT_Impact_Score | Frequency_Score | Severity_Score | Opportunity_Score | Priority | Priority_Rank | Cumulative_Cost_USD | Cumulative_Cost_Pct | Pareto_Flag
Drilling | 213 | 1252 | 24710780 | 5.8779 | 1.5305 | 100 | 100 | 100 | 27.8014 | 85.5603 | CRITICAL | 1 | 24710780 | 31.1987 | TOP_80_PERCENT
Mechanical | 171 | 1052 | 20725787 | 6.152 | 1.5848 | 81.5459 | 81.7518 | 77.2973 | 100 | 84.4385 | CRITICAL | 2 | 45436567 | 57.3662 | TOP_80_PERCENT
Weather | 161 | 942 | 18659538 | 5.8509 | 1.5217 | 71.9774 | 71.7153 | 71.8919 | 16.1263 | 60.7245 | MEDIUM | 3 | 64096105 | 80.9249 | REMAINDER
Logistics | 104 | 606 | 11991643 | 5.8269 | 1.5096 | 41.0991 | 41.0584 | 41.0811 | 0 | 32.8655 | LOW | 4 | 76087748 | 96.065 | REMAINDER
Personnel | 28 | 156 | 3116660 | 5.5714 | 1.5357 | 0 | 0 | 0 | 34.7152 | 6.943 | LOW | 5 | 79204408 | 100 | REMAINDER

## Well_Opportunity
Well_ID | Rig_ID | Drilling_Days | Total_Footage_ft | Avg_ROP_ft_hr | Total_Drilling_Cost_USD | Weather_Delay_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | ROP_Benchmark_ft_hr | ROP_Gap_ft_hr | Cost_Impact_Score | NPT_Impact_Score | Performance_Gap_Score | Frequency_Score | Opportunity_Score | Priority | Priority_Rank
W040 | R002 | 28 | 18509.8 | 34.2754 | 12137950.94 | 27 | 21 | 130 | 2491660 | 33.7323 | 0 | 97.6414 | 100 | 0 | 100 | 79.1745 | HIGH | 1
W007 | R001 | 33 | 21584.9 | 34.2727 | 14628770.85 | 14 | 16 | 128 | 2533329 | 33.7323 | 0 | 100 | 97.8261 | 0 | 61.5385 | 71.7642 | HIGH | 2
W009 | R001 | 27 | 16290.9 | 31.3663 | 11956185.14 | 24 | 15 | 100 | 1979163 | 33.7323 | 2.366 | 68.6321 | 67.3913 | 100 | 53.8462 | 71.6383 | HIGH | 3
W013 | R003 | 36 | 22553.7 | 32.7356 | 16182108.87 | 16 | 20 | 96 | 1920000 | 33.7323 | 0.99673 | 65.2833 | 63.0435 | 42.1274 | 92.3077 | 65.497 | HIGH | 4
W036 | R002 | 25 | 16733 | 33.9652 | 11091091.98 | 5 | 19 | 108 | 2069994 | 33.7323 | 0 | 73.7735 | 76.087 | 0 | 84.6154 | 61.7655 | MEDIUM | 5
W010 | R002 | 29 | 18581.1 | 33.2452 | 12551454.43 | 19 | 16 | 106 | 2031661 | 33.7323 | 0.48711 | 71.6037 | 73.913 | 20.5882 | 61.5385 | 59.9649 | MEDIUM | 6
W001 | R004 | 26 | 16495 | 32.8035 | 12003516.78 | 7 | 19 | 88 | 1796660 | 33.7323 | 0.92883 | 58.3017 | 54.3478 | 39.2574 | 84.6154 | 58.7671 | MEDIUM | 7
W019 | R003 | 25 | 15697.8 | 33.8384 | 10717808.92 | 24 | 13 | 114 | 2280000 | 33.7323 | 0 | 85.6606 | 82.6087 | 0 | 38.4615 | 58.3257 | MEDIUM | 8
W011 | R004 | 36 | 22974 | 33.9056 | 16212768.29 | 31 | 16 | 104 | 2123328 | 33.7323 | 0 | 76.7924 | 71.7391 | 0 | 61.5385 | 57.1198 | MEDIUM | 9
W046 | R003 | 29 | 19388.9 | 34.8452 | 12933266.13 | 20 | 16 | 102 | 2040000 | 33.7323 | 0 | 72.0757 | 69.5652 | 0 | 61.5385 | 54.9255 | MEDIUM | 10
W043 | R002 | 30 | 19217.9 | 33.4967 | 12906481.26 | 10 | 18 | 94 | 1801662 | 33.7323 | 0.23562 | 58.5849 | 60.8696 | 9.9586 | 76.9231 | 53.0984 | MEDIUM | 11
W020 | R003 | 26 | 17159.9 | 34.2012 | 11719190.56 | 14 | 20 | 90 | 1800000 | 33.7323 | 0 | 58.4908 | 56.5217 | 0 | 92.3077 | 53.0638 | MEDIUM | 12
W021 | R002 | 30 | 19096.8 | 33.28 | 13145292.25 | 30 | 16 | 94 | 1801664 | 33.7323 | 0.45229 | 58.585 | 60.8696 | 19.1162 | 61.5385 | 51.8531 | MEDIUM | 13
W030 | R002 | 33 | 20756.7 | 32.873 | 14266132.13 | 14 | 15 | 90 | 1724996 | 33.7323 | 0.85926 | 54.2453 | 56.5217 | 36.317 | 53.8462 | 51.1489 | MEDIUM | 14
W048 | R002 | 30 | 17931 | 32.5013 | 12603788.4 | 39 | 14 | 86 | 1648329 | 33.7323 | 1.231 | 49.9056 | 52.1739 | 52.027 | 46.1538 | 50.1466 | MEDIUM | 15
W002 | R001 | 28 | 18303.9 | 32.635 | 12906810.88 | 0 | 13 | 88 | 1741664 | 33.7323 | 1.0973 | 55.1888 | 54.3478 | 46.3775 | 38.4615 | 49.8708 | LOW | 16
W041 | R002 | 25 | 15201.9 | 32.0492 | 10742273.1 | 6 | 14 | 76 | 1456662 | 33.7323 | 1.6831 | 39.0566 | 41.3043 | 71.1367 | 46.1538 | 47.454 | LOW | 17
W028 | R002 | 33 | 21527.8 | 33.4239 | 14462989.11 | 15 | 15 | 90 | 1724995 | 33.7323 | 0.30835 | 54.2452 | 56.5217 | 13.0325 | 53.8462 | 46.492 | LOW | 18
W035 | R003 | 33 | 20790.7 | 33.3033 | 14687778.32 | 43 | 12 | 92 | 1840000 | 33.7323 | 0.42895 | 60.7549 | 58.6957 | 18.13 | 30.7692 | 45.718 | LOW | 19
W033 | R002 | 25 | 16706.9 | 35.1348 | 10913961.71 | 18 | 16 | 90 | 1724995 | 33.7323 | 0 | 54.2452 | 56.5217 | 0 | 61.5385 | 45.424 | LOW | 20
W032 | R004 | 31 | 20171.8 | 34.539 | 13999009.8 | 15 | 15 | 86 | 1755829 | 33.7323 | 0 | 55.9905 | 52.1739 | 0 | 53.8462 | 43.4094 | LOW | 21
W018 | R004 | 26 | 18151.7 | 34.8804 | 12308393.58 | 0 | 14 | 88 | 1796662 | 33.7323 | 0 | 58.3019 | 54.3478 | 0 | 46.1538 | 43.2234 | LOW | 22
W003 | R004 | 28 | 18763 | 34.6875 | 12784056.41 | 14 | 13 | 88 | 1796663 | 33.7323 | 0 | 58.3019 | 54.3478 | 0 | 38.4615 | 41.6849 | LOW | 23
W045 | R004 | 25 | 15766.1 | 32.642 | 11426115.78 | 9 | 10 | 80 | 1633331 | 33.7323 | 1.0903 | 49.0567 | 45.6522 | 46.0816 | 15.3846 | 40.8761 | LOW | 24
W023 | R004 | 32 | 21362.9 | 34.8016 | 14445134.24 | 0 | 14 | 84 | 1714995 | 33.7323 | 0 | 53.6792 | 50 | 0 | 46.1538 | 40.5185 | LOW | 25
W006 | R002 | 30 | 20616.1 | 35.1587 | 13143205.35 | 12 | 15 | 84 | 1609994 | 33.7323 | 0 | 47.7357 | 50 | 0 | 53.8462 | 39.9767 | LOW | 26
W026 | R004 | 31 | 20855 | 34.7661 | 14459113.13 | 9 | 11 | 90 | 1837497 | 33.7323 | 0 | 60.6133 | 56.5217 | 0 | 23.0769 | 39.9605 | LOW | 27
W005 | R002 | 27 | 16853.1 | 32.0207 | 11873271.59 | 10 | 13 | 64 | 1226662 | 33.7323 | 1.7115 | 26.0377 | 28.2609 | 72.3395 | 38.4615 | 38.3386 | LOW | 28
W047 | R004 | 25 | 17327 | 35.1512 | 11659169.74 | 2 | 13 | 78 | 1592495 | 33.7323 | 0 | 46.7452 | 43.4783 | 0 | 38.4615 | 34.9227 | LOW | 29
W015 | R003 | 25 | 16635.9 | 34.4632 | 11401518.43 | 8 | 14 | 76 | 1520000 | 33.7323 | 0 | 42.6417 | 41.3043 | 0 | 46.1538 | 34.4815 | LOW | 30
W038 | R004 | 34 | 21390.1 | 33.4735 | 15149998.79 | 46 | 15 | 68 | 1388328 | 33.7323 | 0.25876 | 35.1886 | 32.6087 | 10.9365 | 53.8462 | 33.4247 | LOW | 31
W022 | R001 | 30 | 19737.2 | 33.7763 | 13405027.07 | 47 | 13 | 74 | 1464580 | 33.7323 | 0 | 39.5048 | 39.1304 | 0 | 38.4615 | 31.3016 | LOW | 32
W034 | R001 | 28 | 17777 | 33.6807 | 12356618.88 | 44 | 12 | 74 | 1464578 | 33.7323 | 0.051573 | 39.5046 | 39.1304 | 2.1797 | 30.7692 | 30.199 | LOW | 33
W029 | R002 | 28 | 18474 | 33.8211 | 12278777.35 | 2 | 14 | 70 | 1341662 | 33.7323 | 0 | 32.5471 | 34.7826 | 0 | 46.1538 | 29.3179 | LOW | 34
W050 | R004 | 22 | 15197 | 36.1468 | 10027597.8 | 19 | 11 | 74 | 1510831 | 33.7323 | 0 | 42.1227 | 39.1304 | 0 | 23.0769 | 29.1409 | LOW | 35
W044 | R003 | 31 | 19496.2 | 33.1719 | 13817299.17 | 8 | 12 | 64 | 1280000 | 33.7323 | 0.56035 | 29.0568 | 28.2609 | 23.6836 | 30.7692 | 28.1257 | LOW | 36
W039 | R002 | 29 | 19931 | 35.1524 | 12786789.7 | 11 | 13 | 70 | 1341663 | 33.7323 | 0 | 32.5472 | 34.7826 | 0 | 38.4615 | 27.7795 | LOW | 37
W025 | R004 | 26 | 15854.2 | 32.405 | 11627789.13 | 28 | 11 | 54 | 1102497 | 33.7323 | 1.3273 | 19.0095 | 17.3913 | 56.0986 | 23.0769 | 26.8362 | LOW | 38
W024 | R002 | 32 | 20685.1 | 33.7209 | 13722096.47 | 19 | 12 | 68 | 1303329 | 33.7323 | 0.011349 | 30.3773 | 32.6087 | 0.47969 | 30.7692 | 25.034 | LOW | 39
W012 | R004 | 29 | 18457.2 | 33.4397 | 13227460.52 | 30 | 11 | 64 | 1306664 | 33.7323 | 0.29263 | 30.5661 | 28.2609 | 12.3683 | 23.0769 | 24.8524 | LOW | 40
W008 | R002 | 32 | 19659.2 | 31.3706 | 14065082.15 | 25 | 10 | 40 | 766663 | 33.7323 | 2.3617 | 0 | 2.1739 | 99.817 | 15.3846 | 23.5838 | LOW | 41
W037 | R002 | 32 | 20535.1 | 33.7097 | 13749815.59 | 21 | 9 | 72 | 1379996 | 33.7323 | 0.022599 | 34.717 | 36.9565 | 0.95518 | 7.6923 | 23.1196 | LOW | 42
W027 | R002 | 34 | 22391.9 | 34.2441 | 14655693.1 | 38 | 10 | 66 | 1264997 | 33.7323 | 0 | 28.2076 | 30.4348 | 0 | 15.3846 | 20.5583 | LOW | 43
W031 | R002 | 31 | 20249.1 | 33.7687 | 13420380.1 | 38 | 11 | 60 | 1149994 | 33.7323 | 0 | 21.698 | 23.913 | 0 | 23.0769 | 18.1879 | LOW | 44
W049 | R003 | 36 | 22777.1 | 33.4886 | 15941431 | 28 | 9 | 60 | 1200000 | 33.7323 | 0.24368 | 24.5285 | 23.913 | 10.2991 | 7.6923 | 18.1615 | LOW | 45
W016 | R004 | 29 | 18696.2 | 33.2086 | 13214359.14 | 27 | 10 | 50 | 1020830 | 33.7323 | 0.52367 | 14.3868 | 13.0435 | 22.1331 | 15.3846 | 15.7998 | LOW | 46
W017 | R001 | 28 | 17999.2 | 34.0668 | 12367526.71 | 30 | 11 | 54 | 1068748 | 33.7323 | 0 | 17.0992 | 17.3913 | 0 | 23.0769 | 14.9479 | LOW | 47
W004 | R002 | 33 | 20231.9 | 33.7436 | 13777407.37 | 40 | 11 | 52 | 996663 | 33.7323 | 0 | 13.0189 | 15.2174 | 0 | 23.0769 | 12.9763 | LOW | 48
W042 | R004 | 28 | 18254.8 | 34.3746 | 12572413.42 | 24 | 8 | 52 | 1061665 | 33.7323 | 0 | 16.6982 | 15.2174 | 0 | 0 | 9.6487 | LOW | 49
W014 | R004 | 35 | 22280.1 | 32.6689 | 16280284.48 | 9 | 8 | 38 | 775830 | 33.7323 | 1.0634 | 0.51889 | 0 | 44.9465 | 0 | 9.1709 | LOW | 50

## Rig_Opportunity
Rig_ID | Wells_Drilled | Drilling_Days | Total_Footage_ft | Avg_ROP_ft_hr | Total_Drilling_Cost_USD | Weather_Delay_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | ROP_Benchmark_ft_hr | ROP_Gap_ft_hr | Cost_Impact_Score | NPT_Impact_Score | Performance_Gap_Score | Frequency_Score | Opportunity_Score | Priority | Priority_Rank
R002 | 20 | 596 | 383889.4 | 33.5415 | 258293934.08 | 399 | 282 | 1610 | 30858241 | 33.6145 | 0.073009 | 100 | 100 | 27.0095 | 100 | 85.4019 | CRITICAL | 1
R004 | 16 | 463 | 301996.1 | 33.9592 | 211397181.03 | 270 | 199 | 1186 | 24214105 | 33.6145 | 0 | 67.7566 | 61.1722 | 0 | 58.9109 | 50.79 | MEDIUM | 2
R001 | 6 | 174 | 111693.1 | 33.3442 | 77620939.53 | 159 | 80 | 518 | 10252062 | 33.6145 | 0.27031 | 0 | 0 | 100 | 0 | 20 | LOW | 3
R003 | 8 | 241 | 154500.2 | 33.6875 | 107400401.4 | 161 | 116 | 694 | 13880000 | 33.6145 | 0 | 17.6061 | 16.1172 | 0 | 17.8218 | 13.7558 | LOW | 4

## Top_Root_Causes
NPT_Category | NPT_Events | NPT_Hours | NPT_Cost_USD | Avg_NPT_Duration_hr | Avg_Severity_Score | Cost_Impact_Score | NPT_Impact_Score | Frequency_Score | Severity_Score | Opportunity_Score | Priority | Priority_Rank | Cumulative_Cost_USD | Cumulative_Cost_Pct | Pareto_Flag
Drilling | 213 | 1252 | 24710780 | 5.8779 | 1.5305 | 100 | 100 | 100 | 27.8014 | 85.5603 | CRITICAL | 1 | 24710780 | 31.1987 | TOP_80_PERCENT
Mechanical | 171 | 1052 | 20725787 | 6.152 | 1.5848 | 81.5459 | 81.7518 | 77.2973 | 100 | 84.4385 | CRITICAL | 2 | 45436567 | 57.3662 | TOP_80_PERCENT
Weather | 161 | 942 | 18659538 | 5.8509 | 1.5217 | 71.9774 | 71.7153 | 71.8919 | 16.1263 | 60.7245 | MEDIUM | 3 | 64096105 | 80.9249 | REMAINDER
Logistics | 104 | 606 | 11991643 | 5.8269 | 1.5096 | 41.0991 | 41.0584 | 41.0811 | 0 | 32.8655 | LOW | 4 | 76087748 | 96.065 | REMAINDER
Personnel | 28 | 156 | 3116660 | 5.5714 | 1.5357 | 0 | 0 | 0 | 34.7152 | 6.943 | LOW | 5 | 79204408 | 100 | REMAINDER

## Top_Wells
Well_ID | Rig_ID | Drilling_Days | Total_Footage_ft | Avg_ROP_ft_hr | Total_Drilling_Cost_USD | Weather_Delay_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | ROP_Benchmark_ft_hr | ROP_Gap_ft_hr | Cost_Impact_Score | NPT_Impact_Score | Performance_Gap_Score | Frequency_Score | Opportunity_Score | Priority | Priority_Rank
W040 | R002 | 28 | 18509.8 | 34.2754 | 12137950.94 | 27 | 21 | 130 | 2491660 | 33.7323 | 0 | 97.6414 | 100 | 0 | 100 | 79.1745 | HIGH | 1
W007 | R001 | 33 | 21584.9 | 34.2727 | 14628770.85 | 14 | 16 | 128 | 2533329 | 33.7323 | 0 | 100 | 97.8261 | 0 | 61.5385 | 71.7642 | HIGH | 2
W009 | R001 | 27 | 16290.9 | 31.3663 | 11956185.14 | 24 | 15 | 100 | 1979163 | 33.7323 | 2.366 | 68.6321 | 67.3913 | 100 | 53.8462 | 71.6383 | HIGH | 3
W013 | R003 | 36 | 22553.7 | 32.7356 | 16182108.87 | 16 | 20 | 96 | 1920000 | 33.7323 | 0.99673 | 65.2833 | 63.0435 | 42.1274 | 92.3077 | 65.497 | HIGH | 4
W036 | R002 | 25 | 16733 | 33.9652 | 11091091.98 | 5 | 19 | 108 | 2069994 | 33.7323 | 0 | 73.7735 | 76.087 | 0 | 84.6154 | 61.7655 | MEDIUM | 5
W010 | R002 | 29 | 18581.1 | 33.2452 | 12551454.43 | 19 | 16 | 106 | 2031661 | 33.7323 | 0.48711 | 71.6037 | 73.913 | 20.5882 | 61.5385 | 59.9649 | MEDIUM | 6
W001 | R004 | 26 | 16495 | 32.8035 | 12003516.78 | 7 | 19 | 88 | 1796660 | 33.7323 | 0.92883 | 58.3017 | 54.3478 | 39.2574 | 84.6154 | 58.7671 | MEDIUM | 7
W019 | R003 | 25 | 15697.8 | 33.8384 | 10717808.92 | 24 | 13 | 114 | 2280000 | 33.7323 | 0 | 85.6606 | 82.6087 | 0 | 38.4615 | 58.3257 | MEDIUM | 8
W011 | R004 | 36 | 22974 | 33.9056 | 16212768.29 | 31 | 16 | 104 | 2123328 | 33.7323 | 0 | 76.7924 | 71.7391 | 0 | 61.5385 | 57.1198 | MEDIUM | 9
W046 | R003 | 29 | 19388.9 | 34.8452 | 12933266.13 | 20 | 16 | 102 | 2040000 | 33.7323 | 0 | 72.0757 | 69.5652 | 0 | 61.5385 | 54.9255 | MEDIUM | 10

## Top_Rigs
Rig_ID | Wells_Drilled | Drilling_Days | Total_Footage_ft | Avg_ROP_ft_hr | Total_Drilling_Cost_USD | Weather_Delay_hr | NPT_Events | NPT_Hours | NPT_Cost_USD | ROP_Benchmark_ft_hr | ROP_Gap_ft_hr | Cost_Impact_Score | NPT_Impact_Score | Performance_Gap_Score | Frequency_Score | Opportunity_Score | Priority | Priority_Rank
R002 | 20 | 596 | 383889.4 | 33.5415 | 258293934.08 | 399 | 282 | 1610 | 30858241 | 33.6145 | 0.073009 | 100 | 100 | 27.0095 | 100 | 85.4019 | CRITICAL | 1
R004 | 16 | 463 | 301996.1 | 33.9592 | 211397181.03 | 270 | 199 | 1186 | 24214105 | 33.6145 | 0 | 67.7566 | 61.1722 | 0 | 58.9109 | 50.79 | MEDIUM | 2
R001 | 6 | 174 | 111693.1 | 33.3442 | 77620939.53 | 159 | 80 | 518 | 10252062 | 33.6145 | 0.27031 | 0 | 0 | 100 | 0 | 20 | LOW | 3
R003 | 8 | 241 | 154500.2 | 33.6875 | 107400401.4 | 161 | 116 | 694 | 13880000 | 33.6145 | 0 | 17.6061 | 16.1172 | 0 | 17.8218 | 13.7558 | LOW | 4

## Pareto_Root_Cause
NPT_Category | NPT_Cost_USD | Cumulative_Cost_USD | Cumulative_Cost_Pct | Pareto_Flag
Drilling | 24710780 | 24710780 | 31.1987 | TOP_80_PERCENT
Mechanical | 20725787 | 45436567 | 57.3662 | TOP_80_PERCENT
Weather | 18659538 | 64096105 | 80.9249 | REMAINDER
Logistics | 11991643 | 76087748 | 96.065 | REMAINDER
Personnel | 3116660 | 79204408 | 100 | REMAINDER